## Issued Work Order (DARJEELING)
Issued Work Order (DARJEELING)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/13042 |  | New | SVS | 1454/NKWSMD | MADAN SHARMA | 29-09-2022 | 26-07-2023
2 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/12983 |  | New | SVS | 2472/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 06-02-2023 | 06-02-2024
3 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/11953 |  | New | SVS | 1562/NKWSMD | VINAYAK CONSTRUCTION | 21-10-2022 | 21-10-2023
4 | DARJEELING | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 |  | New | SVS | 818/NKWSMD | VINAYAK CONSTRUCTION | 30-06-2022 | 25-02-2023
5 | DARJEELING | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 |  | New | SVS | 818/NKWSMD | VINAYAK CONSTRUCTION | 30-06-2022 | 25-02-2023
6 | DARJEELING | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16534 |  | New | SVS | 1291/NKWSMD | SHAKTI CONSTRUCTION | 17-10-2023 | 16-10-2024
7 | DARJEELING | Arjun Mahal mouzas ( Buraganj Gram Panchaayat) water supply scheme | SM/03172 | SM/13395 | Augmentation | SVS | 58/SWSD | M/S UTPAL CHAKRABORTY & CO. | 10-04-2023 | 08-08-2023 | 407
8 | DARJEELING | Bairagi Piped Water Supply Scheme | SM/05946 | SM/07218 | Retrofitting | MVS | 1276/SWSD | SUBIR CH. CHOWDHURY | 14-08-2020
9 | DARJEELING | Bairagi Piped Water Supply Scheme | SM/05946 | SM/07218 | Retrofitting | MVS | 1275/SWSD | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 14-08-2020 | 19-08-2020 | 503
10 | DARJEELING | Bairagi Piped Water Supply Scheme | SM/05946 | SM/07218 | Retrofitting | MVS | 1274/SWSD | SUDIP BASAK | 14-08-2020
11 | DARJEELING | BAIRATISAL WATER SUPPLY SCHEME | SM/00131 | SM/10097 | Augmentation | MVS | 970/SWSD | M/S KAMAK ENGINEERS & CO | 01-08-2022 | 29-03-2023 | 2935
12 | DARJEELING | BAIRATISAL WATER SUPPLY SCHEME | SM/00131 | SM/10097 | Augmentation | MVS | 870/SWSD | M/S G.C. CONSTRUCTION & CO. | 21-07-2022 | 14-10-2022 | 1125
13 | DARJEELING | BAIRATISAL WATER SUPPLY SCHEME | SM/00131 | SM/10469 | Augmentation | MVS | 652/SWSD | FAIRDEAL ASSOCIATES | 15-06-2023 | 10-02-2024 | 1619
14 | DARJEELING | BAIRATISAL WATER SUPPLY SCHEME | SM/00131 | SM/10108 | Augmentation | MVS | 1204/SWSD | BRM DEVELOPERS | 11-08-2023 | 07-04-2024 | 482
15 | DARJEELING | BANDARGACHA WATER SUPPLY SCHEME | SM/00006 | SM/07042 | Retrofitting | MVS | 1269/SWSD | M/S MATRI CONSTRUCTION | 14-08-2020
16 | DARJEELING | BANDARGACHA WATER SUPPLY SCHEME | SM/00006 | SM/07220 | Retrofitting | MVS | 1271/SWSD | SWAPAN CHANDRA DAS | 14-08-2020
17 | DARJEELING | BANDARGACHA WATER SUPPLY SCHEME | SM/00006 | SM/07220 | Retrofitting | MVS | 1273/SWSD | PRADIP GUHA | 14-08-2020
18 | DARJEELING | BANDARGACHA WATER SUPPLY SCHEME | SM/00006 | SM/10714 | Augmentation | MVS | 817/SWSD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 19-07-2022 | 16-03-2023 | 739
19 | DARJEELING | BANDARGACHA WATER SUPPLY SCHEME | SM/00006 | SM/07220 | Retrofitting | MVS | 1270/SWSD | M/S SHIVAJI ROY | 14-08-2020
20 | DARJEELING | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME | SM/11786 |  | New | MVS | 1150/SWSD | MAHADEO PRASAD AGARWAL & CO | 08-08-2023 | 04-04-2024 | 775
21 | DARJEELING | BARA CHENGA PIPED WATER SUPPLY SCHEME | SM/10816 |  | New | MVS | 825/NKWSMD | M/S KAMAK ENGINEERS AND CO. | 30-06-2022 | 25-02-2023
22 | DARJEELING | BARASADVITA WATER SUPPLY SCHEME | SM/01124 | SM/07030 | Retrofitting | MVS | 1015/SWSD | M/S G.C. CONSTRUCTION & CO. | 11-12-2020 | 20-01-2021 | 156
23 | DARJEELING | BARASADVITA WATER SUPPLY SCHEME | SM/01124 | SM/15924 | Augmentation | MVS | 1192/SWSD | RAMESH AGARWAL | 10-08-2023 | 06-04-2024 | 534
24 | DARJEELING | BARASADVITA WATER SUPPLY SCHEME | SM/01124 | SM/07030 | Retrofitting | MVS | 1014/SWSD | VIJAY KUMAR ARORA | 11-12-2020 | 20-01-2021 | 1
25 | DARJEELING | BARBATIA KHASMAHAL PWSS | SM/18189 |  | New | SVS | 182/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 04-05-2023 | 31-10-2023
26 | DARJEELING | Bhalamanshi Piped Water Supply Scheme | SM/05387 | SM/07045 | Retrofitting | MVS | 1090/SWSD | SHRI ANUP BASU | 18-12-2020 | 01-02-2021 | 1
27 | DARJEELING | Bhalamanshi Piped Water Supply Scheme | SM/05387 | SM/07045 | Retrofitting | MVS | 695/SWSD | SHRI ANUP BASU | 02-08-2021 | 16-09-2021
28 | DARJEELING | BHIRGAON DHARGAON PWSS | SM/18714 |  | New | SVS | 893/NKWSMD | RINZI SHERPA | 07-08-2023 | 03-02-2024
29 | DARJEELING | BIJANBARI PIPED WATER SUPPLY SCHEME. | SM/15869 |  | New | SVS | 89/NKWSMD | VAISHNO CONSTRUCTION | 27-04-2023 | 23-12-2023
30 | DARJEELING | Birsing Piped Water Supply Scheme | SM/05422 | SM/09079 | Retrofitting | SVS | 1221/SWSD | M/S MATRI CONSTRUCTION | 01-11-2021 | 06-12-2021 | 679
31 | DARJEELING | Birsing Piped Water Supply Scheme | SM/05422 |  |  | MVS | 1281/SWSD | VIJAY KUMAR ARORA | 14-08-2020
32 | DARJEELING | Birsing Piped Water Supply Scheme | SM/05422 | SM/09079 | Retrofitting | SVS | 1222/SWSD | PRADIP GUHA | 01-11-2021 | 21-11-2021 | 255
33 | DARJEELING | Birsing Piped Water Supply Scheme | SM/05422 | SM/07422 | Retrofitting | SVS | 1281/SWSD | VIJAY KUMAR ARORA | 14-08-2020
34 | DARJEELING | BLOOMFIELD TEA GARDEN PWSS | SM/15910 |  | New | SVS | 720/NKWSMD | HARI PRASAD CHETTRI | 18-07-2023 | 14-03-2024
35 | DARJEELING | Buraganj & Jatur Mouza - Rural Water Supply Scheme | SM/03175 | SM/13393 | Augmentation | MVS | 335/SWSD | DEBRAJ ENTERPRISE | 08-05-2023 | 21-08-2023 | 441
36 | DARJEELING | Buraganj GP (Hatidoba Mouza) New Rural Water Supply Scheme | SM/03091 | SM/13428 | Augmentation | SVS | 654/SWSD | M/S DOLPHIN CONSTRUCTION CO | 15-06-2023 | 13-10-2023 | 207
37 | DARJEELING | Buraganj Gram Panchayat Village W/S Scheme ( For Chuchur Muchur Mouza) | SM/03078 | SM/13427 | Augmentation | SVS | 2576/SWSD | UJJWAL ROY | 23-02-2023 | 08-06-2023 | 661
38 | DARJEELING | CHAINPURAY PIPED WATER SUPPLY SCHEME | SM/15881 |  | New | SVS | 680/NKWSMD | VAISHNO CONSTRUCTION | 12-07-2023 | 10-10-2023
39 | DARJEELING | CHAMTA WATER SUPPLY SCHEME | SM/00135 | SM/10107 | Augmentation | MVS | 860/SWSD | BISWADEEP CONSTRUCTION | 21-07-2022 | 04-10-2022 | 297
40 | DARJEELING | CHAMTA WATER SUPPLY SCHEME | SM/00135 | SM/10107 | Augmentation | MVS | 875/SWSD | M/S UTPAL CHAKRABORTY & CO. | 21-07-2022 | 04-10-2022 | 304
41 | DARJEELING | CHAMTA WATER SUPPLY SCHEME | SM/00135 | SM/10107 | Augmentation | MVS | 876/SWSD | SUBIR CH. CHOWDHURY | 21-07-2022 | 14-10-2022 | 500
42 | DARJEELING | CHAMTA WATER SUPPLY SCHEME | SM/00135 | SM/10107 | Augmentation | MVS | 871/SWSD | NARENDRA KUMAR | 21-07-2022 | 09-10-2022 | 344
43 | DARJEELING | CHEGRA KHASMAHAL Piped Water Supply Scheme | SM/16141 |  | New | SVS | 184/NKWSMD | GREEN VALLEY CONSTRUCTION | 04-05-2023 | 31-10-2023
44 | DARJEELING | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | SM/15877 |  | New | SVS | 261/NKWSMD | NIMA SHERPA | 15-05-2023 | 12-09-2023
45 | DARJEELING | Choongtoong & Lizahill Tea Garden water supply scheme | SM/12269 |  | New | MVS | 1447/NKWSMD | SUDESH RAYA MAJHI | 29-09-2022 | 26-07-2023
46 | DARJEELING | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13439 |  | New | SVS | 1041/SWSD | SUDIP BASAK | 27-07-2023 | 25-09-2023 | 71
47 | DARJEELING | Damdama Piped Water Supply Scheme | SM/05955 | SM/07425 | Retrofitting | MVS | 1525/SWSD | ARUN KUMAR SHRIVASTAVA | 14-08-2020 |  | 550
48 | DARJEELING | Damdama Piped Water Supply Scheme | SM/05955 | SM/07425 | Retrofitting | MVS | 1086/SWSD | DEBOL,S ENTERPRISE | 18-12-2020 | 07-01-2021 | 353
49 | DARJEELING | Damdama Piped Water Supply Scheme | SM/05955 | SM/14835 | Augmentation | MVS | 364/SSD | SEBU CHAKRABORTY | 10-08-2023 | 24-09-2023 | 45
50 | DARJEELING | Dangarvita Piped Water Supply Scheme | SM/06058 | SM/07424 | Retrofitting | MVS | 1089/ SWSD | BHOLA GHOSH | 14-08-2020 |  | 301
51 | DARJEELING | Dangarvita Piped Water Supply Scheme | SM/06058 | SM/07424 | Retrofitting | MVS | 1088/ SWSD | BHOLA GHOSH | 14-08-2020 |  | 411
52 | DARJEELING | DANGIA PIPED WATER SUPPLY SCHEME | SM/15896 |  | New | MVS | 183/NKWSMD | HARI PRASAD CHETTRI | 04-05-2023 | 30-12-2023
53 | DARJEELING | Deburam Piped Water Supply Scheme | SM/05943 |  |  | MVS | 1087/SWSD | RAJEEV RANJAN OJHA | 18-12-2020 | 27-01-2021 | 493
54 | DARJEELING | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13958 |  | New | SVS | 2004/NKWSMD | ABHINAY CHETTRI | 23-12-2022 | 21-06-2023
55 | DARJEELING | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13960 |  | New | SVS | 2003/NKWSMD | SRINIWAS AGARWAL | 23-12-2022 | 21-06-2023
56 | DARJEELING | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13957 |  | New | SVS | 2148/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 20-01-2023 | 17-09-2023
57 | DARJEELING | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11943 |  | New | SVS | 2081/NKWSMD | SUNRISE ENTERPRISES | 10-01-2023 | 09-07-2023
58 | DARJEELING | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/13571 |  | New | SVS | 2734/NKWSMD | SRINIWAS AGARWAL | 03-03-2023 | 02-03-2024
59 | DARJEELING | Dhulia Piped Water Supply Scheme | SM/05401 | SM/09078 | Retrofitting | MVS | 961/SWSD | DEBOL,S ENTERPRISE | 02-09-2021 | 17-09-2021 | 153
60 | DARJEELING | Dhulia Piped Water Supply Scheme | SM/05401 | SM/09078 | Retrofitting | MVS | 960/SWSD | M/S SHIVAJI ROY | 02-09-2021 | 17-09-2021 | 129
61 | DARJEELING | Dhulia Piped Water Supply Scheme | SM/05401 | SM/12038 | Augmentation | MVS | 2095/SWSD | KAMAL GHOSH | 22-12-2022 | 07-03-2023 | 299
62 | DARJEELING | Dhulia Piped Water Supply Scheme | SM/05401 |  |  | MVS | 1083/SWSD | KAMAL GHOSH | 18-12-2020 | 07-01-2021 | 1
63 | DARJEELING | Dumriguri Water Supply Scheme | SM/01664 | SM/07427 | Retrofitting | SVS | 1278/SWSD | M/S ASHIRBAD ENTERPRISE | 14-08-2020
64 | DARJEELING | Dumriguri Water Supply Scheme | SM/01664 | SM/10476 | Augmentation | SVS | 1978/SWSD | DRISHTI CONSTRUCTION | 26-10-2023 | 22-06-2024 | 839
65 | DARJEELING | Dumriguri Water Supply Scheme | SM/01664 | SM/07428 | Retrofitting | SVS | 1012/ SWSD | U.K CONSTRUCTIONS | 14-08-2020
66 | DARJEELING | Dumriguri Water Supply Scheme | SM/01664 | SM/07427 | Retrofitting | SVS | 1279/SWSD | AKASH ENTERPRISE | 14-08-2020
67 | DARJEELING | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) | SM/13509 |  | New | MVS | 651/SWSD | AKASH ENTERPRISE | 15-06-2023 | 12-11-2023 | 767
68 | DARJEELING | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | SM/18880 | Augmentation | SVS | 2228/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 09-12-2024 | 07-06-2025
69 | DARJEELING | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 |  | New | SVS | 826/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 30-06-2022 | 25-02-2023
70 | DARJEELING | Ghusuru Piped Water Supply Scheme | SM/05951 | SM/12036 | Augmentation | MVS | 2365/SWSD | SUBIR CH. CHOWDHURY | 24-01-2023 | 24-04-2023 | 472
71 | DARJEELING | Ghusuru Piped Water Supply Scheme | SM/05951 | SM/07423 | Retrofitting | MVS | 1215/SWSD | ARUN KUMAR SHRIVASTAVA | 01-11-2021 | 16-12-2021 | 759
72 | DARJEELING | Ghusuru Piped Water Supply Scheme | SM/05951 | SM/07423 | Retrofitting | MVS | 1084/ SWSD | BUDDHADEV NAG | 14-08-2020 |  | 429
73 | DARJEELING | GOKE PIPED WATER SUPPLY SCHEME. | SM/15873 |  | New | SVS | 1293/NKWSMD | VAISHNO CONSTRUCTION | 17-10-2023 | 16-10-2024
74 | DARJEELING | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | SM/14418 |  | New | SVS | 2521/NKWSMD | GARGO TRADERS | 15-02-2023 | 15-02-2024
75 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/13959 |  | New | SVS | 1879/NKWSMD | ROSHAN BISWAKARMA | 14-12-2022 | 12-06-2023
76 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12179 |  | New | SVS | 1622/NKWSMD | VINAYAK CONSTRUCTION | 03-11-2022 | 03-11-2023
77 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | SM/12128 |  | New | SVS | 1451/NKWSMD | GARGO TRADERS | 29-09-2022 | 26-07-2023
78 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | SM/12736 |  | New | SVS | 1618/NKWSMD | GARGO TRADERS | 03-11-2022 | 02-05-2023
79 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/11944 |  | New | SVS | 1619/NKWSMD | YAMA CONSTRUCTIONS LLP | 03-11-2022 | 02-05-2023
80 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | SM/11856 |  | New | SVS | 677/NKWSMD | SATHI CONSTRUCTION COMPANY | 12-07-2023 | 08-01-2024
81 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | SM/11889 |  | New | SVS | 1529/NKWSMD | KUNCHAN JUNGA ENTERPRISES | 18-10-2022 | 16-04-2023
82 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS | SM/15224 |  | New | SVS | 685/NKWSMD | GARGO TRADERS | 12-07-2023 | 11-07-2024
83 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/11954 |  | New | SVS | 1530/NKWSMD | VINAYAK CONSTRUCTION | 18-10-2022 | 15-06-2023
84 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. | SM/13041 |  | New | SVS | 1560/NKWSMD | SRINIWAS AGARWAL | 21-10-2022 | 21-10-2023
85 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/13956 |  | New | SVS | 118/NKWSMD | SUMAN THAKURI | 28-04-2023 | 24-12-2023
86 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/11891 |  | New | SVS | 1146/NKWSMD | GARGO TRADERS | 29-09-2022 | 26-07-2023
87 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS | SM/11855 |  | New | SVS | 1525/NKWSMD | SUMAN PRADHAN | 17-10-2022 | 14-06-2023
88 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/12178 |  | New | SVS | 1494/NKWSMD | ALLIED INSTRUMENTS | 14-10-2022 | 10-08-2023
89 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | SM/12178 |  | New | SVS | 1494/NKWSMD | ALLIED INSTRUMENTS | 14-10-2022 | 10-08-2023
90 | DARJEELING | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | SM/11890 |  | New | SVS | 1449/NKWSMD | SRINIWAS AGARWAL | 29-09-2022 | 26-07-2023
91 | DARJEELING | Ground Water Based Piped Water Supply Scheme for Budharu Gaon & Adj. Mouzas | SM/03571 | SM/07041 | Retrofitting | SVS | 691/SWSD | SUDIP BASAK | 02-08-2021 | 21-09-2021
92 | DARJEELING | Ground Water Based Piped Water Supply Scheme for Gangaram Tea Garden Mouza | SM/03103 | SM/13394 | Augmentation | SVS | 670/SWSD | RAJEEV RANJAN OJHA | 16-06-2023 | 13-12-2023 | 567
93 | DARJEELING | Ground Water Based Piped Water Supply Scheme for ORD Terai Tea Garden Mouza | SM/03104 | SM/12749 | Augmentation | SVS | 2655/SWSD | VIJAY KUMAR ARORA | 02-03-2023 | 29-08-2023 | 555
94 | DARJEELING | Ground Water Based Piped Water Supply Scheme for Uttar Banagaon Kismat Mouza | SM/03105 | SM/13433 | Augmentation | SVS | 976/SWSD | MANAS KUMAR SAHA | 25-07-2023 | 06-03-2024 | 444
95 | DARJEELING | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 |  | New | MVS | 100/NKWSMD | INTERIOR'S NEST | 15-01-2024 | 14-01-2025
96 | DARJEELING | Guabari Piped Water Supply Scheme | SM/05402 | SM/07217 | Retrofitting | MVS | 1277/SWSD | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 14-08-2020 |  | 103
97 | DARJEELING | Guabari Piped Water Supply Scheme | SM/05402 | SM/07217 | Retrofitting | MVS | 1008/SWSD | UJJWAL ROY | 11-12-2020 | 10-01-2021
98 | DARJEELING | Hansqua Tea Garden Mouzas ( Hetmuri Singihora Gram Panchaayat) water supply scheme | SM/03176 | SM/13391 | Augmentation | MVS | 2919/SWSD | SUBIR CH. CHOWDHURY | 24-03-2023 | 20-10-2023 | 918
99 | DARJEELING | HATTA PIPED WATER SUPPLY SCHEME. | SM/15883 |  | New | SVS | 413/NKWSMD | SAGARMATHA CONSTRUCTION CO. | 05-06-2023 | 02-12-2023
100 | DARJEELING | Hatta Water Supply Scheme | SM/09449 |  | New | SVS | 621/NKWSMD | HARI PRASAD CHETTRI | 21-02-2022 | 21-07-2022
101 | DARJEELING | HUM TUKDAH KHASMAHAL PWSS | SM/18316 |  | New | MVS | 674/NKWSMD | RAMESH AGARWAL | 12-07-2023 | 11-07-2024
102 | DARJEELING | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme | SM/16142 |  | New | SVS | 718/NKWSMD | GARGO TRADERS | 18-07-2023 | 17-07-2024
103 | DARJEELING | Kalam w/s scheme | SM/02547 | SM/09829 | Augmentation | MVS | 36/SWSD | VIJAY KUMAR ARORA | 07-04-2022 | 16-07-2022 | 804
104 | DARJEELING | Kalam w/s scheme | SM/02547 | SM/09829 | Augmentation | MVS | 2081/SWSD | KAMAL GHOSH | 03-02-2022 | 04-04-2022 | 324
105 | DARJEELING | Kalam w/s scheme | SM/02547 | SM/09829 | Augmentation | MVS | 2354/SWSD | SHRI ANNAPURNA DISTRIBUTORS | 15-12-2023 | 12-06-2024 | 382
106 | DARJEELING | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) | SM/15892 |  | New | SVS | 125/NKWSMD | GREEN VALLEY CONSTRUCTION | 28-04-2023 | 26-08-2023
107 | DARJEELING | KALKUT WATER SUPPLY SCHEME | SM/00136 | SM/08296 | Retrofitting | MVS | 711/SWSD | ARUN KUMAR SHRIVASTAVA | 03-08-2021 | 12-09-2021 | 426
108 | DARJEELING | KALKUT WATER SUPPLY SCHEME | SM/00136 | SM/08296 | Retrofitting | MVS | 712/SWSD | M/S G.C. CONSTRUCTION & CO. | 03-08-2021 | 02-10-2021 | 753
109 | DARJEELING | KALKUT WATER SUPPLY SCHEME | SM/00136 | SM/18385 | Augmentation | MVS | 1023/SWSD | S.G.CONSTRUCTION | 26-07-2023 | 24-09-2023 | 262
110 | DARJEELING | KALKUT WATER SUPPLY SCHEME | SM/00136 | SM/18385 | Augmentation | MVS | 1031/SWSD | A.B. GANAPATI CONSTRUCTION | 26-07-2023 | 25-08-2023 | 133
111 | DARJEELING | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. | SM/16238 |  | New | SVS | 712/NKWSMD | SRINIWAS AGARWAL | 17-07-2023 | 14-11-2023
112 | DARJEELING | KASHIRAM PIPED WATER SUPPLY SCHEME | SM/18613 |  | New | MVS | 1366/SWSD | UNIBRO INFRASERV PRIVATE LIMITED | 18-08-2023 | 14-04-2024 | 804
113 | DARJEELING | Kawakhali Water Supply Scheme | SM/01819 | SM/18386 | Augmentation | MVS | 1230/SWSD | FAIRDEAL ASSOCIATES | 14-08-2023 | 25-04-2024 | 248
114 | DARJEELING | Kawakhali Water Supply Scheme | SM/01819 | SM/07033 | Retrofitting | SVS | 707/SWSD | DEBASHIS SINHA | 03-08-2021 | 01-12-2021
115 | DARJEELING | KHARIBARI WATER SUPPLY SCHEME | SM/00007 | SM/10073 | Augmentation | MVS | 2429/SWSD | HIMADRI DAM & CO. | 21-03-2022 | 04-06-2022 | 300
116 | DARJEELING | KHARIBARI WATER SUPPLY SCHEME | SM/00007 | SM/10073 | Augmentation | MVS | 873/SWSD | PALLAB BHOWAL | 21-07-2022 | 14-10-2022 | 496
117 | DARJEELING | KHARIBARI WATER SUPPLY SCHEME | SM/00007 | SM/09204 | Augmentation | SVS | 1216/SWSD | TUSHAR KANTI SEAL | 01-11-2021 | 26-11-2021 | 451
118 | DARJEELING | KHARIBARI WATER SUPPLY SCHEME | SM/00007 | SM/10073 | Augmentation | MVS | 872/SWSD | PALLAB BHOWAL | 21-07-2022 | 17-01-2023 | 474
119 | DARJEELING | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/16753 |  | New | MVS | 1159/SWSD | RAMESH KUMAR AGARWAL & CO | 09-08-2023 | 05-04-2024 | 1475
120 | DARJEELING | KOLBONG KHASMAHAL PWSS | SM/15840 |  | New | SVS | 189/NKWSMD | SRINIWAS AGARWAL | 04-05-2023 | 31-10-2023
121 | DARJEELING | Lahugaon Bidhannagar & Adj. Mouzas W/S Scheme | SM/02990 | SM/10025 | Augmentation | MVS | 867/SWSD | PALLAB BHOWAL | 21-07-2022 | 17-01-2023 | 207
122 | DARJEELING | Lahugaon Bidhannagar & Adj. Mouzas W/S Scheme | SM/02990 | SM/10025 | Augmentation | MVS | 2376/SWSD | FAIRDEAL ASSOCIATES | 24-01-2023 | 12-08-2023 | 717
123 | DARJEELING | Lalman Water Supply Scheme | SM/01744 | SM/07216 | Retrofitting | MVS | 708/SWSD | M/S UTPAL CHAKRABORTY & CO. | 03-08-2021 | 01-11-2021 | 433
124 | DARJEELING | Lalman Water Supply Scheme | SM/01744 | SM/07038 | Retrofitting | SVS | 706/SWSD | RAJEEV RANJAN OJHA | 03-08-2021 | 01-12-2021 | 289
125 | DARJEELING | Lalman Water Supply Scheme | SM/01744 | SM/12807 | Augmentation | MVS | 649/SWSD | S.G.CONSTRUCTION. | 15-06-2023 | 10-02-2024 | 3
126 | DARJEELING | Lalman Water Supply Scheme | SM/01744 | SM/07038 | Retrofitting | SVS | 1009/SWSD | SEBU CHAKRABORTY | 10-09-2021 | 25-09-2021 | 102
127 | DARJEELING | LAMAGAON PIPED WATER SUPPLY SCHEME. | SM/15868 |  | New | SVS | 221/NKWSMD | TULSI NIROLA | 10-05-2023 | 09-05-2024
128 | DARJEELING | Lamahatta 8th & 9th Mile Piped Water Supply Scheme [GTA] | SM/05398 | SM/10261 | Retrofitting | MVS | 123/EE/DD/PHED | SHREE VAISHNO ENTERPRISES | 10-02-2021 | 10-02-2022
129 | DARJEELING | LATPANICHAR PIPED WATER SUPPLY SCHEME | SM/16162 |  | New | MVS | 120/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 28-04-2023 | 25-10-2023
130 | DARJEELING | LODHAMA PIPED WATER SUPPLY SCHEME. | SM/15872 |  | New | SVS | 88/NKWSMD | KAMAL AND COMPANY | 27-04-2023 | 24-10-2023
131 | DARJEELING | LOHAGARH WATER SUPPLY SCHEME | SM/09426 |  | New | SVS | 459/NKWSMD | SHREE VAISHNO ENTERPRISES | 14-01-2022 | 14-04-2022
132 | DARJEELING | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME | SM/16159 |  | New | SVS | 415/NKWSMD | HARI PRASAD CHETTRI | 05-06-2023 | 02-12-2023
133 | DARJEELING | M.M.TERAI PIPED WATER SUPPLY SCHEME | SM/11775 |  | New | SVS | 2094/SWSD | SUDIP BASAK | 22-12-2022 | 07-03-2023 | 350
134 | DARJEELING | MADHYA BANSGAON WATER SUPPLY SCHEME | SM/00005 | SM/07034 | Retrofitting | SVS | 692/SWSD | M/S G.C. CONSTRUCTION & CO. | 02-08-2021 | 16-09-2021
135 | DARJEELING | MADHYA BANSGAON WATER SUPPLY SCHEME | SM/00005 | SM/07035 | Retrofitting | SVS | 693/SWSD | KAMAL GHOSH | 02-08-2021 | 06-09-2021
136 | DARJEELING | MADHYA BANSGAON WATER SUPPLY SCHEME | SM/00005 | SM/07035 | Retrofitting | SVS | 942/SWSD | SEBU CHAKRABORTY | 14-08-2020 |  | 100
137 | DARJEELING | MADHYA BANSGAON WATER SUPPLY SCHEME | SM/00005 | SM/10724 | Augmentation | SVS | 1130/SWSD | UNIBRO INFRASERV PRIVATE LIMITED | 07-08-2023 | 18-04-2024
138 | DARJEELING | MADHYA BANSGAON WATER SUPPLY SCHEME | SM/00005 | SM/07034 | Retrofitting | SVS | 1263/SWSD | NARENDRA KUMAR | 14-08-2020
139 | DARJEELING | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME | SM/15894 |  | New | SVS | 122/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 28-04-2023 | 25-10-2023
140 | DARJEELING | MAHAL DIRAM TEA GARDEN PWSS | SM/13623 |  | New | SVS | 2655/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 28-02-2023 | 27-08-2023
141 | DARJEELING | MAHANADI FOREST PIPED WATER SUPPLY SCHEME | SM/15648 |  | New | SVS | 439/NKWSMD | RUKMANI ENGINEERING WORKS | 07-06-2023 | 04-12-2023
142 | DARJEELING | MAJUA PIPED WATER SUPPLY SCHEME. | SM/15874 |  | New | SVS | 124/NKWSMD | DENDUP BHUTIA AND COMPANY | 28-04-2023 | 25-10-2023
143 | DARJEELING | Mandalaguri Water Supply Scheme | SM/08096 | SM/12799 | Augmentation | SVS | 1081/SWSD | M/S BIJAN KUMAR DUTTA | 02-08-2023 | 14-03-2024 | 867
144 | DARJEELING | Mandila Jhar Piped Water Supply Scheme. | SM/18784 |  | New | SVS | 1812/SWSD | KRISHNA TRADING CO. | 03-10-2023 | 30-05-2024 | 239
145 | DARJEELING | MANEDARA PIPED WATER SUPPLY SCHEME. | SM/15885 |  | New | SVS | 437/NKWSMD | ALLIED INSTRUMENTS | 07-06-2023 | 02-02-2024
146 | DARJEELING | MANGALSING AND ADJ RURAL PIPED WATER SUPPLY SCHEME | SM/01132 | SM/07029 | Retrofitting | MVS | 1282/SWSD | NARAYAN CH GHOSH | 14-08-2020 |  | 182
147 | DARJEELING | MANGALSING AND ADJ RURAL PIPED WATER SUPPLY SCHEME | SM/01132 | SM/12773 | Augmentation | MVS | 868/SWSD | M/S DOLPHIN CONSTRUCTION CO | 14-07-2023 | 10-01-2024 | 626
148 | DARJEELING | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) | SM/13440 |  | New | MVS | 2504/SWSD | BUDDHADEV NAG | 10-02-2023 | 11-05-2023 | 588
149 | DARJEELING | MATIGARAHAT WATER SUPPLY SCHEME | SM/00132 | SM/14517 | Augmentation | MVS | 1082/SWSD | SRINIWAS AGARWAL | 02-08-2023 | 13-05-2024 | 706
150 | DARJEELING | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. | SM/10790 |  | New | SVS | 608/NKWSMD | M/S KAMAK ENGINEERS AND CO. | 26-05-2022 | 21-01-2023
151 | DARJEELING | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. | SM/10790 | SM/18879 | Augmentation | SVS | 2228/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 09-12-2024 | 07-06-2025
152 | DARJEELING | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | SM/10819 |  | New | MVS | 826/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 30-06-2022 | 25-02-2023
153 | DARJEELING | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | SM/10788 |  | New | MVS | 607/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 26-05-2022 | 21-01-2023
154 | DARJEELING | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | SM/10789 |  | New | SVS | 608/NKWSMD | M/S KAMAK ENGINEERS AND CO. | 26-05-2022 | 21-01-2023
155 | DARJEELING | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12751 |  | New | MVS | 1977/SWSD | EASHAN POLYMERS PRIVATE LIMITED | 26-10-2023 | 23-05-2024 | 757
156 | DARJEELING | MONGPOO CINKONA PLANTATION, ROLAK & LONKU KHASMAHAL PWSS | SM/17191 |  | New | MVS | 98/NKWSMD | VAISHNO CONSTRUCTION | 28-04-2023 | 25-10-2023
157 | DARJEELING | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. | SM/15878 |  | New | SVS | 119/NKWSMD | SAGARMATHA CONSTRUCTION CO. | 28-04-2023 | 25-10-2023
158 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 850/SWSD | UJJWAL ROY | 21-07-2022 | 04-10-2022 | 472
159 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 1405/SWSD | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 21-08-2023 | 19-11-2023 | 74
160 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 2074/SWSD | KAMIRUL SK & CO | 13-01-2023 | 08-04-2023 | 851
161 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 848/SWSD | BUDDHADEV NAG | 21-07-2022 | 29-09-2022 | 507
162 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 847/SWSD | M/S G.C. CONSTRUCTION & CO. | 21-07-2022 | 04-10-2022 | 465
163 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 2438/SWSD | DEBRAJ ENTERPRISE | 21-03-2022 | 14-06-2022 | 107
164 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 37/SWSD | SUBIR CH. CHOWDHURY | 07-04-2022 | 16-07-2022 | 853
165 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 849/SWSD | AKASH ENTERPRISE | 21-07-2022 | 14-10-2022 | 365
166 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 869/SWSD | NARAYAN CH GHOSH | 21-07-2022 | 04-10-2022 | 488
167 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 859/SWSD | PALLAB BHOWAL | 21-07-2022 | 19-10-2022 | 929
168 | DARJEELING | NAXALBARI WATER SUPPLY SCHEME | SM/00133 | SM/10183 | Augmentation | MVS | 38/SWSD | ARUN KUMAR SHRIVASTAVA | 07-04-2022 | 16-07-2022 | 115
169 | DARJEELING | Nichitpur Piped Water Supply Scheme | SM/13438 |  | New | SVS | 643/SWSD | U.K CONSTRUCTIONS | 15-06-2023 | 28-09-2023 | 264
170 | DARJEELING | Nipania Piped water Supply Scheme. | SM/10815 | SM/18881 | Augmentation | MVS | 2228/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 09-12-2024 | 07-06-2025
171 | DARJEELING | Nipania Piped water Supply Scheme. | SM/10815 |  | New | MVS | 825/NKWSMD | M/S KAMAK ENGINEERS AND CO. | 30-06-2022 | 25-02-2023
172 | DARJEELING | Omi Piped Water Supply Scheme | SM/06081 | SM/07426 | Retrofitting | MVS | 1085/SWSD | UJJWAL ROY | 18-12-2020 | 22-01-2021 | 37
173 | DARJEELING | Omi Piped Water Supply Scheme | SM/06081 | SM/07426 | Retrofitting | MVS | 694/SWSD | S.K. BANIK | 02-08-2021 | 01-09-2021 | 650
174 | DARJEELING | Omi Piped Water Supply Scheme | SM/06081 | SM/07426 | Retrofitting | MVS | 1085/SWSD | UJJWAL ROY | 18-12-2020 | 22-01-2021 | 587
175 | DARJEELING | PANIGHATA Piped Water Supply Scheme | SM/16144 |  | New | SVS | 110/NKWSMD | YAMA CONSTRUCTIONS LLP | 28-04-2023 | 25-10-2023
176 | DARJEELING | PANTHABARI FOREST Piped Water Supply Scheme | SM/16143 |  | New | SVS | 32/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 17-04-2023 | 16-07-2023
177 | DARJEELING | Paschim Madati Piped Water Supply Scheme | SM/05464 | SM/07031 | Retrofitting | SVS | 1524/ SWSD | SUBIR CH. CHOWDHURY | 14-08-2020 |  | 12
178 | DARJEELING | Paschim Madati Piped Water Supply Scheme | SM/05464 | SM/12037 | Augmentation | SVS | 2366/SWSD | AKASH ENTERPRISE | 24-01-2023 | 09-04-2023 | 33
179 | DARJEELING | Paschim Madati Piped Water Supply Scheme | SM/05464 | SM/12037 | Augmentation | SVS | 1829/SWSD | VIJAY KUMAR ARORA | 13-01-2022 | 07-02-2022 | 118
180 | DARJEELING | Paschim Madati Piped Water Supply Scheme | SM/05464 | SM/07031 | Retrofitting | SVS | 1081/SWSD | M/S G.C. CONSTRUCTION & CO. | 18-12-2020 | 27-01-2021
181 | DARJEELING | Paschim Madati Piped Water Supply Scheme | SM/05464 | SM/07032 | Retrofitting | SVS | 1082/SWSD | M/S G.C. CONSTRUCTION & CO. | 18-12-2020 | 17-01-2021
182 | DARJEELING | Pathar Hirhirar Chhat Piped Water Supply Scheme | SM/13508 |  | New | MVS | 859/SWSD | SUBIR CH. CHOWDHURY | 12-07-2023 | 22-02-2024 | 764
183 | DARJEELING | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15655 |  | New | SVS | 116/NKWSMD | SRINIWAS AGARWAL | 28-04-2023 | 27-04-2024
184 | DARJEELING | Pipe water supply scheme for 14th mile under Kurseong Division, PHED, GTA | SM/10193 | SM/11336 | Retrofitting | SVS | 800/NKWSMD | PREM KUMAR PRADHAN | 30-06-2022 | 29-08-2022
185 | DARJEELING | Pipe water supply scheme for Jangpana under Kurseong Division, PHED, GTA | SM/10189 | SM/11332 | Retrofitting | SVS | 837/KWSMD | MS JAGANNATH PRASAD | 30-06-2022 | 29-08-2022
186 | DARJEELING | Piped water supply scheme for Singtam Tea Garden | SM/11338 |  | New | SVS | 687/NKWSMD | NIMA SHERPA | 12-07-2023 | 08-01-2024
187 | DARJEELING | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11351 |  | New | SVS | 984/NKWSMD | PRASANT NIROLA | 12-07-2022 | 10-09-2022
188 | DARJEELING | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11344 |  | New | SVS | 955/NKWSMD | LAL BAHADUR THAPA | 12-07-2022 | 10-09-2022
189 | DARJEELING | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11349 |  | New | SVS | 986/NKWSMD | PHURBA RUMBA | 23-08-2023 | 22-10-2023
190 | DARJEELING | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11345 |  | New | SVS | 956/NKWSMD | RAMESH THAPA | 12-07-2022 | 10-09-2022
191 | DARJEELING | Piped Water Supply Scheme at Goethals Siding and Upper Kharay Busty with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11352 |  | New | MVS | 1445/NKWSMD | NIPENDRA TAMANG | 28-09-2022 | 27-11-2022
192 | DARJEELING | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11347 |  | New | SVS | 954/NKWSMD | BIRU KHAWAS | 12-07-2022 | 10-09-2022
193 | DARJEELING | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11348 |  | New | SVS | 1748/NKWSMD | BITIS PRADHAN AND BROTHERS | 25-11-2022 | 24-01-2023
194 | DARJEELING | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED | SM/19038 |  | New | SVS | 3/NKWSMD | YAMA CONSTRUCTIONS LLP | 03-01-2024 | 02-01-2025
195 | DARJEELING | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11346 |  | New | SVS | 958/NKWSMD | NABIN RAI | 12-07-2022 | 10-09-2022
196 | DARJEELING | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11350 |  | New | SVS | 957/NKWSMD | PHURBA RUMBA | 12-07-2022 | 10-09-2022
197 | DARJEELING | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. | SM/11353 |  | New | SVS | 953/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 12-07-2022 | 10-09-2022
198 | DARJEELING | Piped water supply scheme for Daragoan Lekharga. | SM/10836 |  | New | SVS | 613/NKWSMD | SUNIL SHARMA | 26-05-2022 | 25-07-2022
199 | DARJEELING | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/16628 |  | New | SVS | 104/NKWSMD | SHAKTI CONSTRUCTION | 28-04-2023 | 27-04-2024
200 | DARJEELING | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/15884 |  | New | SVS | 718/NKWSMD | GARGO TRADERS | 18-07-2023 | 17-07-2024
201 | DARJEELING | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/16352 |  | New | SVS | 107/NKWSMD | SRINIWAS AGARWAL | 28-04-2023 | 24-12-2023
202 | DARJEELING | Piped water supply scheme for Kolbong | SM/10834 |  | New | SVS | 610/NKWSMD | HEMRAJ NIROLA | 26-05-2022 | 22-11-2022
203 | DARJEELING | Piped water supply scheme for Kolbong | SM/10834 |  | New | SVS | 610/NKWSMD | HEMRAJ NIROLA | 26-05-2022 | 22-11-2022
204 | DARJEELING | Piped water supply scheme for Lower Bish Acre, Ghayabari. | SM/11397 |  | New | SVS | 2002/NKWSMD | KAMAL PRADHAN | 23-12-2022 | 23-03-2023
205 | DARJEELING | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | SM/16535 |  | New | SVS | 92/NKWSMD | VINAYAK CONSTRUCTION | 27-04-2023 | 26-04-2024
206 | DARJEELING | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | SM/10835 |  | New | MVS | 1119/NKWSMD | AMRIT KUMAR SUBBA | 05-08-2022 | 01-02-2023
207 | DARJEELING | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | SM/10837 |  | New | SVS | 614/NKWSMD | KAMAKHYA ENTERPRISES | 26-05-2022 | 25-07-2022
208 | DARJEELING | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | SM/10837 |  | New | SVS | 614/NKWSMD | KAMAKHYA ENTERPRISES | 26-05-2022 | 25-07-2022
209 | DARJEELING | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 |  | New | SVS | 628/NKWSMD | HARI PRASAD CHETTRI | 26-05-2022 | 25-07-2022
210 | DARJEELING | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 |  | New | SVS | 628/NKWSMD | HARI PRASAD CHETTRI | 26-05-2022 | 25-07-2022
211 | DARJEELING | Piped water supply scheme for Singbuli factory gaon | SM/10831 |  | New | SVS | 611/NKWSMD | M/S JAI BHAWANI CONSTRUCTION CO | 26-05-2022 | 25-07-2022
212 | DARJEELING | Piped water supply scheme for Thulung Gaon | SM/10830 |  | New | SVS | 612/NKWSMD | SEWARO CONSTRUCTION COMPANY | 26-05-2022 | 25-07-2022
213 | DARJEELING | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | SM/18317 |  | New | SVS | 671/NKWSMD | YAMA CONSTRUCTIONS LLP | 12-07-2023 | 11-07-2024
214 | DARJEELING | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) | SM/16386 |  | New | SVS | 2736/NKWSMD | M/S. ASHOK KUMAR PERIWAL | 03-03-2023 | 02-03-2024
215 | DARJEELING | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD | SM/18727 |  | New | MVS | 987/NKWSMD | GARGO TRADERS | 23-08-2023 | 22-08-2024
216 | DARJEELING | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (GUNAWAR) (PART) | SM/15649 |  | New | SVS | 1289/NKWSMD | SHAKTI CONSTRUCTION | 17-10-2023 | 13-06-2024
217 | DARJEELING | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | SM/15897 |  | New | MVS | 411/NKWSMD | RAMESH AGARWAL | 05-06-2023 | 31-01-2024
218 | DARJEELING | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/15876 |  | New | SVS | 682/NKWSMD | RAMESH AGARWAL | 12-07-2023 | 11-07-2024
219 | DARJEELING | Purba Bansgaon Piped Water Supply Scheme | SM/05388 | SM/07215 | Retrofitting | SVS | 696/SWSD | AKASH ENTERPRISE | 02-08-2021 | 06-09-2021 | 312
220 | DARJEELING | Purba Bansgaon Piped Water Supply Scheme | SM/05388 | SM/07040 | Retrofitting | SVS | 1007/SWSD | KAMAL GHOSH | 11-12-2020 | 10-01-2021
221 | DARJEELING | Purba Madati Piped Water Supply Scheme | SM/05488 | SM/07043 | Retrofitting | SVS | 1828/SWSD | BIMAN DUTTA | 13-01-2022 | 07-02-2022
222 | DARJEELING | Purba Madati Piped Water Supply Scheme | SM/05488 | SM/07070 | Retrofitting | SVS | 1079/SWSD | SHRI ANUP BASU | 18-12-2020 | 27-01-2021 | 286
223 | DARJEELING | Purba Madati Piped Water Supply Scheme | SM/05488 | SM/07043 | Retrofitting | SVS | 1080/SWSD | SUBIR CH. CHOWDHURY | 18-12-2020 | 22-01-2021
224 | DARJEELING | Purba Madati Piped Water Supply Scheme | SM/05488 | SM/07043 | Retrofitting | SVS | 1523/SWSD | DEBASHIS SINHA | 14-08-2020
225 | DARJEELING | PWS scheme for 3rd Division Soom TE - GP - Soom Singtam | SM/08938 | SM/10767 | Retrofitting | SVS | 493/NKWSMD | MS JAGANNATH PRASAD | 24-05-2022 | 23-07-2022
226 | DARJEELING | PWS Scheme for Augmentation and Extension of 3rd Mile village | SM/10325 | SM/11380 | Retrofitting | SVS | 941/NKWSMD | BIMLA GURUNG | 12-07-2022 | 10-09-2022
227 | DARJEELING | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12368 |  | New | MVS | 2362/NKWSMD | YAMA CONSTRUCTIONS LLP | 01-02-2023 | 01-02-2024
228 | DARJEELING | PWS scheme for Barbotia (upper & lower) GP Bloomfield Risheehat | SM/08932 | SM/10773 | Retrofitting | SVS | 498/NKWSMD | PROSENJIT BASAK | 24-05-2022 | 23-07-2022
229 | DARJEELING | PWS Scheme for Bijuwa gaon | SM/10328 | SM/11389 | Retrofitting | SVS | 939/NKWSMD | KIRAN NIROLA | 12-07-2022 | 10-09-2022
230 | DARJEELING | PWS scheme for Bothay Goth GP Soom Singtam | SM/08931 | SM/10766 | Retrofitting | SVS | 524/NKWSMD | RAMESH PRADHAN AND CO. | 25-05-2022 | 24-07-2022
231 | DARJEELING | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | SM/18640 |  | New | MVS | 881/NKWSMD | GARGO TRADERS | 03-08-2023 | 02-08-2024
232 | DARJEELING | PWS scheme for Dhupighari Bloomfield GP Bloomfiled Risheehat | SM/08930 | SM/10772 | Retrofitting | SVS | 497/NKWSMD | KIRAN SUBBA | 24-05-2022 | 23-07-2022
233 | DARJEELING | PWS Scheme for Edenvale Tea Garden | SM/18710 |  | New | SVS | 894/NKWSMD | YAMA CONSTRUCTIONS LLP | 07-08-2023 | 03-02-2024
234 | DARJEELING | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | SM/15650 |  | New | SVS | 2656/NKWSMD | ABHINAY CHETTRI | 28-02-2023 | 27-08-2023
235 | DARJEELING | PWS Scheme for Glenburn Singritam and Enroute Villages | SM/10333 | SM/11393 | Retrofitting | MVS | 686/NKWSMD | PUSHKAR GURUNG | 12-07-2023 | 08-01-2024
236 | DARJEELING | PWS scheme for Gorkhey FV GP Daragoan Srikhola | SM/08929 | SM/10770 | Retrofitting | SVS | 495/NKWSMD | NIMA SHERPA | 24-05-2022 | 23-07-2022
237 | DARJEELING | PWS scheme for Gorukatta GP Naya Nore | SM/08933 | SM/10768 | Retrofitting | SVS | 494/NKWSMD | MS D.R ENTERPRISES | 24-05-2022 | 23-07-2022
238 | DARJEELING | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA | SM/18917 |  | New | MVS | 1746/NKWSMD | DAJUBHAI CONSTRUCTION | 19-09-2024 | 19-09-2025
239 | DARJEELING | PWS scheme for Lingsaybong GP Lodhoma II | SM/08926 | SM/10822 | Retrofitting | SVS | 629/NKWSMD | HARI PRASAD CHETTRI | 26-05-2022 | 25-07-2022
240 | DARJEELING | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. | SM/12367 |  | New | SVS | 2471/NKWSMD | SHAKTI CONSTRUCTION | 06-02-2023 | 06-02-2024
241 | DARJEELING | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | SM/11399 |  | New | SVS | 187/NKWSMD | PREM CHANDRA RAI | 04-05-2023 | 30-12-2023
242 | DARJEELING | PWS Scheme for Marybong | SM/10327 | SM/11379 | Retrofitting | SVS | 943/NKWSMD | MANI KUMAR CHHETRI | 12-07-2022 | 10-09-2022
243 | DARJEELING | PWS Scheme for Mirik Khasmahal | SM/18650 |  | New | SVS | 918/NKWSMD | SHAKTI CONSTRUCTION | 11-08-2023 | 10-08-2024
244 | DARJEELING | PWS Scheme for Musey Khola Gaon to Dokan Dhura | SM/10324 | SM/11818 | Retrofitting | SVS | 1306/NKWSMD | JANG BAHADUR GURUNG | 31-10-2023 | 30-12-2023
245 | DARJEELING | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | SM/11398 |  | New | SVS | 2351/NKWSMD | SHAKTI CONSTRUCTION | 01-02-2023 | 31-07-2023
246 | DARJEELING | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/12366 |  | New | MVS | 2494/NKWSMD | VINAYAK CONSTRUCTION | 09-02-2023 | 09-02-2024
247 | DARJEELING | PWS scheme for Samadhan GP Srikhola Daragoan | SM/08924 | SM/10771 | Retrofitting | SVS | 496/NKWSMD | SUNIL SHARMA | 24-05-2022 | 23-07-2022
248 | DARJEELING | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | SM/15895 |  | New | SVS | 434/NKWSMD | SRINIWAS AGARWAL | 06-06-2023 | 03-12-2023
249 | DARJEELING | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | SM/11396 |  | New | SVS | 2082/NKWSMD | SWAD CONSTRUCTION | 10-01-2023 | 09-07-2023
250 | DARJEELING | PWS scheme for Soom 1st Division GP Soom Singtam | SM/08937 | SM/10774 | Retrofitting | SVS | 556/NKWSMD | NAVRATNA CONSTRUCTION CO | 26-05-2022 | 25-07-2022
251 | DARJEELING | PWS scheme for Soom 2nd Division GP Soom Singtam | SM/08936 | SM/10765 | Retrofitting | SVS | 555/NKWSMD | NAVRATNA CONSTRUCTION CO | 26-05-2022 | 25-07-2022
252 | DARJEELING | PWS scheme for St. Mary's & Goethals | SM/15661 |  | New | MVS | 2670/NKWSMD | SITA SHARMA | 01-03-2023 | 28-08-2023
253 | DARJEELING | PWS Scheme for Takdah Bazar | SM/10330 | SM/11392 | Retrofitting | SVS | 950/NKWSMD | NAVRATNA CONSTRUCTION CO | 12-07-2022 | 08-01-2023
254 | DARJEELING | PWS Scheme for Toryak Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/19033 |  | New | SVS | 1328/NKWSMD | SHAKTI CONSTRUCTION | 03-11-2023 | 02-11-2024
255 | DARJEELING | PWS scheme for Tower Dara / goan GP Relling | SM/08927 | SM/11383 | Retrofitting | SVS | 1443/NKWSMD | SUMAN PRADHAN | 28-09-2022 | 27-11-2022
256 | DARJEELING | PWS scheme for upper Bansbotay (Funded by WBSEDCL) GP, Lodhoma I | SM/08923 | SM/10780 | Retrofitting | SVS | 592/NKWSMD | HARI PRASAD CHETTRI | 26-05-2022 | 25-07-2022
257 | DARJEELING | PWS scheme for upper Bansbotay (Funded by WBSEDCL) GP, Lodhoma I | SM/08923 | SM/11384 | Retrofitting | SVS | 849/NKWSMD | BIJAY CHETTRI | 27-07-2023 | 25-09-2023
258 | DARJEELING | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. | SM/11395 |  | New | SVS | 186/NKWSMD | PREM CHANDRA RAI | 04-05-2023 | 31-10-2023
259 | DARJEELING | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | SM/10802 |  | New | SVS | 605/NKWSMD | NAVRATNA CONSTRUCTION CO | 26-05-2022 | 22-11-2022
260 | DARJEELING | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10809 |  | New | SVS | 2083/NKWSMD | MS CHAMLING CONSTRUCTION | 10-01-2023 | 10-04-2023
261 | DARJEELING | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | SM/10799 |  | New | SVS | 601/NKWSMD | HIMALI CONSTRUCTION COMPANY | 26-05-2022 | 25-07-2022
262 | DARJEELING | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | SM/10807 |  | New | SVS | 603/NKWSMD | HARI PRASAD CHETTRI | 26-05-2022 | 25-07-2022
263 | DARJEELING | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | SM/10806 |  | New | SVS | 606/NKWSMD | NARESH RAI | 26-05-2022 | 25-07-2022
264 | DARJEELING | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA | SM/10828 |  | New | SVS | 831/NKWSMD | BIKRAM RAI | 30-06-2022 | 28-09-2022
265 | DARJEELING | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA | SM/10827 |  | New | SVS | 609/NKWSMD | NAVRATNA CONSTRUCTION CO | 26-05-2022 | 22-11-2022
266 | DARJEELING | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA | SM/10805 |  | New | SVS | 1749/NKWSMD | ROSHAN BISWAKARMA | 25-11-2022 | 23-02-2023
267 | DARJEELING | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | SM/10803 |  | New | SVS | 602/NKWSMD | ROSHAN BISWAKARMA | 26-05-2022 | 25-07-2022
268 | DARJEELING | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA | SM/10826 |  | New | MVS | 1121/NKWSMD | PREM CHANDRA RAI | 05-08-2022 | 01-02-2023
269 | DARJEELING | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA | SM/10800 |  | New | SVS | 1653/NKWSMD | ABHINAY CHETTRI | 04-11-2022 | 02-02-2023
270 | DARJEELING | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA | SM/10804 |  | New | SVS | 1988/NKWSMD | KUMAR CHHETRI | 23-12-2022 | 21-06-2023
271 | DARJEELING | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA | SM/10810 |  | New | SVS | 600/NKWSMD | NARAYAN THAPA | 26-05-2022 | 24-08-2022
272 | DARJEELING | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | SM/10798 |  | New | SVS | 1117/NKWSMD | BOBBY PRADHAN | 05-08-2022 | 01-02-2023
273 | DARJEELING | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10808 |  | New | SVS | 604/NKWSMD | KARUNAMAYA ENTERPRISES | 26-05-2022 | 22-11-2022
274 | DARJEELING | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA | SM/10801 |  | New | SVS | 1118/NKWSMD | PREM CHANDRA RAI | 05-08-2022 | 01-02-2023
275 | DARJEELING | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | SM/10825 |  | New | SVS | 836/NKWSMD | AJAY RAI | 30-06-2022 | 28-09-2022
276 | DARJEELING | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | SM/10829 |  | New | SVS | 1120/NKWSMD | BIKRAM RAI | 05-08-2022 | 01-02-2023
277 | DARJEELING | Rangali Gram Panchayat Village Water Supply Scheme (For Rangali Mouza) | SM/03076 | SM/13429 | Augmentation | SVS | 2918/SWSD | M/S BIRAT CONSTRUCTION | 24-03-2023 | 10-10-2023 | 631
278 | DARJEELING | RANIDANGA RANGAPANI WATER SUPPLY SCHEME | SM/00004 | SM/07036 | Retrofitting | MVS | 1265/SWSD | M/S UTPAL CHAKRABORTY & CO. | 14-08-2020
279 | DARJEELING | RANIDANGA RANGAPANI WATER SUPPLY SCHEME | SM/00004 | SM/07036 | Retrofitting | MVS | 1266/SWSD | M/S UTPAL CHAKRABORTY & CO. | 14-08-2020
280 | DARJEELING | RANIDANGA RANGAPANI WATER SUPPLY SCHEME | SM/00004 | SM/07037 | Retrofitting | MVS | 1262/SWSD | M/S UTPAL CHAKRABORTY & CO. | 14-08-2020
281 | DARJEELING | RANIDANGA RANGAPANI WATER SUPPLY SCHEME | SM/00004 | SM/18637 | Augmentation | MVS | 1240/SWSD | THE MAHADEV CONSTRUCTION | 16-08-2023 | 12-05-2024 | 252
282 | DARJEELING | RELLING PIPED WATER SUPPLY SCHEME. | SM/15879 |  | New | SVS | 426/NKWSMD | NIMA SHERPA | 06-06-2023 | 05-06-2024
283 | DARJEELING | RESHOP BAZAR PIPED WATER SUPPLY SCHEME | SM/15882 |  | New | SVS | 123/NKWSMD | VAISHNO CONSTRUCTION | 28-04-2023 | 24-12-2023
284 | DARJEELING | RIMBICK Piped Water Supply Scheme | SM/16123 |  | New | SVS | 681/NKWSMD | NIMA SHERPA | 12-07-2023 | 11-07-2024
285 | DARJEELING | RIMBICK WATER SUPPLY SCHEME | SM/09427 |  | New | SVS | 8/NKWSMD | NIMA SHERPA | 04-04-2022 | 01-10-2022
286 | DARJEELING | RIMBICK WATER SUPPLY SCHEME | SM/09427 |  | New | SVS | 8/NKWSMD | NIMA SHERPA | 04-04-2022 | 01-10-2022
287 | DARJEELING | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME | SM/16160 |  | New | SVS | 121/NKWSMD | MS. SURYA I PVT. LTD COMPANY | 28-04-2023 | 24-12-2023
288 | DARJEELING | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/16161 |  | New | SVS | 101/NKWSMD | HARI PRASAD CHETTRI | 28-04-2023 | 25-10-2023
289 | DARJEELING | RONGCHONG AND LABDA PWSS | SM/18729 |  | New | MVS | 936/NKWSMD | VINAYAK CONSTRUCTION | 16-08-2023 | 15-08-2024
290 | DARJEELING | SALBERI WATER SUPPLY SCHEME | SM/00819 | SM/09830 | Augmentation | MVS | 2080/SWSD | HIMADRI DAM & CO. | 03-02-2022 | 19-04-2022 | 410
291 | DARJEELING | SALBERI WATER SUPPLY SCHEME | SM/00819 | SM/09830 | Augmentation | MVS | 2077/SWSD | SUDIP BASAK | 03-02-2022 | 04-04-2022 | 47
292 | DARJEELING | SALBERI WATER SUPPLY SCHEME | SM/00819 | SM/09830 | Augmentation | MVS | 2078/SWSD | M/S G.C. CONSTRUCTION & CO. | 03-02-2022 | 04-04-2022 | 441
293 | DARJEELING | SALBERI WATER SUPPLY SCHEME | SM/00819 | SM/09830 | Augmentation | MVS | 2079/SWSD | BUDDHADEV NAG | 03-02-2022 | 15-03-2022 | 198
294 | DARJEELING | SALBERI WATER SUPPLY SCHEME | SM/00819 | SM/09830 | Augmentation | MVS | 2202/SWSD | SUBIR CH. CHOWDHURY | 17-02-2022 | 16-08-2022 | 333
295 | DARJEELING | SHYAMDHAN WATER SUPPLY SCHEME | SM/00137 | SM/07046 | Retrofitting | MVS | 690/SWSD | SHIVNATH DEY | 02-08-2021 | 22-08-2021 | 229
296 | DARJEELING | SHYAMDHAN WATER SUPPLY SCHEME | SM/00137 | SM/18421 | Augmentation | MVS | 107/SWSD | M/S YOUNG ASSOCIATES | 15-01-2024 | 02-08-2024 | 222
297 | DARJEELING | SHYAMDHAN WATER SUPPLY SCHEME | SM/00137 | SM/07046 | Retrofitting | MVS | 689/SWSD | BUDDHADEV NAG | 02-08-2021 | 22-08-2021 | 10
298 | DARJEELING | SHYAMDHAN WATER SUPPLY SCHEME | SM/00137 | SM/07046 | Retrofitting | MVS | 1526/ SWSD | PROSANTA KUMAR DAS | 14-08-2020
299 | DARJEELING | SHYAMDHAN WATER SUPPLY SCHEME | SM/00137 | SM/07046 | Retrofitting | MVS | 1219/SWSD | M/S SHIVAJI ROY | 01-11-2021 | 21-11-2021 | 100
300 | DARJEELING | SHYAMDHAN WATER SUPPLY SCHEME | SM/00137 | SM/18421 | Augmentation | MVS | 1049/SWSD | M/S BIRAT CONSTRUCTION | 28-07-2023 | 13-02-2024 | 97
301 | DARJEELING | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10817 |  | New | SVS | 826/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 30-06-2022 | 25-02-2023
302 | DARJEELING | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10817 | SM/18878 | Augmentation | SVS | 2228/NKWSMD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 09-12-2024 | 07-06-2025
303 | DARJEELING | SINGALILA FOREST PWSS | SM/16771 |  | New | SVS | 87/NKWSMD | NIMA SHERPA | 27-04-2023 | 26-04-2024
304 | DARJEELING | Singla Tea Garden water supply scheme. | SM/11339 |  | New | SVS | 1289/NKWSMD | VINAYAK CONSTRUCTION | 08-09-2022 | 05-06-2023
305 | DARJEELING | Singla Tea Garden water supply scheme. | SM/11339 |  | New | SVS | 1289/NKWSMD | VINAYAK CONSTRUCTION | 08-09-2022 | 05-06-2023
306 | DARJEELING | SITTONG KHASMAHAL PWSS | SM/18336 |  | New | SVS | 850/NKWSMD | HIMALAYAN CONSTRUCTION | 27-07-2023 | 26-07-2024
307 | DARJEELING | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme | SM/16385 |  | New | MVS | 676/NKWSMD | SRINIWAS AGARWAL | 12-07-2023 | 11-07-2024
308 | DARJEELING | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | SM/18723 |  | New | MVS | 1288/NKWSMD | INTERIOR'S NEST | 17-10-2023 | 16-10-2024
309 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND | SM/10470 |  | New | MVS | 753/SWSD | ROY ENGINEERS | 08-07-2022 | 06-09-2022 | 1018
310 | DARJEELING | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING | SM/10824 |  | New | MVS | 753/SWSD | ROY ENGINEERS | 08-07-2022 | 06-09-2022 | 938
311 | DARJEELING | Sukhia Pokhri Bajar Piped Water Supply scheme under GTA | SM/05523 | SM/11378 | Retrofitting | SVS | 938/NKWSMD | KAMAKHYA ENTERPRISES | 12-07-2022 | 10-09-2022
312 | DARJEELING | Sukhia Pokhri Bajar Piped Water Supply scheme under GTA | SM/05523 | SM/10258 | Retrofitting | MVS | 123/EE/DD/PHED | SHREE VAISHNO ENTERPRISES | 10-02-2021 | 10-02-2022
313 | DARJEELING | SUKNA PIPED WATER SUPPLY SCHEME | SM/15653 |  | New | SVS | 2874/NKWSMD | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 23-03-2023 | 19-09-2023
314 | DARJEELING | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | SM/15647 |  | New | SVS | 2873/NKWSMD | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 23-03-2023 | 18-11-2023
315 | DARJEELING | Tarbandha Piped Water Supply Scheme | SM/05944 | SM/15269 | Augmentation | MVS | 333/SWSD | PRADIP GUHA | 08-05-2023 | 07-06-2023 | 438
316 | DARJEELING | Tarbandha Piped Water Supply Scheme | SM/05944 |  |  | MVS | 1280/SWSD | AKASH ENTERPRISE | 14-08-2020
317 | DARJEELING | THAKURGANJ WATER SUPPLY SCHEME | SM/00134 | SM/09827 | Augmentation | MVS | 861/SWSD | BHOLA GHOSH | 21-07-2022 | 09-10-2022 | 55
318 | DARJEELING | THAKURGANJ WATER SUPPLY SCHEME | SM/00134 | SM/09827 | Augmentation | MVS | 2439/SWSD | M/S DEBRAJ ENTERPRISE | 21-03-2022 | 04-06-2022 | 317
319 | DARJEELING | THAKURGANJ WATER SUPPLY SCHEME | SM/00134 | SM/09827 | Augmentation | MVS | 862/SWSD | M/S UTPAL CHAKRABORTY & CO. | 21-07-2022 | 04-10-2022 | 267
320 | DARJEELING | THAKURGANJ WATER SUPPLY SCHEME | SM/00134 | SM/09827 | Augmentation | MVS | 273/SWSD | HIMADRI DAM & CO. | 06-05-2022 | 02-11-2022 | 180
321 | DARJEELING | THAKURGANJ WATER SUPPLY SCHEME | SM/00134 | SM/09827 | Augmentation | MVS | 864/SWSD | SHIVNATH DEY | 21-07-2022 | 25-08-2022 | 130
322 | DARJEELING | THAKURGANJ WATER SUPPLY SCHEME | SM/00134 | SM/09827 | Augmentation | MVS | 863/SWSD | AKASH ENTERPRISE | 21-07-2022 | 19-10-2022 | 330
323 | DARJEELING | Trihana T G Mouza ( Upper Bagdogra Gram Panchaayat) water supply scheme | SM/03173 | SM/12748 | Augmentation | SVS | 1675/SWSD | S.K. BANIK | 10-11-2022 | 24-01-2023 | 406
324 | DARJEELING | Trihana T G Mouza ( Upper Bagdogra Gram Panchaayat) water supply scheme | SM/03173 | SM/12748 | Augmentation | SVS | 1690/SWSD | S.K. BANIK | 19-09-2023 | 03-11-2023 | 143
325 | DARJEELING | Tukbar Tea Garden Piped Water Supply scheme under GTA | SM/05532 | SM/13352 | Retrofitting | SVS | 1617/NKWSMD | MANI KUMAR CHHETRI | 03-11-2022 | 02-01-2023
326 | DARJEELING | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | SM/16157 |  | New | SVS | 108/NKWSMD | RAMESH AGARWAL | 28-04-2023 | 26-08-2023
327 | DARJEELING | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. | SM/15909 |  | New | SVS | 418/NKWSMD | HARI PRASAD CHETTRI | 05-06-2023 | 02-12-2023
328 | DARJEELING | UTTAR BAGDOGRA WATER SUPPLY SCHEME | SM/00003 | SM/08295 | Retrofitting | SVS | 713/SWSD | HIMADRI DAM & CO. | 03-08-2021 | 01-11-2021
329 | DARJEELING | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | SM/13955 |  | New | SVS | 2152/NKWSMD | VINAYAK CONSTRUCTION | 20-01-2023 | 19-07-2023
330 | DARJEELING | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14148 |  | New | SVS | 2519/NKWSMD | GARGO TRADERS | 15-02-2023 | 15-02-2024
331 | DARJEELING | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | SM/14532 |  | New | SVS | 362/NKWSMD | YAMA CONSTRUCTIONS LLP | 29-05-2023 | 28-05-2024
332 | DARJEELING | Water Supply Scheme for Pauchakulguri & adj. mouzas | SM/03266 | SM/09828 | Augmentation | MVS | 2436/SWSD | U.K CONSTRUCTIONS | 21-03-2022 | 04-06-2022 | 400
333 | DARJEELING | Water Supply Scheme for Pauchakulguri & adj. mouzas | SM/03266 | SM/09828 | Augmentation | MVS | 868/SWSD | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 21-07-2022 | 04-10-2022 | 18
334 | DARJEELING | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | SM/14530 |  | New | SVS | 1279/NKWSMD | SHAKTI CONSTRUCTION | 17-10-2023 | 16-10-2024
335 | DARJEELING | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | SM/11942 |  | New | SVS | 2644/NKWSMD | HIMALAYAN CONSTRUCTION | 24-02-2023 | 23-08-2023
336 | DARJEELING | Water Supply Scheme for Uttar Ramdhan & Adj. Mouzas | SM/03570 | SM/10477 | Augmentation | MVS | 856/SWSD | PALLAB BHOWAL | 21-07-2022 | 29-10-2022 | 150
337 | DARJEELING | Water Supply Scheme for Uttar Ramdhan & Adj. Mouzas | SM/03570 | SM/07049 | Retrofitting | MVS | 1011/SWSD | M/S DEBRAJ ENTERPRISE | 11-12-2020 | 20-01-2021
338 | DARJEELING | Water Supply Scheme for Uttar Ramdhan & Adj. Mouzas | SM/03570 | SM/07049 | Retrofitting | MVS | 1013/SWSD | NARENDRA KUMAR | 11-12-2020 | 15-01-2021
339 | DARJEELING | Water Supply Scheme for Uttar Ramdhan & Adj. Mouzas | SM/03570 | SM/07047 | Retrofitting | MVS | 1010/SWSD | M/S DEBRAJ ENTERPRISE | 11-12-2020 | 15-01-2021
340 | DARJEELING | Water Supply Scheme for Uttar Ramdhan & Adj. Mouzas | SM/03570 | SM/07047 | Retrofitting | MVS | 1009/SWSD | M/S DEBRAJ ENTERPRISE | 11-12-2020 | 10-01-2021
Total | [10 empty] | 51171