## Issued Work Order (JALPAIGURI)
Issued Work Order (JALPAIGURI)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | JALPAIGURI | Aibhil Tea Garden Area Piped Water Supply Scheme | SM/05475 |  |  | MVS | 1283/JD | SUNIL ROY | 18-11-2020 | 17-01-2021
2 | JALPAIGURI | Aibhil Tea Garden Area Piped Water Supply Scheme | SM/05475 |  |  | MVS | 177/JSSD | PRITAM DUTTA | 25-08-2022 | 24-09-2022 | 65
3 | JALPAIGURI | Aibhil Tea Garden Area Piped Water Supply Scheme | SM/05475 |  |  | MVS | 223/JD | SUNIL ROY | 12-02-2021 | 04-03-2021 | 200
4 | JALPAIGURI | Aibhil Tea Garden Area Piped Water Supply Scheme | SM/05475 | SM/17185 | Augmentation | SVS | 366/JD | BARUN KUMAR DUTTA | 26-05-2023 | 24-08-2023 | 137
5 | JALPAIGURI | Ambari Tea Garden Area Piped Water Supply Scheme | SM/05930 | SM/06837 | Retrofitting | SVS | 1279/JD | NEW KUNDU ENTERPRISE | 18-11-2020 | 18-12-2020 | 8
6 | JALPAIGURI | Ambari Tea Garden Area Piped Water Supply Scheme | SM/05930 | SM/06837 | Retrofitting | SVS | 361/RWS | SANDIP BANIK | 08-09-2020 | 23-09-2020
7 | JALPAIGURI | Ambari Tea Garden Area Piped Water Supply Scheme | SM/05930 | SM/06837 | Retrofitting | SVS | 361/RWS | SANDIP BANIK | 08-09-2020 | 23-09-2020
8 | JALPAIGURI | Ambari Tea Garden Area Piped Water Supply Scheme | SM/05930 | SM/06837 | Retrofitting | SVS | 1085//RWS | SANDIP BANIK | 19-09-2023 | 09-10-2023 | 41
9 | JALPAIGURI | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 |  | New | MVS | 29/JD | SUKES BASU MAJUMDAR | 10-04-2023 | 07-10-2023 | 1627
10 | JALPAIGURI | ANGRABHASA WATER SUPPLY SCHEME | SM/00154 | SM/10071 | Augmentation | MVS | 878/JD | M/S R.N. TRADERS | 05-04-2022 | 04-07-2022 | 822
11 | JALPAIGURI | Bagrakote Tea Garden Area Piped Water Supply Scheme. | SM/08874 |  | New | SVS | 351/JD | M/S GARGO TRADERS | 03-02-2022 | 04-05-2022 | 291
12 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 326/JD | MINTU CHAKRABORTY | 02-02-2022 | 03-05-2022 | 992
13 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 325/JD | NARAYAN CHANDRA SAHA | 02-02-2022 | 03-05-2022 | 7
14 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 322/JD | UNIBRO INFRASERV PRIVATE LIMITED | 02-02-2022 | 03-05-2022 | 1136
15 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 483/JD | DREAM CONSTRUCTION | 11-03-2025 | 10-05-2025 | 158
16 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 323/JD | UNIBRO INFRASERV PRIVATE LIMITED | 02-02-2022 | 03-05-2022 | 546
17 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 327/JD | M/S S.G. CONSTRUCTION | 02-02-2022 | 03-05-2022 | 1013
18 | JALPAIGURI | BAIKUR WATER SUPPLY SCHEME | SM/00031 | SM/10089 | Augmentation | MVS | 324/JD | CALCON CONSTRUCTIONS | 02-02-2022 | 03-05-2022 | 897
19 | JALPAIGURI | Bamandanga Tea Garden Area Piped Water Supply Scheme. | SM/06550 |  |  | MVS | 1987/JD | M/S A.B.G. CONSTRUCTION | 03-12-2021 | 02-01-2022 | 1000
20 | JALPAIGURI | BANARHAT BAZAR WATER SUPPLY SCHEME | SM/00025 | SM/10044 | Augmentation | MVS | 2459/JD | PRADIP SAHA | 23-02-2024 | 24-03-2024 | 500
21 | JALPAIGURI | BANARHAT BAZAR WATER SUPPLY SCHEME | SM/00025 | SM/10044 | Augmentation | MVS | 421/JD | PRADIP SAHA | 12-06-2024 | 12-07-2024 | 342
22 | JALPAIGURI | BANARHAT BAZAR WATER SUPPLY SCHEME | SM/00025 | SM/10044 | Augmentation | MVS | 1851/JD | SOUVIK SAHA | 15-12-2023 | 29-01-2024 | 193
23 | JALPAIGURI | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 |  | New | MVS | 775/JD | RAGHU DAS | 27-03-2023 | 23-09-2023 | 128
24 | JALPAIGURI | Baradighi Tea Garden Area Piped Water Supply Scheme | SM/06307 | SM/15059 | Augmentation | SVS | 613/JD | PRIYABRATA KARMAKAR | 09-03-2023 | 24-03-2023 | 129
25 | JALPAIGURI | Baradighi Tea Garden Area Piped Water Supply Scheme | SM/06307 | SM/15059 | Augmentation | SVS | 362/JD | PRIYABRATA KARMAKAR | 20-02-2023 | 06-03-2023 | 200
26 | JALPAIGURI | Baradighi Tea Garden Area Piped Water Supply Scheme | SM/06307 |  |  | MVS | 989/JSSD | PRIYABRATA KARMAKAR | 03-01-2022 | 13-01-2022 | 112
27 | JALPAIGURI | Baradighi Tea Garden Area Piped Water Supply Scheme | SM/06307 |  |  | MVS | 2120/JD | DIPAK KUMAR CHAKRABORTY | 16-12-2021 | 30-01-2022 | 1000
28 | JALPAIGURI | BARAGHARIA Piped Water Supply Scheme. | SM/17649 |  | New | MVS | 93/JD | SCEC BOENTER KDAS JOINT VENTURE | 25-04-2023 | 22-10-2023 | 1145
29 | JALPAIGURI | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 |  | New | SVS | 736/JD | MOTI INDUSTRIES | 26-07-2024 | 09-10-2024 | 200
30 | JALPAIGURI | Barnes Water Supply Scheme | SM/01823 | SM/10090 | Augmentation | MVS | 331/JD | SUKES BASU MAJUMDAR | 02-02-2022 | 03-05-2022 | 1056
31 | JALPAIGURI | Barnes Water Supply Scheme | SM/01823 | SM/10090 | Augmentation | MVS | 330/JD | R.S CONSTRUCTION | 02-02-2022 | 03-05-2022 | 772
32 | JALPAIGURI | Barnes Water Supply Scheme | SM/01823 | SM/10090 | Augmentation | MVS | 328/JD | ASHIT KUMAR SINGHA | 02-02-2022 | 03-05-2022 | 580
33 | JALPAIGURI | Barnes Water Supply Scheme | SM/01823 | SM/10090 | Augmentation | MVS | 329/JD | ASHIT KUMAR SINGHA | 02-02-2022 | 03-05-2022 | 562
34 | JALPAIGURI | Basilardanga Piped Water Supply Scheme | SM/05336 | SM/08077 | Retrofitting | MVS | 1538/JD | DIPAK KUMAR CHAKRABORTY | 31-12-2020 | 30-01-2021 | 247
35 | JALPAIGURI | Basilardanga Piped Water Supply Scheme | SM/05336 | SM/08077 | Retrofitting | MVS | 1053/JD | PARESH CHANDRA GUHA | 12-10-2020 | 26-12-2020 | 255
36 | JALPAIGURI | Basilardanga Piped Water Supply Scheme | SM/05336 | SM/08077 | Retrofitting | MVS | 631/JD | PARESH CHANDRA GUHA | 13-03-2023 | 27-04-2023 | 300
37 | JALPAIGURI | Batabari Tea Garden Area Piped Water supply Scheme | SM/05934 |  |  | MVS | 1452/JD | M/S M.B. DESIGN | 10-09-2021 | 20-09-2021 | 40
38 | JALPAIGURI | Batabari Tea Garden Area Piped Water supply Scheme | SM/05934 |  |  | MVS | 751/JD | JITENDRA NATH ROY | 13-05-2021 | 02-06-2021
39 | JALPAIGURI | Batabari Tea Garden Area Piped Water supply Scheme | SM/05934 |  |  | MVS | 1305/JD | JITENDRA NATH ROY | 24-11-2020 | 24-12-2020
40 | JALPAIGURI | Batabari Tea Garden Area Piped Water supply Scheme | SM/05934 |  |  | MVS | 1982/JD | PRIYABRATA KARMAKAR | 03-12-2021 | 18-12-2021 | 218
41 | JALPAIGURI | Batabari Tea Garden Area Piped Water supply Scheme | SM/05934 | SM/16773 | Augmentation | SVS | 62/JSSD | CHANDAN GHOSH | 23-05-2025 | 22-06-2025 | 71
42 | JALPAIGURI | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 |  | New | MVS | 2458/JD | UDAYAN BOSE | 22-12-2022 | 21-01-2023 | 691
43 | JALPAIGURI | Bhandani Piped Water Supply Scheme | SM/05145 | SM/06958 | Retrofitting | MVS | 49/JD | ASIM GUPTA | 07-01-2021 | 08-03-2021 | 225
44 | JALPAIGURI | Bhandani Piped Water Supply Scheme | SM/05145 | SM/06958 | Retrofitting | MVS | 42/JD | DULAL CHOUDHURY | 06-01-2021 | 06-04-2021 | 660
45 | JALPAIGURI | Bhangamali Piped Water Supply Scheme | SM/05314 |  |  | MVS | 1271/JD | MRINMOY KANTI DUTTA | 18-11-2020 | 01-02-2021 | 454
46 | JALPAIGURI | Bhangamali Piped Water Supply Scheme | SM/05314 | SM/15096 | Augmentation | MVS | 2026/JD | MRINMOY KANTI DUTTA | 19-11-2024 | 19-03-2025 | 94
47 | JALPAIGURI | Bhangarhat Piped Water Supply Scheme | SM/06071 |  |  | MVS | 1076/JD | DIPANKAR DUTTA | 02-07-2021 | 01-08-2021 | 501
48 | JALPAIGURI | Bhangarhat Piped Water Supply Scheme | SM/06071 |  |  | MVS | 1086/JD | MRINMOY KANTI DUTTA | 05-07-2021 | 04-08-2021 | 495
49 | JALPAIGURI | Bhangarhat Piped Water Supply Scheme | SM/06071 |  |  | MVS | 1651/JD | DIPANKAR DUTTA | 08-10-2021 | 29-10-2021 | 398
50 | JALPAIGURI | Bhangarhat Piped Water Supply Scheme | SM/06071 |  |  | MVS | 1650/JD | BILTU DAS | 08-10-2021 | 07-11-2021 | 420
51 | JALPAIGURI | Bhangarhat Piped Water Supply Scheme | SM/06071 | SM/15032 | Augmentation | MVS | 1528/JD | DIPAK KUMAR CHAKRABORTY | 01-10-2024 | 31-10-2024 | 195
52 | JALPAIGURI | Bhangarhat Piped Water Supply Scheme | SM/06071 |  |  | MVS | 1991/JD | M/S DEY & ROY CHOUDHURY | 03-12-2021 | 24-12-2021 | 194
53 | JALPAIGURI | BHATIPARA WATER SUPPLY SCHEME | SM/00894 | SM/13277 | Augmentation | MVS | 1261/JD | RANA DEY | 13-09-2023 | 28-10-2023 | 147
54 | JALPAIGURI | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 |  | New | SVS | 751/JD | BISWANATH GHOSH | 24-03-2023 | 20-09-2023 | 425
55 | JALPAIGURI | Binnaguri W/S Scheme | SM/02163 | SM/09344 | Augmentation | SVS | 332/JD | M/S NANDY ENTERPRISE | 02-02-2022 | 02-06-2022 | 1974
56 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 | SM/06115 |  | MVS | 1763/JD | SAPTASWA SARKAR | 08-12-2023 | 17-01-2024 | 587
57 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 | SM/06115 |  | MVS | 1888/JD | B.M CONSTRUCTION | 25-11-2021 | 09-01-2022 | 417
58 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 |  |  | MVS | 674/JD | SUKES BASU MAJUMDAR | 04-04-2025 | 03-06-2025 | 44
59 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 | SM/06115 |  | MVS | 675/JD | M/S BOSE ENTERPRISE | 04-04-2025 | 03-06-2025 | 1601
60 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 |  |  | MVS | 676/JD | BISWANATH GHOSH | 04-04-2025 | 03-06-2025 | 578
61 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 | SM/06115 |  | MVS | 1518/JD | D. S. ENTERPRISE | 16-10-2023 | 30-11-2023 | 1103
62 | JALPAIGURI | BINNAGURI WATER SUPPLY SCHEME | SM/00041 | SM/06115 |  | MVS | 611/JD | D. S. ENTERPRISE | 26-03-2025 | 25-05-2025 | 795
63 | JALPAIGURI | Boalmari Piped Water Supply Scheme | SM/04852 | SM/06838 | Retrofitting | MVS | 1496/JD | KANAI LAL SEN | 22-12-2020 | 05-02-2021 | 265
64 | JALPAIGURI | Boalmari Piped Water Supply Scheme | SM/04852 | SM/06838 | Retrofitting | MVS | 475/RWS | KABYA ENTERPRISE | 15-10-2020 | 14-11-2020
65 | JALPAIGURI | Boalmari Piped Water Supply Scheme | SM/04852 | SM/06838 | Retrofitting | MVS | 1105/JD | UMWEL ENGINEER PRIVATE LIMITED | 20-10-2020 | 18-01-2021 | 142
66 | JALPAIGURI | Caron Tea garden Piped Water Supply Scheme | SM/04787 | SM/09859 | Augmentation | SVS | 470/JSSD | SANDIP BANIK | 05-10-2021 | 20-10-2021 | 108
67 | JALPAIGURI | Chalauni Tea Garden Area Piped Water Supply Scheme | SM/05362 |  |  | MVS | 1092/JD | BILTU DAS | 15-10-2020 | 13-01-2021 | 37
68 | JALPAIGURI | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15264 |  | New | SVS | 24/JD | PRASENJIT BASAK | 10-04-2023 | 07-10-2023 | 736
69 | JALPAIGURI | CHALSA WATER SUPPLY SCHEME | SM/00033 |  |  | MVS | 210/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 11-02-2021 | 27-04-2021 | 332
70 | JALPAIGURI | CHALSA WATER SUPPLY SCHEME | SM/00033 | SM/05273 |  | MVS | 164/JSSD | BAJRANG ENTERPRISE | 24-08-2022 | 23-09-2022 | 100
71 | JALPAIGURI | CHALSA WATER SUPPLY SCHEME | SM/00033 | SM/05273 |  | MVS | 1070/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 02-07-2021 | 16-08-2021 | 809
72 | JALPAIGURI | CHALSA WATER SUPPLY SCHEME | SM/00033 | SM/05273 |  | MVS | 1988/JD | SADHAN KARMAKAR | 03-12-2021 | 24-12-2021 | 400
73 | JALPAIGURI | CHALSA WATER SUPPLY SCHEME | SM/00033 | SM/05273 |  | MVS | 2431/JD | ALICK DUTTA | 24-12-2024 | 22-02-2025 | 335
74 | JALPAIGURI | CHALSA WATER SUPPLY SCHEME | SM/00033 | SM/05273 |  | MVS | 161/JSSD | ALICK DUTTA | 24-08-2022 | 23-09-2022 | 115
75 | JALPAIGURI | CHAMURCHI BAZAR WATER SUPPLY SCHEME | SM/00029 | SM/08876 | Augmentation | MVS | 627/JD | SANKAR DAS | 13-03-2023 | 27-04-2023 | 834
76 | JALPAIGURI | CHAMURCHI BAZAR WATER SUPPLY SCHEME | SM/00029 | SM/08876 | Augmentation | MVS | 1463/JD | MALAY BHOWMIK | 06-10-2023 | 20-11-2023 | 302
77 | JALPAIGURI | Chengmari Tea Garden Area Piped Water Supply Scheme | SM/05945 |  |  | MVS | 651/JSSD | NEW KUNDU ENTERPRISE | 25-02-2021 | 17-03-2021 | 99
78 | JALPAIGURI | Chengmari Tea Garden Area Piped Water Supply Scheme | SM/05945 |  |  | MVS | 644/JSSD | ARUP SARKAR | 25-02-2021 | 17-03-2021 | 97
79 | JALPAIGURI | Chengmari Tea Garden Area Piped Water Supply Scheme | SM/05945 |  |  | MVS | 1071/JD | SUDIP BASAK | 02-07-2021 | 16-08-2021 | 386
80 | JALPAIGURI | Chengmari Tea Garden Area Piped Water Supply Scheme | SM/05945 |  |  | MVS | 652/JSSD | SOMNATH ROY | 25-02-2021 | 17-03-2021 | 100
81 | JALPAIGURI | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 |  | New | MVS | 848/JD. | S & P ENTERPRISE | 28-07-2023 | 24-01-2024 | 92
82 | JALPAIGURI | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 |  | New | MVS | 849/JD. | S & P ENTERPRISE | 28-07-2023 | 24-01-2024 | 826
83 | JALPAIGURI | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 |  | New | MVS | 847/JD | S & P ENTERPRISE | 28-07-2023 | 24-01-2024
84 | JALPAIGURI | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 |  | New | MVS | 1531/JD | PRIYABRATA KARMAKAR | 01-10-2024 | 31-10-2024 | 168
85 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1091/JD | NARENDRA KUMAR | 05-07-2021 | 26-07-2021 | 94
86 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1435/JD | NARAYAN CHAKRABORTY | 08-09-2021 | 08-10-2021 | 678
87 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1625/JD | MAA JAGADHATRI CONSTRUCTION | 05-10-2021 | 20-10-2021 | 264
88 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1444/JD | ALOKE DEY | 09-09-2021 | 09-10-2021 | 499
89 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/18283 | Augmentation | SVS | 936/JD | MAA MANASA VYAPAAR | 08-08-2023 | 04-02-2024 | 1579
90 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/04647 |  | MVS | 1091/JD | NARENDRA KUMAR | 05-07-2021 | 26-07-2021 | 69
91 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 167/JD | ASIM GUPTA | 19-01-2023 | 09-02-2023 | 198
92 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1443/JD | NARENDRA KUMAR | 09-09-2021 | 09-10-2021 | 419
93 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1989/JD | SAHA CONSTRUCTION | 03-12-2021 | 02-01-2022 | 1003
94 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 476/JD | ASIM GUPTA | 01-04-2021 | 22-04-2021 | 1
95 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/18283 | Augmentation | SVS | 1708/JD | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 04-12-2023 | 01-06-2024 | 1192
96 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/05524 |  | MVS | 1323/JD | MAA JAGADHATRI CONSTRUCTION | 17-06-2022 | 08-07-2022 | 96
97 | JALPAIGURI | Dabgram-II Water Supply Scheme | SM/01861 | SM/18283 | Augmentation | SVS | 796/JD | NARENDRA KUMAR | 24-07-2023 | 14-08-2023 | 173
98 | JALPAIGURI | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 |  | New | MVS | 778/JD | ASHIT KUMAR SINGHA | 27-03-2023 | 23-09-2023 | 550
99 | JALPAIGURI | DAKSHIN BERUBARI WATER SUPPLY SCHEME | SM/00042 | SM/10086 | Augmentation | SVS | 341/JD | M/S A.B.G. CONSTRUCTION | 03-02-2022 | 04-05-2022 | 300
100 | JALPAIGURI | DAKSHIN BERUBARI WATER SUPPLY SCHEME | SM/00042 | SM/10086 | Augmentation | SVS | 343/JD | SUKES BASU MAJUMDAR | 03-02-2022 | 04-05-2022 | 433
101 | JALPAIGURI | DAKSHIN BERUBARI WATER SUPPLY SCHEME | SM/00042 | SM/10086 | Augmentation | SVS | 340/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 03-02-2022 | 04-05-2022 | 242
102 | JALPAIGURI | DAKSHIN BERUBARI WATER SUPPLY SCHEME | SM/00042 | SM/10086 | Augmentation | SVS | 347/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 03-02-2022 | 04-05-2022 | 283
103 | JALPAIGURI | DAKSHIN BERUBARI WATER SUPPLY SCHEME | SM/00042 | SM/10086 | Augmentation | SVS | 346/JD | M/S SURAJIT DEY AND CO. | 03-02-2022 | 04-05-2022 | 557
104 | JALPAIGURI | DAKSHIN BERUBARI WATER SUPPLY SCHEME | SM/00042 | SM/10086 | Augmentation | SVS | 344/JD | R.S CONSTRUCTION | 03-02-2022 | 04-05-2022 | 440
105 | JALPAIGURI | DAKSHIN CHAK MOULANI WATER SUPPLY SCHEME | SM/00827 | SM/09561 | Augmentation | MVS | 211/JD | UNIBRO INFRASERV PRIVATE LIMITED | 24-01-2022 | 25-03-2022 | 627
106 | JALPAIGURI | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME | SM/14887 |  | New | MVS | 375/A/JD | PARESH CHANDRA GUHA | 30-05-2023 | 26-11-2023 | 1294
107 | JALPAIGURI | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME | SM/16181 |  | New | MVS | 296/JD | M/S SURAJIT DEY AND CO. | 15-05-2023 | 11-11-2023 | 361
108 | JALPAIGURI | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 |  | New | MVS | 1540/JD | SCEC BOENTER AND KDAS JOINT VENTURE | 23-10-2023 | 20-04-2024 | 233
109 | JALPAIGURI | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME | SM/14908 |  | New | SVS | 754/JD | B RAI CONSTRUCTION COMPANY | 24-03-2023 | 20-09-2023 | 280
110 | JALPAIGURI | Dakshin Shalbari Piped Water Supply Scheme | SM/06298 |  |  | MVS | 2040/JD | NARAYAN SARKAR | 07-12-2021 | 28-12-2021 | 441
111 | JALPAIGURI | Dakshin Shalbari Piped Water Supply Scheme | SM/06298 |  |  | MVS | 1408/JD | ASHIT KUMAR SINGHA | 03-09-2021 | 03-10-2021 | 482
112 | JALPAIGURI | Dakshin Shalbari Piped Water Supply Scheme | SM/06298 |  |  | MVS | 1691/JD | NEW KUNDU ENTERPRISE | 28-10-2021 | 27-11-2021 | 494
113 | JALPAIGURI | Dakshin Shalbari Piped Water Supply Scheme | SM/06298 |  |  | MVS | 1540/JD | SAHA CONSTRUCTION | 31-12-2020 | 01-03-2021 | 588
114 | JALPAIGURI | Dakshin Shalbari Piped Water Supply Scheme | SM/06298 | SM/15087 | Augmentation | MVS | 169/RWS | NEW KUNDU ENTERPRISE | 28-02-2023 | 21-03-2023
115 | JALPAIGURI | Dakshin Shalbari Piped Water Supply Scheme | SM/06298 | SM/15087 | Augmentation | MVS | 437/JD. | RABINDRANATH DUTTA | 08-06-2023 | 07-08-2023 | 60
116 | JALPAIGURI | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 |  | New | SVS | 1257/JD | PRASENJIT BASAK | 13-09-2023 | 11-03-2024 | 1178
117 | JALPAIGURI | Debpara Tea Garden Area Piped Water Supply Scheme | SM/05478 |  |  | MVS | 1224/JD | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 09-11-2020 | 08-01-2021
118 | JALPAIGURI | Debpara Tea Garden Area Piped Water Supply Scheme | SM/05478 |  |  | MVS | 1223/JD | DIPANKAR DUTTA | 09-11-2020 | 08-01-2021 | 27
119 | JALPAIGURI | Debpara Tea Garden Area Piped Water Supply Scheme | SM/05478 | SM/11812 | Augmentation | SVS | 1806/JD | JAYDEB SAHA | 14-09-2022 | 05-10-2022 | 20
120 | JALPAIGURI | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/14826 |  | New | SVS | 2330./JD | BISWAJIT BHADURI | 12-12-2024 | 26-01-2025 | 140
121 | JALPAIGURI | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/14826 |  | New | SVS | 96/JD | GLOBAL POWER & CONSTRUCTION CO. | 25-04-2023 | 22-10-2023 | 443
122 | JALPAIGURI | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/14882 |  | New | SVS | 95/JD | K.R. ENTERPRISE | 25-04-2023 | 22-10-2023 | 504
123 | JALPAIGURI | DOMOHINI WATER SUPPLY SCHEME | SM/00040 | SM/09345 | Augmentation | MVS | 2629/JD | M/S PRAFULLA GHOSH | 07-03-2024 | 05-07-2024 | 48
124 | JALPAIGURI | DOMOHINI WATER SUPPLY SCHEME | SM/00040 |  |  | MVS | 1066/JD | PRADIP KR SEN | 02-07-2021 | 23-07-2021 | 197
125 | JALPAIGURI | DOMOHINI WATER SUPPLY SCHEME | SM/00040 | SM/09345 | Augmentation | MVS | 2008/JD | ALOKE DEY | 01-11-2022 | 01-12-2022 | 1004
126 | JALPAIGURI | DOMOHINI WATER SUPPLY SCHEME | SM/00040 | SM/09345 | Augmentation | MVS | 1554/JD | B.M CONSTRUCTION | 01-11-2023 | 31-12-2023 | 1169
127 | JALPAIGURI | Dwarikamari Piped Water Supply Scheme | SM/04853 | SM/06841 | Retrofitting | MVS | 1497/JD | GOUTAM DAS | 22-12-2020 | 21-01-2021 | 42
128 | JALPAIGURI | Dwarikamari Piped Water Supply Scheme | SM/04853 | SM/06841 | Retrofitting | MVS | 1269/JD | BARUN KUMAR DUTTA | 18-11-2020 | 16-02-2021 | 208
129 | JALPAIGURI | Dwarikamari Piped Water Supply Scheme | SM/04853 | SM/06841 | Retrofitting | MVS | 625/JD | ARATI CONSTRUCTION | 13-03-2023 | 27-04-2023 | 247
130 | JALPAIGURI | Dwarikamari Piped Water Supply Scheme | SM/04853 | SM/06841 | Retrofitting | MVS | 1493/JD | SUBRATA GOSWAMI | 22-12-2020 | 21-01-2021 | 163
131 | JALPAIGURI | Engo Tea garden Piped Water Supply Scheme | SM/04784 | SM/07301 | Retrofitting | SVS | 59/JSSD | PRITAM DUTTA | 12-05-2021 | 27-05-2021 | 41
132 | JALPAIGURI | Engo Tea garden Piped Water Supply Scheme | SM/04784 | SM/07301 | Retrofitting | SVS | 68/JSSD | NABIN PRODHAN | 19-05-2021 | 03-06-2021 | 48
133 | JALPAIGURI | Engo Tea garden Piped Water Supply Scheme | SM/04784 | SM/07301 | Retrofitting | SVS | 561/JSSD | JOYDEB SAHA | 01-02-2021 | 16-02-2021
134 | JALPAIGURI | Engo Tea garden Piped Water Supply Scheme | SM/04784 | SM/07301 | Retrofitting | SVS | 63/JSSD | BIMAN DAS | 13-05-2021 | 28-05-2021 | 50
135 | JALPAIGURI | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 |  | New | SVS | 459/JD | ALOKE DEY | 11-03-2025 | 25-04-2025 | 200
136 | JALPAIGURI | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME | SM/14664 |  | New | SVS | 677/JD | SUKES BASU MAJUMDAR | 16-03-2023 | 12-09-2023 | 1659
137 | JALPAIGURI | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 |  | New | MVS | 422/A/JD | M/S SIBU DEY AND CO. | 07-06-2023 | 04-12-2023 | 196
138 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 1073/JD | BISWAJIT BHADURI | 02-07-2021 | 01-08-2021 | 560
139 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 1072/JD | SAHA CONSTRUCTION | 02-07-2021 | 01-08-2021 | 475
140 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/09390 | Augmentation | SVS | 1862/JD | ASIM GUPTA | 20-09-2022 | 15-10-2022 | 157
141 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/09390 | Augmentation | SVS | 545/JD | RABINDRANATH DUTTA | 28-02-2022 | 21-03-2022 | 180
142 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/09390 | Augmentation | SVS | 539/JD | BISWAJIT BHADURI | 25-02-2022 | 27-03-2022 | 377
143 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 61/RWS | NEW KUNDU ENTERPRISE | 09-02-2021 | 24-02-2021 | 45
144 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 1074/JD | M/S SIBU DEY AND CO. | 02-07-2021 | 16-08-2021 | 606
145 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 2036/JD | J.M. CONSTRUCTION | 07-12-2021 | 28-12-2021 | 226
146 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 2035/JD | SOMNATH ROY | 07-12-2021 | 28-12-2021 | 297
147 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/09390 | Augmentation | SVS | 538/JD | ASIM GUPTA | 25-02-2022 | 26-04-2022 | 711
148 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/09390 | Augmentation | SVS | 1741/JD | PROVA CONSTRUCTION | 08-09-2022 | 23-10-2022 | 534
149 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 94/JD | SAPTASWA SARKAR | 14-01-2021 | 28-02-2021 | 69
150 | JALPAIGURI | Garalbari Water Supply Scheme | SM/01860 | SM/08038 | Retrofitting | SVS | 92/JD | BISWAJIT BHADURI | 14-01-2021 | 28-02-2021 | 297
151 | JALPAIGURI | Gatia Tea Garden Area Piped Water Supply Scheme | SM/05886 |  |  | MVS | 455/JSSD | N.M. CONSTRUCTION | 30-12-2020 | 14-01-2021
152 | JALPAIGURI | Gatia Tea Garden Area Piped Water Supply Scheme | SM/05886 |  |  | MVS | 1282/JD | ASIT PAUL | 18-11-2020 | 02-01-2021
153 | JALPAIGURI | Gatia Tea Garden Area Piped Water Supply Scheme | SM/05886 |  |  | MVS | 469/JSSD | D. S. ENTERPRISE | 05-10-2021 | 20-10-2021 | 107
154 | JALPAIGURI | Gatia Tea Garden Area Piped Water Supply Scheme | SM/05886 |  |  | MVS | 1985/JD | GOUTAM DAS | 03-12-2021 | 18-12-2021 | 449
155 | JALPAIGURI | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 |  | New | MVS | 787/JD | M/S S.G. CONSTRUCTION | 27-03-2023 | 23-09-2023 | 811
156 | JALPAIGURI | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14666 |  | New | SVS | 717/JD | ANUGRAH CONSTRUCTION PVT. LTD. | 20-03-2023 | 16-09-2023 | 1475
157 | JALPAIGURI | Ghasmari Piped Water Supply Scheme. | SM/08868 |  | New | MVS | 208/JD | M/S R.N. TRADERS | 24-01-2022 | 24-04-2022 | 513
158 | JALPAIGURI | Grassmore Tea Garden Area Piped Water Supply Scheme | SM/06304 |  |  | MVS | 2039/JD | SWAPAN SAHA | 07-12-2021 | 22-12-2021 | 253
159 | JALPAIGURI | Grassmore Tea Garden Area Piped Water Supply Scheme | SM/06304 | SM/15130 | Augmentation | SVS | 413/A/JD | JAYDEB SAHA | 07-06-2023 | 06-08-2023 | 92
160 | JALPAIGURI | Grassmore Tea Garden Area Piped Water Supply Scheme | SM/06304 |  |  | MVS | 1087/JD | M/S R.N. TRADERS | 05-07-2021 | 04-08-2021 | 465
161 | JALPAIGURI | Grassmore Tea Garden Area Piped Water Supply Scheme | SM/06304 |  |  | MVS | 1087/JD | M/S R.N. TRADERS | 05-07-2021 | 04-08-2021 | 288
162 | JALPAIGURI | Grassmore Tea Garden Area Piped Water Supply Scheme | SM/06304 |  |  | MVS | 1088/JD | D. S. ENTERPRISE | 05-07-2021 | 19-08-2021 | 563
163 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 1257/JD | ALICK DUTTA | 10-08-2021 | 25-08-2021 | 102
164 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 1337/JD | DULAL CHOUDHURY | 23-08-2021 | 22-09-2021 | 58
165 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 744/JD | KAMALESH SEN | 13-05-2021 | 12-06-2021 | 453
166 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 746/JD | RABINDRANATH DUTTA | 13-05-2021 | 02-06-2021 | 264
167 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 744/JD | KAMALESH SEN | 13-05-2021 | 12-06-2021 | 45
168 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 1444/JD | ALOKE DEY | 09-09-2021 | 09-10-2021
169 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Madhya Khuttimari & adj. mouza. | SM/04222 | SM/08078 | Retrofitting | MVS | 1065/JD | GANAPATI CO-OP LABOUR CONT. & CONST. SOCIETY LTD. | 02-07-2021 | 23-07-2021 | 99
170 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Ambari Falakata & adj. mouzas | SM/03525 | SM/08036 | Retrofitting | MVS | 743/JD | NARAYAN SARKAR | 13-05-2021 | 12-06-2021 | 502
171 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Ambari Falakata & adj. mouzas | SM/03525 | SM/08036 | Retrofitting | MVS | 1069/JD | PRAHLAD PRASAD SAHA | 02-07-2021 | 23-07-2021 | 100
172 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Ambari Falakata & adj. mouzas | SM/03525 | SM/08036 | Retrofitting | MVS | 745/JD | GOURAB GUHA ROY | 13-05-2021 | 02-06-2021 | 305
173 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Ambari Falakata & adj. mouzas | SM/03525 | SM/08036 | Retrofitting | MVS | 1340 /JD | MONTOSH GHOSH | 23-08-2021 | 22-09-2021 | 497
174 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Ambari Falakata & adj. mouzas | SM/03525 | SM/08036 | Retrofitting | MVS | 1441/JD | RAGHU DAS | 09-09-2021 | 09-10-2021 | 488
175 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Ambari Falakata & adj. mouzas | SM/03525 | SM/09487 | Augmentation | MVS | 472/JD | SUBIR GHOSH | 20-06-2024 | 10-07-2024 | 231
176 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Arji Maria Kamala Pukhari & adj. mouzas | SM/03531 | SM/06936 | Retrofitting | MVS | 19/JD | BILTU DAS | 14-01-2021 | 15-03-2021 | 498
177 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Arji Maria Kamala Pukhari & adj. mouzas | SM/03531 | SM/06936 | Retrofitting | MVS | 1536/JD | PRADIP SAHA | 31-12-2020 | 30-01-2021
178 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Arji Maria Kamala Pukhari & adj. mouzas | SM/03531 | SM/06936 | Retrofitting | MVS | 1545/JD | R.S CONSTRUCTION | 31-12-2020 | 14-02-2021 | 241
179 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Arji Maria Kamala Pukhari & adj. mouzas | SM/03531 | SM/06936 | Retrofitting | MVS | 1494/JD | R.S CONSTRUCTION | 22-12-2020 | 05-02-2021 | 290
180 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Arji Maria Kamala Pukhari & adj. mouzas | SM/03531 | SM/06936 | Retrofitting | MVS | 707/JD | M/S R.K SINGHA & SONS | 13-07-2023 | 12-08-2023 | 186
181 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Chakia Bhita & adj. mouzas | SM/03506 | SM/08285 | Retrofitting | MVS | 754/JD | ANUP SARKAR | 13-05-2021 | 03-06-2021 | 500
182 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Chakia Bhita & adj. mouzas | SM/03506 | SM/08285 | Retrofitting | MVS | 1404/JD | SAPTASWA SARKAR | 03-09-2021 | 03-10-2021 | 557
183 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Chakia Bhita & adj. mouzas | SM/03506 | SM/08285 | Retrofitting | MVS | 1339/JD | PRADIP SAHA | 23-08-2021 | 22-09-2021 | 500
184 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Chakia Bhita & adj. mouzas | SM/03506 | SM/08285 | Retrofitting | MVS | 2045/JD | BARUN KUMAR DUTTA | 07-12-2021 | 28-12-2021 | 500
185 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/08037 | Retrofitting | MVS | 1081/RWS | M/S DEY & ROY CHOUDHURY | 19-09-2023 | 19-10-2023 | 588
186 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/08037 | Retrofitting | MVS | 97/JD | ANUP KUMAR KUNDU | 15-01-2021 | 16-03-2021 | 409
187 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/08037 | Retrofitting | MVS | 363/RWS | M/S.DEY & ROY CHOUDHURY | 08-09-2020 | 23-09-2020
188 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/15131 | Retrofitting | MVS | 1269/JD | M/S DEY & ROY CHOUDHURY | 13-09-2023 | 13-10-2023
189 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/09519 | Augmentation | MVS | 537/JD | M/S DEY & ROY CHOUDHURY | 25-02-2022 | 27-03-2022 | 470
190 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/08037 | Retrofitting | MVS | 96/JD | M/S KARMAKAR CONSTRACTION | 15-01-2021 | 14-02-2021 | 4
191 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/08037 | Retrofitting | MVS | 93/JD | M/S DEY & ROY CHOUDHURY | 14-01-2021 | 15-03-2021 | 220
192 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/09519 | Augmentation | MVS | 599/JD | M/S DEY & ROY CHOUDHURY | 09-03-2023 | 30-03-2023 | 125
193 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/08037 | Retrofitting | MVS | 363/RWS | M/S.DEY & ROY CHOUDHURY | 08-09-2020 | 23-09-2020
194 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mahitnagar & adj. mouzas | SM/03521 | SM/09519 | Augmentation | MVS | 601/JD | M/S DEY & ROY CHOUDHURY | 09-03-2023 | 30-03-2023 | 111
195 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mallick Sobha & adj. mouzas | SM/03515 | SM/09100 | Retrofitting | MVS | 882/JD | M/S NANDY ENTERPRISE | 05-04-2022 | 04-06-2022 | 806
196 | JALPAIGURI | Ground Water Based Piped Water Supply Scheme for Mallick Sobha & adj. mouzas | SM/03515 | SM/09100 | Retrofitting | MVS | 193/JD | BOSE ENTERPRISE | 21-01-2022 | 22-03-2022 | 1453
197 | JALPAIGURI | Ground water based water supply scheme for Chauhaddi and adjoining mouzas | SM/03964 | SM/07893 | Retrofitting | MVS | 1338/JD | ASIT PAUL | 23-08-2021 | 22-09-2021 | 499
198 | JALPAIGURI | Ground water based water supply scheme for Chauhaddi and adjoining mouzas | SM/03964 | SM/07893 | Retrofitting | MVS | 1405/JD | RABINDRANATH DUTTA | 03-09-2021 | 03-10-2021 | 365
199 | JALPAIGURI | Ground water based water supply scheme for Chauhaddi and adjoining mouzas | SM/03964 | SM/07893 | Retrofitting | MVS | 1256/JD | HARIPADA BANERJEE | 10-08-2021 | 25-08-2021
200 | JALPAIGURI | Ground water based water supply scheme for Chauhaddi and adjoining mouzas | SM/03964 | SM/07893 | Retrofitting | MVS | 289/JD | HARIPADA BANERJEE | 23-02-2021 | 25-03-2021
201 | JALPAIGURI | Ground water based water supply scheme for Chauhaddi and adjoining mouzas | SM/03964 | SM/15033 | Augmentation | MVS | 1587/JD | SAHA CONSTRUCTION | 06-11-2023 | 06-12-2023 | 117
202 | JALPAIGURI | Ground Water Based Water Supply Scheme for Por Jhar Area | SM/03854 | SM/15302 | Augmentation | SVS | 1158/SWSD | AKASH ENTERPRISE | 09-08-2023 | 05-04-2024 | 1072
203 | JALPAIGURI | HAIHAIPATHAR PWSS | SM/16852 |  | New | MVS | 454/JD. | M/S R.N. TRADERS | 08-06-2023 | 05-12-2023 | 199
204 | JALPAIGURI | Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/05573 |  |  | MVS | 1288/JD | RANA DEY | 18-11-2020 | 01-02-2021 | 6
205 | JALPAIGURI | Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/05573 |  |  | MVS | 46/JD | UDAYAN BOSE | 07-01-2021 | 08-03-2021 | 504
206 | JALPAIGURI | Hasludanga Piped Water Supply Scheme | SM/06116 |  |  | MVS | 1275/JD | M/S R.N. TRADERS | 18-11-2020 | 16-02-2021 | 722
207 | JALPAIGURI | Hasludanga Piped Water Supply Scheme | SM/06116 |  |  | MVS | 1544/JD | M/S ROY & SARKAR CONSTRUCTION | 31-12-2020 | 14-02-2021 | 470
208 | JALPAIGURI | Hila Tea Garden Piped Water Supply Scheme | SM/04785 | SM/06957 | Retrofitting | SVS | 149/JD | SCEC BOENTER KDAS JOINT VENTURE | 19-01-2022 | 18-02-2022 | 640
209 | JALPAIGURI | Hila Tea Garden Piped Water Supply Scheme | SM/04785 | SM/10070 | Augmentation | SVS | 564/JSSD | SAHA CONSTRUCTION | 05-03-2024 | 04-04-2024 | 156
210 | JALPAIGURI | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | SM/10775 |  | New | MVS | 1227/JD | M/S SIBU DEY AND CO. | 01-06-2022 | 01-07-2022 | 129
211 | JALPAIGURI | Indong Tea Garden Area Piped Water Supply Scheme. | SM/08873 |  | New | SVS | 690/JD | KANAI LAL SEN | 15-03-2022 | 13-06-2022 | 1129
212 | JALPAIGURI | Jabaramli Piped Water Supply Scheme | SM/06072 |  |  | MVS | 1716/JD | RAGHU DAS | 29-10-2021 | 19-11-2021 | 571
213 | JALPAIGURI | Jabaramli Piped Water Supply Scheme | SM/06072 |  |  | MVS | 1056/JD | RAGHU DAS | 27-04-2022 | 18-05-2022
214 | JALPAIGURI | Jabaramli Piped Water Supply Scheme | SM/06072 |  |  | MVS | 2038/JD | A.P CONSTRUCTION | 07-12-2021 | 28-12-2021 | 307
215 | JALPAIGURI | Jabaramli Piped Water Supply Scheme | SM/06072 |  |  | MVS | 1174/JD | SUKES BASU MAJUMDAR | 04-11-2020 | 19-12-2020 | 960
216 | JALPAIGURI | Jalapara Water Supply Scheme | SM/07103 | SM/10043 | Augmentation | MVS | 2757/JD | ANUP KUMAR KUNDU | 15-03-2024 | 14-04-2024 | 250
217 | JALPAIGURI | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 |  | New | SVS | 139/JD | ALLIED INSTRUMENTS | 28-04-2023 | 25-10-2023 | 679
218 | JALPAIGURI | Jogesh Chandra Tea Garden Area Piped Water Supply Scheme | SM/06280 | SM/15068 | Augmentation | SVS | 815/RWS | RANA DEY | 14-07-2023 | 04-08-2023 | 10
219 | JALPAIGURI | Jogesh Chandra Tea Garden Area Piped Water Supply Scheme | SM/06280 |  |  | MVS | 730/JD | SANDIP BANIK | 17-03-2022 | 07-04-2022 | 231
220 | JALPAIGURI | Jogesh Chandra Tea Garden Area Piped Water Supply Scheme | SM/06280 |  |  | MVS | 1439/JD | SANDIP BANIK | 09-09-2021 | 09-10-2021 | 563
221 | JALPAIGURI | Jogesh Chandra Tea Garden Area Piped Water Supply Scheme | SM/06280 |  |  | MVS | 1395/JD | M/S SURAJIT DEY AND CO. | 02-09-2021 | 02-10-2021 | 599
222 | JALPAIGURI | Juranti Tea Garden Area Piped Water Supply Scheme | SM/05578 | SM/06847 | Retrofitting | SVS | 1200/JD | NARAYAN CHANDRA SAHA | 18-11-2020 | 16-02-2021 | 85
223 | JALPAIGURI | Juranti Tea Garden Area Piped Water Supply Scheme | SM/05578 | SM/10069 | Augmentation | SVS | 348/JD | ASIT PAUL | 24-05-2023 | 20-11-2023 | 246
224 | JALPAIGURI | Juranti Tea Garden Area Piped Water Supply Scheme | SM/05578 | SM/06847 | Retrofitting | SVS | 1277/JD | NARAYAN CHANDRA SAHA | 18-11-2020 | 16-02-2021 | 738
225 | JALPAIGURI | Kajaldighi Piped Water Supply Scheme | SM/05143 | SM/06839 | Retrofitting | MVS | 1276/JD | NISHITH RANJAN KARMAKAR | 18-11-2020 | 16-02-2021 | 117
226 | JALPAIGURI | Kajaldighi Piped Water Supply Scheme | SM/05143 | SM/06839 | Retrofitting | MVS | 1085/JD | GOUTAM DAS | 05-07-2021 | 25-07-2021 | 176
227 | JALPAIGURI | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 |  | New | MVS | 247/JD | S.S. CONSTRUCTION | 10-05-2023 | 06-11-2023 | 1226
228 | JALPAIGURI | KANTADIGHI KUMARPARA TEA GARDEN | SM/14879 |  | New | MVS | 2037/JD | SAPTASWA SARKAR | 21-11-2024 | 19-02-2025 | 124
229 | JALPAIGURI | KAOAGAP PIPED WATER SUPPLY SCHEME | SM/14199 |  | New | MVS | 777/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 27-03-2023 | 23-09-2023 | 407
230 | JALPAIGURI | Karbala Tea Garden Area Piped Water Supply Scheme | SM/05933 |  |  | MVS | 211/JD | GOURAB GUHA ROY | 11-02-2021 | 13-03-2021 | 54
231 | JALPAIGURI | Karbala Tea Garden Area Piped Water Supply Scheme | SM/05933 |  |  | MVS | 1296/JD | GOURAB GUHA ROY | 23-11-2020 | 07-01-2021 | 72
232 | JALPAIGURI | Karbala Tea Garden Area Piped Water Supply Scheme | SM/05933 | SM/15298 | Augmentation | SVS | 41/JD | MALAY BHOWMIK | 13-04-2023 | 12-07-2023 | 362
233 | JALPAIGURI | Karbala Tea Garden Area Piped Water Supply Scheme | SM/05933 |  |  | MVS | 1984/JD | PRADIP SAHA | 03-12-2021 | 18-12-2021 | 501
234 | JALPAIGURI | Kathalguri Tea Garden Area Piped Water Supply Scheme | SM/05932 | SM/09392 | Augmentation | SVS | 630/JD | J.M. CONSTRUCTION | 13-03-2023 | 27-04-2023 | 334
235 | JALPAIGURI | Kathalguri Tea Garden Area Piped Water Supply Scheme | SM/05932 |  |  | MVS | 1294/JD | RABINDRANATH DUTTA | 23-11-2020 | 07-01-2021 | 242
236 | JALPAIGURI | Kathapara Water Supply Scheme | SM/01939 | SM/09563 | Augmentation | MVS | 1746/JD | SCEC BOENTER KDAS JOINT VENTURE | 08-09-2022 | 23-10-2022 | 2065
237 | JALPAIGURI | Khalai Gram Piped Water Supply Scheme | SM/04844 | SM/07892 | Retrofitting | MVS | 290/JD | PARESH CHANDRA ROY | 23-02-2021 | 15-03-2021 | 249
238 | JALPAIGURI | Khalai Gram Piped Water Supply Scheme | SM/04844 | SM/07892 | Retrofitting | MVS | 296/JD | M/S SIBU DEY AND CO. | 24-02-2021 | 26-03-2021 | 461
239 | JALPAIGURI | Khalai Gram Piped Water Supply Scheme | SM/04844 | SM/07892 | Retrofitting | MVS | 1990/JD | M/S R.N. TRADERS | 03-12-2021 | 02-01-2022 | 106
240 | JALPAIGURI | Khalai Gram Piped Water Supply Scheme | SM/04844 | SM/07892 | Retrofitting | MVS | 1990/JD | M/S R.N. TRADERS | 03-12-2021 | 02-01-2022 | 686
241 | JALPAIGURI | KHARIJA -BERUBARI (GHUGHUDANGA) W/S SCHEME | SM/00893 | SM/10088 | Augmentation | MVS | 1066/JD | M/S R.N. TRADERS | 28-04-2022 | 26-08-2022 | 435
242 | JALPAIGURI | KHARIJA -BERUBARI (GHUGHUDANGA) W/S SCHEME | SM/00893 | SM/10088 | Augmentation | MVS | 1099/JD | BANSBERIA CONSTRUCTION CO. | 12-05-2022 | 09-09-2022 | 2468
243 | JALPAIGURI | Kilkote Tea Garden Area Piped Water Supply Scheme | SM/05931 | SM/09461 | Augmentation | SVS | 499/RWS | VEDATRAYEE AND CO. | 23-07-2021 | 07-08-2021 | 100
244 | JALPAIGURI | Kilkote Tea Garden Area Piped Water Supply Scheme | SM/05931 |  |  | MVS | 1297/JD | VEDATRAYEE AND CO. | 23-11-2020 | 23-12-2020 | 18
245 | JALPAIGURI | Kilkote Tea Garden Area Piped Water Supply Scheme | SM/05931 | SM/09461 | Augmentation | SVS | 1715/JD | M/S SURAJIT DEY AND CO. | 29-10-2021 | 13-11-2021 | 119
246 | JALPAIGURI | Kilkote Tea Garden Area Piped Water Supply Scheme | SM/05931 |  |  | MVS | 1594/JD | M/S SURAJIT DEY AND CO. | 31-12-2020 | 01-03-2021 | 218
247 | JALPAIGURI | Kilkote Tea Garden Area Piped Water Supply Scheme | SM/05931 | SM/09461 | Augmentation | SVS | 1283/RWS | PINTU DAS | 28-11-2023 | 18-12-2023 | 45
248 | JALPAIGURI | Kilkote Tea Garden Area Piped Water Supply Scheme | SM/05931 | SM/09461 | Augmentation | SVS | 732/JD | PINTU DAS | 22-03-2023 | 12-04-2023 | 70
249 | JALPAIGURI | KRANTI WATER SUPPLY SCHEME | SM/00018 | SM/09994 | Augmentation | MVS | 207/JD | M/S A.B.G. CONSTRUCTION | 24-01-2022 | 25-03-2022 | 637
250 | JALPAIGURI | KRANTI WATER SUPPLY SCHEME | SM/00018 | SM/09994 | Augmentation | MVS | 914/JD | M/S A.B.G. CONSTRUCTION | 07-04-2022 | 05-08-2022 | 373
251 | JALPAIGURI | KRANTI WATER SUPPLY SCHEME | SM/00018 | SM/09994 | Augmentation | MVS | 210/JD | BOSE ENTERPRISE | 24-01-2022 | 24-04-2022
252 | JALPAIGURI | KRANTI WATER SUPPLY SCHEME | SM/00018 | SM/09994 | Augmentation | MVS | 209/JD | M/S SIBU DEY AND CO. | 24-01-2022 | 24-04-2022 | 662
253 | JALPAIGURI | Kumarpara Piped Water Supply Scheme. | SM/18491 |  | New | MVS | 773/JD | UNIBRO INFRASERV PRIVATE LIMITED | 27-03-2023 | 23-09-2023
254 | JALPAIGURI | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 |  | New | SVS | 192/JD | R.S CONSTRUCTION | 21-01-2022 | 22-03-2022 | 991
255 | JALPAIGURI | Kumlai Tea Garden Area Piped Water Supply Scheme. | SM/08875 |  | New | SVS | 1535/JD | MUMTAJ ALAM | 03-07-2025 | 17-08-2025 | 388
256 | JALPAIGURI | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15262 |  | New | MVS | 824/JD | S.S. CONSTRUCTION | 30-03-2023 | 26-09-2023 | 628
257 | JALPAIGURI | LATAGURI WATER SUPPLY SCHEME | SM/00028 |  |  | MVS | 995/JSSD | ALICK DUTTA | 05-01-2022 | 20-01-2022 | 116
258 | JALPAIGURI | LATAGURI WATER SUPPLY SCHEME | SM/00028 | SM/13278 | Augmentation | MVS | 1899/JD | CALCON CONSTRUCTIONS | 26-09-2022 | 25-12-2022 | 1406
259 | JALPAIGURI | LATAGURI WATER SUPPLY SCHEME | SM/00028 | SM/13278 | Augmentation | MVS | 262/JSSD | GOPRO CONSTRUCTION | 25-09-2024 | 25-10-2024 | 61
260 | JALPAIGURI | LATAGURI WATER SUPPLY SCHEME | SM/00028 | SM/13278 | Augmentation | MVS | 2059/JD | M/S SURAJIT DEY AND CO. | 03-11-2022 | 01-02-2023 | 1122
261 | JALPAIGURI | LATAGURI WATER SUPPLY SCHEME | SM/00028 | SM/13278 | Augmentation | MVS | 877/JD | SCEC BOENTER KDAS JOINT VENTURE | 05-04-2022 | 04-07-2022 | 1118
262 | JALPAIGURI | LATAGURI WATER SUPPLY SCHEME | SM/00028 | SM/13278 | Augmentation | MVS | 207/JD | M/S A.B.G. CONSTRUCTION | 24-01-2022 | 25-03-2022 | 4
263 | JALPAIGURI | Luksan Bazar Water Supply Scheme | SM/02729 | SM/06955 | Retrofitting | SVS | 566/JSSD | ALICK DUTTA | 01-02-2021 | 16-02-2021
264 | JALPAIGURI | Luksan Bazar Water Supply Scheme | SM/02729 | SM/06955 | Retrofitting | SVS | 1547/JD | SCEC BOENTER KDAS JOINT VENTURE | 31-12-2020 | 16-03-2021 | 92
265 | JALPAIGURI | Luksan Bazar Water Supply Scheme | SM/02729 | SM/06955 | Retrofitting | SVS | 547/JD | ALICK DUTTA | 28-02-2022 | 30-03-2022 | 105
266 | JALPAIGURI | Luksan Bazar Water Supply Scheme | SM/02729 | SM/06955 | Retrofitting | SVS | 1315/JD | ANUP SARKAR | 16-06-2022 | 31-07-2022 | 621
267 | JALPAIGURI | Luksan Bazar Water Supply Scheme | SM/02729 | SM/06955 | Retrofitting | SVS | 548/JD | GAP ENGINEERS ENTERPRISES | 28-02-2022 | 14-04-2022 | 347
268 | JALPAIGURI | Luksan Bazar Water Supply Scheme | SM/02729 | SM/06955 | Retrofitting | SVS | 566/JSSD | ALICK DUTTA | 01-02-2021 | 16-02-2021 | 8
269 | JALPAIGURI | Madhabdanga Piped Water Supply Scheme | SM/05031 | SM/06938 | Retrofitting | MVS | 399/JD | M/S SIBU DEY AND CO. | 24-02-2023 | 17-03-2023 | 100
270 | JALPAIGURI | Madhabdanga Piped Water Supply Scheme | SM/05031 | SM/06938 | Retrofitting | MVS | 1537/JD | ANUP SARKAR | 31-12-2020 | 01-03-2021 | 50
271 | JALPAIGURI | Madhabdanga Piped Water Supply Scheme | SM/05031 | SM/06938 | Retrofitting | MVS | 48/JD | M/S SIBU DEY AND CO. | 07-01-2021 | 08-03-2021 | 208
272 | JALPAIGURI | Madhabdanga Piped Water Supply Scheme | SM/05031 | SM/06938 | Retrofitting | MVS | 471/RWS | ALICK DUTTA | 15-10-2020 | 14-11-2020
273 | JALPAIGURI | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 |  | New | MVS | 28/JD | SUKES BASU MAJUMDAR | 10-04-2023 | 07-10-2023 | 985
274 | JALPAIGURI | MADHYA KHAGRABARI WATER SUPPLY SCHEME | SM/00808 | SM/10028 | Augmentation | MVS | 189/JD | M/S A.B.G. CONSTRUCTION | 21-01-2022 | 22-03-2022 | 1013
275 | JALPAIGURI | MADHYA KHAGRABARI WATER SUPPLY SCHEME | SM/00808 | SM/10028 | Augmentation | MVS | 213/JD | NARAYAN CHANDRA SAHA | 24-01-2022 | 25-03-2022 | 485
276 | JALPAIGURI | MADHYA KHAGRABARI WATER SUPPLY SCHEME | SM/00808 | SM/10028 | Augmentation | MVS | 194/JD | M/S A.B.G. CONSTRUCTION | 21-01-2022 | 22-03-2022 | 296
277 | JALPAIGURI | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 |  | New | MVS | 367/JD | MINTU CHAKRABORTY | 26-05-2023 | 22-11-2023 | 521
278 | JALPAIGURI | Manabari Tea Garden Area Piped Water Supply Scheme. | SM/06532 |  |  | MVS | 2168/JD | ASHIT KUMAR SINGHA | 22-12-2021 | 12-01-2022 | 550
279 | JALPAIGURI | Manabari Tea Garden Area Piped Water Supply Scheme. | SM/06532 |  |  | MVS | 2166/JD | KANAI LAL SEN | 22-12-2021 | 06-01-2022 | 450
280 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 510/JSSD | DEEP CONSTRUCTION | 03-11-2021 | 18-11-2021 | 108
281 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 1029/W/JSSD | SUBIR GHOSH | 31-01-2022 | 15-02-2022 | 110
282 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 76/JSSD | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 22-07-2022 | 06-08-2022 | 103
283 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/15098 | Augmentation | MVS | 701/JD | M/S. D.K. DEY & CO.. | 13-07-2023 | 11-09-2023 | 327
284 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 654/JSSD | DEEP CONSTRUCTION | 25-02-2021 | 12-03-2021 | 98
285 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 163/JSSD | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 24-08-2022 | 23-09-2022 | 70
286 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 102/JD | SUBIR SEN | 18-01-2021 | 02-02-2021 | 141
287 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 208/JD | ABHIJIT SARKAR | 11-02-2021 | 26-02-2021
288 | JALPAIGURI | Mathachulka Piped Water Supply Scheme | SM/05027 | SM/08284 | Retrofitting | MVS | 93/JSSD | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 22-07-2022 | 21-08-2022 | 35
289 | JALPAIGURI | MAYNAGURI WATER SUPPLY SCHEME | SM/00024 | SM/10042 | Augmentation | SVS | 225/JD | M/S SURAJIT DEY AND CO. | 25-01-2022 | 25-05-2022 | 2426
290 | JALPAIGURI | MAYNAGURI WATER SUPPLY SCHEME | SM/00024 | SM/10042 | Augmentation | SVS | 226/JD | M/S SURAJIT DEY AND CO. | 25-01-2022 | 25-05-2022 | 45
291 | JALPAIGURI | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 |  | New | SVS | 40/JD | SANDIP BANIK | 13-04-2023 | 10-10-2023 | 784
292 | JALPAIGURI | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 |  | New | SVS | 1503/JD | SANDIP BANIK | 30-09-2024 | 29-11-2024 | 286
293 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 |  |  | MVS | 996/JSSD | ALICK DUTTA | 05-01-2022 | 20-01-2022
294 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 | SM/11813 | Augmentation | MVS | 1669/JD | DIPAK KUMAR CHAKRABORTY | 24-11-2023 | 24-12-2023
295 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 |  |  | MVS | 1045/JSSD | DREAM CONSTRUCTION | 24-01-2022 | 08-02-2022
296 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 |  |  | MVS | 1056/JSSD | ALICK DUTTA | 24-01-2022 | 08-02-2022
297 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 | SM/11813 | Augmentation | MVS | 89/JSSD | GOURAB GUHA ROY | 22-07-2022 | 01-08-2022 | 125
298 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 |  |  | MVS | 1693/JD | KULDIP KAPOOR | 28-10-2021 | 12-11-2021 | 508
299 | JALPAIGURI | Metelibajar w/s scheme | SM/02548 |  |  | MVS | 1981/JD | M/S DEY & ROY CHOUDHURY | 03-12-2021 | 18-12-2021 | 399
300 | JALPAIGURI | Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/06301 |  |  | MVS | 1717/JD | JITENDRA NATH ROY | 29-10-2021 | 19-11-2021 | 570
301 | JALPAIGURI | Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/06301 |  |  | MVS | 288/JD | PROFULLA GHOSH | 02-02-2022 | 04-03-2022 | 565
302 | JALPAIGURI | Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/06301 |  |  | MVS | 1078/JD | AJIT KUMAR NAG | 02-07-2021 | 01-08-2021 | 496
303 | JALPAIGURI | Mogalkata Tea Garden Area Piped Water Supply Scheme | SM/06301 | SM/15075 | Augmentation | MVS | 1971/JD | JITENDRA NATH ROY | 03-01-2024 | 23-01-2024 | 196
304 | JALPAIGURI | MONDALGHAT WATER SUPPLY SCHEME | SM/00891 | SM/10087 | Augmentation | SVS | 345/JD | M/S SURAJIT DEY AND CO. | 03-02-2022 | 04-05-2022 | 514
305 | JALPAIGURI | MONDALGHAT WATER SUPPLY SCHEME | SM/00891 | SM/10087 | Augmentation | SVS | 338/JD | SIBU DEY | 03-02-2022 | 04-05-2022 | 247
306 | JALPAIGURI | MONDALGHAT WATER SUPPLY SCHEME | SM/00891 | SM/10087 | Augmentation | SVS | 339/JD | BISWANATH GHOSH | 03-02-2022 | 04-05-2022 | 253
307 | JALPAIGURI | Nagaisuree Tea Garden Area Piped Water Supply Scheme | SM/05359 | SM/06844 | Retrofitting | SVS | 1273/JD | SADHAN KARMAKAR | 18-11-2020 | 16-02-2021 | 426
308 | JALPAIGURI | Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/05885 |  |  | MVS | 1060/JD | BOSE ENTERPRISE | 13-10-2020 | 10-02-2021
309 | JALPAIGURI | Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/05885 | SM/15300 | Augmentation | SVS | 1291/JD | BOSE ENTERPRISE | 18-11-2020 | 16-02-2021 | 324
310 | JALPAIGURI | NAGRAKATA WATER SUPPLY SCHEME | SM/00037 | SM/05269 |  | MVS | 1983/JD | D. S. ENTERPRISE | 03-12-2021 | 02-01-2022 | 969
311 | JALPAIGURI | NAGRAKATA WATER SUPPLY SCHEME | SM/00037 | SM/05269 |  | MVS | 1692/JD | ANUP KUMAR KUNDU | 28-10-2021 | 18-11-2021 | 717
312 | JALPAIGURI | NAGRAKATA WATER SUPPLY SCHEME | SM/00037 | SM/05269 |  | MVS | 1427/JD | NEW KUNDU ENTERPRISE | 07-09-2021 | 28-09-2021 | 426
313 | JALPAIGURI | NAGRAKATA WATER SUPPLY SCHEME | SM/00037 | SM/05269 |  | MVS | 294/JSSD | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 27-09-2023 | 27-10-2023 | 117
314 | JALPAIGURI | NAGRAKATA WATER SUPPLY SCHEME | SM/00037 | SM/05269 |  | MVS | 636/JD | NARAYAN CHANDRA SAHA | 28-03-2025 | 12-05-2025
315 | JALPAIGURI | Nakhati Tea Garden Area Piped Water supply Scheme | SM/05884 | SM/06842 | Retrofitting | SVS | 1118/JD | R.S CONSTRUCTION | 02-11-2020 | 01-01-2021 | 237
316 | JALPAIGURI | Nakhati Tea Garden Area Piped Water supply Scheme | SM/05884 | SM/15116 | Augmentation | SVS | 122/JD | ADITRI ENTERPRISE | 16-01-2025 | 02-03-2025 | 44
317 | JALPAIGURI | Nayasailya Tea Garden Piped Water Supply Scheme | SM/04786 | SM/06956 | Retrofitting | SVS | 560/JSSD | PRIYABRATA KARMAKAR | 01-02-2021 | 16-02-2021
318 | JALPAIGURI | Nayasailya Tea Garden Piped Water Supply Scheme | SM/04786 | SM/06956 | Retrofitting | SVS | 13/JD | GOUTAM DAS | 04-01-2021 | 18-02-2021 | 81
319 | JALPAIGURI | Nayasailya Tea Garden Piped Water Supply Scheme | SM/04786 | SM/06956 | Retrofitting | SVS | 752/JD | GAP ENGINEERS ENTERPRISE | 13-05-2021 | 12-06-2021 | 15
320 | JALPAIGURI | Nayasailya Tea Garden Piped Water Supply Scheme | SM/04786 | SM/06956 | Retrofitting | SVS | 298/JSSD | ARATI CONSTRUCTION | 15-10-2020 | 30-10-2020 | 175
321 | JALPAIGURI | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 |  | New | MVS | 244/JD | SRINIWAS AGARWAL | 08-05-2023 | 04-11-2023 | 296
322 | JALPAIGURI | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15115 |  | New | MVS | 238/JD | PRASENJIT BASAK | 08-05-2023 | 04-11-2023 | 888
323 | JALPAIGURI | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 |  | New | MVS | 798/JD. | MD HAKIMUDDIN | 24-07-2023 | 20-01-2024 | 2260
324 | JALPAIGURI | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 |  | New | MVS | 1571/JD | MD HAKIMUDDIN | 04-10-2024 | 02-01-2025 | 732
325 | JALPAIGURI | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 |  | New | MVS | 2432/JD | MD HAKIMUDDIN | 24-12-2024 | 04-03-2025 | 238
326 | JALPAIGURI | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14911 |  | New | SVS | 943/JD | J.M. CONSTRUCTION | 08-08-2023 | 04-02-2024 | 340
327 | JALPAIGURI | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15296 |  | New | MVS | 242/JD | M/S SURAJIT DEY AND CO. | 08-05-2023 | 04-11-2023 | 409
328 | JALPAIGURI | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 |  | New | MVS | 800/JD. | GHANASHYAM SARKAR | 24-07-2023 | 20-01-2024 | 594
329 | JALPAIGURI | ODLABARI WATER SUPPLY SCHEME | SM/00140 | SM/13790 | Augmentation | SVS | 880/JD | M/S SURAJIT DEY AND CO. | 05-04-2022 | 04-07-2022 | 872
330 | JALPAIGURI | ODLABARI WATER SUPPLY SCHEME | SM/00140 | SM/13790 | Augmentation | SVS | 881/JD | CALCON CONSTRUCTIONS | 05-04-2022 | 04-07-2022 | 290
331 | JALPAIGURI | ODLABARI WATER SUPPLY SCHEME | SM/00140 | SM/13790 | Augmentation | SVS | 191/JSSD | BIMAN DAS | 02-09-2022 | 02-10-2022 | 112
332 | JALPAIGURI | ODLABARI WATER SUPPLY SCHEME | SM/00140 | SM/13790 | Augmentation | SVS | 186/JSSD | BIMAN DAS | 31-08-2022 | 30-09-2022 | 132
333 | JALPAIGURI | ODLABARI WATER SUPPLY SCHEME | SM/00140 | SM/13790 | Augmentation | SVS | 162/JSSD | BIMAN DAS | 24-08-2022 | 23-09-2022 | 173
334 | JALPAIGURI | Palasbari Tea Garden Area Piped Water Supply Scheme | SM/05942 |  |  | MVS | 1303/JD | D S ENTERPRISE | 24-11-2020 | 08-01-2021 | 40
335 | JALPAIGURI | Palasbari Tea Garden Area Piped Water Supply Scheme | SM/05942 |  |  | MVS | 1280/JD | SANKAR DAS | 18-11-2020 | 02-01-2021 | 97
336 | JALPAIGURI | Palasbari Tea Garden Area Piped Water Supply Scheme | SM/05942 |  |  | MVS | 132/JD | SANKAR DAS | 14-01-2022 | 04-02-2022 | 109
337 | JALPAIGURI | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 |  | New | MVS | 1764/JD | UNIBRO INFRASERV PRIVATE LIMITED | 08-12-2023 | 05-06-2024
338 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 |  |  | MVS | 535/JD | DIPANKAR DUTTA | 24-02-2022 | 26-03-2022 | 140
339 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 |  |  | MVS | 1539/JD | PROVA CONSTRUCTION | 31-12-2020 | 01-03-2021 | 706
340 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 | SM/15076 | Augmentation | MVS | 284/RWS | PARAMJYOTI ENTERPRISE | 29-03-2023 | 19-04-2023 | 95
341 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 | SM/15076 | Augmentation | MVS | 170/RWS | SAHA CONSTRUCTION | 28-02-2023 | 21-03-2023 | 42
342 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 |  |  | MVS | 2042/JD | MONOTOSH ROY | 07-12-2021 | 28-12-2021
343 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 |  |  | MVS | 2041/JD | RANA DEY | 07-12-2021 | 28-12-2021 | 445
344 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 |  |  | MVS | 1298/JD | MONOTOSH ROY | 23-11-2020 | 07-01-2021 | 711
345 | JALPAIGURI | Paschim Salbari Piped Water Supply Scheme | SM/06120 |  |  | MVS | 1077/JD | NARAYAN CHANDRA SAHA | 02-07-2021 | 01-08-2021 | 470
346 | JALPAIGURI | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 |  | New | MVS | 264/JD | ANUP SARKAR | 10-05-2023 | 06-11-2023 | 374
347 | JALPAIGURI | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15978 |  | New | SVS | 346/JD. | SRINIWAS AGARWAL | 23-05-2023 | 19-11-2023
348 | JALPAIGURI | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 |  | New | SVS | 1707/JD | M/S KAMAK ENGINEERS AND CO. | 04-12-2023 | 01-06-2024 | 190
349 | JALPAIGURI | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 |  | New | SVS | 398/A/JD | GARGO TRADERS | 06-06-2023 | 03-12-2023 | 544
350 | JALPAIGURI | PATKATA ZONE-III PIPED WATER SUPPLY | SM/14878 |  | New | SVS | 957/JD | JAYA SARKAR | 09-08-2024 | 07-12-2024 | 297
351 | JALPAIGURI | Patkidaha Piped Water Supply Scheme | SM/04800 | SM/07304 | Retrofitting | MVS | 209/JD | PRABIR SHOME | 11-02-2021 | 13-03-2021 | 169
352 | JALPAIGURI | Patkidaha Piped Water Supply Scheme | SM/04800 | SM/06961 | Retrofitting | MVS | 1542/JD | SUKES BASU MAJUMDAR | 31-12-2020 | 01-03-2021
353 | JALPAIGURI | Patkidaha Piped Water Supply Scheme | SM/04800 | SM/06961 | Retrofitting | MVS | 1541/JD | KULDIP KAPOOR | 31-12-2020 | 14-02-2021 | 2
354 | JALPAIGURI | Patkidaha Piped Water Supply Scheme | SM/04800 | SM/15085 | Augmentation | MVS | 1529/JD | SADHAN KARMAKAR | 01-10-2024 | 31-10-2024
355 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 |  | New | MVS | 269/JSSD | PRADIP SAHA | 25-09-2024 | 25-10-2024 | 20
356 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 |  | New | MVS | 755/JD | PRADIP SAHA | 24-03-2023 | 20-09-2023 | 304
357 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 |  | New | SVS | 676/JD | NISHITH RANJAN KARMAKAR | 16-03-2023 | 12-09-2023 | 161
358 | JALPAIGURI | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 |  | New | SVS | 716/JD | BOSE ENTERPRISE | 20-03-2023 | 16-09-2023 | 537
359 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/15101 | Augmentation | SVS | 2494/JD | SUKES BASU MAJUMDAR | 28-02-2024 | 29-03-2024 | 946
360 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/09463 | Augmentation | SVS | 1298/JD | B.M CONSTRUCTION | 14-06-2022 | 13-08-2022 | 500
361 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 1973/JD | B.M CONSTRUCTION | 03-01-2024 | 24-01-2024 | 363
362 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 437/RWS | SINGHA CONSTRUCTION | 09-10-2020 | 08-11-2020
363 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 98/JD | SINGHA CONSTRUCTION | 15-01-2021 | 14-02-2021
364 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 99/JD | B.M CONSTRUCTION | 15-01-2021 | 16-03-2021 | 64
365 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 748/JD | DEBASISH DEY | 13-05-2021 | 12-06-2021 | 521
366 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 1334/JD | B.M CONSTRUCTION | 23-08-2021 | 07-09-2021 | 147
367 | JALPAIGURI | Porapara & adj. mouzas W/S Scheme | SM/03340 | SM/08035 | Retrofitting | SVS | 1334/JD | B.M CONSTRUCTION | 23-08-2021 | 07-09-2021 | 354
368 | JALPAIGURI | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 |  | New | SVS | 436/JD. | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 08-06-2023 | 07-08-2023 | 97
369 | JALPAIGURI | PURBA DAUKIMARI WATER SUPPLY SCHEME | SM/00818 |  |  | MVS | 1258/JD | RABINDRANATH DUTTA | 10-08-2021 | 25-08-2021 | 90
370 | JALPAIGURI | PURBA DAUKIMARI WATER SUPPLY SCHEME | SM/00818 |  |  | MVS | 333/JD | SUKES BASU MAJUMDAR | 02-02-2022 | 02-06-2022 | 1586
371 | JALPAIGURI | PURBA DAUKIMARI WATER SUPPLY SCHEME | SM/00818 |  |  | MVS | 130/JD | RABINDRANATH DUTTA | 14-01-2022 | 04-02-2022 | 89
372 | JALPAIGURI | Purba Duramari Piped Water Supply Scheme | SM/06321 | SM/15326 | Augmentation | MVS | 334/JD | MONTOSH GHOSH | 22-05-2023 | 21-07-2023 | 97
373 | JALPAIGURI | Purba Duramari Piped Water Supply Scheme | SM/06321 | SM/15326 | Augmentation | MVS | 803/JD. | DEEP CONSTRUCTION | 24-07-2023 | 14-08-2023 | 283
374 | JALPAIGURI | Purba Duramari Piped Water Supply Scheme | SM/06321 |  |  | MVS | 1059/JSSD | ADITRI ENTERPRISE | 24-01-2022 | 08-02-2022 | 99
375 | JALPAIGURI | Purba Duramari Piped Water Supply Scheme | SM/06321 |  |  | MVS | 1986/JD | M/S SIBU DEY AND CO. | 03-12-2021 | 02-01-2022 | 838
376 | JALPAIGURI | Purba Duramari Piped Water Supply Scheme | SM/06321 |  |  | MVS | 1714/JD | LOKNATH CONSTRUCTION | 29-10-2021 | 13-11-2021 | 376
377 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 1291/JD | ARATI CONSTRUCTION | 14-06-2022 | 05-07-2022 | 50
378 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 1075/JD | ARATI CONSTRUCTION | 02-07-2021 | 01-08-2021 | 422
379 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 295/JD | MONOJ GHOSH | 24-02-2021 | 26-03-2021 | 204
380 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 295/JD | MONOJ GHOSH | 24-02-2021 | 26-03-2021 | 253
381 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/09564 | Augmentation | MVS | 1587/JD | SAHA CONSTRUCTION | 06-11-2023 | 06-12-2023 | 37
382 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 628/JD | SANKAR DAS | 13-03-2023 | 27-04-2023 | 423
383 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 291/JD | A.P CONSTRUCTION | 23-02-2021 | 25-03-2021 | 2
384 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 2044/JD | ARATI CONSTRUCTION | 07-12-2021 | 28-12-2021 | 396
385 | JALPAIGURI | Purba Magurmari & adj. mouzas W/S Scheme | SM/03341 | SM/07891 | Retrofitting | MVS | 1690/JD | ANUP SARKAR | 28-10-2021 | 27-11-2021 | 360
386 | JALPAIGURI | Purba Salbari Water Supply Scheme | SM/01365 | SM/09861 | Augmentation | MVS | 879/JD | M/S GARGO TRADERS | 05-04-2022 | 03-08-2022 | 2101
387 | JALPAIGURI | Raipur Tea Garden Area Piped Water Supply scheme | SM/06311 |  |  | MVS | 1270/JD | ANUP KUMAR KUNDU | 18-11-2020 | 16-02-2021 | 80
388 | JALPAIGURI | RAMSAI WATER SUPPLY SCHEME | SM/00020 | SM/10033 | Augmentation | MVS | 206/JD | ASHIT KUMAR SINGHA | 24-01-2022 | 24-04-2022 | 908
389 | JALPAIGURI | RAMSAI WATER SUPPLY SCHEME | SM/00020 | SM/10033 | Augmentation | MVS | 190/JD | PARESH CHANDRA GUHA | 21-01-2022 | 21-04-2022 | 1076
390 | JALPAIGURI | RAMSAI WATER SUPPLY SCHEME | SM/00020 | SM/10033 | Augmentation | MVS | 191/JD | M/S R.N. TRADERS | 21-01-2022 | 21-04-2022 | 1084
391 | JALPAIGURI | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14880 |  | New | MVS | 940/JD | M/S SARKAR ENTERPRISE | 08-08-2023 | 04-02-2024 | 991
392 | JALPAIGURI | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 |  | New | MVS | 845/JD | GOEL CONSTRUCTION CO. | 28-07-2023 | 24-01-2024 | 1681
393 | JALPAIGURI | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 |  | New | MVS | 460/JD | GOEL CONSTRUCTION CO. | 11-03-2025 | 10-05-2025 | 320
394 | JALPAIGURI | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14885 |  | New | MVS | 2749/JD | GOEL CONSTRUCTION CO. | 14-03-2024 | 13-04-2024 | 696
395 | JALPAIGURI | Red Bank Tea Garden Piped Water Supply Scheme | SM/05361 | SM/06843 | Retrofitting | MVS | 1295/JD | M/S R.N. TRADERS | 23-11-2020 | 21-02-2021 | 749
396 | JALPAIGURI | Riabari Tea Garden Area Piped Water Supply Scheme | SM/05483 |  |  | MVS | 1287/JD | SAPTASWA SARKAR | 18-11-2020 | 16-02-2021
397 | JALPAIGURI | Sajnapara Piped Water Supply Scheme | SM/04854 | SM/06959 | Retrofitting | SVS | 1543/JD | RAGHU DAS | 31-12-2020 | 16-03-2021 | 24
398 | JALPAIGURI | Sajnapara Piped Water Supply Scheme | SM/04854 | SM/07302 | Retrofitting | SVS | 221/JD | RAGHU DAS | 12-02-2021 | 14-03-2021 | 26
399 | JALPAIGURI | Sajnapara Piped Water Supply Scheme | SM/04854 | SM/09391 | Augmentation | MVS | 1801/JD | RAGHU DAS | 14-09-2022 | 05-10-2022 | 51
400 | JALPAIGURI | Sajnapara Piped Water Supply Scheme | SM/04854 | SM/07302 | Retrofitting | SVS | 1976/JD | ALOKE DEY | 03-01-2024 | 02-02-2024 | 95
401 | JALPAIGURI | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 |  | New | SVS | 714/JD | SANTALALL & BROTHERS | 20-03-2023 | 16-09-2023 | 404
402 | JALPAIGURI | Samsing Tea Garden Area Piped Water Supply Scheme | SM/05883 |  |  | MVS | 568/JSSD | PINTU DAS | 01-02-2021 | 16-02-2021 | 100
403 | JALPAIGURI | Samsing Tea Garden Area Piped Water Supply Scheme | SM/05883 |  |  | MVS | 224/JD | M/S. D.K. DEY & CO.. | 12-02-2021 | 29-03-2021 | 171
404 | JALPAIGURI | Samsing Tea Garden Area Piped Water Supply Scheme | SM/05883 |  |  | MVS | 1304/JD | LOKNATH CONSTRUCTIOIN | 24-11-2020 | 23-01-2021 | 398
405 | JALPAIGURI | SANYASIKATA MOUZA WATER SUPPLY SCHEME | SM/00155 | SM/09996 | Augmentation | SVS | 1228/JD | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 01-06-2022 | 29-09-2022 | 1541
406 | JALPAIGURI | SANYASIKATA MOUZA WATER SUPPLY SCHEME | SM/00155 | SM/09996 | Augmentation | SVS | 1100/JD | UMWELT ENGINEER PRIVATE LIMITED | 12-05-2022 | 10-08-2022 | 2280
407 | JALPAIGURI | Saogaon Tea Garden Area Piped Water Supply Scheme. | SM/06531 |  |  | MVS | 289/JD | NARAYAN CHANDRA SAHA | 02-02-2022 | 18-04-2022 | 1996
408 | JALPAIGURI | Saptibari Piped Water Supply Scheme. | SM/18759 |  | New | MVS | 1352/JD | SCEC BOENTER KDAS JOINT VENTURE | 26-09-2023 | 24-03-2024 | 770
409 | JALPAIGURI | Saptibari Piped Water Supply Scheme. | SM/18759 |  | New | MVS | 1350/JD | SCEC BOENTER KDAS JOINT VENTURE | 26-09-2023 | 24-03-2024
410 | JALPAIGURI | Saptibari Piped Water Supply Scheme. | SM/18759 |  | New | MVS | 1351/JD | SCEC BOENTER KDAS JOINT VENTURE | 26-09-2023 | 24-03-2024 | 1462
411 | JALPAIGURI | Sathkaya Tea Garden Area Piped Water Supply Scheme | SM/05570 |  |  | MVS | 1274/JD | LOKNATH CONSTRUCTIOIN | 18-11-2020 | 17-01-2021 | 396
412 | JALPAIGURI | Sathkaya Tea Garden Area Piped Water Supply Scheme | SM/05570 |  |  | MVS | 565/JSSD | SOMNATH ROY | 01-02-2021 | 16-02-2021 | 111
413 | JALPAIGURI | Satkhamar Piped Water Supply Scheme. | SM/18760 |  | New | MVS | 1671/JD | SUKES BASU MAJUMDAR | 24-11-2023 | 22-05-2024 | 2390
414 | JALPAIGURI | Satkhamar Piped Water Supply Scheme. | SM/18760 |  | New | MVS | 737/JD | ASIM GUPTA | 26-07-2024 | 09-10-2024 | 493
415 | JALPAIGURI | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 |  | New | SVS | 753/JD | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 24-03-2023 | 20-09-2023 | 986
416 | JALPAIGURI | SHIKARPUR WATER SUPPLY SCHEME | SM/00027 | SM/09562 | Augmentation | MVS | 2622/JD | SCEC BOENTER AND KDAS JOINT VENTURE | 07-03-2024 | 01-01-2025 | 412
417 | JALPAIGURI | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 |  | New | MVS | 823/JD | S.S. CONSTRUCTION | 30-03-2023 | 26-09-2023 | 891
418 | JALPAIGURI | Sisubari Tea Garden Piped Water Supply Scheme | SM/16778 |  | New | SVS | 710/JD | PRADIP SAHA | 13-07-2023 | 09-01-2024 | 125
419 | JALPAIGURI | Songachhi Tea Garden Area Piped Water Supply Scheme | SM/06309 | SM/15077 | Augmentation | SVS | 441/JD. | PINAKI MITRA | 08-06-2023 | 07-08-2023 | 81
420 | JALPAIGURI | Songachhi Tea Garden Area Piped Water Supply Scheme | SM/06309 |  |  | MVS | 1302/JD | M/S M.B. DESIGN | 24-11-2020 | 24-12-2020 | 310
421 | JALPAIGURI | Songachhi Tea Garden Area Piped Water Supply Scheme | SM/06309 |  |  | MVS | 1535/JD | ALOKE DEY | 31-12-2020 | 01-03-2021 | 205
422 | JALPAIGURI | Songachhi Tea Garden Area Piped Water Supply Scheme | SM/06309 |  |  | MVS | 2037/JD | R.S CONSTRUCTION | 07-12-2021 | 22-12-2021 | 48
423 | JALPAIGURI | Songachhi Tea Garden Area Piped Water Supply Scheme | SM/06309 |  |  | MVS | 557/RWS | R.S CONSTRUCTION | 01-09-2022 | 02-09-2022 | 40
424 | JALPAIGURI | Songachhi Tea Garden Area Piped Water Supply Scheme | SM/06309 |  |  | MVS | 1089/JD | R.S CONSTRUCTION | 05-07-2021 | 19-08-2021 | 179
425 | JALPAIGURI | SUKANI WATER SUPPLY SCHEME | SM/00149 | SM/09995 | Augmentation | MVS | 1434/JD | SUBRATA GOSWAMI | 05-10-2023 | 04-11-2023 | 408
426 | JALPAIGURI | SUKANI WATER SUPPLY SCHEME | SM/00149 | SM/09995 | Augmentation | MVS | 1262/JD | BILTU DAS | 13-09-2023 | 13-10-2023 | 438
427 | JALPAIGURI | SUKANI WATER SUPPLY SCHEME | SM/00149 | SM/09995 | Augmentation | MVS | 709/JD | MRINMOY KANTI DUTTA | 13-07-2023 | 12-08-2023 | 399
428 | JALPAIGURI | SUKANI WATER SUPPLY SCHEME | SM/00149 | SM/09995 | Augmentation | MVS | 1229/JD | MINTU CHAKRABORTY | 01-06-2022 | 29-09-2022 | 1715
429 | JALPAIGURI | SUKANI WATER SUPPLY SCHEME | SM/00149 | SM/09995 | Augmentation | MVS | 1101/JD | BANSBERIA CONSTRUCTION CO. | 12-05-2022 | 09-09-2022 | 550
430 | JALPAIGURI | SUKANI WATER SUPPLY SCHEME | SM/00149 | SM/09995 | Augmentation | MVS | 1263/JD | ANUP KUMAR KUNDU | 13-09-2023 | 13-10-2023 | 918
431 | JALPAIGURI | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 |  | New | SVS | 2755/JD | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 15-03-2024 | 13-06-2024 | 136
432 | JALPAIGURI | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. | SM/08578 |  | New | SVS | 255/JSSD | ARUP SARKAR | 24-09-2024 | 24-10-2024 | 60
433 | JALPAIGURI | Syli Tea Garden Area Piped Water Supply Scheme | SM/05569 |  |  | MVS | 1285/JD | M/S SURAJIT DEY AND CO. | 18-11-2020 | 16-02-2021 | 15
434 | JALPAIGURI | Syli Tea Garden Area Piped Water Supply Scheme | SM/05569 | SM/15117 | Augmentation | SVS | 1922/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 30-10-2024 | 30-10-2025 | 489
435 | JALPAIGURI | Syli Tea Garden Area Piped Water Supply Scheme | SM/05569 | SM/15117 | Augmentation | SVS | 128/JD | SAHA CONSTRUCTION | 28-04-2023 | 27-07-2023 | 300
436 | JALPAIGURI | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 |  | New | SVS | 938/JD | M/S RATAN KUMAR DAS GUPTA AND CO | 08-08-2023 | 04-02-2024 | 210
437 | JALPAIGURI | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/14883 |  | New | MVS | 265/JD | M/S SARKAR ENTERPRISE | 10-05-2023 | 06-11-2023 | 774
438 | JALPAIGURI | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 |  | New | MVS | 351/JD | SUKES BASU MAJUMDAR | 24-05-2023 | 20-11-2023 | 1230
439 | JALPAIGURI | UTTAR BHUSKADANGA &GARTALI JALPESH WITH PROVISION OF W/S TO JALPESH MELA | SM/00021 | SM/09099 | Retrofitting | MVS | 254/JD | MRINMOY KANTI DUTTA | 31-01-2022 | 01-04-2022 | 429
440 | JALPAIGURI | UTTAR BHUSKADANGA &GARTALI JALPESH WITH PROVISION OF W/S TO JALPESH MELA | SM/00021 |  |  | MVS | 69/RWS | BALARAM GHOSH | 12-02-2021 | 27-02-2021 | 96
441 | JALPAIGURI | Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/06323 |  |  | MVS | 1995/JD | M/S SURAJIT DEY AND CO. | 03-12-2021 | 02-01-2022 | 208
442 | JALPAIGURI | Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme | SM/06323 |  |  | MVS | 1994/JD | PARESH CHANDRA GUHA | 03-12-2021 | 02-01-2022 | 793
443 | JALPAIGURI | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME | SM/14919 |  | New | SVS | 773/JD | UNIBRO INFRASERV PRIVATE LIMITED | 27-03-2023 | 23-09-2023
444 | JALPAIGURI | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME | SM/14914 |  | New | MVS | 699/JD | M/S SIBU DEY AND CO. | 13-07-2023 | 09-01-2024 | 193
445 | JALPAIGURI | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14886 |  | New | MVS | 395/A/JD | S.S. CONSTRUCTION | 05-06-2023 | 02-12-2023 | 779
446 | JALPAIGURI | Water Supply Scheme for Arji Garalbari & adj. mouzas | SM/04772 | SM/06840 | Retrofitting | MVS | 1498/JD | BISWAJIT BHADURI | 22-12-2020 | 21-01-2021 | 22
447 | JALPAIGURI | Water Supply Scheme for Arji Garalbari & adj. mouzas | SM/04772 | SM/06840 | Retrofitting | MVS | 1268/JD | NARAYAN CHAKRABORTY | 18-11-2020 | 16-02-2021
448 | JALPAIGURI | Water Supply Scheme for Arji Garalbari & adj. mouzas | SM/04772 | SM/06840 | Retrofitting | MVS | 521/RWS | RANJIT KARMAKAR | 30-07-2021 | 14-08-2021 | 67
449 | JALPAIGURI | Water Supply Scheme for Arji Garalbari & adj. mouzas | SM/04772 | SM/06840 | Retrofitting | MVS | 600/JD | RANJIT KARMAKAR | 09-03-2023 | 30-03-2023 | 52
450 | JALPAIGURI | Water Supply Scheme for Charerbari & Adj. Mouzas | SM/03578 | SM/06937 | Retrofitting | MVS | 222/JD | M/S DEY & ROY CHOUDHURY | 12-02-2021 | 29-03-2021 | 256
451 | JALPAIGURI | Water Supply Scheme for Charerbari & Adj. Mouzas | SM/03578 | SM/06937 | Retrofitting | MVS | 91/JD | KAMALESH SEN | 14-01-2021 | 28-02-2021 | 423
452 | JALPAIGURI | Water Supply Scheme for Charerbari & Adj. Mouzas | SM/03578 | SM/06937 | Retrofitting | MVS | 1552/JD | NEW KUNDU ENTERPRISE | 31-12-2020 | 14-02-2021 | 20
453 | JALPAIGURI | Water Supply Scheme for Charerbari & Adj. Mouzas | SM/03578 | SM/06937 | Retrofitting | MVS | 100/JD | SANKAR DAS | 18-01-2021 | 04-03-2021 | 343
454 | JALPAIGURI | Water Supply Scheme for Charerbari & Adj. Mouzas | SM/03578 | SM/06937 | Retrofitting | MVS | 1284/JD | RAGHU DAS | 18-11-2020 | 02-01-2021 | 3
455 | JALPAIGURI | Water Supply Scheme for Hope Tea Garden Mouza | SM/04783 | SM/06953 | Retrofitting | SVS | 30/JD | UMWELT ENGINEER PRIVATE LIMITED | 05-01-2021 | 21-03-2021 | 277
456 | JALPAIGURI | Water Supply Scheme for Hope Tea Garden Mouza | SM/04783 | SM/09862 | Augmentation | SVS | 293/JSSD | GOUTAM DAS | 27-09-2023 | 27-10-2023 | 207
457 | JALPAIGURI | Water Supply Scheme for Hope Tea Garden Mouza | SM/04783 | SM/09862 | Augmentation | SVS | 1049/JSSD | GOUTAM DAS | 24-01-2022 | 08-02-2022 | 120
458 | JALPAIGURI | Water Supply Scheme for Jiti Tea Garden Mouza | SM/04789 | SM/06952 | Retrofitting | SVS | 1549/JD | CALCON CONSTRUCTIONS | 31-12-2020 | 01-03-2021 | 698
459 | JALPAIGURI | Water Supply Scheme for Jiti Tea Garden Mouza | SM/04789 | SM/06952 | Retrofitting | SVS | 1550/JD | PARAMJYOTI ENTERPRISE | 31-12-2020 | 30-01-2021
460 | JALPAIGURI | Water Supply Scheme for Jiti Tea Garden Mouza | SM/04789 | SM/06952 | Retrofitting | SVS | 94/JSSD | ARUP SARKAR | 22-07-2022 | 21-08-2022 | 15
461 | JALPAIGURI | Water Supply Scheme for Jiti Tea Garden Mouza | SM/04789 | SM/06952 | Retrofitting | SVS | 82/JSSD | ARUP SARKAR | 22-07-2022 | 11-08-2022 | 61
462 | JALPAIGURI | Water Supply Scheme for Jiti Tea Garden Mouza | SM/04789 | SM/06952 | Retrofitting | SVS | 563/JSSD | NARAYAN CHANDRA ADHIKARY | 01-02-2021 | 16-02-2021
463 | JALPAIGURI | Water Supply Scheme for Mainatali & Adj. Mouzas | SM/03592 | SM/06960 | Retrofitting | SVS | 41/JD | BALAJI UDDYOG | 06-01-2021 | 07-03-2021 | 53
464 | JALPAIGURI | Water Supply Scheme for Mainatali & Adj. Mouzas | SM/03592 | SM/06960 | Retrofitting | SVS | 51/JD | UMWELT ENGINEER PRIVATE LIMITED | 08-01-2021 | 09-03-2021 | 15
465 | JALPAIGURI | Water Supply Scheme for Mainatali & Adj. Mouzas | SM/03592 | SM/07303 | Retrofitting | SVS | 310/JD | SANJIT SAHA | 26-02-2021 | 28-03-2021 | 496
466 | JALPAIGURI | WATER SUPPLY SCHEME FOR PURBA BATABARI (PART) &ADJ.MOUZA | SM/01814 | SM/09864 | Augmentation | MVS | 863/JD | UNIBRO INFRASERV PRIVATE LIMITED | 01-04-2022 | 30-06-2022 | 780
467 | JALPAIGURI | Youngtong Tea Garden Area Piped Water Supply Scheme | SM/05357 | SM/06846 | Retrofitting | SVS | 1080/JD | ASHIT KUMAR SINGHA | 15-10-2020 | 29-11-2020 | 79
468 | JALPAIGURI | Youngtong Tea Garden Area Piped Water Supply Scheme | SM/05357 | SM/15299 | Augmentation | SVS | 439/JD. | ASHIS DUTTA | 08-06-2023 | 07-08-2023 | 50
469 | JALPAIGURI | Youngtong Tea Garden Area Piped Water Supply Scheme | SM/05357 | SM/15299 | Augmentation | SVS | 500/JSSD | D. S. ENTERPRISE | 02-01-2024 | 01-02-2024 | 24
Total | [10 empty] | 185371