## Issued Work Order (UTTAR DINAJP
Issued Work Order (UTTAR DINAJPUR)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | UTTAR DINAJPUR | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 |  | New | MVS | 621/RD/PHE | M/S SOMNATH KUNDU | 28-02-2023 | 28-02-2024 | 956
2 | UTTAR DINAJPUR | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 |  | New | MVS | 1035/RD/PHE | SOVAN KUMAR ROY | 04-04-2023 | 30-12-2023
3 | UTTAR DINAJPUR | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. | SM/13456 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 208
4 | UTTAR DINAJPUR | Amalbari Piped Water Supply Scheme | SM/06059 | SM/07073 | Retrofitting | MVS | 1418/RD/PHE | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 11-12-2020 | 10-01-2021 | 246
5 | UTTAR DINAJPUR | Amalbari Piped Water Supply Scheme | SM/06059 | SM/07073 | Retrofitting | MVS | 1417/RD/PHE | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 11-12-2020 | 10-01-2021 | 247
6 | UTTAR DINAJPUR | Amalbari Piped Water Supply Scheme | SM/06059 | SM/07073 | Retrofitting | MVS | 1420/RD/PHE | SANJIB BHATTACHARJEE | 11-12-2020 | 10-01-2021 | 249
7 | UTTAR DINAJPUR | Amalbari Piped Water Supply Scheme | SM/06059 | SM/07073 | Retrofitting | MVS | 467/RD/PHE | M/S BHOWMIK ENTERPRISE | 26-02-2021 | 28-03-2021 | 180
8 | UTTAR DINAJPUR | Amalbari Piped Water Supply Scheme | SM/06059 | SM/07073 | Retrofitting | MVS | 1440/RD/PHE | DIPANKAR SARKAR | 11-12-2020 | 10-01-2021 | 245
9 | UTTAR DINAJPUR | Amalbari Piped Water Supply Scheme | SM/06059 | SM/07073 | Retrofitting | MVS | 1419/RD/PHE | LOKENATH CO-OP LBOUR CONTRACT &CONSTRUCTION SOCIETY LTD. | 11-12-2020 | 10-01-2021 | 248
10 | UTTAR DINAJPUR | Amalijhari Piped Water Supply Scheme | SM/06042 | SM/07146 | Retrofitting | MVS | 1438/RD/PHE | M/S P.S ENTERPRISE | 11-12-2020 | 10-01-2021 | 225
11 | UTTAR DINAJPUR | Amalijhari Piped Water Supply Scheme | SM/06042 | SM/07146 | Retrofitting | MVS | 1437/RD/PHE | HAQUE CONSTRUCTION | 11-12-2020 | 10-01-2021 | 212
12 | UTTAR DINAJPUR | Amalijhari Piped Water Supply Scheme | SM/06042 | SM/07146 | Retrofitting | MVS | 1421/RD/PHE | MAA SHEETALA ENTERPRISE | 11-12-2020 | 10-01-2021 | 228
13 | UTTAR DINAJPUR | Amalijhari Piped Water Supply Scheme | SM/06042 | SM/07146 | Retrofitting | MVS | 1435/RD/PHE | SAMIRAN PODDAR | 11-12-2020 | 10-01-2021 | 223
14 | UTTAR DINAJPUR | Amalijhari Piped Water Supply Scheme | SM/06042 | SM/07146 | Retrofitting | MVS | 1439/RD/PHE | AJIT PARMANIK | 11-12-2020 | 10-01-2021 | 227
15 | UTTAR DINAJPUR | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. | SM/12707 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 215
16 | UTTAR DINAJPUR | ATGHARA PIPED WATER SUPPLY SCHEME | SM/13796 |  | New | MVS | 290/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 01-02-2023 | 01-02-2024 | 1250
17 | UTTAR DINAJPUR | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15215 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 110
18 | UTTAR DINAJPUR | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12778 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 184
19 | UTTAR DINAJPUR | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/16536 |  | New | MVS | 1068/RD/PHE | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 11-04-2023 | 23-04-2023 | 1235
20 | UTTAR DINAJPUR | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ | SM/11643 |  | New | MVS | 589/RD/PHE | PRASANTA DUTTA | 24-02-2023 | 24-02-2024 | 890
21 | UTTAR DINAJPUR | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16222 |  | New | MVS | 1277/RD/PHE | BHOLA PAUL | 08-05-2023 | 02-02-2024 | 832
22 | UTTAR DINAJPUR | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16223 |  | New | MVS | 1278/RD/PHE | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 08-05-2023 | 02-02-2024 | 835
23 | UTTAR DINAJPUR | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 |  | New | MVS | 3746/RD/PHE | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 18-12-2024 | 01-02-2025
24 | UTTAR DINAJPUR | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/14146 |  | New | MVS | 563/RD/PHE | BHOLA PAUL | 23-02-2023 | 23-02-2024 | 1012
25 | UTTAR DINAJPUR | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 |  | New | MVS | 587/RD/PHE | M/S MAA TARA CONSTRUCTION BIRNAGAR | 24-02-2023 | 24-02-2024 | 1749
26 | UTTAR DINAJPUR | BALARAMPUR PIPED WATER SUPPLY SCHEME | SM/13520 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 56
27 | UTTAR DINAJPUR | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 |  | New | MVS | 68/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 16-01-2023 | 16-01-2024 | 1201
28 | UTTAR DINAJPUR | BALDIABASA Piped Water Supply Scheme | SM/13234 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 934
29 | UTTAR DINAJPUR | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/17631 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
30 | UTTAR DINAJPUR | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16505 |  | New | SVS | 680/RD/PHE | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 06-03-2023 | 04-06-2023 | 156
31 | UTTAR DINAJPUR | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11825 |  | New | MVS | 561/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23-02-2023 | 23-02-2024 | 1448
32 | UTTAR DINAJPUR | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. | SM/16471 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
33 | UTTAR DINAJPUR | BANIKANER ALISA RAHATPUR PWSS | SM/12522 |  | New | MVS | 551/RD/PHE | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 23-02-2023 | 21-10-2023 | 386
34 | UTTAR DINAJPUR | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18167 |  | New | SVS | 1557/RD/PHE | UTTAM SAHA | 29-05-2023 | 27-08-2023
35 | UTTAR DINAJPUR | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
36 | UTTAR DINAJPUR | BARA MIRCHA Piped Water Supply Scheme | SM/12397 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 353
37 | UTTAR DINAJPUR | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 186
38 | UTTAR DINAJPUR | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 |  | New | SVS | 297/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 01-02-2023 | 01-02-2024
39 | UTTAR DINAJPUR | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
40 | UTTAR DINAJPUR | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/16226 |  | New | MVS | 2628/RD/PHE | A D ENTERPRISE | 13-09-2023 | 10-05-2024 | 128
41 | UTTAR DINAJPUR | Barobila Water Supply Scheme | SM/01863 | SM/06726 | Retrofitting | MVS | 1241/RD/PHE | BHOLA PAUL | 16-10-2020 | 25-11-2020 | 357
42 | UTTAR DINAJPUR | Barua Piped Water Supply Scheme | SM/04984 |  |  | MVS | 861/RD/PHE | MS SARKAR ENTERPRISE ABDULGHATA | 12-08-2020 | 26-09-2020
43 | UTTAR DINAJPUR | Barua Piped Water Supply Scheme | SM/04984 |  |  | MVS | 859/RD/PHE | TAPAN KUMAR DUTTA | 12-08-2020 | 26-09-2020 | 558
44 | UTTAR DINAJPUR | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 |  | New | MVS | 1991/RD/PHE | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 14-11-2022 | 14-11-2023 | 1061
45 | UTTAR DINAJPUR | BASATPUT Piped Water Supply Scheme | SM/15129 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 32
46 | UTTAR DINAJPUR | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/15904 |  | New | MVS | 670/RD/PHE | M/S LOKENATH CONSTRUCTION | 06-03-2023 | 05-03-2024 | 1447
47 | UTTAR DINAJPUR | BELAN Piped Water Supply Scheme | SM/13233 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
48 | UTTAR DINAJPUR | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 |  | New | MVS | 67/RD/HE | BHOLA PAUL | 16-01-2023 | 16-01-2024 | 850
49 | UTTAR DINAJPUR | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 |  | New | MVS | 3736/RD/PHE | BHOLA PAUL | 18-12-2024 | 01-02-2025 | 70
50 | UTTAR DINAJPUR | Bhagabati Water Supply Scheme | SM/01894 | SM/09139 | Retrofitting | SVS | 2153/RD/PHE | M/S P.S. ENTERPRISE | 12-11-2021 | 12-12-2021
51 | UTTAR DINAJPUR | Bhagabati Water Supply Scheme | SM/01894 | SM/07390 | Retrofitting | MVS | 1564/RD/PHE | M/S LOKENATH CONSTRUCTION | 24-12-2020 | 22-02-2021 | 991
52 | UTTAR DINAJPUR | BHATOL WATER SUPPLY SCHEME | SM/00897 | SM/09170 | Retrofitting | SVS | 424/RD/PHE | JEET CONSTRUCTION | 16-02-2022 | 18-03-2022 | 6
53 | UTTAR DINAJPUR | BHATOL WATER SUPPLY SCHEME | SM/00897 | SM/15124 | Augmentation | MVS | 553/RD/PHE | KAMIRUL SK & CO. | 23-02-2023 | 23-02-2024 | 2028
54 | UTTAR DINAJPUR | BHATOL WATER SUPPLY SCHEME | SM/00897 | SM/09170 | Retrofitting | SVS | 2070/RD/PHE | JEET CONSTRUCTION | 02-11-2021 | 02-12-2021 | 362
55 | UTTAR DINAJPUR | BHIKHANPUR PWSS | SM/18628 |  | New | MVS | 2474/RD/PHE | M/S PINKI CONSTRUCTION | 24-08-2023 | 20-04-2024 | 289
56 | UTTAR DINAJPUR | Bhojpur Piped Water Supply Scheme | SM/06050 | SM/07977 | Retrofitting | MVS | 343/RD/PHE | M/S LOKENATH CONST | 01-02-2021 | 02-04-2021 | 2467
57 | UTTAR DINAJPUR | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. | SM/14239 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
58 | UTTAR DINAJPUR | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. | SM/15147 |  | New | MVS | 747/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 16-03-2023 | 15-03-2024 | 527
59 | UTTAR DINAJPUR | Bindol Piped Water Supply Scheme | SM/05142 | SM/18993 | Retrofitting | MVS | 2873/RD/PHE | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 17-10-2023 | 01-12-2023 | 20
60 | UTTAR DINAJPUR | Bindol Piped Water Supply Scheme | SM/05142 | SM/07390 | Retrofitting | MVS | 1529/RD/PHE | AJIT PARMANIK | 23-12-2020 | 06-02-2021 | 1007
61 | UTTAR DINAJPUR | BIRSINGGACHH MINI PIPED WATER SUPPLY SCHEME IN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18166 |  | New | SVS | 2379/RD/PHE | MOTI INDUSTRIES | 14-08-2023 | 12-11-2023 | 129
62 | UTTAR DINAJPUR | Butijhari Piped Water Supply Scheme | SM/06038 | SM/07142 | Retrofitting | MVS | 1412/RD/PHE | SANYAL ENTERPRISE | 11-12-2020 | 20-01-2021 | 1357
63 | UTTAR DINAJPUR | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 |  | New | MVS | 3735/RD/PHE | UJJWAL DAS | 18-12-2024 | 01-02-2025
64 | UTTAR DINAJPUR | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 |  | New | MVS | 74/RD/PHE | UJJWAL DAS | 16-01-2023 | 16-01-2024 | 1488
65 | UTTAR DINAJPUR | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. | SM/16258 |  | New | MVS | 749/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 16-03-2023 | 15-03-2024 | 1056
66 | UTTAR DINAJPUR | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 |  | New | MVS | 292/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 01-02-2023 | 01-02-2024 | 1431
67 | UTTAR DINAJPUR | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 |  | New | MVS | 3737/RD/PHE | AJIT PRAMANIK | 18-12-2024 | 01-02-2025
68 | UTTAR DINAJPUR | CHAKULIA WATER SUPPLY SCHEME | SM/00275 | SM/11196 | Augmentation | MVS | 2016/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1439
69 | UTTAR DINAJPUR | CHAKULIA WATER SUPPLY SCHEME | SM/00275 | SM/09183 | Retrofitting | SVS | 2083/RD/PHE | TAPAN KUMAR MAJUMDER | 02-11-2021 | 02-12-2021 | 230
70 | UTTAR DINAJPUR | Chandanpur Piped Water Supply Scheme | SM/05002 |  |  | MVS | 860/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12-08-2020 | 26-09-2020 | 1177
71 | UTTAR DINAJPUR | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/14641 |  | New | MVS | 568/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23-02-2023 | 23-02-2024 | 401
72 | UTTAR DINAJPUR | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 |  | New | MVS | 76/RD/PHE | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 16-01-2023 | 16-01-2024 | 699
73 | UTTAR DINAJPUR | Chandol Piped Water Supply Scheme | SM/04983 |  |  | MVS | 861/RD/PHE | MS SARKAR ENTERPRISE ABDULGHATA | 12-08-2020 | 26-09-2020 | 595
74 | UTTAR DINAJPUR | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 |  | New | MVS | 291/RD/PHE | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 01-02-2023 | 01-02-2024 | 1191
75 | UTTAR DINAJPUR | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 |  | New | MVS | 576/RD/PHE | UTTAM SAHA | 23-02-2023 | 20-11-2023 | 784
76 | UTTAR DINAJPUR | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. | SM/15146 |  | New | MVS | 3741/RD/PHE | UTTAM SAHA | 18-12-2024 | 01-02-2025
77 | UTTAR DINAJPUR | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16647 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
78 | UTTAR DINAJPUR | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK | SM/11863 |  | New | MVS | 588/RD/PHE | UTTAM SAHA | 24-02-2023 | 24-02-2024 | 1101
79 | UTTAR DINAJPUR | Chhota Parua and adj. mouzas water supply scheme | SM/02915 | SM/12643 | Augmentation | SVS | 1914/RD/PHE | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 28-10-2022 | 12-12-2022 | 115
80 | UTTAR DINAJPUR | Chhota Parua and adj. mouzas water supply scheme | SM/02915 | SM/06727 | Retrofitting | MVS | 1243/RD/PHE | PRASANTA DUTTA | 16-10-2020 | 25-11-2020 | 456
81 | UTTAR DINAJPUR | Chhota Parua and adj. mouzas water supply scheme | SM/02915 | SM/06727 | Retrofitting | MVS | 496/RD/PHE | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17-02-2023 | 03-04-2023 | 56
82 | UTTAR DINAJPUR | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12780 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
83 | UTTAR DINAJPUR | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14167 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 844
84 | UTTAR DINAJPUR | CHOPRA WATER SUPPLY SCHEME | SM/00654 | SM/09182 | Retrofitting | SVS | 2082/RD/PHE | M/S LUCKY CONSTRUCTION | 02-11-2021 | 02-12-2021 | 752
85 | UTTAR DINAJPUR | CHOPRA WATER SUPPLY SCHEME | SM/00654 | SM/10129 | Augmentation | MVS | 1272/RD/PHE | UTTAM SAHA | 24-06-2022 | 08-08-2022 | 566
86 | UTTAR DINAJPUR | CHOPRA WATER SUPPLY SCHEME | SM/00654 | SM/09182 | Retrofitting | SVS | 1272/RD/PHE | UTTAM SAHA | 24-06-2022 | 08-08-2022 | 770
87 | UTTAR DINAJPUR | Choprabari Piped Water Supply Scheme | SM/05146 | SM/06730 | Retrofitting | MVS | 1242/RD/PHE | AJIT PARMANIK | 16-10-2020 | 25-11-2020 | 4
88 | UTTAR DINAJPUR | CHOUKAI Pipe Water Supply Scheme | SM/15304 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
89 | UTTAR DINAJPUR | DAKSHIN ARIAGAON Pipe Water Supply Scheme | SM/15305 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
90 | UTTAR DINAJPUR | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
91 | UTTAR DINAJPUR | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12781 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
92 | UTTAR DINAJPUR | Dakshin Jibhakata Scheme | SM/01339 | SM/07390 | Retrofitting | MVS | 1540/RD/PHE | CALCON CONSTRUCTION | 23-12-2020 | 06-02-2021 | 1052
93 | UTTAR DINAJPUR | Dakshin Kundal Pukhar Piped Water Supply Scheme | SM/05481 | SM/07140 | Retrofitting | MVS | 1426/RD/PHE | S.B.CONSTRUCTION | 11-12-2020 | 10-01-2021 | 379
94 | UTTAR DINAJPUR | Dakshin Kundal Pukhar Piped Water Supply Scheme | SM/05481 | SM/07140 | Retrofitting | MVS | 1428/RD/PHE | M/S BHOWMIK ENTERPRISE | 11-12-2020 | 10-01-2021 | 366
95 | UTTAR DINAJPUR | Dakshin Kundal Pukhar Piped Water Supply Scheme | SM/05481 | SM/07140 | Retrofitting | MVS | 1429/RD/PHE | IDEAL CO-OP LABOUR CONTRACT &CONST SOCIETY LTD. | 11-12-2020 | 10-01-2021 | 203
96 | UTTAR DINAJPUR | Dakshin Kundal Pukhar Piped Water Supply Scheme | SM/05481 | SM/07140 | Retrofitting | MVS | 1427/RD/PHE | CHAITANYA SAMAL | 11-12-2020 | 10-01-2021 | 366
97 | UTTAR DINAJPUR | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16495 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 778
98 | UTTAR DINAJPUR | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16491 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
99 | UTTAR DINAJPUR | DAKSHIN RAMPUR Piped Water Supply Scheme | SM/13232 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 1357
100 | UTTAR DINAJPUR | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12782 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 374
101 | UTTAR DINAJPUR | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18168 |  | New | SVS | 1305/RD/PHE | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 12-05-2023 | 06-02-2024 | 424
102 | UTTAR DINAJPUR | DAMODARKHURI Piped Water Supply Scheme | SM/13236 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
103 | UTTAR DINAJPUR | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14168 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
104 | UTTAR DINAJPUR | Debiganj W/S Scheme | SM/02162 | SM/07390 | Retrofitting | MVS | 1539/RD/PHE | SANYAL ENTERPRISE | 23-12-2020 | 06-02-2021 | 343
105 | UTTAR DINAJPUR | Debiganj W/S Scheme | SM/02162 | SM/06728 | Retrofitting | SVS | 1236/RD/PHE | HAQUE CONSTRUCTION | 16-10-2020 | 25-11-2020
106 | UTTAR DINAJPUR | Debiganj W/S Scheme | SM/02162 | SM/14229 | Augmentation | SVS | 57/RD/PHE | SUBHASIS MAJUMDER SUBHASIS@REDIFFMAIL.COM | 16-01-2023 | 02-03-2023 | 50
107 | UTTAR DINAJPUR | Dehar Piped Water Supply Scheme | SM/06060 | SM/07145 | Retrofitting | MVS | 1424/RD/PHE | RAHUL ENTERPRISE | 11-12-2020 | 10-01-2021 | 247
108 | UTTAR DINAJPUR | Dehar Piped Water Supply Scheme | SM/06060 | SM/07145 | Retrofitting | MVS | 1422/RD/PHE | KARTICK BISWAS | 11-12-2020 | 10-01-2021 | 245
109 | UTTAR DINAJPUR | Dehar Piped Water Supply Scheme | SM/06060 | SM/07145 | Retrofitting | MVS | 1436/RD/PHE | MAA BICHITRA CONSTRUCTION | 11-12-2020 | 10-01-2021 | 238
110 | UTTAR DINAJPUR | Dehar Piped Water Supply Scheme | SM/06060 | SM/07145 | Retrofitting | MVS | 1423/RD/PHE | NIMAI DAS | 11-12-2020 | 10-01-2021 | 241
111 | UTTAR DINAJPUR | Dehar Piped Water Supply Scheme | SM/06060 | SM/07145 | Retrofitting | MVS | 1425/RD/PHE | MS SARKAR ENTERPRISE ABDULGHATA | 11-12-2020 | 10-01-2021 | 245
112 | UTTAR DINAJPUR | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18169 |  | New | SVS | 1558/RD/PHE | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 29-05-2023 | 27-08-2023 | 250
113 | UTTAR DINAJPUR | Dhamdhol Piped Water Supply Scheme. | SM/14639 |  | New | MVS | 565/RD/PHE | M/S LOKENATH CONSTRUCTION | 23-02-2023 | 23-02-2024 | 604
114 | UTTAR DINAJPUR | DHARAMPUR WATER SUPPLY SCHEME | SM/00277 | SM/09185 | Retrofitting | SVS | 2085/RD/PHE | M/S CHOUDHURY CONSTRUCTION | 02-11-2021 | 02-12-2021 | 453
115 | UTTAR DINAJPUR | DHARAMPUR WATER SUPPLY SCHEME | SM/00277 | SM/12394 | Augmentation | MVS | 125/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 20-01-2023 | 20-01-2024 | 1241
116 | UTTAR DINAJPUR | DHARAMPUR WATER SUPPLY SCHEME | SM/00277 | SM/12393 | Augmentation | MVS | 114/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 20-01-2023 | 20-01-2024 | 1097
117 | UTTAR DINAJPUR | DHARAMPUR WATER SUPPLY SCHEME | SM/00277 | SM/09184 | Retrofitting | SVS | 2084/RD/PHE | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 02-11-2021 | 02-12-2021 | 310
118 | UTTAR DINAJPUR | DHARAMPUR WATER SUPPLY SCHEME | SM/00277 | SM/09184 | Retrofitting | SVS | 435/RD/PHE | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 16-02-2022 | 18-03-2022 | 80
119 | UTTAR DINAJPUR | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/18298 |  | New | MVS | 1999/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 13-07-2023 | 25-07-2023 | 749
120 | UTTAR DINAJPUR | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. | SM/14827 |  | New | SVS | 535/RD/PHE | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. DEBASISHGHOSHDG76@GMAIL.COM | 22-02-2023 | 23-05-2023 | 162
121 | UTTAR DINAJPUR | DHULAHAR WATER SUPPLY SCHEME | SM/00285 | SM/10548 | Augmentation | SVS | 2020/RD/PHE | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 17-11-2022 | 16-01-2023 | 936
122 | UTTAR DINAJPUR | DHULAHAR WATER SUPPLY SCHEME | SM/00285 |  |  | MVS | 2080/RD/PHE | RAHUL ENTERPRISE | 02-11-2021 | 02-12-2021 | 292
123 | UTTAR DINAJPUR | DILWARPUR WATER SUPPLY SCHEME | SM/00294 | SM/09176 | Retrofitting | SVS | 428/RD/PHE | MAA SHEETALA ENTERPRISE | 16-02-2022 | 18-03-2022 | 160
124 | UTTAR DINAJPUR | DILWARPUR WATER SUPPLY SCHEME | SM/00294 | SM/09176 | Retrofitting | SVS | 2076/RD/PHE | M/S GHOSH CONSTRUCTION | 02-11-2021 | 02-12-2021 | 156
125 | UTTAR DINAJPUR | DILWARPUR WATER SUPPLY SCHEME | SM/00294 | SM/09989 | Augmentation | SVS | 1015/RD/PHED | BHOLA PAUL | 12-05-2022 | 26-06-2022 | 992
126 | UTTAR DINAJPUR | DILWARPUR WATER SUPPLY SCHEME | SM/00294 |  |  | MVS | 410/RD/PHE | SARNALI ENTERPRISE | 29-01-2025 | 28-02-2025
127 | UTTAR DINAJPUR | DILWARPUR WATER SUPPLY SCHEME | SM/00294 |  |  | MVS | 3027/RD/PHE | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 03-10-2024 | 02-11-2024 | 65
128 | UTTAR DINAJPUR | DOHASO PWSS | SM/18304 |  | New | MVS | 2091/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 27-07-2023 | 22-04-2024
129 | UTTAR DINAJPUR | Dwipnagar Piped Water Supply Scheme. | SM/18180 |  | New | MVS | 1133/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24-04-2023 | 19-01-2024 | 612
130 | UTTAR DINAJPUR | Faridpur Piped Water Supply Scheme | SM/06047 | SM/07139 | Retrofitting | MVS | 1413/RD/PHE | M/S MAATARA CONSTRUCTION | 11-12-2020 | 20-01-2021 | 458
131 | UTTAR DINAJPUR | Faridpur Piped Water Supply Scheme | SM/06047 | SM/07139 | Retrofitting | MVS | 1413/RD/PHE | M/S MAATARA CONSTRUCTION | 11-12-2020 | 20-01-2021 | 289
132 | UTTAR DINAJPUR | Faridpur Piped Water Supply Scheme | SM/06047 | SM/12640 | Augmentation | SVS | 1915/RD/PHE | M/S P.S. ENTERPRISE | 28-10-2022 | 12-12-2022 | 25
133 | UTTAR DINAJPUR | FASHIA DIATION PIPED WATER SUPPLY SCHEME | SM/14129 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
134 | UTTAR DINAJPUR | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13012 |  | New | MVS | 554/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23-02-2023 | 20-11-2023 | 171
135 | UTTAR DINAJPUR | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12783 |  | New | SVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 141
136 | UTTAR DINAJPUR | Ghirnigaon Khas Water Supply Scheme | SM/01360 | SM/07389 | Retrofitting | MVS | 1532/RD/PHE | SANYAL ENTERPRISE | 23-12-2020 | 06-02-2021 | 1303
137 | UTTAR DINAJPUR | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12784 |  | New | SVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
138 | UTTAR DINAJPUR | GOALPOKHER WATER SUPPLY SCHEME | SM/00280 | SM/11726 | Augmentation | MVS | 2026/RD/PHE | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1824
139 | UTTAR DINAJPUR | GOALPOKHER WATER SUPPLY SCHEME | SM/00280 | SM/09186 | Retrofitting | SVS | 2086/RD/PHE | HAQUE CONSTRUCTION | 02-11-2021 | 02-12-2021 | 182
140 | UTTAR DINAJPUR | GODASAMAL Piped Water Supply Scheme | SM/15128 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 5
141 | UTTAR DINAJPUR | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. | SM/12785 |  | New | MVS | 299/RD/PHE | UTTAM SAHA | 01-02-2023 | 01-02-2024 | 1144
142 | UTTAR DINAJPUR | Gorahar Piped Water Supply Scheme. | SM/14640 |  | New | SVS | 564/RD/PHE | SANYAL ENTERPRISE | 23-02-2023 | 23-02-2024 | 892
143 | UTTAR DINAJPUR | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 |  | New | MVS | 1281/RD/PHE | UTTAM SAHA | 08-05-2023 | 02-02-2024 | 2056
144 | UTTAR DINAJPUR | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11642 |  | New | MVS | 12/RD/PHE | M/S P.S. ENTERPRISE | 02-01-2025 | 16-02-2025
145 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Biprit & adjoining mouzas | SM/03918 | SM/06722 | Retrofitting | MVS | 1244/RD/PHE | PRASANTO DUTTA | 16-10-2020 | 25-11-2020 | 366
146 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Mahamadpur & Adjoining Mouzas | SM/03752 | SM/06725 | Retrofitting | MVS | 1239/RD/PHE | TAPAN KUMAR DUTTA | 16-10-2020 | 25-11-2020 | 139
147 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Mahamadpur & Adjoining Mouzas | SM/03752 | SM/06725 | Retrofitting | MVS | 1239/RD/PHE | TAPAN KUMAR DUTTA | 16-10-2020 | 25-11-2020 | 3
148 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Khesra & adj. mouzas. | SM/04231 | SM/07389 | Retrofitting | MVS | 1525/RD/PHE | UTTAM SAHA | 23-12-2020 | 06-02-2021 | 279
149 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Piplan & adj.mouzas. | SM/04124 | SM/07389 | Retrofitting | MVS | 1562/RD/PHE | UTTAM SAHA | 24-12-2020 | 22-02-2021 | 912
150 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Bamair & adj. mouzas. | SM/04474 | SM/07390 | Retrofitting | MVS | 1531/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23-12-2020 | 06-02-2021 | 331
151 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Bamair & adj. mouzas. | SM/04474 | SM/12639 | Augmentation | SVS | 1911/RD/PHE | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 28-10-2022 | 12-12-2022 | 169
152 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Deona & adj. mouzas. | SM/04502 | SM/07390 | Retrofitting | MVS | 1542/RD/PHE | MAMATA USHA ENTERPRISE | 23-12-2020 | 01-02-2021 | 694
153 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Goagoan & adj. mouzas. | SM/04503 | SM/07389 | Retrofitting | MVS | 1535/RD/PHE | ALOK ENTERPRISE | 23-12-2020 | 06-02-2021 | 220
154 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Gopalpur & adj. mouzas | SM/03509 | SM/07390 | Retrofitting | MVS | 1533/RD/PHE | M/S LOKENATH CONST | 23-12-2020 | 06-02-2021 | 84
155 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Gutin & adj. mouzas. | SM/04455 | SM/07390 | Retrofitting | MVS | 1528/RD/PHE | M/S LOKENATH CONST | 23-12-2020 | 06-02-2021 | 842
156 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Intia & adj. mouzas. | SM/04480 | SM/07389 | Retrofitting | MVS | 1541/RD/PHE | UTTAM SAHA | 23-12-2020 | 01-02-2021 | 700
157 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Majlishpur & adj. mouzas. | SM/04518 | SM/07389 | Retrofitting | MVS | 1532/RD/PHE | SANYAL ENTERPRISE | 23-12-2020 | 06-02-2021
158 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Majlishpur & adj. mouzas. | SM/04518 | SM/07389 | Retrofitting | MVS | 1558/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24-12-2020 | 22-02-2021 | 621
159 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Pokheria & adj. mouzas. | SM/04488 | SM/14226 | Augmentation | SVS | 62/RD/PHE | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 16-01-2023 | 02-03-2023
160 | UTTAR DINAJPUR | Ground Water Based Piped Water Supply Scheme for Pokheria & adj. mouzas. | SM/04488 | SM/07390 | Retrofitting | MVS | 1530/RD/PHE | AJIT PARMANIK | 23-12-2020 | 06-02-2021 | 1679
161 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Baruna & Adj. Mouzas | SM/03697 | SM/12641 | Augmentation | SVS | 1907/RD/PHE | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 28-10-2022 | 12-12-2022
162 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Baruna & Adj. Mouzas | SM/03697 | SM/07390 | Retrofitting | MVS | 1527/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23-12-2020 | 06-02-2021 | 959
163 | UTTAR DINAJPUR | Ground water based water supply scheme for Jaingaon and adjoining mouzas | SM/03969 | SM/12652 | Augmentation | SVS | 1923/RD/PHE | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 28-10-2022 | 12-12-2022 | 67
164 | UTTAR DINAJPUR | Ground water based water supply scheme for Jaingaon and adjoining mouzas | SM/03969 | SM/07390 | Retrofitting | MVS | 1538/RD/PHE | M/S SOMNATH KUNDU | 23-12-2020 | 06-02-2021 | 1678
165 | UTTAR DINAJPUR | Ground water based water supply scheme for Lodhan and adjoining mouzas | SM/03979 | SM/06731 | Retrofitting | MVS | 1240/RD/PHE | J.D.J. ENTERPRISE | 16-10-2020 | 25-11-2020 | 505
166 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Mahua & adjoining mouzas | SM/03914 |  |  | MVS | 59/RD/PHE | SUDIP MITRA SUDIP.RNJ@GMAIL.COM | 16-01-2023 | 02-03-2023 | 50
167 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Mahua & adjoining mouzas | SM/03914 | SM/07977 | Retrofitting | MVS | 344/RD/PHE | J.D.J. ENTERPRISE | 01-02-2021 | 02-04-2021 | 1766
168 | UTTAR DINAJPUR | Ground water based water supply scheme for Nalbithi Madhabpur | SM/03968 | SM/06723 | Retrofitting | MVS | 1238/RD/PHE | M/S LOKENATH CONST | 16-10-2020 | 25-11-2020 | 430
169 | UTTAR DINAJPUR | Ground water based water supply scheme for Paharajpur and adjoining mouzas | SM/03977 | SM/07390 | Retrofitting | MVS | 1560/RD/PHE | J.D.J. ENTERPRISE | 24-12-2020 | 22-02-2021 | 1333
170 | UTTAR DINAJPUR | Ground Water Based Water Supply Scheme for Tungail Bilpara & Adj. Mouzas | SM/03707 | SM/07390 | Retrofitting | MVS | 1524/RD/PHE | SANYAL ENTERPRISE | 23-12-2020 | 06-02-2021 | 1001
171 | UTTAR DINAJPUR | Gunabari Water Supply Scheme | SM/01911 | SM/14228 | Augmentation | SVS | 58/RD/PHE | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 16-01-2023 | 02-03-2023 | 50
172 | UTTAR DINAJPUR | Gunabari Water Supply Scheme | SM/01911 | SM/07390 | Retrofitting | MVS | 1534 /RD/PHE | M/S LOKENATH CONSTRUCTION | 23-12-2020 | 06-02-2021 | 374
173 | UTTAR DINAJPUR | Gunabari Water Supply Scheme | SM/01911 | SM/07390 | Retrofitting | MVS | 1540/RD/PHE | CALCON CONSTRUCTION | 23-12-2020 | 06-02-2021
174 | UTTAR DINAJPUR | Gunabari Water Supply Scheme | SM/01911 | SM/07389 | Retrofitting | MVS | 1535/RD/PHE | ALOK ENTERPRISE | 23-12-2020 | 06-02-2021 | 375
175 | UTTAR DINAJPUR | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16219 |  | New | MVS | 1275/RD/PHE | UJJWAL DAS | 08-05-2023 | 02-02-2024 | 965
176 | UTTAR DINAJPUR | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 |  | New | MVS | 2021/RD/PHE | BHOLA PAUL | 17-11-2022 | 15-02-2023
177 | UTTAR DINAJPUR | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. | SM/16220 |  | New | MVS | 1276/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 08-05-2023 | 02-02-2024 | 828
178 | UTTAR DINAJPUR | HEMENPUR Piped Water Supply Scheme | SM/14180 |  | New | MVS | 950/RD/PHE | M/S.SADHANA ENTERPRISE | 29-03-2023 | 28-05-2023 | 320
179 | UTTAR DINAJPUR | HEMENPUR Piped Water Supply Scheme | SM/14180 |  | New | MVS | 875/RD/PHE | SANDIP SARKAR | 27-03-2023 | 26-05-2023 | 123
180 | UTTAR DINAJPUR | HEMTABAD WATER SUPPLY SCHEME. | SM/00282 | SM/09175 | Retrofitting | SVS | 2075/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 02-11-2021 | 02-12-2021 | 390
181 | UTTAR DINAJPUR | HEMTABAD WATER SUPPLY SCHEME. | SM/00282 | SM/09175 | Retrofitting | SVS | 484/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 25-02-2022 | 27-03-2022 | 385
182 | UTTAR DINAJPUR | HEMTABAD WATER SUPPLY SCHEME. | SM/00282 | SM/11799 | Augmentation | MVS | 2028/RD/PHE | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1336
183 | UTTAR DINAJPUR | HEMTABAD WATER SUPPLY SCHEME. | SM/00282 | SM/11727 | Augmentation | MVS | 2021/RD/PHE | BHOLA PAUL | 17-11-2022 | 15-02-2023 | 451
184 | UTTAR DINAJPUR | IKARCHALA PWSS | SM/18294 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 422
185 | UTTAR DINAJPUR | ILLUABARI PWSS | SM/18449 |  | New | MVS | 2301/RD/PHE | M/S. B. PAUL & COMPANY | 04-08-2023 | 30-04-2024 | 662
186 | UTTAR DINAJPUR | ITAHAR WATER SUPPLY SCHEME | SM/00276 | SM/09174 | Retrofitting | SVS | 2074/RD/PHE | TAPAN KUMAR MAJUMDER | 02-11-2021 | 02-12-2021 | 430
187 | UTTAR DINAJPUR | ITAHAR WATER SUPPLY SCHEME | SM/00276 | SM/09174 | Retrofitting | SVS | 483/RD/PHE | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 25-02-2022 | 27-03-2022 | 116
188 | UTTAR DINAJPUR | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/13795 |  | New | MVS | 289/RD/PHE | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 01-02-2023 | 01-02-2024 | 1688
189 | UTTAR DINAJPUR | JAGDISHPUR PWSS | SM/18287 |  | New | MVS | 2001/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13-07-2023 | 25-07-2023 | 246
190 | UTTAR DINAJPUR | JAMIRA Piped Water Supply Scheme | SM/14179 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 74
191 | UTTAR DINAJPUR | Jayhat Piped Water Supply Scheme | SM/04920 |  |  | MVS | 862/RD/PHE | UTTAM SAHA | 12-08-2020 | 26-09-2020 | 438
192 | UTTAR DINAJPUR | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12786 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
193 | UTTAR DINAJPUR | JHITKAI PWSS | SM/18476 |  | New | MVS | 3742/RD/PHE | BHOLA PAUL | 18-12-2024 | 01-02-2025
194 | UTTAR DINAJPUR | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13738 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
195 | UTTAR DINAJPUR | JUJHARPUR WATER SUPPLY SCHEME | SM/00291 | SM/09194 | Retrofitting | SVS | 2382/RD/PHE | SAHA CONSTRUCTION | 24-12-2021 | 23-01-2022 | 181
196 | UTTAR DINAJPUR | JUJHARPUR WATER SUPPLY SCHEME | SM/00291 | SM/12395 | Augmentation | SVS | 126/RD/PHE | A D ENTERPRISE | 20-01-2023 | 20-01-2024 | 449
197 | UTTAR DINAJPUR | KABUTARKHOPI Piped Water Supply Scheme | SM/13235 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 1428
198 | UTTAR DINAJPUR | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 |  | New | MVS | 97/RD/PHE | SANYAL ENTERPRISE | 19-01-2023 | 19-01-2024 | 614
199 | UTTAR DINAJPUR | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13013 |  | New | MVS | 1535/RD/PHE | M/S P.S. ENTERPRISE | 24-05-2023 | 08-07-2023
200 | UTTAR DINAJPUR | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 |  | New | MVS | 3747/RD/PHE | AJIT PRAMANIK | 18-12-2024 | 01-02-2025
201 | UTTAR DINAJPUR | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/18451 |  | New | MVS | 2090/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 27-07-2023 | 22-04-2024 | 1282
202 | UTTAR DINAJPUR | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12787 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
203 | UTTAR DINAJPUR | Kamartor Piped Water Supply Scheme | SM/06061 |  |  | MVS | 2840/RD/PHE | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 23-09-2024 | 13-10-2024 | 123
204 | UTTAR DINAJPUR | Kamartor Piped Water Supply Scheme | SM/06061 | SM/07071 | Retrofitting | MVS | 1414/RD/PHE | J.D.J. ENTERPRISE | 11-12-2020 | 20-01-2021 | 1804
205 | UTTAR DINAJPUR | KANKI-MATIARI WATER SUPPLY SCHEME | SM/00684 | SM/09191 | Retrofitting | SVS | 437/RD/PHE | TAPAN KUMAR MAJUMDER | 16-02-2022 | 18-03-2022 | 66
206 | UTTAR DINAJPUR | KANKI-MATIARI WATER SUPPLY SCHEME | SM/00684 | SM/09191 | Retrofitting | SVS | 2091/RD/PHE | TAPAN KUMAR MAJUMDER | 02-11-2021 | 02-12-2021 | 124
207 | UTTAR DINAJPUR | KANKI-MATIARI WATER SUPPLY SCHEME | SM/00684 | SM/09985 | Augmentation | MVS | 1018/RD/PHED | M/S SARKAR ENTERPRISE | 12-05-2022 | 26-06-2022 | 568
208 | UTTAR DINAJPUR | KARANDIGHI WATER SUPPLY SCHEME | SM/00647 | SM/11721 | Augmentation | MVS | 47/RD/PHE | M/S P.S. ENTERPRISE | 03-01-2025 | 17-02-2025 | 50
209 | UTTAR DINAJPUR | KARANDIGHI WATER SUPPLY SCHEME | SM/00647 | SM/09188 | Retrofitting | SVS | 2088/RD/PHE | MAA SHEETALA ENTERPRISE | 02-11-2021 | 02-12-2021 | 821
210 | UTTAR DINAJPUR | KARANDIGHI WATER SUPPLY SCHEME | SM/00647 | SM/11721 | Augmentation | MVS | 2030/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17-11-2022 | 15-02-2023 | 2047
211 | UTTAR DINAJPUR | KARANDIGHI WATER SUPPLY SCHEME | SM/00647 | SM/09188 | Retrofitting | SVS | 436/RD/PHE | M/S BHOWMIK CONSTRUCTION | 16-02-2022 | 18-03-2022 | 30
212 | UTTAR DINAJPUR | KARANDIGHI WATER SUPPLY SCHEME | SM/00647 | SM/11794 | Augmentation | MVS | 2017/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17-11-2022 | 15-02-2023 | 234
213 | UTTAR DINAJPUR | Kasba NM water supply scheme | SM/02509 | SM/09171 | Retrofitting | SVS | 2071/RD/PHE | S.B.CONSTRUCTION | 02-11-2021 | 02-12-2021 | 161
214 | UTTAR DINAJPUR | Kasba NM water supply scheme | SM/02509 |  |  | MVS | 417/RD/PHE | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 29-01-2025 | 15-03-2025
215 | UTTAR DINAJPUR | Kasba NM water supply scheme | SM/02509 | SM/09171 | Retrofitting | SVS | 425/RD/PHE | S.B.CONSTRUCTION | 16-02-2022 | 18-03-2022 | 172
216 | UTTAR DINAJPUR | Kasba NM water supply scheme | SM/02509 | SM/11797 | Augmentation | MVS | 757/RD/PHE | BHOLA PAUL | 17-03-2023 | 13-09-2023 | 1835
217 | UTTAR DINAJPUR | KASBA WATER SUPPLY SCHEME | SM/00665 | SM/09173 | Retrofitting | SVS | 2073/RD/PHE | SUBHASIS MAJUMDER | 02-11-2021 | 02-12-2021 | 232
218 | UTTAR DINAJPUR | KASBA WATER SUPPLY SCHEME | SM/00665 | SM/11796 | Augmentation | MVS | 2019/RD/PHE | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 17-11-2022 | 15-02-2023 | 829
219 | UTTAR DINAJPUR | KASBA WATER SUPPLY SCHEME | SM/00665 |  |  | MVS | 3571/RD/PHE | SAHA CONSTRUCTION | 05-12-2024 | 19-01-2025
220 | UTTAR DINAJPUR | KASBA WATER SUPPLY SCHEME | SM/00665 |  |  | MVS | 3572/RD/PHE | SANTI TRADERS | 05-12-2024 | 19-01-2025 | 34
221 | UTTAR DINAJPUR | KASBA WATER SUPPLY SCHEME | SM/00665 | SM/09173 | Retrofitting | SVS | 427/RD/PHE | SUBHASIS MAJUMDER | 16-02-2022 | 18-03-2022 | 102
222 | UTTAR DINAJPUR | Kashimpur Piped Water Supply Scheme. | SM/18182 |  | New | MVS | 1132/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 24-04-2023 | 19-01-2024 | 680
223 | UTTAR DINAJPUR | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 65
224 | UTTAR DINAJPUR | Khalsi Piped Water Supply Scheme. | SM/18179 |  | New | MVS | 1129/RD/PHE | SANYAL ENTERPRISE | 24-04-2023 | 19-01-2024 | 970
225 | UTTAR DINAJPUR | KHANTA WATER SUPPLY SCHEME | SM/00816 | SM/09189 | Retrofitting | SVS | 434/RD/PHE | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 16-02-2022 | 18-03-2022
226 | UTTAR DINAJPUR | KHANTA WATER SUPPLY SCHEME | SM/00816 | SM/09189 | Retrofitting | SVS | 2089/RD/PHE | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 02-11-2021 | 02-12-2021 | 375
227 | UTTAR DINAJPUR | KHANTA WATER SUPPLY SCHEME | SM/00816 | SM/15125 | Augmentation | MVS | 570/RD/PHE | PRASANTA DUTTA | 23-02-2023 | 23-02-2024 | 261
228 | UTTAR DINAJPUR | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 |  | New | MVS | 3738/RD/PHE | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 18-12-2024 | 01-02-2025
229 | UTTAR DINAJPUR | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 |  | New | MVS | 73/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 16-01-2023 | 16-01-2024 | 1159
230 | UTTAR DINAJPUR | Khowaspur Piped Water Supply Scheme | SM/06043 | SM/07143 | Retrofitting | MVS | 1430/RD/PHE | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 11-12-2020 | 10-01-2021 | 487
231 | UTTAR DINAJPUR | Khowaspur Piped Water Supply Scheme | SM/06043 | SM/07143 | Retrofitting | MVS | 1431/RD/PHE | M/S PIONEER ENTERPRISE | 11-12-2020 | 10-01-2021 | 499
232 | UTTAR DINAJPUR | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12789 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 9
233 | UTTAR DINAJPUR | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/14166 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
234 | UTTAR DINAJPUR | Kotar Piped Water Supply Scheme | SM/04985 |  |  | MVS | 865/RD/PHE | SOMNATH KUNDU | 12-08-2020 | 26-09-2020 | 653
235 | UTTAR DINAJPUR | Kotar Piped Water Supply Scheme | SM/04985 |  |  | MVS | 1908/RD/PHE | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 28-10-2022 | 12-12-2022 | 35
236 | UTTAR DINAJPUR | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR | SM/11821 |  | New | MVS | 96/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19-01-2023 | 19-01-2024 | 954
237 | UTTAR DINAJPUR | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 |  | New | MVS | 552/RD/PHE | SANYAL ENTERPRISE | 23-02-2023 | 21-10-2023 | 956
238 | UTTAR DINAJPUR | KUNORE WATER SUPPLY SCHEME | SM/00806 | SM/09172 | Retrofitting | SVS | 2072/RD/PHE | M/S BHOWMIK ENTERPRISE | 02-11-2021 | 02-12-2021 | 187
239 | UTTAR DINAJPUR | KUNORE WATER SUPPLY SCHEME | SM/00806 | SM/09172 | Retrofitting | SVS | 426/RD/PHE | M/S BHOWMIK ENTERPRISE | 16-02-2022 | 18-03-2022 | 198
240 | UTTAR DINAJPUR | KUNORE WATER SUPPLY SCHEME | SM/00806 | SM/11795 | Augmentation | MVS | 2023/RD/PHE | UJJWAL DAS | 17-11-2022 | 15-02-2023 | 1365
241 | UTTAR DINAJPUR | LAKHIPUR WATER SUPPLY SCHEME | SM/00278 |  |  | MVS | 2081/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 02-11-2021 | 02-12-2021 | 462
242 | UTTAR DINAJPUR | LAKHIPUR WATER SUPPLY SCHEME | SM/00278 | SM/11724 | Augmentation | SVS | 2027/RD/PHE | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1632
243 | UTTAR DINAJPUR | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 |  | New | SVS | 1306/RD/PHE | UNIVERSAL ENTERPRISES | 12-05-2023 | 06-02-2024 | 301
244 | UTTAR DINAJPUR | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 |  | New | MVS | 296/RD/PHE | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 01-02-2023 | 01-02-2024 | 1620
245 | UTTAR DINAJPUR | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 |  | New | MVS | 3739/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 18-12-2024 | 01-02-2025 | 116
246 | UTTAR DINAJPUR | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 |  | New | MVS | 71/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 16-01-2023 | 16-01-2024 | 1105
247 | UTTAR DINAJPUR | Mahadevpur Piped Water Supply Scheme | SM/04832 |  |  | MVS | 858/RD/PHE | AJIT PARMANIK | 12-08-2020 | 26-09-2020 | 1060
248 | UTTAR DINAJPUR | Majihar Piped Water Supply Scheme | SM/04982 |  |  | MVS | 866/RD/ PHE | PRASANTA DUTTA | 12-08-2020 | 26-09-2020 | 594
249 | UTTAR DINAJPUR | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. | SM/15516 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
250 | UTTAR DINAJPUR | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11865 |  | New | MVS | 1992/RD/PHE | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 14-11-2022 | 14-11-2023 | 398
251 | UTTAR DINAJPUR | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT | SM/11824 |  | New | MVS | 555/RD/PHE | UTTAM SAHA | 23-02-2023 | 23-02-2024 | 332
252 | UTTAR DINAJPUR | MALGAON AND ADJ. MOUZA RURAL PIPED WATER SUPPLY SCHEME | SM/01150 | SM/07389 | Retrofitting | MVS | 1536/RD/PHE | UTTAM SAHA | 23-12-2020 | 06-02-2021 | 703
253 | UTTAR DINAJPUR | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13502 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 1251
254 | UTTAR DINAJPUR | MALKOT Pipe Water Supply Scheme | SM/15303 |  | New | MVS | 2066/RD/PHE | KAMIRUL SK & CO. | 21-07-2023 | 29-07-2023 | 113
255 | UTTAR DINAJPUR | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 |  | New | MVS | 548/RD/PHE | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 23-02-2023 | 21-10-2023 | 1118
256 | UTTAR DINAJPUR | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 |  | New | MVS | 3556/RD/PHE | UJJWAL DAS | 05-12-2024 | 19-01-2025 | 200
257 | UTTAR DINAJPUR | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 |  | New | MVS | 57/RD/PHE | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 03-01-2025 | 17-02-2025 | 287
258 | UTTAR DINAJPUR | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | SM/13014 |  | New | MVS | 113/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 20-01-2023 | 20-01-2024 | 1495
259 | UTTAR DINAJPUR | MANORA Piped Water Supply Scheme | SM/15126 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
260 | UTTAR DINAJPUR | MARNAI WATER SUPPLY SCHEME | SM/00281 | SM/09178 | Retrofitting | SVS | 2078/RD/PHE | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 02-11-2021 | 02-12-2021 | 392
261 | UTTAR DINAJPUR | MARNAI WATER SUPPLY SCHEME | SM/00281 | SM/09178 | Retrofitting | SVS | 430/RD/PHE | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16-02-2022 | 18-03-2022
262 | UTTAR DINAJPUR | Maslandpur Piped Water Supply Scheme | SM/05022 |  |  | MVS | 495/RD/PHE | GOPES SAHA | 17-02-2023 | 03-04-2023 | 177
263 | UTTAR DINAJPUR | Maslandpur Piped Water Supply Scheme | SM/05022 |  |  | MVS | 857/RD/PHE | PRASANTA DUTTA | 12-08-2020 | 26-09-2020 | 773
264 | UTTAR DINAJPUR | MATIKUNDA RURAL PIPED WATER SUPPLY SCHEME | SM/01136 | SM/07384 | Retrofitting | SVS | 1389/RD/PHE | M/S HINDUSTHAN CONSTRUCTION | 09-12-2020 | 08-01-2021 | 282
265 | UTTAR DINAJPUR | MATIKUNDA RURAL PIPED WATER SUPPLY SCHEME | SM/01136 | SM/07384 | Retrofitting | SVS | 1387/RD/PHE | M/S LUCKY CONSTRUCTION | 09-12-2020 | 08-01-2021 | 20
266 | UTTAR DINAJPUR | MATIKUNDA RURAL PIPED WATER SUPPLY SCHEME | SM/01136 | SM/07384 | Retrofitting | SVS | 1388/RD/PHE | M/S CHOUDHURY CONSTRUCTION | 09-12-2020 | 08-01-2021 | 280
267 | UTTAR DINAJPUR | MIRJADPUR Piped Water Supply Scheme | SM/14627 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
268 | UTTAR DINAJPUR | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 |  | New | MVS | 1274/RD/PHE | UTTAM SAHA | 08-05-2023 | 02-02-2024 | 513
269 | UTTAR DINAJPUR | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 |  | New | MVS | 3748/RD/PHE | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 18-12-2024 | 01-02-2025
270 | UTTAR DINAJPUR | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17199 |  | New | MVS | 3026/RD/PHE | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 03-10-2024 | 17-11-2024
271 | UTTAR DINAJPUR | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16490 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 1554
272 | UTTAR DINAJPUR | Noabari and Adj. mouzas water supply scheme | SM/02916 | SM/07389 | Retrofitting | MVS | 1563/RD/PHE | SANYAL ENTERPRISE | 24-12-2020 | 22-02-2021 | 153
273 | UTTAR DINAJPUR | Noabari and Adj. mouzas water supply scheme | SM/02916 | SM/07389 | Retrofitting | MVS | 1416/RD/PHE | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 15-05-2023 | 01-07-2023
274 | UTTAR DINAJPUR | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 |  | New | MVS | 3734/RD/PHE | BHOLA PAUL | 18-12-2024 | 01-02-2025
275 | UTTAR DINAJPUR | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/15148 |  | New | MVS | 556/RD/PHE | BHOLA PAUL | 23-02-2023 | 20-11-2023 | 136
276 | UTTAR DINAJPUR | Pakhuria Piped Water Supply Scheme | SM/05001 |  |  | MVS | 354/RD/PHE | M/S SOMNATH KUNDU | 01-02-2021 | 02-04-2021 | 2054
277 | UTTAR DINAJPUR | Palaibari Piped Water Supply Scheme. | SM/18181 |  | New | MVS | 1128/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 24-04-2023 | 19-01-2024
278 | UTTAR DINAJPUR | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 |  | New | MVS | 295/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 01-02-2023 | 01-02-2024 | 1907
279 | UTTAR DINAJPUR | PANDITPOTA PIPED WATER SUPPLY SCHEME | SM/13542 |  | New | MVS | 569/RD/PHE | SANYAL ENTERPRISE | 23-02-2023 | 23-02-2024 | 856
280 | UTTAR DINAJPUR | PANJIPARA WATER SUPPLY SCHEME | SM/00273 | SM/11801 | Augmentation | MVS | 2025/RD/PHE | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 17-11-2022 | 15-02-2023 | 62
281 | UTTAR DINAJPUR | PANJIPARA WATER SUPPLY SCHEME | SM/00273 | SM/11800 | Augmentation | MVS | 2024/RD/PHE | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1099
282 | UTTAR DINAJPUR | PANJIPARA WATER SUPPLY SCHEME | SM/00273 | SM/09190 | Retrofitting | SVS | 2090/RD/PHE | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 02-11-2021 | 02-12-2021 | 425
283 | UTTAR DINAJPUR | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 |  | New | MVS | 3733/RD/PHE | SANYAL ENTERPRISE | 18-12-2024 | 01-02-2025
284 | UTTAR DINAJPUR | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16494 |  | New | MVS | 748/RD/PHE | SANYAL ENTERPRISE | 16-03-2023 | 15-03-2024 | 1127
285 | UTTAR DINAJPUR | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block | SM/12083 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 225
286 | UTTAR DINAJPUR | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block | SM/12085 |  | New | SVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
287 | UTTAR DINAJPUR | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18147 |  | New | SVS | 1559/RD/PHE | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 29-05-2023 | 27-08-2023 | 206
288 | UTTAR DINAJPUR | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR | SM/11820 |  | New | MVS | 1993/RD/PHE | M/S LOKENATH CONSTRUCTION | 14-11-2022 | 14-11-2023 | 1021
289 | UTTAR DINAJPUR | Pawakhali Piped Water Supply Scheme | SM/05471 | SM/07141 | Retrofitting | MVS | 1415/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 11-12-2020 | 20-01-2021 | 601
290 | UTTAR DINAJPUR | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12790 |  | New | SVS | 536/RD/PHE | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 22-02-2023 | 23-05-2023 | 273
291 | UTTAR DINAJPUR | Piped Water Supply Scheme for Bheur & Adj. Mouzas | SM/03739 | SM/07390 | Retrofitting | MVS | 493/RD/PHE | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17-02-2023 | 03-04-2023 | 150
292 | UTTAR DINAJPUR | Piped Water Supply Scheme for Bheur & Adj. Mouzas | SM/03739 | SM/07390 | Retrofitting | MVS | 1557/RD/PHE | UTTAM SAHA | 24-12-2020 | 22-02-2021 | 865
293 | UTTAR DINAJPUR | Piped Water Supply Scheme for Kaligang & Adj. Mouzas | SM/03585 | SM/07390 | Retrofitting | MVS | 1544/RD/PHE | NEOGI ENTERPRISE | 23-12-2020 | 01-02-2021 | 481
294 | UTTAR DINAJPUR | Piped Water Supply Scheme for Mahinagar& Adj. Mouzas | SM/03740 | SM/07390 | Retrofitting | MVS | 1543/RD/PHE | SANYAL ENTERPRISE | 23-12-2020 | 01-02-2021 | 322
295 | UTTAR DINAJPUR | Piped Water Supply Scheme for Phulatti & Adj. Mouzas | SM/03738 | SM/07385 | Retrofitting | MVS | 1392/RD/PHE | PRASANTA DUTTA | 09-12-2020 | 13-01-2021 | 23
296 | UTTAR DINAJPUR | Piped Water Supply Scheme for Phulatti & Adj. Mouzas | SM/03738 | SM/07385 | Retrofitting | MVS | 1260/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 25-06-2021 | 25-07-2021 | 110
297 | UTTAR DINAJPUR | Piped Water Supply Scheme for Phulatti & Adj. Mouzas | SM/03738 | SM/07385 | Retrofitting | MVS | 476/RD/PHE | SUBHAS CHOWDHURY | 26-02-2021 | 12-04-2021 | 70
298 | UTTAR DINAJPUR | Piped Water Supply Scheme for Phulatti & Adj. Mouzas | SM/03738 | SM/12646 | Augmentation | SVS | 1921/RD/PHE | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 28-10-2022 | 12-12-2022 | 62
299 | UTTAR DINAJPUR | Piped Water Supply Scheme for Phulatti & Adj. Mouzas | SM/03738 | SM/07385 | Retrofitting | MVS | 1393/RD/PHE | M/S P.S ENTERPRISE | 09-12-2020 | 08-01-2021
300 | UTTAR DINAJPUR | Piped Water Supply Scheme for Phulatti & Adj. Mouzas | SM/03738 | SM/07385 | Retrofitting | MVS | 1223/RD/PHE | DONE ENTERPRISE | 18-06-2021 | 18-07-2021 | 153
301 | UTTAR DINAJPUR | Piped Water Supply Scheme for Poaltair & Adj. Mouzas | SM/03591 | SM/07390 | Retrofitting | MVS | 1539/RD/PHE | SANYAL ENTERPRISE | 23-12-2020 | 06-02-2021 | 420
302 | UTTAR DINAJPUR | Piped Water Supply Scheme for Shridharpur & Adj. Mouzas | SM/03590 | SM/07390 | Retrofitting | MVS | 1526/RD/PHE | AJIT PARMANIK | 23-12-2020 | 06-02-2021 | 1065
303 | UTTAR DINAJPUR | Pirojpur & adj. mouzas W/S Scheme | SM/03344 | SM/07389 | Retrofitting | MVS | 1559/RD/PHE | AJIT PARMANIK | 24-12-2020 | 22-02-2021 | 1584
304 | UTTAR DINAJPUR | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 |  | New | MVS | 675/RD/PHE | UJJWAL DAS | 06-03-2023 | 01-11-2023 | 461
305 | UTTAR DINAJPUR | PRATAPPUR PIPED WATER SUPPLY SCHEME | SM/14128 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 240
306 | UTTAR DINAJPUR | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. | SM/16229 |  | New | SVS | 2407/RD/PHE | S.G. CONSTRUCTION | 17-08-2023 | 13-04-2024 | 668
307 | UTTAR DINAJPUR | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13550 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 79
308 | UTTAR DINAJPUR | Purba Durlavpur Piped Water Supply Scheme | SM/04918 |  |  | MVS | 410/RD/PHE | SARNALI ENTERPRISE | 29-01-2025 | 28-02-2025 | 160
309 | UTTAR DINAJPUR | Purba Durlavpur Piped Water Supply Scheme | SM/04918 |  |  | MVS | 864/RD/PHE | M/S LOKENATH CONSTRUCTION | 12-08-2020 | 26-09-2020 | 1367
310 | UTTAR DINAJPUR | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12791 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
311 | UTTAR DINAJPUR | Purba Rampur Piped Water Supply Scheme | SM/06037 | SM/07144 | Retrofitting | MVS | 1416/RD/PHE | PRASANTA DUTTA | 11-12-2020 | 20-01-2021 | 84
312 | UTTAR DINAJPUR | Purbba Chutiakhor Piped Water Supply Scheme | SM/06039 | SM/07977 | Retrofitting | MVS | 342/RD/PHE | SANYAL ENTERPRISE | 01-02-2021 | 02-04-2021 | 1657
313 | UTTAR DINAJPUR | Purbba Chutiakhor Piped Water Supply Scheme | SM/06039 | SM/07977 | Retrofitting | MVS | 2658/RD/PHE | KARTICK BISWAS | 15-09-2023 | 30-10-2023 | 543
314 | UTTAR DINAJPUR | PURBBA GOMAIDIGHI PWSS | SM/18448 |  | New | SVS | 2470/RD/PHE | PRADIP KUMAR PAUL | 24-08-2023 | 20-04-2024 | 968
315 | UTTAR DINAJPUR | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 |  | New | MVS | 70/RD/PHE | SANYAL ENTERPRISE | 16-01-2023 | 16-01-2024 | 1003
316 | UTTAR DINAJPUR | Puria Piped Water Supply Scheme | SM/06041 | SM/07977 | Retrofitting | MVS | 362/RD | UTTAM SAHA | 04-02-2021 | 16-03-2021 | 561
317 | UTTAR DINAJPUR | RAGHABPUR WATER SUPPLY SCHEME | SM/00289 | SM/09192 | Retrofitting | SVS | 2092/RD/PHE | M/S DOLPHIN CONSTRUCTION | 02-11-2021 | 02-12-2021 | 252
318 | UTTAR DINAJPUR | RAGHABPUR WATER SUPPLY SCHEME | SM/00289 | SM/09192 | Retrofitting | SVS | 433/RD/PHE | M/S DOLPHIN CONSTRUCTION | 16-02-2022 | 18-03-2022 | 48
319 | UTTAR DINAJPUR | RAGHABPUR WATER SUPPLY SCHEME | SM/00289 | SM/11728 | Augmentation | SVS | 2022/RD/PHE | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1324
320 | UTTAR DINAJPUR | RAMGANJ WATER SUPPLY SCHEME | SM/00651 | SM/11802 | Augmentation | MVS | 2018/RD/PHE | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 17-11-2022 | 15-02-2023 | 1530
321 | UTTAR DINAJPUR | RAMGANJ WATER SUPPLY SCHEME | SM/00651 | SM/13115 | Augmentation | MVS | 758/RD/PHE | PRASANTA DUTTA | 17-03-2023 | 13-09-2023
322 | UTTAR DINAJPUR | RAMGANJ WATER SUPPLY SCHEME | SM/00651 | SM/09187 | Retrofitting | SVS | 2087/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 02-11-2021 | 02-12-2021 | 545
323 | UTTAR DINAJPUR | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 |  | New | MVS | 294/RD/PHE | UTTAM SAHA | 01-02-2023 | 01-02-2024 | 727
324 | UTTAR DINAJPUR | RANIGANJ Piped Water Supply Scheme | SM/14181 |  | New | MVS | 2475/RD/PHE | UJJWAL DAS | 24-08-2023 | 20-04-2024 | 520
325 | UTTAR DINAJPUR | RAUTARA Pipe Water Supply Scheme | SM/15306 |  | New | MVS | 2481/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 24-08-2023 | 05-09-2023 | 306
326 | UTTAR DINAJPUR | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. | SM/18161 |  | New | SVS | 1560/RD/PHE | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 29-05-2023 | 27-08-2023 | 201
327 | UTTAR DINAJPUR | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. | SM/12792 |  | New | MVS | 673/RD/PHE | UTTAM SAHA | 06-03-2023 | 05-03-2024 | 1969
328 | UTTAR DINAJPUR | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 |  | New | MVS | 98/RD/PHE | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 19-01-2023 | 19-01-2024 | 829
329 | UTTAR DINAJPUR | Sahavita Piped Water Supply Scheme | SM/05000 |  |  | MVS | 856/RD/PHE | SANYAL ENTERPRISE | 12-08-2020 | 26-09-2020 | 930
330 | UTTAR DINAJPUR | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/16493 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 872
331 | UTTAR DINAJPUR | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/17255 |  | New | MVS | 1280/RD/PHE | UTTAM SAHA | 08-05-2023 | 02-02-2024 | 1213
332 | UTTAR DINAJPUR | SARIABAD WATER SUPPLY SCHEME | SM/00292 | SM/09179 | Retrofitting | SVS | 431/RD/PHE | M/S ARVI CONSTRUCTION | 16-02-2022 | 18-03-2022 | 175
333 | UTTAR DINAJPUR | SARIABAD WATER SUPPLY SCHEME | SM/00292 | SM/11798 | Augmentation | SVS | 3749/RD/PHED | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 18-12-2024 | 01-02-2025 | 201
334 | UTTAR DINAJPUR | SARIABAD WATER SUPPLY SCHEME | SM/00292 |  |  | MVS | 2031/RD/PHE | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 17-11-2022 | 16-01-2023 | 79
335 | UTTAR DINAJPUR | SARIABAD WATER SUPPLY SCHEME | SM/00292 | SM/11798 | Augmentation | SVS | 2031/RD/PHE | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 17-11-2022 | 16-01-2023 | 1120
336 | UTTAR DINAJPUR | SARIABAD WATER SUPPLY SCHEME | SM/00292 | SM/09179 | Retrofitting | SVS | 2079/RD/PHE | M/S GHOSH CONSTRUCTION | 02-11-2021 | 02-12-2021 | 165
337 | UTTAR DINAJPUR | SARJAPUR Piped Water Supply Scheme | SM/15127 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
338 | UTTAR DINAJPUR | SASAN WATER SUPPLY SCHEME | SM/00287 |  |  | MVS | 2077/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION | 02-11-2021 | 02-12-2021 | 124
339 | UTTAR DINAJPUR | SASAN WATER SUPPLY SCHEME | SM/00287 | SM/10040 | Augmentation | SVS | 1016/RD/PHED | M/S HINDUSTHAN CONSTRUCTION | 12-05-2022 | 26-06-2022 | 944
340 | UTTAR DINAJPUR | SASAN WATER SUPPLY SCHEME | SM/00287 | SM/09177 | Retrofitting | SVS | 429/RD/PHE | TAPAN KUMAR MAJUMDER | 16-02-2022 | 18-03-2022 | 125
341 | UTTAR DINAJPUR | Sathaur Piped Water Supply Scheme | SM/13231 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024 | 397
342 | UTTAR DINAJPUR | Sergram Piped Water Supply Scheme | SM/06051 | SM/07072 | Retrofitting | MVS | 1434/RD/PHE | AJIT PARMANIK | 11-12-2020 | 10-01-2021
343 | UTTAR DINAJPUR | Sergram Piped Water Supply Scheme | SM/06051 | SM/07072 | Retrofitting | MVS | 1432/RD/PHE | M/S P.S ENTERPRISE | 11-12-2020 | 10-01-2021
344 | UTTAR DINAJPUR | Sergram Piped Water Supply Scheme | SM/06051 | SM/07072 | Retrofitting | MVS | 1433/RD/PHE | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 11-12-2020 | 10-01-2021 | 380
345 | UTTAR DINAJPUR | Sherpur Piped Water Supply Scheme | SM/05006 | SM/13015 | Augmentation | SVS | 1920/RD/PHE | BIKASH KAR | 28-10-2022 | 12-12-2022 | 57
346 | UTTAR DINAJPUR | Sherpur Piped Water Supply Scheme | SM/05006 |  |  | MVS | 1692/RD/PHE | APEX ENTERPRISES | 10-06-2024 | 25-07-2024 | 90
347 | UTTAR DINAJPUR | Sherpur Piped Water Supply Scheme | SM/05006 |  |  | MVS | 355/RD/PHE | AJIT PARMANIK | 01-02-2021 | 02-04-2021 | 312
348 | UTTAR DINAJPUR | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. | SM/12793 |  | New | MVS | 2568/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 723
349 | UTTAR DINAJPUR | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/15211 |  | New | MVS | 2629/RD/PHE | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 13-09-2023 | 25-09-2023 | 34
350 | UTTAR DINAJPUR | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 |  | New | MVS | 72/RD/PHE | SANYAL ENTERPRISE ABHIJITSANYAL2010@GMAIL.COM | 16-01-2023 | 16-01-2024 | 1074
351 | UTTAR DINAJPUR | Siripur W/S Scheme | SM/02165 |  |  | MVS | 63/RD/PHE | M/S DOLPHIN CONSTRUCTION DOLPHIN.RGJ@GMAIL.COM | 16-01-2023 | 02-03-2023 | 50
352 | UTTAR DINAJPUR | Siripur W/S Scheme | SM/02165 | SM/06729 | Retrofitting | MVS | 1234/RD/ PHE | SAMIRAN PODDAR | 16-10-2020 | 25-11-2020
353 | UTTAR DINAJPUR | SITALGAON PIPED WATER SUPPLY SCHEME | SM/00279 | SM/09990 | Augmentation | SVS | 178/RD/PHE | MAA TARA CONSTRUCTION | 27-01-2022 | 13-03-2022 | 16
354 | UTTAR DINAJPUR | SITALGAON PIPED WATER SUPPLY SCHEME | SM/00279 | SM/09990 | Augmentation | SVS | 1017/RD/PHED | HAQUE CONSTRUCTION | 12-05-2022 | 26-06-2022 | 867
355 | UTTAR DINAJPUR | SITALGAON PIPED WATER SUPPLY SCHEME | SM/00279 | SM/09193 | Retrofitting | SVS | 2381/RD/PHE | M/S LUCKY CONSTRUCTION | 24-12-2021 | 23-01-2022 | 123
356 | UTTAR DINAJPUR | Sitgram Piped Water Supply Scheme | SM/04986 | SM/07390 | Retrofitting | MVS | 1537/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23-12-2020 | 06-02-2021 | 514
357 | UTTAR DINAJPUR | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. | SM/16221 |  | New | MVS | 1273/RD/PHE | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 08-05-2023 | 02-02-2024 | 976
358 | UTTAR DINAJPUR | Sripur Piped Water Supply Scheme | SM/04919 | SM/06724 | Retrofitting | MVS | 1237/RD/ PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16-10-2020 | 25-11-2020 | 211
359 | UTTAR DINAJPUR | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/16224 |  | New | MVS | 806/RD/PHE | M/S MAA TARA CONSTRUCTION BIRNAGAR | 21-03-2023 | 16-12-2023 | 1327
360 | UTTAR DINAJPUR | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. | SM/17436 |  | New | MVS | 1279/RD/PHE | SANYAL ENTERPRISE | 08-05-2023 | 02-02-2024 | 1037
361 | UTTAR DINAJPUR | Surun Piped Water Supply Scheme | SM/05003 |  |  | MVS | 863/RD/PHE | M/S MAATARA CONSTRUCTION | 12-08-2020 | 26-09-2020 | 702
362 | UTTAR DINAJPUR | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. | SM/13503 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
363 | UTTAR DINAJPUR | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR | SM/11819 |  | New | MVS | 1994/RD/PHE | M/S MAA TARA CONSTRUCTION BIRNAGAR | 14-11-2022 | 14-11-2023 | 1118
364 | UTTAR DINAJPUR | TUNIBHITA PWSS | SM/18291 |  | New | MVS | 2477/RD/PHE | CALCON CONSTRUCTION | 24-08-2023 | 05-09-2023
365 | UTTAR DINAJPUR | Udaypur and adj. mouzas water supply scheme | SM/02917 | SM/07389 | Retrofitting | MVS | 494/RD/PHE | SANKAR DAS | 17-02-2023 | 03-04-2023 | 200
366 | UTTAR DINAJPUR | Udaypur and adj. mouzas water supply scheme | SM/02917 | SM/07389 | Retrofitting | MVS | 1561/RD/PHE | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24-12-2020 | 22-02-2021 | 758
367 | UTTAR DINAJPUR | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12794 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
368 | UTTAR DINAJPUR | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12795 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024
369 | UTTAR DINAJPUR | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 |  | New | MVS | 69/RD/PHE | M/S MAA TARA CONSTRUCTION BIRNAGAR | 16-01-2023 | 16-01-2024 | 417
370 | UTTAR DINAJPUR | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 |  | New | MVS | 66/RD/PHE | SANYAL ENTERPRISE | 16-01-2023 | 16-01-2024 | 694
371 | UTTAR DINAJPUR | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. | SM/12796 |  | New | MVS | 2567/RD/PHE | ROY ENGINEERS. (PATNA) | 01-09-2023 | 28-05-2024 | 32
372 | UTTAR DINAJPUR | UTTAR SHAHAPUR PWSS | SM/18475 |  | New | MVS | 2590/RD/PHE | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 11-09-2023 | 07-06-2024
Total | [10 empty] | 181991