## Issued Work Order (MALDAH)
Issued Work Order (MALDAH)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | MALDAH | Adatala Piped Water Supply Scheme | SM/04808 |  |  | MVS | 1953/MD | USHA ENTERPRISE | 28-08-2020 | 26-12-2020
2 | MALDAH | AIHO WATER SUPPLY SCHEME | SM/00162 | SM/15155 | Augmentation | SVS | 1211/MD | M/S FRIENDS CONSTRUCTION & CO. | 22-03-2023 | 18-09-2023 | 552
3 | MALDAH | AIHO WATER SUPPLY SCHEME | SM/00162 | SM/15188 | Augmentation | SVS | 4589/MD | FUTURE | 22-11-2023 | 20-05-2024 | 535
4 | MALDAH | AIHO WATER SUPPLY SCHEME | SM/00162 | SM/15188 | Augmentation | SVS | 980/MD | FUTURE | 04-03-2024 | 18-04-2024 | 593
5 | MALDAH | Akalpur and Adjoining Mouzas New Piped Water Supply Scheme | SM/03206 | SM/06851 | Retrofitting | MVS | 2716/MD | M/S AMIT KUMAR GUPTA | 10-11-2020 | 25-12-2020 | 1122
6 | MALDAH | ALINAGAR Piped Water Supply Scheme | SM/13431 |  | New | MVS | 940/MD | BANIK BROTHERS | 27-02-2023 | 24-11-2023 | 739
7 | MALDAH | Altor and Adjoining Mouzas Piped Water Supply Scheme | SM/03199 | SM/06852 | Retrofitting | MVS | 2713/MAAD | MANIK CHANDRA SAHA | 10-11-2020 | 25-12-2020 | 303
8 | MALDAH | Altor and Adjoining Mouzas Piped Water Supply Scheme | SM/03199 | SM/12312 | Augmentation | MVS | 3364/MD | M/S BABLU ENTERPRISE | 29-08-2023 | 13-10-2023 | 419
9 | MALDAH | ANANDIPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME | SM/02713 | SM/06853 | Retrofitting | MVS | 2719/MD | MANAS KUMAR SAHA | 10-11-2020 | 10-12-2020 | 475
10 | MALDAH | ARAZI JALSA PIPED WATER SUPPLY SCHEME. | SM/13734 |  | New | MVS | 2008/MD | M/S TAPAS KUMAR CHAKRABORTY & CO | 17-05-2023 | 11-02-2024 | 8
11 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 1649/MD | UTTAM KUMAR GHOSH | 13-04-2023 | 10-10-2023 | 996
12 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 4772/MD | J. M. CONSTRUCTION | 05-12-2023 | 19-01-2024 | 297
13 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 1572/MD | USHA ENTERPRISE | 10-04-2023 | 09-04-2024 | 2118
14 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 5249/MD | CHARU CONSTRUCTION | 22-12-2023 | 05-02-2024 | 499
15 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 1477/MD | CHARU CONSTRUCTION | 30-03-2023 | 29-04-2023 | 296
16 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 1476/MD | UTTAM KUMAR GHOSH | 30-03-2023 | 29-04-2023 | 279
17 | MALDAH | ARIADANGA WATER SUPPLY SCHEME | SM/00069 | SM/10181 | Augmentation | MVS | 155/MD | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 08-01-2024 | 22-02-2024 | 298
18 | MALDAH | Arjuna and adj. mouzas water supply scheme | SM/02976 | SM/06854 | Retrofitting | MVS | 2717/MD | UNIVERSAL ENTERPRIESES | 10-11-2020 | 25-12-2020 | 1417
19 | MALDAH | Baherpur and adj. mouzas water supply scheme | SM/02964 | SM/07973 | Retrofitting | MVS | 435/MD | PROJECT INDIA | 08-02-2021 | 09-04-2021 | 1236
20 | MALDAH | BAIRAT Piped Water Supply Scheme | SM/12743 |  | New | MVS | 581/MD | USHA ENTERPRISE | 09-02-2023 | 09-02-2024 | 1683
21 | MALDAH | Bakhra Water Supply Scheme | SM/01530 | SM/06855 | Retrofitting | MVS | 2464/MD | UTTAM KUMAR GHOSH | 12-10-2020 | 11-11-2020
22 | MALDAH | BALUPUR WATER SUPPLY SCHEME | SM/00866 | SM/07973 | Retrofitting | MVS | 2379/MD | FUTURE | 13-08-2021 | 12-09-2021
23 | MALDAH | BALUPUR WATER SUPPLY SCHEME | SM/00866 | SM/07973 | Retrofitting | MVS | 2378/MD | ACHARYYA CONSTRUCTION | 13-08-2021 | 12-09-2021 | 313
24 | MALDAH | BALUPUR WATER SUPPLY SCHEME | SM/00866 | SM/07973 | Retrofitting | MVS | 512/MD | JAL PRAVAHIKA PVT. LTD. | 09-02-2021 | 10-04-2021 | 132
25 | MALDAH | BALUPUR WATER SUPPLY SCHEME | SM/00866 | SM/07973 | Retrofitting | MVS | 5247/MD | M/S. TEWARI CONSTRUCTION | 22-12-2023 | 05-02-2024 | 924
26 | MALDAH | BAMANGRAM (BAMANGOLA) WATER SUPPLY SCHEME | SM/00062 | SM/10138 | Augmentation | MVS | 1132/MD | M/S S. DAS & ENTERPRISE | 20-05-2022 | 20-05-2023 | 2962
27 | MALDAH | Barachak Water Sub-mission Scheme | SM/02298 | SM/08760 | Retrofitting | MVS | 1650/MAAD | UTTAM KUMAR GHOSH | 03-11-2021 | 18-12-2021 | 405
28 | MALDAH | Barachak Water Sub-mission Scheme | SM/02298 | SM/08760 | Retrofitting | MVS | 1651/MAAD | DHRITIPALI | 03-11-2021 | 18-12-2021
29 | MALDAH | Barachak Water Sub-mission Scheme | SM/02298 | SM/08760 | Retrofitting | MVS | 1653/MAAD | USHA ENTERPRISE | 03-11-2021 | 02-01-2022
30 | MALDAH | Barachak Water Sub-mission Scheme | SM/02298 | SM/08760 | Retrofitting | MVS | 1832/MAAD | DHRITIPALI | 27-09-2022 | 11-11-2022
31 | MALDAH | Bejpura Piped Water Supply Scheme | SM/05332 | SM/07973 | Retrofitting | MVS | 2152/MD | NEOGI ENTERPRISE | 16-09-2020 | 31-10-2020 | 217
32 | MALDAH | Bejpura Piped Water Supply Scheme | SM/05332 | SM/07973 | Retrofitting | MVS | 1487/MD | CHARU CONSTRUCTION | 23-06-2022 | 23-07-2022 | 176
33 | MALDAH | Belungaon Piped Water Supply Scheme | SM/04829 |  |  | MVS | 1955/MD | UTTAM KUMAR GHOSH | 28-08-2020 | 26-12-2020 | 1
34 | MALDAH | Belungaon Piped Water Supply Scheme | SM/04829 |  |  | MVS | 5246/MD | M/S BANERJEE CONSTRUCTION | 22-12-2023 | 05-02-2024 | 472
35 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 306/MD | RANJIT ADHIKARY | 28-01-2021 | 27-02-2021
36 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 307/MD | S. R. CONSTRUCTION | 28-01-2021 | 27-02-2021 | 319
37 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 308/MD | CHARU CONSTRUCTION | 28-01-2021 | 27-02-2021
38 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 305/MD | KRISHNENDU DUTTA | 28-01-2021 | 27-02-2021 | 522
39 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 451/MD | M/S. TEWARI CONSTRUCTION | 08-02-2021 | 10-03-2021 | 360
40 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 2315/MD | M/S RADHA KRISHNA ENTERPRISE | 30-09-2020 | 01-10-2020
41 | MALDAH | Bhabuk and Adjoining Mouzas Water Supply Scheme | SM/03160 | SM/07972 | Retrofitting | MVS | 2316/MD | M/S AYUSH BUILDERS | 30-09-2020 | 01-10-2020
42 | MALDAH | BHADAR Piped Water Supply Scheme | SM/12768 |  | New | MVS | 1996/MD | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 17-05-2023 | 11-02-2024 | 832
43 | MALDAH | Bhado Water Sub-Mission Scheme | SM/02235 | SM/07973 | Retrofitting | MVS | 2704/MD | GHOSH BROTHERS | 10-11-2020 | 09-01-2021 | 2225
44 | MALDAH | Bhairabpur Piped Water Supply Scheme | SM/05486 | SM/07973 | Retrofitting | MVS | 2142/MD | SUBHAS CHANDRA KESHARI | 16-09-2020 | 15-11-2020 | 1483
45 | MALDAH | Bihari Water Quality Sub mission Scheme | SM/02326 | SM/07007 | Retrofitting | MVS | 4774/MD | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 05-12-2023 | 19-01-2024 | 259
46 | MALDAH | Bihari Water Quality Sub mission Scheme | SM/02326 | SM/07007 | Retrofitting | MVS | 2440/MD | BEE GEE CONSTRUCTION | 12-10-2020 | 11-11-2020 | 200
47 | MALDAH | Bihari Water Quality Sub mission Scheme | SM/02326 | SM/07007 | Retrofitting | MVS | 2445/MD | M/S SABANA CONSTRUCTION | 12-10-2020 | 11-11-2020 | 435
48 | MALDAH | Bijrabhita Water Supply Scheme | SM/01581 | SM/07973 | Retrofitting | MVS | 2534/MD | M/S PARIMAL DAS | 15-10-2020 | 14-12-2020
49 | MALDAH | BINGOL WATER SUPPLY SCHEME | SM/00184 | SM/15948 | Augmentation | SVS | 2321/MD | M/S. TEWARI CONSTRUCTION | 08-06-2023 | 07-06-2024 | 349
50 | MALDAH | BULBULCHANDI WATER SUPPLY SCHEME | SM/00175 | SM/09422 | Augmentation | MVS | 1125/MD | ACQUA CONSTRUCTION CONSORTIUM | 19-05-2022 | 19-05-2023 | 2929
51 | MALDAH | CHAKSUKUR PIPED WATER SUPPLY SCHEME. | SM/13719 |  | New | MVS | 1035/MD | HANNAN BUILDERS PVT. LTD. | 13-03-2023 | 12-03-2024 | 1900
52 | MALDAH | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. | SM/12632 |  | New | MVS | 875/MD | M/S TRILOCHAN CONSTRUCTION CO | 22-02-2023 | 22-02-2024 | 550
53 | MALDAH | Dahara and Adj. Mouzas Water Supply Scheme | SM/03114 | SM/07973 | Retrofitting | MVS | 386/MD | PARIJAT RAY | 17-01-2024 | 02-03-2024 | 1260
54 | MALDAH | Dahara and Adj. Mouzas Water Supply Scheme | SM/03114 | SM/07973 | Retrofitting | MVS | 2684/MD | MADE & TRADE CO. | 06-11-2020 | 05-01-2021 | 599
55 | MALDAH | Dakshin Brindabanpur Water Supply Scheme | SM/03072 | SM/06857 | Retrofitting | MVS | 1525/MD | M/S DAS CONSTRUCTION | 05-05-2021 | 04-06-2021 | 536
56 | MALDAH | Dakshin Chandipur Water Supply Scheme | SM/01458 | SM/06848 | Retrofitting | MVS | 1121/MAAD | BHOLANATH CONSTRUCTION | 09-11-2020 | 09-12-2020 | 290
57 | MALDAH | Dakshin Gouripur and. adj. mouzas water supply scheme | SM/02975 | SM/06858 | Retrofitting | MVS | 3046/MD | S DUTTA | 11-12-2020 | 10-01-2021 | 160
58 | MALDAH | Dakshin Gouripur and. adj. mouzas water supply scheme | SM/02975 | SM/06858 | Retrofitting | MVS | 2736/MD | M/S SABANA CONSTRUCTION | 18-11-2022 | 18-12-2022 | 50
59 | MALDAH | Dakshin Mahendrapur & Adj. Mouzas W/S Scheme | SM/02843 | SM/07973 | Retrofitting | MVS | 385/MD | RAHANUL ALAM | 17-01-2024 | 02-03-2024 | 183
60 | MALDAH | Dakshin Mahendrapur & Adj. Mouzas W/S Scheme | SM/02843 | SM/07973 | Retrofitting | MVS | 2683/MD | MADE & TRADE CO. | 06-11-2020 | 21-12-2020 | 11
61 | MALDAH | Dalla and adjoining mouzas ground water based water supply scheme | SM/02846 | SM/07973 | Retrofitting | MVS | 4767/MD | A. B. CONSTRUCTION | 05-12-2023 | 19-01-2024 | 350
62 | MALDAH | Dalla and adjoining mouzas ground water based water supply scheme | SM/02846 | SM/07973 | Retrofitting | MVS | 2438/MD | M/S JHA CONSTRUCTION | 12-10-2020 | 11-12-2020 | 1
63 | MALDAH | Daulatnagar and Adjoining Mouzas Piped Water Supply Scheme | SM/03167 | SM/07973 | Retrofitting | MVS | 553/MD | NEOGI ENTERPRISE | 12-02-2021 | 13-04-2021 | 1846
64 | MALDAH | Daulatpur & Adj. Mouzas W/S Scheme | SM/02847 | SM/07972 | Retrofitting | MVS | 2314/MD | PRITAM ENTERPRISE | 30-09-2020 | 01-10-2020 | 55
65 | MALDAH | Daulatpur & Adj. Mouzas W/S Scheme | SM/02847 | SM/07972 | Retrofitting | MVS | 266/MD | M/S. TEWARI CONSTRUCTION | 28-01-2021 | 27-02-2021 | 502
66 | MALDAH | Daulatpur & Adj. Mouzas W/S Scheme | SM/02847 | SM/07972 | Retrofitting | MVS | 569/MD | M/S TRILOCHAN CONSTRUCTION CO | 15-02-2021 | 01-04-2021 | 1917
67 | MALDAH | DEOTALA WATER SUPPLY SCHEME | SM/00163 | SM/09986 | Augmentation | MVS | 868/MD | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 08-04-2022 | 08-04-2023 | 821
68 | MALDAH | GAURIA Piped Water Supply Scheme. | SM/12079 |  | New | MVS | 1036/MD | SOVAN KUMAR ROY | 13-03-2023 | 08-12-2023 | 297
69 | MALDAH | GOUR AREA & AUGMENTATION FOR MAHADIPUR WATER SUPPLY SCHEME | SM/00868 | SM/09649 | Retrofitting | MVS | 1738/MAAD | BANIK BROTHERS | 24-11-2021 | 23-01-2022 | 1498
70 | MALDAH | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 |  | New | MVS | 1910/MD | M/S SINHA CONSTRUCTION CO. | 11-05-2023 | 05-02-2024 | 2865
71 | MALDAH | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 |  | New | MVS | 4321/MD | WELFARE ENGINEERING CO-OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 16-10-2023 | 12-07-2024 | 752
72 | MALDAH | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/11590 |  | New | MVS | 3372/MD | M/S SABANA CONSTRUCTION | 29-08-2023 | 13-10-2023 | 1912
73 | MALDAH | Ground Water Based Piped Water Supply Scheme for Khanpur Hulaspur & adjoining mouzas | SM/04244 | SM/07973 | Retrofitting | MVS | 2955/MD | BIDYUT MAHALDAR | 07-12-2022 | 06-01-2023 | 137
74 | MALDAH | Ground Water Based Piped Water Supply Scheme for Khanpur Hulaspur & adjoining mouzas | SM/04244 | SM/07973 | Retrofitting | MVS | 48/MD | BIDYUT MAHALDAR | 13-01-2022 | 03-02-2022 | 163
75 | MALDAH | Ground Water Based Piped Water Supply Scheme for Khanpur Hulaspur & adjoining mouzas | SM/04244 | SM/07973 | Retrofitting | MVS | 2139/MD | M/S TRILOCHAN CONSTRUCTION CO | 16-09-2020 | 31-10-2020 | 1368
76 | MALDAH | Ground Water Based Piped Water Supply Scheme for Arapur | SM/04843 | SM/15141 | Augmentation | SVS | 324/MAAD | S. R. CONSTRUCTION | 21-02-2023 | 22-04-2023 | 298
77 | MALDAH | Ground Water Based Piped Water Supply Scheme for Arapur | SM/04843 |  |  | MVS | 325/MAAD | S. R. ENTERPRISE | 21-02-2023 | 22-04-2023
78 | MALDAH | Ground Water Based Piped Water Supply Scheme for Arapur | SM/04843 |  |  | MVS | 1829/MAAD | BANIK BROTHERS | 27-09-2022 | 11-11-2022 | 36
79 | MALDAH | Ground Water Based Piped Water Supply Scheme for Bahirgachhi & adj. mouzas | SM/03518 | SM/07972 | Retrofitting | MVS | 555/MD | BEE GEE CONSTRUCTION | 12-02-2021 | 14-03-2021 | 1064
80 | MALDAH | Ground Water Based Piped Water Supply Scheme for Bahirgachhi & adj. mouzas | SM/03518 | SM/07972 | Retrofitting | MVS | 270/MD | M/S KUNDU CONSTRUCTION | 28-01-2021 | 27-02-2021 | 149
81 | MALDAH | Ground Water Based Piped Water Supply Scheme for Bahirgachhi & adj. mouzas | SM/03518 | SM/07972 | Retrofitting | MVS | 556/MD | UTTAM KUMAR GHOSH | 12-02-2021 | 29-03-2021 | 272
82 | MALDAH | Ground Water Based Piped Water Supply Scheme for Bahirgachhi & adj. mouzas | SM/03518 | SM/07972 | Retrofitting | MVS | 4766/MD | IDEAL CONSTRUCTION | 05-12-2023 | 19-01-2024 | 292
83 | MALDAH | Ground Water Based Piped Water Supply Scheme for Bara Phulbari | SM/04840 |  |  | MVS | 951/MAAD | TWO BROTHERS CONSTRUCTION | 23-05-2023 | 07-07-2023 | 74
84 | MALDAH | Ground Water Based Piped Water Supply Scheme for Gobindapur & adj. mouzas. | SM/04470 | SM/06860 | Retrofitting | MVS | 2262/MD | UTTAM KUMAR DUTTA | 29-09-2020 | 13-11-2020 | 757
85 | MALDAH | Ground Water Based Piped Water Supply Scheme for Mahanandapur mouza. | SM/04308 | SM/06866 | Retrofitting | MVS | 2714/MD | NEOGI ENTERPRISE | 10-11-2020 | 10-12-2020 | 133
86 | MALDAH | Ground Water Based Piped Water Supply Scheme for Mahanandapur mouza. | SM/04308 | SM/06866 | Retrofitting | MVS | 3052/MD | M/S AYUSH BUILDERS | 09-08-2023 | 08-09-2023 | 257
87 | MALDAH | Ground Water Based Piped Water Supply Scheme for Moyna & adj. mouzas. | SM/04446 | SM/07973 | Retrofitting | MVS | 49/MD | S. R. CONSTRUCTION | 13-01-2022 | 14-03-2022 | 1001
88 | MALDAH | Ground Water Based Piped Water Supply Scheme for Moyna & adj. mouzas. | SM/04446 | SM/07973 | Retrofitting | MVS | 2991/MD | S. R. CONSTRUCTION | 07-12-2022 | 21-01-2023 | 402
89 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 300/MD | PABITRA MONDAL | 28-01-2021 | 27-02-2021 | 191
90 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 301/MD | A. K. SIKDAR | 28-01-2021 | 27-02-2021 | 129
91 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 302/MD | MARSS INTERNATIONAL | 28-01-2021 | 27-02-2021 | 69
92 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 303/MD | ACHARYYA CONSTRUCTION | 28-01-2021 | 27-02-2021 | 240
93 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 304/MD | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 28-01-2021 | 27-02-2021 | 65
94 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 2310/MD | BABLU GHOSH | 30-09-2020 | 01-10-2020
95 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 2311/MD | D. K. INDUSTRIES | 30-09-2020 | 01-10-2020
96 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 296/MD | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 28-01-2021 | 27-02-2021
97 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 297/MD | M/S BANERJEE CONSTRUCTION | 28-01-2021 | 27-02-2021
98 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 298/MD | M/S BANERJEE CONSTRUCTION | 28-01-2021 | 27-02-2021
99 | MALDAH | Ground Water Based Piped Water Supply Scheme for Parameswarpur & adj. mouzas | SM/03516 | SM/07972 | Retrofitting | MVS | 299/MD | S. N. CONSTRUCTION | 28-01-2021 | 27-02-2021 | 395
100 | MALDAH | Ground Water Based Piped Water Supply Scheme for Saiyadpur & adj. mouzas | SM/03514 | SM/12311 | Augmentation | MVS | 1638/MD | SHREE BISHNU CONSTRUCTION | 12-04-2023 | 27-05-2023 | 2
101 | MALDAH | Ground Water Based Piped Water Supply Scheme for Saiyadpur & adj. mouzas | SM/03514 |  |  | MVS | 2136/MD | MANIK CHANDRA SAHA | 16-09-2020 | 31-10-2020 | 306
102 | MALDAH | Ground Water Based Piped Water Supply Scheme for Saiyadpur & adj. mouzas | SM/03514 | SM/12311 | Augmentation | MVS | 3371/MD | S. R. CONSTRUCTION | 29-08-2023 | 13-10-2023 | 125
103 | MALDAH | Ground Water Based Piped Water Supply Scheme for Uttar Nazirpur | SM/04845 | SM/15144 | Augmentation | MVS | 304/MAAD | PRITAM ENTERPRISE | 11-03-2024 | 10-04-2024 | 75
104 | MALDAH | Ground Water Based Water Supply Scheme for Arbara & adjoining mouzas | SM/03910 | SM/07972 | Retrofitting | MVS | 2459/MD | TARUN KUMAR DEY | 12-10-2020 | 11-11-2020
105 | MALDAH | Ground Water Based Water Supply Scheme for Arbara & adjoining mouzas | SM/03910 | SM/07972 | Retrofitting | MVS | 2460/MD | M/S N. N. ENTERPRISE | 12-10-2020 | 11-11-2020
106 | MALDAH | Ground Water Based Water Supply Scheme for Arbara & adjoining mouzas | SM/03910 | SM/07972 | Retrofitting | MVS | 2461/MD | M/S STAR INDIA CONSTRUTION | 12-10-2020 | 11-11-2020
107 | MALDAH | Ground Water Based Water Supply Scheme for Arbara & adjoining mouzas | SM/03910 | SM/07972 | Retrofitting | MVS | 2462/MD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12-10-2020 | 11-11-2020
108 | MALDAH | Ground Water Based Water Supply Scheme for Arbara & adjoining mouzas | SM/03910 | SM/07972 | Retrofitting | MVS | 2463/MD | IDEAL CONSTRUCTION | 12-10-2020 | 11-11-2020
109 | MALDAH | Ground Water Based Water Supply Scheme for Arbara & adjoining mouzas | SM/03910 | SM/07972 | Retrofitting | MVS | 2196/MD | S & G CONSTRUCTION | 22-09-2022 | 22-10-2022 | 109
110 | MALDAH | Ground water based water supply scheme for Dakshin Sahar and adjoining mouzas | SM/03939 | SM/07972 | Retrofitting | MVS | 2458/MD | M/S. TEWARI CONSTRUCTION | 12-10-2020 | 11-11-2020 | 148
111 | MALDAH | Ground water based water supply scheme for Dakshin Sahar and adjoining mouzas | SM/03939 | SM/07972 | Retrofitting | MVS | 2456/MD | M/S BANERJEE CONSTRUCTION | 12-10-2020 | 11-11-2020
112 | MALDAH | Ground water based water supply scheme for Dakshin Sahar and adjoining mouzas | SM/03939 | SM/07972 | Retrofitting | MVS | 2457/MD | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12-10-2020 | 11-11-2020
113 | MALDAH | Ground water based water supply scheme for Dhanjana & adjoining mouzas | SM/03931 | SM/06859 | Retrofitting | MVS | 4775/MD | ANUKUL CHANDRA DAS | 05-12-2023 | 19-01-2024 | 138
114 | MALDAH | Ground water based water supply scheme for Dhanjana & adjoining mouzas | SM/03931 | SM/06859 | Retrofitting | MVS | 2718/MD | NIRENDRA NATH KUNDU | 10-11-2020 | 10-12-2020 | 1054
115 | MALDAH | Ground water based water supply scheme for Gourhanda & adjoining mouzas | SM/03892 | SM/06861 | Retrofitting | MVS | 2721/MD | SUBHAS CHANDRA KESHARI | 10-11-2020 | 25-12-2020
116 | MALDAH | Ground Water Based Water Supply Scheme for Gun Sankrul & Adjoining Mouzas | SM/03662 | SM/07973 | Retrofitting | MVS | 2261/MD | MILLENNIUM ENTERPRISR | 29-09-2020 | 13-11-2020
117 | MALDAH | Ground water based water supply scheme for Kendua & adjoining mouzas | SM/03932 | SM/07972 | Retrofitting | MVS | 283/MD | ANUKUL CHANDRA DAS | 28-01-2021 | 27-02-2021 | 1
118 | MALDAH | Ground water based water supply scheme for Kendua & adjoining mouzas | SM/03932 | SM/07972 | Retrofitting | MVS | 3458/MD | M/S /FAIZUL HAQUE BISWAS | 07-09-2023 | 07-10-2023 | 883
119 | MALDAH | Ground water based water supply scheme for Kendua & adjoining mouzas | SM/03932 | SM/07972 | Retrofitting | MVS | 448/MD | FAIZUL HAQUE BISWAS | 08-02-2021 | 10-03-2021 | 579
120 | MALDAH | Ground water based water supply scheme for Kendua & adjoining mouzas | SM/03932 | SM/07972 | Retrofitting | MVS | 2301/MD | BIDYUT MAHALDAR | 30-09-2020 | 01-10-2020 | 1
121 | MALDAH | Ground water based water supply scheme for Kendua & adjoining mouzas | SM/03932 | SM/07972 | Retrofitting | MVS | 281/MD | M/S. TEWARI CONSTRUCTION | 28-01-2021 | 27-02-2021 | 423
122 | MALDAH | Ground water based water supply scheme for Kendua & adjoining mouzas | SM/03932 | SM/07972 | Retrofitting | MVS | 282/MD | FAIZUL HAQUE BISWAS | 28-01-2021 | 27-02-2021 | 359
123 | MALDAH | Ground Water Based Water Supply Scheme for Khanpur & adjoining mouzas | SM/03916 | SM/07973 | Retrofitting | MVS | 554/MD | RAY CONSTRUCTION CO. | 12-02-2021 | 14-03-2021 | 996
124 | MALDAH | Ground water based water supply scheme for Kutubsahar and adjoining mouzas | SM/03975 | SM/07973 | Retrofitting | MVS | 2135/MD | HANNAN BUILDERS PVT. LTD. | 16-09-2020 | 15-12-2020 | 1967
125 | MALDAH | Ground water based water supply scheme for Kutubsahar and adjoining mouzas | SM/03975 | SM/07973 | Retrofitting | MVS | 4769/MD | ACHARYYA CONSTRUCTION | 05-12-2023 | 19-01-2024 | 300
126 | MALDAH | Ground water based water supply scheme for Kutubsahar and adjoining mouzas | SM/03975 | SM/07973 | Retrofitting | MVS | 978/MD | DHRITIPALI | 04-03-2024 | 18-04-2024 | 297
127 | MALDAH | Ground Water Based Water Supply Scheme for Rampur & adjoining mouzas | SM/03912 | SM/07972 | Retrofitting | MVS | 284/MD | A. K. SIKDAR | 28-01-2021 | 27-02-2021 | 184
128 | MALDAH | Ground Water Based Water Supply Scheme for Rampur & adjoining mouzas | SM/03912 | SM/07972 | Retrofitting | MVS | 2546/MD | ANUKUL CHANDRA DAS | 03-11-2022 | 03-12-2022 | 93
129 | MALDAH | Ground Water Based Water Supply Scheme for Rampur & adjoining mouzas | SM/03912 | SM/07972 | Retrofitting | MVS | 287/MD | ACHARYYA CONSTRUCTION | 28-01-2021 | 27-02-2021 | 278
130 | MALDAH | Ground Water Based Water Supply Scheme for Rampur & adjoining mouzas | SM/03912 | SM/07972 | Retrofitting | MVS | 286/MD | S. N. CONSTRUCTION | 28-01-2021 | 27-02-2021 | 378
131 | MALDAH | Ground Water Based Water Supply Scheme for Rampur & adjoining mouzas | SM/03912 | SM/07972 | Retrofitting | MVS | 449/MD | TARUN KUMAR DEY | 08-02-2021 | 10-03-2021 | 505
132 | MALDAH | Ground Water Based Water Supply Scheme for Rampur & adjoining mouzas | SM/03912 | SM/07972 | Retrofitting | MVS | 285/MD | M/S BANERJEE CONSTRUCTION | 28-01-2021 | 27-02-2021 | 1
133 | MALDAH | Ground Water Based Water Supply Scheme for Sadlichak & adjoining mouzas | SM/03917 | SM/07973 | Retrofitting | MVS | 1962/MD | BEE GEE CONSTRUCTION | 31-08-2020 | 30-09-2020 | 144
134 | MALDAH | Ground Water Based Water Supply Scheme for Sadlichak & adjoining mouzas | SM/03917 | SM/07973 | Retrofitting | MVS | 3810/MD | RABIUL ISLAM | 16-10-2023 | 15-11-2023 | 225
135 | MALDAH | Habibpur Piped Water Supply Scheme | SM/05036 |  |  | MVS | 2143/MD | KRISHNENDU DUTTA | 16-09-2020 | 15-11-2020 | 33
136 | MALDAH | HARDAMNAGAR WATER SUPPLY SCHEME | SM/00828 | SM/06862 | Retrofitting | SVS | 2380/MD | PARIJAT RAY | 13-08-2021 | 12-09-2021 | 438
137 | MALDAH | Itakhola Water Supply Scheme | SM/01468 | SM/08760 | Retrofitting | MVS | 1651/MAAD | DHRITIPALI | 03-11-2021 | 18-12-2021 | 209
138 | MALDAH | Jagannathpur Piped Water Supply Scheme | SM/05495 | SM/07973 | Retrofitting | MVS | 2141/MD | DEBAPRIYA SAHA | 16-09-2020 | 31-10-2020 | 995
139 | MALDAH | JATRADANGA WATER SUPPLY SCHEME | SM/00186 | SM/12734 | Augmentation | SVS | 2830/MD | M/S KUNDU CONSTRUCTION | 25-07-2023 | 20-04-2024 | 1127
140 | MALDAH | JIBJALSAR Piped Water Supply Scheme | SM/12182 |  | New | SVS | 195/MD | ACHARYYA CONSTRUCTION | 19-01-2023 | 19-04-2023 | 125
141 | MALDAH | Jot Basanta Water Supply Scheme | SM/01534 | SM/08283 | Retrofitting | MVS | 2036/MAAD | BINA CONSTRUCTION | 16-11-2022 | 31-12-2022 | 103
142 | MALDAH | Kankot Water Supply Scheme | SM/01531 | SM/07972 | Retrofitting | MVS | 267/MD | MANIK CHOUDHURY | 28-01-2021 | 27-02-2021 | 196
143 | MALDAH | Kankot Water Supply Scheme | SM/01531 | SM/07972 | Retrofitting | MVS | 3811/MD | PRITAM ENTERPRISE | 29-09-2023 | 29-10-2023 | 200
144 | MALDAH | Kankot Water Supply Scheme | SM/01531 | SM/07972 | Retrofitting | MVS | 557/MD | RAY CONSTRUCTION CO. | 12-02-2021 | 14-03-2021
145 | MALDAH | Khopakati Piped Water Supply Scheme | SM/05320 | SM/07973 | Retrofitting | MVS | 2138/MD | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 16-09-2020 | 15-12-2020 | 412
146 | MALDAH | Khopakati Piped Water Supply Scheme | SM/05320 | SM/07973 | Retrofitting | MVS | 5245/MD | M/S FOUR STAR CONSTRUCTION | 22-12-2023 | 05-02-2024 | 697
147 | MALDAH | Konar & Adj. Mouzas W/S Scheme | SM/02845 | SM/07972 | Retrofitting | MVS | 288/MD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28-01-2021 | 27-02-2021 | 548
148 | MALDAH | Konar & Adj. Mouzas W/S Scheme | SM/02845 | SM/07972 | Retrofitting | MVS | 290/MD | M/S SABANA CONSTRUCTION | 28-01-2021 | 27-02-2021 | 597
149 | MALDAH | Konar & Adj. Mouzas W/S Scheme | SM/02845 | SM/07972 | Retrofitting | MVS | 2313/MD | M/S EHAN ENTERPRISE | 30-09-2020 | 01-10-2020
150 | MALDAH | Konar & Adj. Mouzas W/S Scheme | SM/02845 | SM/07972 | Retrofitting | MVS | 289/MD | JOYDEB SENGUPTA | 28-01-2021 | 27-02-2021 | 6
151 | MALDAH | Konar & Adj. Mouzas W/S Scheme | SM/02845 | SM/07972 | Retrofitting | MVS | 450/MD | M/S. TEWARI CONSTRUCTION | 08-02-2021 | 10-03-2021 | 459
152 | MALDAH | KUSHIDA WATER SUPPLY SCHEME | SM/00158 |  |  | MVS | 1569/MD | SUBHAS CHANDRA KESHARI | 10-04-2023 | 05-01-2024 | 337
153 | MALDAH | Lakshmighat Water Supply Scheme | SM/01599 | SM/08283 | Retrofitting | MVS | 2035/MAAD | ANJIMA CONSTRUCTION CO. | 16-11-2022 | 31-12-2022 | 80
154 | MALDAH | Mabrakpur & adjoining mouzas water supply scheme | SM/02841 | SM/07972 | Retrofitting | MVS | 3365/MD | GOBINDA ENTERPRISE | 29-08-2023 | 13-10-2023 | 819
155 | MALDAH | Mabrakpur & adjoining mouzas water supply scheme | SM/02841 | SM/07972 | Retrofitting | MVS | 591/MD | NIRENDRA NATH KUNDU | 18-02-2021 | 19-04-2021 | 615
156 | MALDAH | Mabrakpur & adjoining mouzas water supply scheme | SM/02841 | SM/07972 | Retrofitting | MVS | 295/MD | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 28-01-2021 | 27-02-2021 | 26
157 | MALDAH | Mabrakpur & adjoining mouzas water supply scheme | SM/02841 | SM/07972 | Retrofitting | MVS | 509/MD | M/S KUNDU CONSTRUCTION | 09-02-2021 | 11-03-2021 | 1011
158 | MALDAH | Magura Water Sub-mission Scheme | SM/02240 | SM/07973 | Retrofitting | MVS | 2551/MD | MILLENNIUM ENTERPRISR | 15-10-2020 | 14-12-2020 | 1026
159 | MALDAH | Magura Water Sub-mission Scheme | SM/02240 | SM/07973 | Retrofitting | MVS | 2443/MD | M/S KUNDU CONSTRUCTION | 12-10-2020 | 11-11-2020
160 | MALDAH | Mahabbatpur Water sub-mission scheme | SM/02435 | SM/08760 | Retrofitting | MVS | 1652/MAAD | S. R. CONSTRUCTION | 03-11-2021 | 18-12-2021 | 499
161 | MALDAH | Mahabbatpur Water sub-mission scheme | SM/02435 | SM/08760 | Retrofitting | MVS | 207/MAAD | M/S PARIMAL DAS | 08-02-2021 | 09-04-2021 | 15
162 | MALDAH | Mahabbatpur Water sub-mission scheme | SM/02435 | SM/08760 | Retrofitting | MVS | 206/MAAD | BANIK BROTHERS | 08-02-2021 | 09-04-2021
163 | MALDAH | Mahabbatpur Water sub-mission scheme | SM/02435 | SM/08760 | Retrofitting | MVS | 1649/MAAD | GOUTAM SAHA | 03-11-2021 | 18-12-2021
164 | MALDAH | Mahammadpur Water Supply Scheme | SM/01535 | SM/06865 | Retrofitting | MVS | 1963/MD | A. K. CONSTRUCTION | 31-08-2020 | 30-09-2020
165 | MALDAH | Mahammadpur Water Supply Scheme | SM/01535 | SM/06865 | Retrofitting | MVS | 1963/MD | A. K. CONSTRUCTION | 31-08-2020 | 30-09-2020
166 | MALDAH | Mahammadpur Water Supply Scheme | SM/01535 | SM/06865 | Retrofitting | MVS | 4770/MD | M/S EHAN ENTERPRISE | 05-12-2023 | 19-01-2024 | 210
167 | MALDAH | MAHESHPUR WATER SUPPLY SCHEME | SM/00166 | SM/12362 | Augmentation | MVS | 3179/MD | M/S NIRAPADA BHATTACHARJEE | 23-12-2022 | 23-12-2023 | 2811
168 | MALDAH | MAHESHPUR WATER SUPPLY SCHEME | SM/00166 |  |  | MVS | 2442/MD | M/S PRATIMA CONSTRUCTION | 12-10-2020 | 11-11-2020 | 10
169 | MALDAH | MAHISHBATHAN PIPED WATER SUPPLY SCHEME | SM/00179 | SM/16383 | Augmentation | SVS | 2005/MD | M/S DAS CONSTRUCTION | 17-05-2023 | 01-07-2023 | 179
170 | MALDAH | MALATIPUR WATER SUPPLY SCHEME | SM/00160 | SM/09987 | Augmentation | MVS | 2914/MD | DEEP CONSTRUCTION | 31-07-2023 | 27-01-2024 | 1368
171 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 1731/MAAD | M/S MOON LIGHT CONSTRUCTION & CO. | 24-11-2021 | 08-01-2022 | 376
172 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 1730/MAAD | MD. TALEB ALI | 24-11-2021 | 23-01-2022 | 1025
173 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 1732/MAAD | M/S MOON LIGHT CONSTRUCTION & CO. | 24-11-2021 | 23-01-2022 | 1113
174 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 1734/MAAD | M/S KUNDU CONSTRUCTION | 24-11-2021 | 08-01-2022 | 896
175 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09592 | Retrofitting | MVS | 1735/MAAD | GOBINDA ENTERPRISE | 24-11-2021 | 23-01-2022 | 1492
176 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09592 | Retrofitting | MVS | 1736/MAAD | BANIK BROTHERS | 24-11-2021 | 23-01-2022 | 2119
177 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09648 | Retrofitting | MVS | 1739/MAAD | M/S AMIT KUMAR GUPTA | 24-11-2021 | 23-01-2022 | 1740
178 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09659 | Retrofitting | MVS | 1741/MAAD | M/S TRILOCHAN CONSTRUCTION CO. | 24-11-2021 | 23-01-2022 | 1554
179 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09652 | Retrofitting | MVS | 1728/MAAD | DEY CONSTRUCTION | 24-11-2021 | 23-01-2022 | 1583
180 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09654 | Retrofitting | MVS | 1763/MAAD | SUDIP DEY | 24-11-2021 | 23-01-2022 | 996
181 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09587 | Retrofitting | MVS | 1022/MAAD | ACHARYYA CONSTRUCTION | 12-05-2022 | 11-07-2022 | 708
182 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09587 | Retrofitting | MVS | 1023/MAAD | DHRITIPALI | 12-05-2022 | 26-06-2022 | 390
183 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09658 | Retrofitting | MVS | 1024/MAAD | BENGAL ENGINEERING COMPANY | 12-05-2022 | 26-06-2022 | 270
184 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09659 | Retrofitting | MVS | 1012/MAAD | M/S ALISA CONSTRUCTION | 12-05-2022 | 11-07-2022 | 355
185 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09659 | Retrofitting | MVS | 1014/MAAD | M/S ALISA CONSTRUCTION | 12-05-2022 | 11-07-2022
186 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09651 | Retrofitting | MVS | 1745/MAAD | FUTURE | 24-11-2021 | 23-01-2022 | 1300
187 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09657 | Retrofitting | MVS | 1740/MAAD | M/S TRILOCHAN CONSTRUCTION CO. | 24-11-2021 | 23-01-2022 | 1283
188 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09661 | Retrofitting | MVS | 1746/MAAD | A. K. CONSTRUCTION | 24-11-2021 | 23-01-2022 | 1570
189 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09655 | Retrofitting | MVS | 1747/MAAD | A. K. CONSTRUCTION | 24-11-2021 | 23-01-2022 | 795
190 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09658 | Retrofitting | MVS | 1748/MAAD | MILLENNIUM ENTERPRISE | 24-11-2021 | 23-01-2022 | 1007
191 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09662 | Retrofitting | MVS | 1749/MAAD | SOVON KUMAR DAS | 24-11-2021 | 23-01-2022 | 1081
192 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09660 | Retrofitting | MVS | 1750/MAAD | M/S N. N. ENTERPRISE | 24-11-2021 | 08-01-2022
193 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09663 | Retrofitting | MVS | 1759/MAAD | ABANI BHUSAN GHOSH | 24-11-2021 | 08-01-2022 | 805
194 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09663 | Retrofitting | MVS | 1760/MAAD | M/S. JHA CONSTRUCTION | 24-11-2021 | 23-01-2022 | 994
195 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09660 | Retrofitting | MVS | 1761/MAAD | BHOLANATH CONSTRUCTION | 24-11-2021 | 23-01-2022 | 1113
196 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09588 | Retrofitting | SVS | 2020/MAAD | MANIK CHOUDHURY | 29-12-2021 | 27-02-2022 | 409
197 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09646 | Retrofitting | MVS | 1994/MAAD | BANIK BROTHERS | 27-12-2021 | 27-03-2022 | 3410
198 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09587 | Retrofitting | MVS | 1755/MAAD | ACHARYYA CONSTRUCTION | 24-11-2021 | 08-01-2022 | 424
199 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09587 | Retrofitting | MVS | 1756/MAAD | ACHARYYA CONSTRUCTION | 24-11-2021 | 08-01-2022 | 418
200 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09591 | Retrofitting | MVS | 1757/MAAD | A. B. CONSTRUCTION | 24-11-2021 | 08-01-2022 | 602
201 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09662 | Retrofitting | MVS | 1399/MAAD | PARIJAT RAY | 26-07-2022 | 24-09-2022 | 529
202 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09660 | Retrofitting | MVS | 1400/MAAD | M/S N. N. ENTERPRISE | 26-07-2022 | 24-09-2022 | 708
203 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09662 | Retrofitting | MVS | 1534/MAAD | SAHA CONSTRUCTION | 05-08-2022 | 04-10-2022 | 798
204 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09591 | Retrofitting | MVS | 1534/MAAD | SAHA CONSTRUCTION | 05-08-2022 | 04-10-2022
205 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09587 | Retrofitting | MVS | 1469/MAAD | S. R. ENTERPRISE | 29-07-2022 | 12-09-2022 | 113
206 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09587 | Retrofitting | MVS | 1466/MAAD | TARUN KANTI BAGCHI | 29-07-2022 | 12-09-2022 | 117
207 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09662 | Retrofitting | MVS | 1398/MAAD | SOVON KUMAR DAS | 26-07-2022 | 24-09-2022 | 901
208 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09591 | Retrofitting | MVS | 1473/MAAD | ABHIJIT ENTERPRISE | 29-07-2022 | 12-09-2022 | 125
209 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09652 | Retrofitting | MVS | 1017/MAAD | M/S PARIMAL DAS | 12-05-2022 | 11-07-2022 | 1023
210 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09647 | Retrofitting | MVS | 818/MAAD | BEE GEE CONSTRUCTION | 28-04-2022 | 27-06-2022 | 1770
211 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09647 | Retrofitting | MVS | 819/MAAD | M/S PRATIMA CONSTRUCTION | 28-04-2022 | 12-06-2022 | 596
212 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09652 | Retrofitting | MVS | 820/MAAD | DEY CONSTRUCTION | 28-04-2022 | 27-06-2022 | 1001
213 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09657 | Retrofitting | MVS | 829/MAAD | M/S BABLU ENTERPRISE, | 28-04-2022 | 12-06-2022 | 280
214 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09648 | Retrofitting | MVS | 821/MAAD | FUTURE | 28-04-2022 | 27-06-2022 | 1971
215 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09591 | Retrofitting | MVS | 1477/MAAD | M/S. AYUSH BUILDERS | 29-07-2022 | 12-09-2022 | 125
216 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09655 | Retrofitting | MVS | 1158/MAAD | A. K. CONSTRUCTION | 13-06-2022 | 28-07-2022 | 104
217 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09591 | Retrofitting | MVS | 825/MAAD | GOBINDA ENTERPRISE | 28-04-2022 | 27-06-2022 | 907
218 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09646 | Retrofitting | MVS | 826/MAAD | BANIK BROTHERS | 28-04-2022 | 27-06-2022 | 1807
219 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09661 | Retrofitting | MVS | 822/MAAD | A. K. CONSTRUCTION | 28-04-2022 | 27-06-2022 | 1240
220 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09655 | Retrofitting | MVS | 823/MAAD | SUBHASH CHANDRA KESHARI | 28-04-2022 | 27-06-2022 | 1014
221 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09593 | Retrofitting | MVS | 1015/MAAD | M/S ALISA CONSTRUCTION | 12-05-2022 | 11-07-2022 | 2612
222 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09663 | Retrofitting | MVS | 1016/MAAD | NEOGI ENTERPRISE | 12-05-2022 | 11-07-2022 | 918
223 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 1018/MAAD | MANASH KUMAR SAHA | 12-05-2022 | 11-07-2022 | 1384
224 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09651 | Retrofitting | MVS | 1019/MAAD | M/S ALISA CONSTRUCTION | 12-05-2022 | 11-07-2022 | 1047
225 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09657 | Retrofitting | MVS | 1020/MAAD | M/S MANDAL & SONS | 12-05-2022 | 26-06-2022 | 706
226 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09650 | Retrofitting | MVS | 1021/MAAD | SUDIP DEY | 12-05-2022 | 26-06-2022 | 92
227 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09648 | Retrofitting | MVS | 885/MAAD | M/S AMIT KUMAR GUPTA | 11-05-2023 | 10-07-2023 | 199
228 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11916 | Retrofitting | MVS | 886/MAAD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11-05-2023 | 10-07-2023 | 160
229 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09663 | Retrofitting | MVS | 1753/MAAD | NEOGI ENTERPRISE | 24-11-2021 | 23-01-2022 | 930
230 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09650 | Retrofitting | MVS | 50/MAAD | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 20-01-2022 | 20-04-2022 | 4157
231 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09658 | Retrofitting | MVS | 328/MAAD | M/S BABLU ENTERPRISE, | 21-02-2023 | 22-04-2023 | 206
232 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09593 | Retrofitting | MVS | 1831MAAD | THREE BROTHERS CONSTRUCTION & CO. | 27-09-2022 | 11-11-2022 | 103
233 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09593 | Retrofitting | MVS | 321/MAAD | THREE BROTHERS CONSTRUCTION & CO. | 21-02-2023 | 22-04-2023 | 174
234 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09589 | Retrofitting | MVS | 1865/MAAD | SUDIP DEY | 28-09-2022 | 12-11-2022 | 71
235 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09648 | Retrofitting | MVS | 2033/MAAD | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 16-11-2022 | 31-12-2022 | 192
236 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09592 | Retrofitting | MVS | 2030MAAD | M/S STAR INDIA CONSTRUCTION | 16-11-2022 | 15-01-2023 | 998
237 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 2032/MAAD | THREE BROTHERS CONSTRUCTION & CO. | 16-11-2022 | 31-12-2022 | 201
238 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11912 | Retrofitting | MVS | 3070/MAAD | UNITED FRIENDS UMEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD | 14-12-2023 | 12-02-2024 | 25
239 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11912 | Retrofitting | MVS | 3072/MAAD | MD. TALEB ALI | 14-12-2023 | 12-02-2024 | 167
240 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11912 | Retrofitting | MVS | 3075/MAAD | ACHARYYA CONSTRUCTION | 14-12-2023 | 13-03-2024 | 249
241 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11911 | Retrofitting | MVS | 303/MAAD | M/S N. N. ENTERPRISE | 11-03-2024 | 10-04-2024 | 27
242 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09656 | Retrofitting | MVS | 1742/MAAD | BEE GEE CONSTRUCTION | 24-11-2021 | 23-01-2022 | 1184
243 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09658 | Retrofitting | MVS | 1025/MAAD | BENGAL ENGINEERING COMPANY | 12-05-2022 | 26-06-2022 | 300
244 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09652 | Retrofitting | MVS | 2029/MAAD | M/S MOON LIGHT CONSTRUCTION & CO. | 16-11-2022 | 31-12-2022 | 439
245 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11916 | Retrofitting | MVS | 3078/MAAD | M/S EHAN ENTERPRISE | 14-12-2023 | 12-02-2024 | 131
246 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11912 | Retrofitting | MVS | 3071/MAAD | DEY CONSTRUCTIONS | 14-12-2023 | 12-02-2024 | 100
247 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/11916 | Retrofitting | MVS | 1892/MAAD | ABHIJIT CONSTRUCTION | 12-10-2023 | 11-11-2023 | 200
248 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09659 | Retrofitting | MVS | 1057/MAAD | M/S SABANA CONSTRUCTION | 24-05-2022 | 23-07-2022 | 900
249 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09660 | Retrofitting | MVS | 884/MAAD | M/S N. N. ENTERPRISE | 11-05-2023 | 10-07-2023
250 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09592 | Retrofitting | MVS | 1737/MAAD | BANIK BROTHERS | 24-11-2021 | 23-01-2022 | 315
251 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09589 | Retrofitting | MVS | 1762/MAAD | MANIK CH. SAHA | 24-11-2021 | 23-01-2022 | 1001
252 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09593 | Retrofitting | MVS | 1733/MAAD | M/S MOON LIGHT CONSTRUCTION & CO. | 24-11-2021 | 23-01-2022 | 1182
253 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09647 | Retrofitting | MVS | 1743/MAAD | BEE GEE CONSTRUCTION | 24-11-2021 | 23-01-2022 | 900
254 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09590 | Retrofitting | MVS | 1744/MAAD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24-11-2021 | 23-01-2022 | 1198
255 | MALDAH | MALDA SURFACE WATER Project | SM/01001 | SM/09653 | Retrofitting | MVS | 1729/MAAD | MD. TALEB ALI | 24-11-2021 | 23-01-2022 | 1016
256 | MALDAH | MATHURAPUR WATER SUPPLY SCHEME | SM/00159 | SM/09588 | Retrofitting | SVS | 1751/MAAD | M/S PARIMAL DAS | 24-11-2021 | 23-01-2022 | 1198
257 | MALDAH | MATHURAPUR WATER SUPPLY SCHEME | SM/00159 | SM/09588 | Retrofitting | SVS | 1754/MAAD | M/S MAA TARA CONSTRUCTION | 24-11-2021 | 23-01-2022 | 1246
258 | MALDAH | MATHURAPUR WATER SUPPLY SCHEME | SM/00159 | SM/09588 | Retrofitting | SVS | 1758/MAAD | M/S STAR INDIA CONSTRUCTION | 24-11-2021 | 08-01-2022 | 907
259 | MALDAH | MATHURAPUR WATER SUPPLY SCHEME | SM/00159 | SM/09588 | Retrofitting | SVS | 1752/MAAD | NEOGI ENTERPRISE | 24-11-2021 | 23-01-2022 | 1534
260 | MALDAH | Mekpur and Adjoining mouzaswater Supply Scheme of Maldah under ARWSP During 2009-2010 | SM/02831 | SM/07973 | Retrofitting | MVS | 3366/MD | MANIK CHOUDHURY | 29-08-2023 | 13-10-2023 | 497
261 | MALDAH | Mekpur and Adjoining mouzaswater Supply Scheme of Maldah under ARWSP During 2009-2010 | SM/02831 | SM/07973 | Retrofitting | MVS | 2535/MD | DEBAPRIYA SAHA | 15-10-2020 | 14-12-2020
262 | MALDAH | Mianagar and adjoining mouzas ground water based water supply scheme | SM/02848 | SM/06867 | Retrofitting | MVS | 2439/MD | M/S AMIT KUMAR GUPTA | 12-10-2020 | 26-11-2020 | 285
263 | MALDAH | Mihaghat and adjoining mouzas water supply scheme | SM/02844 | SM/06868 | Retrofitting | SVS | 3001/MD | A. K. CONSTRUCTION | 10-12-2020 | 09-01-2021 | 540
264 | MALDAH | MIRZAPUR (PAKUAHAT) WATER SUPPLY SCHEME | SM/00063 | SM/10317 | Augmentation | MVS | 2917/MD | MATIUR RAHAMAN | 31-07-2023 | 27-01-2024 | 2256
265 | MALDAH | Nagharia Water Supply Scheme | SM/01533 | SM/06849 | Retrofitting | SVS | 1120/MAAD | MILLENNIUM ENTERPRISE | 09-11-2020 | 24-12-2020 | 144
266 | MALDAH | NASIRPUR PIPED WATER SUPPLY SCHEME | SM/00178 | SM/15952 | Augmentation | SVS | 2711/MD | MANAS KUMAR SAHA | 14-07-2023 | 09-04-2024 | 420
267 | MALDAH | Nemua Water Supply Scheme | SM/02746 | SM/07972 | Retrofitting | MVS | 3367/MD | MOMTAJ ALI | 29-08-2023 | 13-10-2023 | 729
268 | MALDAH | Nemua Water Supply Scheme | SM/02746 | SM/07972 | Retrofitting | MVS | 268/MD | BEE GEE CONSTRUCTION | 28-01-2021 | 27-02-2021 | 648
269 | MALDAH | Nemua Water Supply Scheme | SM/02746 | SM/07972 | Retrofitting | MVS | 269/MD | GOBINDA ENTERPRISE | 28-01-2021 | 27-02-2021 | 494
270 | MALDAH | Nemua Water Supply Scheme | SM/02746 | SM/07972 | Retrofitting | MVS | 2312/MD | DEVI ENTERPRISE | 30-09-2020 | 01-10-2020 | 44
271 | MALDAH | Paharpur water sub-mission scheme | SM/02517 | SM/06869 | Retrofitting | MVS | 2465/MD | UTTAM KUMAR GHOSH | 12-10-2020 | 26-11-2020 | 1185
272 | MALDAH | Piped Water Supply Scheme or Kadirpur & adj. mouzas | SM/03304 | SM/06864 | Retrofitting | MVS | 1964/MD | M/S KUNDU CONSTRUCTION | 31-08-2020 | 30-09-2020 | 215
273 | MALDAH | Piped Water Supply Scheme or Kadirpur & adj. mouzas | SM/03304 | SM/06864 | Retrofitting | MVS | 4768/MD | M/S SINHA ENTERPRISE | 05-12-2023 | 19-01-2024 | 158
274 | MALDAH | Piped Water Supply Scheme or Rajarampur & adj. mouzas | SM/03303 | SM/07973 | Retrofitting | MVS | 3369/MD | M/S PRATIMA CONSTRUCTION | 29-08-2023 | 13-10-2023 | 405
275 | MALDAH | Piped Water Supply Scheme or Rajarampur & adj. mouzas | SM/03303 | SM/07973 | Retrofitting | MVS | 2263/MD | UTTAM KUMAR DUTTA | 29-09-2020 | 13-11-2020
276 | MALDAH | Piped Water Supply Scheme for Adhna & adj. mouzas | SM/03249 | SM/06850 | Retrofitting | MVS | 3363/MD | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 29-08-2023 | 13-10-2023 | 260
277 | MALDAH | Piped Water Supply Scheme for Adhna & adj. mouzas | SM/03249 | SM/06850 | Retrofitting | MVS | 2153/MD | TARUN KUMAR DEY | 16-09-2020 | 16-10-2020
278 | MALDAH | Piped Water Supply Scheme for Jalalpur & adj. mouzas | SM/03824 | SM/07973 | Retrofitting | MVS | 2140/MD | FUTURE | 16-09-2020 | 15-11-2020 | 2501
279 | MALDAH | Piped Water Supply Scheme for Malipakar & Adj. Mouzas | SM/03580 | SM/07972 | Retrofitting | MVS | 568/MD | NEOGI ENTERPRISE | 15-02-2021 | 01-04-2021
280 | MALDAH | Piped Water Supply Scheme for Malipakar & Adj. Mouzas | SM/03580 | SM/07972 | Retrofitting | MVS | 271/MD | GOBINDA ENTERPRISE | 28-01-2021 | 27-02-2021 | 309
281 | MALDAH | Piped Water Supply Scheme for Malipakar & Adj. Mouzas | SM/03580 | SM/07972 | Retrofitting | MVS | 272/MD | M/S SABANA CONSTRUCTION | 28-01-2021 | 27-02-2021 | 782
282 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 2295/MD | M/S KAMALA ENTERPRISE | 30-09-2020 | 01-10-2020
283 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 2451/MD | CHARU CONSTRUCTION | 12-10-2020 | 11-11-2020
284 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 2450/MD | GHOSH CONSTRUCTION | 12-10-2020 | 11-11-2020
285 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 2296/MD | JIBON GHOSH | 30-09-2020 | 01-10-2020
286 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 2449/MD | A. B. CONSTRUCTION | 12-10-2020 | 11-11-2020
287 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 3368/MD | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 29-08-2023 | 13-10-2023 | 250
288 | MALDAH | Piped Water Supply Scheme for Purba Binodpur & adj. mouzas | SM/03250 | SM/07972 | Retrofitting | MVS | 2448/MD | PARIJAT RAY | 12-10-2020 | 11-11-2020
289 | MALDAH | Piped Water Supply Scheme for Uttar Kumedpur & adj. mouzas | SM/03823 | SM/07972 | Retrofitting | MVS | 4771/MD | MD WARESH ALI | 05-12-2023 | 19-01-2024 | 497
290 | MALDAH | Piped Water Supply Scheme for Uttar Kumedpur & adj. mouzas | SM/03823 | SM/07972 | Retrofitting | MVS | 274/MD | A. K. CONSTRUCTION | 28-01-2021 | 27-02-2021 | 506
291 | MALDAH | Piped Water Supply Scheme for Uttar Kumedpur & adj. mouzas | SM/03823 | SM/07972 | Retrofitting | MVS | 273/MD | MD WARESH ALI | 28-01-2021 | 27-02-2021 | 305
292 | MALDAH | Piped Water Supply Scheme for Uttar Kumedpur & adj. mouzas | SM/03823 | SM/07972 | Retrofitting | MVS | 3004/MD | FUTURE | 07-10-2021 | 06-11-2021 | 775
293 | MALDAH | Pirpur Water Supply Scheme | SM/01493 |  |  | MVS | 2444/MD | S. N. CONSTRUCTION | 12-10-2020 | 11-11-2020 | 750
294 | MALDAH | Proposed Lalapur & its adj. mouza water supply scheme. | SM/04248 | SM/08760 | Retrofitting | MVS | 1649/MAAD | GOUTAM SAHA | 03-11-2021 | 18-12-2021 | 373
295 | MALDAH | PUTIA PWSS | SM/12194 |  | New | SVS | 593/MD | PARIJAT RAY | 09-02-2023 | 10-05-2023 | 130
296 | MALDAH | PWS Scheme for Barkol and adj. mouzas | SM/02899 | SM/06856 | Retrofitting | MVS | 2720/MD | M/S JHA CONSTRUCTION | 10-11-2020 | 25-12-2020 | 1174
297 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2308/MD | M/S FOUR STAR CONSTRUCTION | 30-09-2020 | 01-10-2020
298 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2302/MD | M/S GULFAM CONSTRUCTION | 30-09-2020 | 01-10-2020
299 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 293/MD | S. R. CONSTRUCTION | 28-01-2021 | 27-02-2021 | 353
300 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 292/MD | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 28-01-2021 | 27-02-2021 | 131
301 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 294/MD | GOBINDA ENTERPRISE | 28-01-2021 | 27-02-2021
302 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2309/MD | M/S UNITED CONCERN | 30-09-2020 | 01-10-2020
303 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2305/MD | M/S MAA TARA ENTERPRISE | 30-09-2020 | 01-10-2020
304 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2306/MD | RABIUL ISLAM | 30-09-2020 | 01-10-2020 | 1
305 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2307/MD | ANJIMA CONSTRUCTION CO. | 30-09-2020 | 01-10-2020
306 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2303/MD | BENGAL CONSTRUCTION | 30-09-2020 | 01-10-2020
307 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 2304/MD | M/S A. B. CONSTRUCTION | 30-09-2020 | 01-10-2020
308 | MALDAH | PWS Scheme for Basara and adj. mouzas | SM/02900 | SM/07972 | Retrofitting | MVS | 291/MD | RANJIT ADHIKARY | 28-01-2021 | 27-02-2021 | 128
309 | MALDAH | PWS Scheme for Gannadia & adj. mouzas | SM/02887 | SM/07972 | Retrofitting | MVS | 265/MD | MANIK CHOUDHURY | 28-01-2021 | 27-02-2021
310 | MALDAH | PWS Scheme for Gannadia & adj. mouzas | SM/02887 | SM/07972 | Retrofitting | MVS | 447/MD | MANIK CHOUDHURY | 08-02-2021 | 10-03-2021 | 159
311 | MALDAH | PWS Scheme for Jagajjibanpur & adj. mouzas | SM/02886 | SM/06863 | Retrofitting | MVS | 2447/MD | MANIK CHOUDHURY | 12-10-2020 | 11-11-2020 | 416
312 | MALDAH | PWS Scheme for Khatil and adj. mouzas | SM/02898 | SM/07972 | Retrofitting | MVS | 310/MD | JOY ENTERPRISE | 28-01-2021 | 27-02-2021 | 151
313 | MALDAH | PWS Scheme for Khatil and adj. mouzas | SM/02898 | SM/07972 | Retrofitting | MVS | 312/MD | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28-01-2021 | 27-02-2021 | 206
314 | MALDAH | PWS Scheme for Khatil and adj. mouzas | SM/02898 | SM/07972 | Retrofitting | MVS | 311/MD | MANAS KUMAR SAHA | 28-01-2021 | 27-02-2021 | 318
315 | MALDAH | PWS Scheme for Khatil and adj. mouzas | SM/02898 | SM/07972 | Retrofitting | MVS | 309/MD | S. R. CONSTRUCTION | 28-01-2021 | 27-02-2021
316 | MALDAH | PWS Scheme for Khatil and adj. mouzas | SM/02898 | SM/07972 | Retrofitting | MVS | 452/MD | GOBINDA ENTERPRISE | 08-02-2021 | 10-03-2021 | 458
317 | MALDAH | PWS Scheme for Khatil and adj. mouzas | SM/02898 | SM/07972 | Retrofitting | MVS | 2300/MD | RATAN KARMAKAR | 30-09-2020 | 01-10-2020
318 | MALDAH | PWS Scheme for Pannapur and adj. mouzas | SM/02901 | SM/06870 | Retrofitting | MVS | 2712/MD | NIRENDRA NATH KUNDU | 10-11-2020 | 25-12-2020
319 | MALDAH | RAHIMPUR Piped Water Supply Scheme | SM/14174 |  | New | MVS | 1571/MD | M/S GUPTA ENTERPRISE | 10-04-2023 | 05-01-2024 | 974
320 | MALDAH | RAJARAM CHAK PIPED WATER SUPPLY SCHEME | SM/14461 |  | New | SVS | 3087/MD | MONDAL CONSTRUCTION | 10-08-2023 | 06-05-2024
321 | MALDAH | Ramchandrapur Water Supply Scheme | SM/01497 | SM/06848 | Retrofitting | MVS | 2007/MAAD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28-12-2021 | 11-02-2022 | 173
322 | MALDAH | Ramchandrapur Water Supply Scheme | SM/01497 | SM/06848 | Retrofitting | MVS | 1066/MAAD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14-10-2020 | 13-11-2020 | 420
323 | MALDAH | Ramnagar Piped Water Supply Scheme | SM/04841 |  |  | MVS | 1954/MD | BANI ENGINEERING CO. | 28-08-2020 | 26-12-2020
324 | MALDAH | Ranghaipur Piped Water Supply Scheme | SM/04831 |  |  | MVS | 2037/MD | PROJECT INDIA | 10-09-2020 | 08-01-2021 | 2040
325 | MALDAH | Ranghaipur Piped Water Supply Scheme | SM/04831 |  |  | MVS | 1475/MD | M/S SHREE CONSORTIUM | 30-03-2023 | 29-04-2023 | 96
326 | MALDAH | Ranghat Piped Water Supply Scheme | SM/04846 |  |  | MVS | 1991/MD | M/S FOUR STAR CONSTRUCTION | 17-05-2023 | 01-06-2023 | 232
327 | MALDAH | Ranghat Piped Water Supply Scheme | SM/04846 |  |  | MVS | 2038/MD | PROJECT INDIA | 10-09-2020 | 08-01-2021 | 945
328 | MALDAH | Sahapur Piped Water Supply Scheme | SM/11968 |  | New | MVS | 2093/MD | S DUTTA | 02-06-2023 | 27-02-2024 | 502
329 | MALDAH | SAHAPUR Piped Water Supply Scheme | SM/12187 |  | New | SVS | 594/MD | M/S /FAIZUL HAQUE BISWAS | 09-02-2023 | 10-05-2023 | 349
330 | MALDAH | Sahazalalpur Water Supply Scheme | SM/01499 | SM/06986 | Retrofitting | SVS | 1129/MAAD | BEE GEE CONSTRUCTION | 11-11-2020 | 11-12-2020 | 531
331 | MALDAH | Sahazalalpur Water Supply Scheme | SM/01499 | SM/06986 | Retrofitting | SVS | 1866/MAAD | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28-09-2022 | 12-11-2022 | 61
332 | MALDAH | Sailpur and Adjoining Mouzas Water Supply Scheme | SM/02719 | SM/06871 | Retrofitting | MVS | 2446/MD | KRISHNENDU DUTTA | 12-10-2020 | 11-11-2020 | 662
333 | MALDAH | Sailpur and Adjoining Mouzas Water Supply Scheme | SM/02719 | SM/06871 | Retrofitting | MVS | 3370/MD | BENGAL ENGINEERING COMPANY | 29-08-2023 | 13-10-2023 | 227
334 | MALDAH | Sambalpur W/S Scheme | SM/02220 | SM/07973 | Retrofitting | MVS | 2437/MD | HANNAN BUILDERS PVT. LTD. | 12-10-2020 | 11-12-2020
335 | MALDAH | Sanjail PWSS in Old Malda Block in District Malda | SM/12337 |  | New | MVS | 455/MD | M/S SHREE CONSORTIUM | 19-01-2024 | 04-03-2024 | 444
336 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2455/MD | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 12-10-2020 | 11-11-2020 | 1
337 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2454/MD | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 12-10-2020 | 11-11-2020
338 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2452/MD | M/S BABLU ENTERPRISE | 12-10-2020 | 11-11-2020 | 1
339 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2453/MD | BENGAL ENGINEERING COMPANY | 12-10-2020 | 11-11-2020 | 1
340 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2299/MD | HIRAK ROY CHOUDHURY | 30-09-2020 | 01-10-2020
341 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2298/MD | BAKUL CHANDRA HALDAR | 30-09-2020 | 01-10-2020 | 3
342 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 2297/MD | M/S E. A. ENTERPRISE | 30-09-2020 | 01-10-2020
343 | MALDAH | Sankail & Adj. Mouzas Water Supply Scheme | SM/03201 | SM/07972 | Retrofitting | MVS | 3102/MD | M/S SINHA ENTERPRISE | 15-12-2020 | 14-01-2021 | 297
344 | MALDAH | Sultanpur Water Supply Scheme | SM/01502 | SM/07973 | Retrofitting | MVS | 2519/MD | PRADIP KUMAR DAS | 14-10-2020 | 28-11-2020 | 783
345 | MALDAH | SWARUPGANJ Piped Water Supply Scheme | SM/12185 |  | New | MVS | 952/MD | BANIK BROTHERS | 28-02-2023 | 25-11-2023 | 498
346 | MALDAH | Talbangrua and Adj. Mouzas Water Supply Scheme | SM/03071 | SM/06872 | Retrofitting | SVS | 2436/MD | M/S TRILOCHAN CONSTRUCTION CO | 12-10-2020 | 26-11-2020
347 | MALDAH | Talimnagar water sub-mission scheme | SM/02434 | SM/08760 | Retrofitting | MVS | 1724/MAAD | S & G CONSTRUCTION | 18-11-2021 | 18-12-2021
348 | MALDAH | Talimnagar water sub-mission scheme | SM/02434 |  |  | MVS | 1065/MAAD | DEY CONSTRUCTION | 14-10-2020 | 13-11-2020
349 | MALDAH | TALPUKUR Piped Water Supply Scheme | SM/12189 |  | New | MVS | 1899/MD | BANIK BROTHERS | 10-05-2023 | 09-05-2024 | 613
350 | MALDAH | Talsur and adj. mouzas water supply scheme | SM/03274 | SM/07973 | Retrofitting | MVS | 2255/MD | TARUN KUMAR BHATTACHARYA | 29-09-2020 | 28-12-2020 | 1084
351 | MALDAH | TILASAN WATER SUPPLY SCHEME | SM/00167 | SM/09567 | Augmentation | MVS | 2178//MD | UTTAM KUMAR GHOSH | 07-06-2023 | 07-07-2023 | 253
352 | MALDAH | TILASAN WATER SUPPLY SCHEME | SM/00167 | SM/09567 | Augmentation | MVS | 1641/MD | UTTAM KUMAR GHOSH | 19-07-2022 | 18-08-2022
353 | MALDAH | TILASAN WATER SUPPLY SCHEME | SM/00167 | SM/09567 | Augmentation | MVS | 996/MD | UTTAM KUMAR GHOSH | 22-04-2022 | 22-04-2023 | 1071
354 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 3573/MD | M/S JHA CONSTRUCTION | 20-12-2021 | 19-01-2022 | 833
355 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 3574/MD | GOBINDA ENTERPRISE | 20-12-2021 | 19-01-2022 | 500
356 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 1641/MD | UTTAM KUMAR GHOSH | 19-07-2022 | 18-08-2022 | 456
357 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 1642/MD | M/S AMIT KUMAR GUPTA | 19-07-2022 | 18-08-2022 | 49
358 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 1640/MD | KRISHNENDU DUTTA | 19-07-2022 | 18-08-2022 | 505
359 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 742/MD | FUTURE | 28-03-2022 | 27-04-2022 | 579
360 | MALDAH | UTTAR CHANDIPUR WATER SUPPLY SCHEME | SM/00867 | SM/07973 | Retrofitting | MVS | 3575/MD | PABITRA MANDAL | 20-12-2021 | 19-01-2022 | 407
361 | MALDAH | UTTAR HARISHCHANDRAPUR WATER SUPPLY SCHEME | SM/00066 | SM/10291 | Augmentation | MVS | 3615/MD | MAHAMAYA BURIMA ENTERPRISE | 21-09-2023 | 19-03-2024 | 1760
Total | [10 empty] | 189578