## Issued Work Order (PURULIA)
Issued Work Order (PURULIA)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | SM/18333 |  | New | MVS | 1418/PD | KOUSHIK CHATTERJEE | 29-09-2023 | 25-06-2024 | 12
2 | PURULIA | AJODHYA WATER SUPPLY SCHEME | SM/00307 | SM/09217 | Augmentation | SVS | 44/PD | TUMPA GORAIN | 07-01-2022 | 21-02-2022 | 508
3 | PURULIA | AJODHYA WATER SUPPLY SCHEME | SM/00307 | SM/09217 | Augmentation | SVS | 1712/PD | TUMPA GORAIN | 04-12-2023 | 02-02-2024
4 | PURULIA | AJODHYA WATER SUPPLY SCHEME | SM/00307 | SM/09217 | Augmentation | SVS | 1803/PD | ANUDIP SAHA | 08-12-2023 | 06-02-2024 | 72
5 | PURULIA | AJODHYA WATER SUPPLY SCHEME | SM/00307 | SM/09217 | Augmentation | SVS | 4856/PSD | MOUSUMI BANERJEE | 29-09-2023 | 09-10-2023 | 14
6 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/09580 | Augmentation | MVS | 154/PD | MS GORAIN CONCERN | 25-01-2022 | 11-03-2022 | 362
7 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/09580 | Augmentation | MVS | 1801/PD | CHAIL CONSTRUCTION | 08-12-2023 | 06-02-2024 | 120
8 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/09580 | Augmentation | MVS | 2126/PD | TUMPA GORAIN | 05-12-2024 | 03-02-2025
9 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/07563 | Retrofitting | MVS | 1441/PD | PREMNATH MITRA | 31-12-2020 | 01-10-2021 | 568
10 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/07563 | Retrofitting | MVS | 1407/PD | M/S KARUNAMOYEE CONSTRUCTION | 29-12-2020 | 12-02-2021 | 254
11 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/07563 | Retrofitting | MVS | 63/PD | KHITISH CHANDRA PATHAK | 15-01-2021 | 01-03-2021
12 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/07563 | Retrofitting | MVS | 180/PD | SADHAN GORAIN | 02-02-2021 | 19-03-2021 | 1019
13 | PURULIA | Arra & Adj. Mouzas New Piped Water Supply Scheme | SM/03037 | SM/09580 | Augmentation | MVS | 155/PD | SUBHAS CHANDRA MAHATO | 25-01-2022 | 11-03-2022 | 194
14 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 107/PD | M/S CHAKRABORTY CONSTRUCTION | 20-01-2023 | 19-02-2023 | 110
15 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/05904 |  | MVS | 107/PD | M/S CHAKRABORTY CONSTRUCTION | 20-01-2023 | 19-02-2023
16 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 108/PD | MOONLIGHT HOUSE | 20-01-2023 | 19-02-2023 | 264
17 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 1745/PD | TUMPA GORAIN | 22-11-2022 | 06-01-2023 | 624
18 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/05904 |  | MVS | 1745/PD | TUMPA GORAIN | 22-11-2022 | 06-01-2023 | 130
19 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 105/PD | MS GORAIN CONCERN | 20-01-2023 | 20-04-2023 | 517
20 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 106/PD | KANTILAL SAO | 20-01-2023 | 06-03-2023 | 349
21 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 1369/PD | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 25-07-2024 | 23-10-2024 | 30
22 | PURULIA | Arsha and Its Adjoning Mouzas New Piped Water Supply Scheme | SM/03094 | SM/10544 | Augmentation | MVS | 109/PD | PRATIK SAHA | 20-01-2023 | 19-02-2023 | 585
23 | PURULIA | BAGMUNDI WATER SUPPLY SCHEME | SM/00800 | SM/09215 | Augmentation | MVS | 208/PD | NIBHAS SINHA | 01-02-2022 | 18-03-2022 | 1144
24 | PURULIA | BAGMUNDI WATER SUPPLY SCHEME | SM/00800 | SM/09215 | Augmentation | MVS | 182/PD | KOUSHIK CHATTERJEE | 31-01-2022 | 17-03-2022 | 1159
25 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 367/PD | SADHAN GORAIN | 04-03-2022 | 18-04-2022 | 2899
26 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 877/PD | ANUP KUMAR SAHA | 23-05-2022 | 07-07-2022 | 495
27 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 651/PD | SOUMITRA CHAKRABORTY | 22-04-2022 | 06-06-2022 | 631
28 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 228/PD | ANUDIP SAHA | 09-02-2022 | 11-03-2022 | 114
29 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 233/PD | SOUMITRA CHAKRABORTY | 09-02-2022 | 26-03-2022 | 196
30 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 234/PD | MS GORAIN CONCERN | 09-02-2022 | 10-04-2022 | 264
31 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 231/PD | SIKHA ENTERPRISES | 09-02-2022 | 26-03-2022 | 115
32 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 891/PD | SIKHA ENTERPRISES | 07-05-2024 | 21-06-2024 | 149
33 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 232/PD | MANATOSH SINGH | 09-02-2022 | 26-03-2022
34 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 314/PD | SANTANU BANERJEE | 25-02-2022 | 11-04-2022 | 1263
35 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 229/PD | BOSE CONSTRUCTION | 09-02-2022 | 26-03-2022 | 382
36 | PURULIA | BALARAMPUR WATER SUPPLY SCHEME | SM/00793 | SM/10046 | Augmentation | SVS | 230/PD | TUMPA GORAIN | 09-02-2022 | 26-03-2022 | 260
37 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 28/RNP | SK ABBAS | 11-01-2021 | 26-01-2021 | 9
38 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 18/RNP | ASHOK KUMAR CHATTERJEE | 11-01-2021 | 26-01-2021 | 3
39 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/09214 | Augmentation | MVS | 37/PD | SANDIP KUMAR DUBEY | 07-01-2022 | 06-02-2022 | 12
40 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/09214 | Augmentation | MVS | 40/PD | M/S. S.P CONSTRUCTION | 07-01-2022 | 06-02-2022 | 57
41 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/09214 | Augmentation | MVS | 38/PD | KHITISH CHANDRA PATHAK | 07-01-2022 | 08-03-2022 | 102
42 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 |  |  | MVS | 529/RNP | RAHIBUDDIN MONDAL | 27-08-2021 | 26-09-2021 | 1
43 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 346/RNP | AMIT PATHAK | 01-06-2022 | 21-06-2022 | 16
44 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 22/RNP | SUDHANSHU OJHA | 11-01-2021 | 26-01-2021
45 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 30/RNP | KHITISH CHANDRA PATHAK | 11-01-2021 | 26-01-2021
46 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 31/RNP | SUBRATA SINGHADEO | 11-01-2021 | 26-01-2021
47 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 20/RNP | MS MITRA SENGUPTA ENTERPRISES | 11-01-2021 | 26-01-2021 | 122
48 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 19/RNP | SANDIP KUMAR DUBEY | 11-01-2021 | 26-01-2021 | 1
49 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 29/RNP | KABERI DUTTA | 11-01-2021 | 26-01-2021 | 1
50 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 34/RNP | PRATIK SAHA | 11-01-2021 | 26-01-2021 | 96
51 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 38/RNP | UTTAM KUMAR DUTTA | 11-01-2021 | 26-01-2021
52 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 33/RNP | CHAIL CONSTRUCTION | 11-01-2021 | 26-01-2021
53 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 21/RNP | DEB SHANKAR LAYEK | 11-01-2021 | 26-01-2021
54 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 32/RNP | SUBHAS CHANDRA MAHATO | 11-01-2021 | 26-01-2021
55 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 23/RNP | TUMPA GORAIN | 11-01-2021 | 26-01-2021
56 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 24/RNP | KANAILAL PAL | 11-01-2021 | 26-01-2021
57 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 25/RNP | SUBRATA SINGHADEO | 11-01-2021 | 26-01-2021
58 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 26/RNP | ROY CONSTRUCTION | 11-01-2021 | 26-01-2021
59 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 35/RNP | KAMAKHYA ENTERPRISE | 11-01-2021 | 26-01-2021
60 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 36/RNP | M/S SAYAK BHATTACHARYA | 11-01-2021 | 26-01-2021
61 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 37/RNP | SUPRIYA MAHANTI MISHRA | 11-01-2021 | 26-01-2021
62 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/07564 | Retrofitting | MVS | 17/RNP | MADHU SUDAN RAKSHIT | 11-01-2021 | 26-01-2021 | 88
63 | PURULIA | Baltora &adj Mouzas Piped Water Supply Scheme | SM/02974 | SM/09214 | Augmentation | MVS | 727/RNP | AMIT PATHAK | 06-12-2021 | 26-12-2021 | 17
64 | PURULIA | BARABAZAR WATER SUPPLY SCHEME | SM/00311 | SM/09209 | Augmentation | SVS | 312/PD | KOUSHIK CHATTERJEE | 25-02-2022 | 11-04-2022 | 1243
65 | PURULIA | BARABAZAR WATER SUPPLY SCHEME | SM/00311 | SM/09209 | Augmentation | SVS | 344/PD | SABYASACHI MISHRA | 04-03-2024 | 03-05-2024 | 204
66 | PURULIA | BARABAZAR WATER SUPPLY SCHEME | SM/00311 | SM/09209 | Augmentation | SVS | 379/PD | PRAVAT SARKAR | 11-03-2022 | 10-05-2022 | 492
67 | PURULIA | Bathanbari w/s scheme | SM/02544 | SM/07836 | Retrofitting | MVS | 155/PD | DEBAKI RANJAN SARKAR | 01-02-2021 | 18-03-2021 | 59
68 | PURULIA | Bathanbari w/s scheme | SM/02544 | SM/07836 | Retrofitting | MVS | 63/PD | KHITISH CHANDRA PATHAK | 15-01-2021 | 01-03-2021 | 146
69 | PURULIA | Bathanbari w/s scheme | SM/02544 | SM/09211 | Augmentation | MVS | 31/PD | KHITISH CHANDRA PATHAK | 07-01-2022 | 21-02-2022 | 99
70 | PURULIA | Bhamuria w/s scheme | SM/02428 | SM/07837 | Retrofitting | MVS | 160/PD | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 01-02-2021 | 18-03-2021
71 | PURULIA | Bhamuria w/s scheme | SM/02428 | SM/07837 | Retrofitting | MVS | 57/PD | ANUP KUMAR SAHA | 15-01-2021 | 01-03-2021 | 136
72 | PURULIA | Bhamuria w/s scheme | SM/02428 | SM/07837 | Retrofitting | MVS | 58/PD | ANUP KUMAR SAHA | 15-01-2021 | 01-03-2021 | 397
73 | PURULIA | Bhamuria w/s scheme | SM/02428 | SM/07837 | Retrofitting | MVS | 61/PD | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 15-01-2021 | 01-03-2021 | 822
74 | PURULIA | Bhamuria w/s scheme | SM/02428 | SM/07837 | Retrofitting | MVS | 59/PD | MANATOSH SINGH | 15-01-2021 | 01-03-2021 | 150
75 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 506/PD | SUDHANSHU OJHA | 31-03-2023 | 15-05-2023 | 37
76 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 648/PD | KABERI DUTTA | 22-04-2022 | 06-06-2022 | 138
77 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 647/PD | SUDHANSHU OJHA | 22-04-2022 | 06-06-2022 | 320
78 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 645/PD | SUPRIYA MAHANTI MISHRA | 22-04-2022 | 06-06-2022 | 254
79 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 644/PD | SIDDHARTHA SANKAR SARKAR | 22-04-2022 | 06-06-2022 | 287
80 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/06826 | Augmentation | SVS | 1390/PD | SOUVIK MANDAL | 01-09-2022 | 16-10-2022 | 10
81 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 1390/PD | SOUVIK MANDAL | 01-09-2022 | 16-10-2022 | 81
82 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 646/PD | INDRAJIT SARKAR | 22-04-2022 | 06-06-2022 | 228
83 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/06826 | Augmentation | SVS | 158/PD | SWAPAN MANDAL | 01-02-2021 | 18-03-2021
84 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 1391/PD | GOUTAM CHAKRABORTY | 01-09-2022 | 16-10-2022 | 117
85 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 915/PD | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 07-05-2024 | 21-06-2024 | 148
86 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 1929/PD | GOUTAM CHAKRABORTY | 22-12-2022 | 05-02-2023 | 149
87 | PURULIA | Bongabari Piped Water Supply Scheme | SM/00797 | SM/10395 | Augmentation | MVS | 1724/PD | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 22-11-2022 | 06-01-2023 | 665
88 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 332/PD | BOSE CONSTRUCTION | 28-02-2022 | 29-04-2022 | 193
89 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 333/PD | BOSE CONSTRUCTION | 28-02-2022 | 29-04-2022 | 797
90 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 334/PD | ROY CONSTRUCTION | 28-02-2022 | 30-03-2022 | 157
91 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 335/PD | ANUP KUMAR SAHA | 28-02-2022 | 29-05-2022 | 460
92 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 880/PD | DEBAKI RANJAN SARKAR | 23-05-2022 | 07-07-2022 | 353
93 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 150/PSD | CHATTERJEE CONSTRUCTION | 04-04-2022 | 29-04-2022 | 57
94 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 937/PD | SANTANU BANERJEE | 16-06-2022 | 31-07-2022 | 551
95 | PURULIA | Bundwan Piped Water Supply Scheme | SM/00567 | SM/10198 | Augmentation | MVS | 98/PSD | CHATTERJEE CONSTRUCTION | 14-03-2022 | 08-04-2022
96 | PURULIA | CHITMU WATER SUPPLY SCHEME | SM/00585 | SM/09216 | Augmentation | SVS | 284/PD | MS D.PALIT AND CO. | 17-02-2022 | 03-04-2022 | 972
97 | PURULIA | Dubra Water Supply Scheme | SM/01839 | SM/14460 | Augmentation | MVS | 102/PD | SUBRATA SINGHADEO | 20-01-2023 | 06-03-2023 | 297
98 | PURULIA | Dubra Water Supply Scheme | SM/01839 | SM/14460 | Augmentation | MVS | 99/PD | NANIGOPAL DEY | 20-01-2023 | 20-04-2023 | 376
99 | PURULIA | Dubra Water Supply Scheme | SM/01839 | SM/14460 | Augmentation | MVS | 101/PD | SOUMITRA CHAKRABORTY | 20-01-2023 | 19-02-2023 | 532
100 | PURULIA | Dubra Water Supply Scheme | SM/01839 | SM/14460 | Augmentation | MVS | 899/PD | SUBRATA SINGHADEO | 07-05-2024 | 06-07-2024 | 142
101 | PURULIA | Dubra Water Supply Scheme | SM/01839 | SM/14460 | Augmentation | MVS | 882/PD | SABYASACHI MISHRA | 03-07-2023 | 17-08-2023 | 338
102 | PURULIA | Dubra Water Supply Scheme | SM/01839 | SM/14460 | Augmentation | MVS | 103/PD | M/S SAYAK BHATTACHARYA | 20-01-2023 | 19-02-2023 | 103
103 | PURULIA | Hutmura Piped Water Supply Scheme | SM/00798 | SM/09037 | Augmentation | MVS | 96/PD | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18-01-2022 | 04-03-2022 | 405
104 | PURULIA | Hutmura Piped Water Supply Scheme | SM/00798 | SM/09037 | Augmentation | MVS | 97/PD | M/S KARUNAMOYEE CONSTRUCTION | 18-01-2022 | 19-03-2022 | 1500
105 | PURULIA | Hutmura Piped Water Supply Scheme | SM/00798 | SM/09037 | Augmentation | MVS | 422/PD | SHYAMAL KUMAR DEY | 17-03-2022 | 01-05-2022 | 261
106 | PURULIA | Hutmura Piped Water Supply Scheme | SM/00798 | SM/09037 | Augmentation | MVS | 98/PD | M/S KARUNAMOYEE CONSTRUCTION | 18-01-2022 | 29-03-2022 | 221
107 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 378/PD | AMAL KUMAR MUKHERJEE | 16-03-2023 | 30-04-2023
108 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 1754/PD | M/S KHAN ENTERPRISE | 22-11-2022 | 06-01-2023 | 131
109 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 936/PD | M/S. S. CHOUDHURY | 16-06-2022 | 31-07-2022 | 2559
110 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 841/PD | SUNNY ELECTRIC CO | 23-05-2022 | 07-07-2022 | 224
111 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 1039/A/PD | PREMNATH MITRA | 07-07-2022 | 05-09-2022 | 333
112 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 1040/PD | AMAL KUMAR MUKHERJEE | 06-07-2022 | 05-08-2022 | 29
113 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 871/PD | AJAY MONDAL | 23-05-2022 | 07-07-2022
114 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 842/PD | PRIYATOSH MUKHERJEE | 23-05-2022 | 07-07-2022 | 301
115 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 843/PD | MOONLIGHT HOUSE | 23-05-2022 | 07-07-2022 | 147
116 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 873/PD | M/S. S. CHOUDHURY | 23-05-2022 | 22-07-2022 | 80
117 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 491/PD | UMA CONSTRUCTION | 16-03-2024 | 15-05-2024 | 733
118 | PURULIA | JAIPUR WATER SUPPLY SCHEME | SM/00566 | SM/10722 | Augmentation | MVS | 1394/PD | AMAL KUMAR MUKHERJEE | 01-09-2022 | 16-10-2022
119 | PURULIA | JHALDA (RURAL PART) WATER SUPPLY SCHEME | SM/01201 | SM/09577 | Augmentation | MVS | 253/PD | BOSE CONSTRUCTION | 10-02-2022 | 11-04-2022 | 598
120 | PURULIA | JHALDA (RURAL PART) WATER SUPPLY SCHEME | SM/01201 | SM/09577 | Augmentation | MVS | 649/PD | BHAGABANDAS KUMAR | 22-04-2022 | 06-06-2022 | 206
121 | PURULIA | JHALDA (RURAL PART) WATER SUPPLY SCHEME | SM/01201 | SM/09577 | Augmentation | MVS | 827/PD | M/S S & P CONSTRUCTION | 17-05-2022 | 01-07-2022 | 1569
122 | PURULIA | JHALDA (RURAL PART) WATER SUPPLY SCHEME | SM/01201 | SM/09577 | Augmentation | MVS | 408/PD | ZAKIR HOSSIN MONDAL | 15-03-2022 | 14-05-2022 | 230
123 | PURULIA | JHALDA (RURAL PART) WATER SUPPLY SCHEME | SM/01201 | SM/09577 | Augmentation | MVS | 68/PD | BHAGABANDAS KUMAR | 17-01-2022 | 03-03-2022 | 259
124 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/09581 | Augmentation | MVS | 1518/PD | RAHIBUDDIN MONDAL | 13-12-2021 | 12-01-2022 | 176
125 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/09581 | Augmentation | MVS | 1528/PD | CHAIL CONSTRUCTION | 13-12-2021 | 12-01-2022 | 117
126 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/09581 | Augmentation | MVS | 1087/PD | SADHAN GORAIN | 07-06-2024 | 06-08-2024 | 24
127 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/09581 | Augmentation | MVS | 1354/PD | SUBRATA SINGHADEO | 25-07-2024 | 23-10-2024 | 55
128 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/09581 | Augmentation | MVS | 1519/PD | M/S ACHARJEE CONSTRUCTION | 13-12-2021 | 12-01-2022 | 248
129 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/07566 | Retrofitting | MVS | 164/PD | RABIN CHANDRA CHAIL | 01-02-2021 | 18-03-2021 | 311
130 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/07566 | Retrofitting | MVS | 163/PD | PRIYATOSH MUKHERJEE | 01-02-2021 | 18-03-2021 | 41
131 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/07566 | Retrofitting | MVS | 162/PD | BASANTA KUMAR SINGHADEO | 01-02-2021 | 18-03-2021 | 301
132 | PURULIA | Kalabani and Adj. Mouzas Water Supply Scheme | SM/03039 | SM/07566 | Retrofitting | MVS | 161/PD | KOUSHIK CHATTERJEE | 01-02-2021 | 18-03-2021 | 156
133 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 335/RNP | SUBHAS CHANDRA MAHATO | 01-06-2022 | 16-07-2022 | 107
134 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 1893/PD | BASANTA KUMAR SINGHADEO | 15-12-2022 | 13-02-2023 | 2925
135 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 1421/PD | M/S NANDY ENTERPRISE | 08-09-2022 | 23-10-2022 | 2659
136 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 1252/PD | PRINCE INDUSTRIES ( INDIA) | 30-08-2022 | 29-10-2022 | 623
137 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 336/RNP | AMIT PATHAK | 01-06-2022 | 16-07-2022 | 109
138 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 333/RNP | NANIGOPAL DEY | 01-06-2022 | 16-07-2022 | 98
139 | PURULIA | Kalyathol and Palaskhola Piped Water Supply Scheme | SM/01127 | SM/11453 | Augmentation | MVS | 334/RNP | NANIGOPAL DEY | 01-06-2022 | 16-07-2022 | 151
140 | PURULIA | KASHIPUR WATER SUPPLY SCHEME | SM/00584 | SM/10047 | Augmentation | SVS | 1893/PD | BASANTA KUMAR SINGHADEO | 15-12-2022 | 13-02-2023 | 59
141 | PURULIA | KASHIPUR WATER SUPPLY SCHEME | SM/00584 | SM/10047 | Augmentation | SVS | 881/PD | SANTANU BANERJEE | 23-05-2022 | 07-07-2022 | 3451
142 | PURULIA | KASHIPUR WATER SUPPLY SCHEME | SM/00584 | SM/10047 | Augmentation | SVS | 260/PD | MUNNA AGROTECH ENTERPRISE | 11-02-2022 | 12-04-2022 | 890
143 | PURULIA | KASHIPUR WATER SUPPLY SCHEME | SM/00584 | SM/10047 | Augmentation | SVS | 807/PD | PRINCE INDUSTRIES ( INDIA) | 06-05-2025 | 20-06-2025 | 233
144 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 874/PD | PRATIK SAHA | 23-05-2022 | 22-06-2022 | 153
145 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 567/PD | GOUTAM CHAKRABORTY | 07-04-2025 | 07-05-2025
146 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 875/PD | SUSANTA KR DUTTA | 23-05-2022 | 07-07-2022 | 320
147 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1079/PD | PRAVAT SARKAR | 12-07-2022 | 26-08-2022 | 251
148 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1058/PD | SOUMITRA CHAKRABORTY | 08-07-2022 | 06-09-2022 | 183
149 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1042/PD | S. R. ENTERPRISE | 07-07-2022 | 21-08-2022 | 170
150 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1043/A/PD | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 07-07-2022 | 05-09-2022 | 261
151 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1054/PD | M/S. MSS RISING ENTERPRISE | 08-07-2022 | 22-08-2022 | 302
152 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1053/PD | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 08-07-2022 | 22-08-2022 | 88
153 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1041/PD | ANUP KUMAR SAHA | 07-07-2022 | 05-09-2022 | 449
154 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1057/PD | ROY CONSTRUCTION | 08-07-2022 | 07-08-2022
155 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1044/PD | ANUP KUMAR SAHA | 07-07-2022 | 05-09-2022 | 109
156 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1039/PD | MANATOSH SINGH | 07-07-2022 | 21-08-2022 | 245
157 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 876/PD | GOUTAM CHAKRABORTY | 23-05-2022 | 07-07-2022 | 433
158 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1055/PD | SUBODH PRAMANIK | 08-07-2022 | 06-09-2022 | 252
159 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1059/PD | NANIGOPAL DEY | 31-08-2021 | 31-08-2022 | 315
160 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 1043/PD | PARTHA PRATIM CHHATAIT | 07-07-2022 | 05-09-2022 | 300
161 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 818/PD | SUSANTA KR DUTTA | 26-06-2023 | 10-08-2023 | 19
162 | PURULIA | Kotshila Piped Water Supply Scheme | SM/00306 | SM/10723 | Augmentation | MVS | 938/PD | SWAPAN MANDAL | 16-06-2022 | 31-07-2022 | 633
163 | PURULIA | Lachhyara and adjoining mouzas ground water based water supply scheme | SM/02861 | SM/09212 | Augmentation | MVS | 55/PD | ASHOK KUMAR CHATTERJEE | 13-01-2022 | 27-02-2022 | 785
164 | PURULIA | LAGDA WATER SUPPLY SCHEME | SM/00312 | SM/09036 | Augmentation | SVS | 1351/PD | GOUTAM CHAKRABORTY | 13-09-2023 | 13-10-2023
165 | PURULIA | LAGDA WATER SUPPLY SCHEME | SM/00312 | SM/09036 | Augmentation | SVS | 1817/PD | M/S CHAKRABORTY CONSTRUCTION | 06-12-2022 | 06-03-2023 | 69
166 | PURULIA | LAGDA WATER SUPPLY SCHEME | SM/00312 | SM/09036 | Augmentation | SVS | 183/PD | GOUTAM CHAKRABORTY | 31-01-2022 | 17-03-2022 | 761
167 | PURULIA | LAGDA WATER SUPPLY SCHEME | SM/00312 | SM/09036 | Augmentation | SVS | 217/PD | SADHAN GORAIN | 08-02-2022 | 25-03-2022 | 1227
168 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 67/RNP | KHITISH CHANDRA PATHAK | 27-01-2021 | 11-02-2021
169 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 789/PD | MADHU SUDAN RAKSHIT | 05-05-2022 | 19-06-2022 | 71
170 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 495/PD | CHANDAN CHATTERJEE | 31-03-2023 | 15-05-2023 | 11
171 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 117/RNP | SANTANU BANERJEE | 08-02-2021 | 23-02-2021 | 50
172 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 251/PD | M/S ACHARJEE CONSTRUCTION | 10-02-2021 | 27-03-2021 | 57
173 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 252/PD | KOUSHIK CHATTERJEE | 10-02-2021 | 27-03-2021 | 153
174 | PURULIA | Madandi Piped Water Supply Scheme | SM/05404 |  |  | MVS | 66/RNP | KHITISH CHANDRA PATHAK | 27-01-2021 | 11-02-2021
175 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 1049/PD | EQUIPMENTS AND SPARES AGENCIES | 08-07-2022 | 22-08-2022 | 953
176 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 836/PD | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 19-05-2022 | 03-07-2022 | 344
177 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 535/PD | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 12-04-2023 | 11-06-2023
178 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 835/PD | NANIGOPAL DEY | 19-05-2022 | 03-07-2022 | 335
179 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 1445/PD | MACHINO TECHNO | 14-09-2022 | 29-10-2022 | 138
180 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 1444/PD | MACHINO TECHNO | 14-09-2022 | 29-10-2022 | 499
181 | PURULIA | MANBAZAR WATER SUPPLY SCHEME | SM/00310 | SM/10719 | Augmentation | MVS | 869/PD | ZAKIR HOSSIN MONDAL | 23-05-2022 | 07-07-2022 | 545
182 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/07839 | Retrofitting | MVS | 158/PD | SWAPAN MANDAL | 01-02-2021 | 18-03-2021 | 206
183 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/07839 | Retrofitting | MVS | 158/PD | SWAPAN MANDAL | 01-02-2021 | 18-03-2021 | 682
184 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/07839 | Retrofitting | MVS | 156/PD | ALOK KUMAR CHAKRABORTY | 01-02-2021 | 18-03-2021 | 21
185 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/07839 | Retrofitting | MVS | 157/PD | GOUTAM CHAKRABORTY | 01-02-2021 | 18-03-2021 | 70
186 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/09943 | Augmentation | MVS | 161/PD | ALOK KUMAR CHAKRABORTY | 25-01-2022 | 11-03-2022 | 256
187 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/07839 | Retrofitting | MVS | 1359/PD | ALOK KUMAR CHAKRABORTY | 25-07-2024 | 23-09-2024
188 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/09943 | Augmentation | MVS | 907/PD | CHANCHAL MISHRA | 07-05-2024 | 06-07-2024
189 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/09943 | Augmentation | MVS | 162/PD | M/S CHAKRABORTY CONSTRUCTION | 25-01-2022 | 11-03-2022 | 191
190 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/09943 | Augmentation | MVS | 1554/PD | PREMNATH MITRA | 15-12-2021 | 13-02-2022 | 228
191 | PURULIA | Manguralalpur and Adj. Mouzas W/S Scheme | SM/02947 | SM/09943 | Augmentation | MVS | 1359/PD | ALOK KUMAR CHAKRABORTY | 25-07-2024 | 23-09-2024
192 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 487/PD | ANUDIP SAHA | 31-03-2023 | 15-05-2023 | 361
193 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 488/PD | M/S CHAKRABORTY CONSTRUCTION | 31-03-2023 | 15-05-2023 | 570
194 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 164/PSD | DEBANJAN SEAL | 18-04-2022 | 13-05-2022 | 278
195 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 421/PD | SB CONSTRUCTION | 21-03-2023 | 05-05-2023 | 452
196 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 422/PD | ASHOKE ADHIKARY | 21-03-2023 | 05-05-2023 | 176
197 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 641/PD | TUSHAR KANTI GORAI | 22-04-2022 | 06-06-2022 | 211
198 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 1764/PD | SUDHANSHU OJHA | 07-12-2023 | 05-02-2024 | 24
199 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 1534/PD | RAKSHIT ENTERPRISE | 16-10-2023 | 30-11-2023 | 29
200 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 1506/PD | CHATTERJEE CONSTRUCTION | 12-10-2023 | 26-11-2023 | 86
201 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 1486/PD | GOUTAM CHAKRABORTY | 12-10-2023 | 26-11-2023 | 280
202 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 1507/PD | SIKHA ENTERPRISES | 12-10-2023 | 26-11-2023 | 93
203 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 1485/PD | GOUTAM CHAKRABORTY | 12-10-2023 | 26-11-2023 | 89
204 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 639/PD | MEGA SOLAR ENERGY | 22-04-2022 | 06-06-2022 | 354
205 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 636/PD | KANAILAL PAL | 20-04-2022 | 04-06-2022 | 117
206 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 162/PSD | RAJ CONSTRUCTION | 18-04-2022 | 13-05-2022 | 127
207 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 161/PSD | SUMAN CHOUDHURY | 18-04-2022 | 13-05-2022 | 118
208 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 877/PD | ANUP KUMAR SAHA | 23-05-2022 | 07-07-2022
209 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 642/PD | DEBSHANKAR LAYEK | 22-04-2022 | 06-06-2022 | 289
210 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 634/PD | MS MITRA SENGUPTA ENTERPRISES | 22-04-2022 | 06-06-2022 | 247
211 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 163/PSD | ARINDAM GOSWAMI | 18-04-2022 | 13-05-2022 | 56
212 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 635/PD | M/S. S.P CONSTRUCTION | 22-04-2022 | 06-06-2022 | 162
213 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 637/PD | MOONLIGHT HOUSE | 22-04-2022 | 06-06-2022 | 148
214 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 638/PD | DEBASISH CHAKRABORTY | 22-04-2022 | 06-06-2022 | 222
215 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 640/PD | RAKSHIT ENTERPRISE | 22-04-2022 | 06-06-2022 | 277
216 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 160/PSD | PRADIPTA CHOUDHURY | 18-04-2022 | 13-05-2022 | 122
217 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 419/PD | KABERI DUTTA | 21-03-2023 | 05-05-2023 | 95
218 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 420/PD | R.K ENTERPRISE | 21-03-2023 | 05-05-2023 | 158
219 | PURULIA | Panradda Piped Water Supply Scheme | SM/05587 |  |  | MVS | 489/PD | M/S SAYAK BHATTACHARYA | 31-03-2023 | 15-05-2023 | 421
220 | PURULIA | PARA WATER SUPPLY SCHEME | SM/00309 | SM/10718 | Augmentation | MVS | 1253/PD | MIDNAPUR PIPE CONCERN | 30-08-2022 | 14-10-2022 | 767
221 | PURULIA | PARA WATER SUPPLY SCHEME | SM/00309 | SM/10718 | Augmentation | MVS | 882/PD | SABYASACHI MISHRA | 03-07-2023 | 17-08-2023
222 | PURULIA | PARA WATER SUPPLY SCHEME | SM/00309 | SM/10718 | Augmentation | MVS | 1081/PD | HAFIJUR RAHAMAN MIDYA | 10-08-2023 | 24-09-2023 | 382
223 | PURULIA | PARA WATER SUPPLY SCHEME | SM/00309 | SM/10718 | Augmentation | MVS | 1010/PD | NIBHAS SINHA | 29-06-2022 | 13-08-2022 | 4296
224 | PURULIA | Per Belia Water Supply Scheme | SM/01742 | SM/07841 | Retrofitting | MVS | 60/PD | TAPAN CHANDRA | 15-01-2021 | 01-03-2021 | 32
225 | PURULIA | Per Belia Water Supply Scheme | SM/01742 | SM/07841 | Retrofitting | MVS | 159/PD | ASHOK KUMAR CHATTERJEE | 01-02-2021 | 18-03-2021 | 161
226 | PURULIA | Piped Water Supply Scheme for Baram & Its Adjoining Mouzas | SM/03670 | SM/09213 | Augmentation | MVS | 1593/PD | SOUMITRA CHAKRABORTY | 17-12-2021 | 31-01-2022 | 278
227 | PURULIA | Piped Water Supply Scheme for Baram & Its Adjoining Mouzas | SM/03670 | SM/09213 | Augmentation | MVS | 1546/PD | SOUMITRA CHAKRABORTY | 15-12-2021 | 14-01-2022 | 1
228 | PURULIA | Piped Water Supply Scheme for Baram & Its Adjoining Mouzas | SM/03670 |  |  | MVS | 1240/PD | SOUMITRA CHAKRABORTY | 01-12-2020 | 15-01-2021
229 | PURULIA | Piped Water Supply Scheme for Baram & Its Adjoining Mouzas | SM/03670 |  |  | MVS | 1409/PD | KOUSHIK CHATTERJEE | 29-12-2020 | 12-02-2021 | 64
230 | PURULIA | Piped Water Supply Scheme for Beldi & its Adj. Mouzas | SM/03680 |  |  | MVS | 1410/PD | BOSE CONSTRUCTION | 29-12-2020 | 12-02-2021 | 126
231 | PURULIA | Piped Water Supply Scheme for Beldi & its Adj. Mouzas | SM/03680 |  |  | MVS | 1241/PD | SUSANTA KR DUTTA | 01-12-2020 | 15-01-2021 | 46
232 | PURULIA | Piped Water Supply Scheme for Kudagara and its Adj. Mouzas | SM/03557 |  |  | MVS | 1411/PD | GOUTAM CHAKRABORTY | 29-12-2020 | 12-02-2021 | 3
233 | PURULIA | Piped Water Supply Scheme for Kudagara and its Adj. Mouzas | SM/03557 | SM/06941 | Retrofitting | MVS | 1710/PD | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 04-12-2023 | 18-01-2024 | 35
234 | PURULIA | Piped Water Supply Scheme for Kudagara and its Adj. Mouzas | SM/03557 |  |  | MVS | 1710/PD | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 04-12-2023 | 18-01-2024 | 95
235 | PURULIA | Piped Water Supply Scheme for Kudagara and its Adj. Mouzas | SM/03557 |  |  | MVS | 1634/PD | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 30-08-2024 | 30-08-2025
236 | PURULIA | Piped Water Supply Scheme for Kudagara and its Adj. Mouzas | SM/03557 |  |  | MVS | 1242/PD | HIRAK KUMAR SAO | 01-12-2020 | 15-01-2021 | 7
237 | PURULIA | Piped Water Supply Scheme for Rangamatia & Adj. Mouzas | SM/03717 | SM/06939 | Retrofitting | MVS | 1408/PD | SANTANU BANERJEE | 29-12-2020 | 12-02-2021 | 188
238 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 64/PD | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 15-01-2021 | 01-03-2021 | 27
239 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 66/PD | SUBODH PRAMANIK | 15-01-2021 | 01-03-2021 | 442
240 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 68/PD | KANTILAL SAO | 15-01-2021 | 01-03-2021 | 134
241 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 23/PSD | SIDDHARTHA SANKAR SARKAR | 13-01-2021 | 27-02-2021
242 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 10/PSD | GYANRANJAN SEN | 13-01-2021 | 27-02-2021 | 5
243 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 67/PD | TUMPA GORAIN | 15-01-2021 | 01-03-2021
244 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 18/PSD | TUSHAR KANTI GORAI | 13-01-2021 | 27-02-2021 | 2
245 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 65/PD | BHAGABANDAS KUMAR | 15-01-2021 | 01-03-2021 | 140
246 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 12/PSD | ANUDIP SAHA | 13-01-2021 | 27-02-2021 | 5
247 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 14/PSD | INDRAJIT SARKAR | 13-01-2021 | 27-02-2021
248 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 11/PSD | SIDDHARTHA SANKAR SARKAR | 13-01-2021 | 27-02-2021
249 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 19/PSD | PRATIK SAHA | 13-01-2021 | 27-02-2021 | 7
250 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 21/PSD | M/S ACHARJEE CONSTRUCTION | 13-01-2021 | 27-02-2021 | 16
251 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 61/PD | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 15-01-2021 | 01-03-2021
252 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 17/PSD | RAKSHIT ENTERPRISE | 13-01-2021 | 27-02-2021 | 2
253 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 13/PSD | M/S. S.P CONSTRUCTION | 13-01-2021 | 27-02-2021 | 4
254 | PURULIA | Piped Water Supply Scheme for Satra & its Adj. Mouzas | SM/03658 |  |  | MVS | 20/PSD | S.K IRFAN | 13-01-2021 | 27-02-2021 | 6
255 | PURULIA | Piped Water Supply Scheme for Sutabai and its adjoining mouzas | SM/03775 | SM/07565 | Retrofitting | MVS | 242/PD | SANTANU BANERJEE | 10-02-2021 | 11-04-2021 | 849
256 | PURULIA | Piped Water Supply Scheme for Sutabai and its adjoining mouzas | SM/03775 | SM/09579 | Augmentation | MVS | 1403/PD | ASHOK KUMAR CHATTERJEE | 01-09-2022 | 16-10-2022 | 541
257 | PURULIA | Piped Water Supply Scheme for Sutabai and its adjoining mouzas | SM/03775 | SM/09579 | Augmentation | MVS | 209/PD | M/S S & P CONSTRUCTION | 01-02-2022 | 18-03-2022 | 201
258 | PURULIA | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 |  | New | MVS | 1416/PD | ANUP KUMAR SAHA | 29-12-2020 | 10-01-2021 | 815
259 | PURULIA | Puncha Piped Water Supply Scheme | SM/00589 | SM/10048 | Augmentation | SVS | 218/PD | JAYANTA KUMAR MONDAL | 08-02-2022 | 25-03-2022 | 2436
260 | PURULIA | Puncha Piped Water Supply Scheme | SM/00589 | SM/10048 | Augmentation | SVS | 1631/PD | SOUVIK MANDAL | 03-11-2022 | 18-12-2022 | 406
261 | PURULIA | Puncha Piped Water Supply Scheme | SM/00589 | SM/10048 | Augmentation | SVS | 935/PD | MS D.PALIT AND CO. | 16-06-2022 | 31-07-2022 | 636
262 | PURULIA | Puncha Piped Water Supply Scheme | SM/00589 | SM/10048 | Augmentation | SVS | 236/PS | SWAPAN MANDAL | 09-02-2022 | 10-04-2022 | 366
263 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | SM/18641 |  | New | MVS | 1421/PD | MS D.PALIT AND CO. | 29-09-2023 | 25-06-2024
264 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/18250 | Augmentation | MVS | 1020/PD | ANUP KUMAR SAHA | 01-08-2023 | 30-09-2023 | 1883
265 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14024 | Augmentation | MVS | 1087/PD | SADHAN GORAIN | 07-06-2024 | 06-08-2024 | 1
266 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14023 | Augmentation | MVS | 97/RNP | JOY GURU ENTERPRISE | 27-02-2025 | 06-03-2025
267 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14024 | Augmentation | MVS | 270/PD | MITHU BUILDERS | 24-02-2023 | 21-11-2023 | 739
268 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/18306 | Augmentation | MVS | 1041/PD | DEBAKI RANJAN SARKAR | 04-08-2023 | 03-10-2023
269 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/18250 | Augmentation | MVS | 1337/PD | MANIRUL ISLAM SK | 08-09-2023 | 04-06-2024 | 568
270 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14669 | Augmentation | MVS | 471/PD | ASHOK KUMAR CHATTERJEE | 28-03-2023 | 27-05-2023 | 1534
271 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14025 | Augmentation | MVS | 461/PD | SANTANU BANERJEE | 27-03-2023 | 26-05-2023 | 995
272 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14669 | Augmentation | MVS | 472/PD | ASHOK KUMAR CHATTERJEE | 28-03-2023 | 23-12-2023 | 360
273 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14670 | Augmentation | MVS | 433/PD | MS D.PALIT AND CO. | 22-03-2023 | 17-12-2023 | 1158
274 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14024 | Augmentation | MVS | 584/PD | M/S RAJ KUMAR KHAN | 20-04-2023 | 19-06-2023 | 1284
275 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/14670 | Augmentation | MVS | 302/PD | M/S KARUNAMOYEE CONSTRUCTION | 28-02-2023 | 29-04-2023 | 728
276 | PURULIA | RAGHUNATHPUR AREA (EAP) WATER SUPPLY SCHEME | SM/01056 | SM/18779 | Augmentation | MVS | 174/PD | RABIN CHANDRA CHAIL | 07-02-2023 | 24-03-2023 | 155
277 | PURULIA | RAM CHANDRAPUR WATER SUPPLY SCHEME | SM/00308 | SM/10045 | Augmentation | SVS | 621/PD | ASHOK KUMAR CHATTERJEE | 20-04-2022 | 04-06-2022 | 7
278 | PURULIA | RAM CHANDRAPUR WATER SUPPLY SCHEME | SM/00308 | SM/10045 | Augmentation | SVS | 288/PD | ANUP KUMAR SAHA | 18-02-2022 | 04-04-2022 | 3066
279 | PURULIA | RAM CHANDRAPUR WATER SUPPLY SCHEME | SM/00308 | SM/10045 | Augmentation | SVS | 147/PD | BASANTA KUMAR SINGHADEO | 24-01-2022 | 10-03-2022 | 1737
280 | PURULIA | RAM CHANDRAPUR WATER SUPPLY SCHEME | SM/00308 | SM/10045 | Augmentation | SVS | 1198/PD | NIBHAS SINHA | 12-08-2022 | 09-05-2023 | 1463
281 | PURULIA | RAM CHANDRAPUR WATER SUPPLY SCHEME | SM/00308 | SM/15039 | Augmentation | MVS | 621/PD | ASHOK KUMAR CHATTERJEE | 20-04-2022 | 04-06-2022 | 313
282 | PURULIA | Ramnagar Piped Water Supply Scheme | SM/05792 |  |  | MVS | 532/PSD | MS GORAIN CONCERN | 28-12-2020 | 12-01-2021 | 51
283 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 494/PD | AMIT PATHAK | 31-03-2023 | 15-05-2023 | 13
284 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 163/RNP | CHANDAN CHATTERJEE | 07-04-2022 | 02-05-2022 | 111
285 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 775/PD | SUBHAS CHANDRA MAHATO | 05-05-2022 | 19-06-2022 | 244
286 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 774/PD | MADHU SUDAN RAKSHIT | 05-05-2022 | 19-06-2022 | 583
287 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 773/PD | CHAIL CONSTRUCTION | 05-05-2022 | 19-06-2022 | 187
288 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 772/PD | PRATIK SAHA | 05-05-2022 | 19-06-2022 | 202
289 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 787/PD | SUBHENDU SEKHAR GORAI | 05-05-2022 | 04-06-2022 | 125
290 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 786/PD | LAKSHMI IRON | 05-05-2022 | 19-06-2022 | 457
291 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 788/PD | ASHOKE ADHIKARY | 05-05-2022 | 04-06-2022 | 150
292 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 785/PD | KHITISH CHANDRA PATHAK | 05-05-2022 | 19-06-2022 | 279
293 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 784/PD | ASHOK KUMAR CHATTERJEE | 05-05-2022 | 19-06-2022 | 487
294 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 164/RNP | SABYASACHI MISHRA | 07-04-2022 | 07-05-2022 | 110
295 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 783/PD | M/S ACHARJEE CONSTRUCTION | 05-05-2022 | 19-06-2022 | 219
296 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 781/PD | SANDIP KUMAR DUBEY | 05-05-2022 | 19-06-2022 | 174
297 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 780/PD | MANATOSH SINGH | 05-05-2022 | 19-06-2022 | 471
298 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 779/PD | UTTAM KUMAR DUTTA | 05-05-2022 | 19-06-2022 | 241
299 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 778/PD | SUBRATA SINGHADEO | 05-05-2022 | 19-06-2022 | 253
300 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 777/PD | S.K IRFAN | 05-05-2022 | 19-06-2022 | 344
301 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 776/PD | SK ABBAS | 05-05-2022 | 19-06-2022 | 346
302 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 166/RNP | AMIT PATHAK | 07-04-2022 | 07-05-2022 | 133
303 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 165/RNP | SK ABBAS | 07-04-2022 | 07-05-2022 | 62
304 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 330/PD | KHITISH CHANDRA PATHAK | 01-03-2024 | 15-04-2024 | 35
305 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 543/RNP | JOY GURU ENTERPRISE | 28-11-2024 | 05-12-2024
306 | PURULIA | Rayband Piped Water Supply Scheme | SM/05522 |  |  | MVS | 782/PD | M/S ACHARJEE CONSTRUCTION | 05-05-2022 | 19-06-2022 | 335
307 | PURULIA | SALTORA-HIJLI WATER SUPPLY SCHEME | SM/00313 | SM/10721 | Augmentation | SVS | 1009/PD | PARTHA PRATIM CHHATAIT | 29-06-2022 | 13-08-2022 | 204
308 | PURULIA | SALTORA-HIJLI WATER SUPPLY SCHEME | SM/00313 | SM/10721 | Augmentation | SVS | 2189/PD | M/S SAYAK BHATTACHARYA | 13-12-2024 | 11-02-2025
309 | PURULIA | SALTORA-HIJLI WATER SUPPLY SCHEME | SM/00313 |  |  | MVS | 2189/PD | M/S SAYAK BHATTACHARYA | 13-12-2024 | 11-02-2025
310 | PURULIA | SALTORA-HIJLI WATER SUPPLY SCHEME | SM/00313 | SM/10721 | Augmentation | SVS | 1082/PD | M/S SAYAK BHATTACHARYA | 10-08-2023 | 09-10-2023
311 | PURULIA | SALTORA-HIJLI WATER SUPPLY SCHEME | SM/00313 | SM/10721 | Augmentation | SVS | 1892/PD | PRAVAT SARKAR | 15-12-2022 | 13-02-2023 | 1145
312 | PURULIA | SALTORA-HIJLI WATER SUPPLY SCHEME | SM/00313 | SM/10721 | Augmentation | SVS | 1891/PD | BALAJI UDDYOG | 15-12-2022 | 13-02-2023 | 821
313 | PURULIA | Santuri Piped Water Supply Scheme | SM/00586 | SM/14459 | Augmentation | SVS | 96/PD | AMIT PATHAK | 20-01-2023 | 19-02-2023 | 54
314 | PURULIA | Santuri Piped Water Supply Scheme | SM/00586 | SM/14459 | Augmentation | SVS | 95/PD | CHANDAN CHATTERJEE | 20-01-2023 | 19-02-2023 | 67
315 | PURULIA | Santuri Piped Water Supply Scheme | SM/00586 | SM/14459 | Augmentation | SVS | 94/PD | MS MITRA SENGUPTA ENTERPRISES | 20-01-2023 | 19-02-2023 | 48
316 | PURULIA | Santuri Piped Water Supply Scheme | SM/00586 | SM/14459 | Augmentation | SVS | 93/PD | KHITISH CHANDRA PATHAK | 20-01-2023 | 20-04-2023 | 298
317 | PURULIA | Santuri Piped Water Supply Scheme | SM/00586 | SM/14459 | Augmentation | SVS | 97/PD | DEBANJAN SEAL | 20-01-2023 | 19-02-2023 | 44
318 | PURULIA | Santuri Piped Water Supply Scheme | SM/00586 | SM/14459 | Augmentation | SVS | 396/PD | M/S ACHARJEE CONSTRUCTION | 16-03-2023 | 30-04-2023 | 45
319 | PURULIA | Sarbari Piped Water Supply Scheme | SM/00590 | SM/10720 | Augmentation | MVS | 868/PD | KHITISH CHANDRA PATHAK | 23-05-2022 | 22-07-2022 | 721
320 | PURULIA | Sarbari Piped Water Supply Scheme | SM/00590 | SM/10720 | Augmentation | MVS | 984/PD | JAYANTA KUMAR MONDAL | 22-06-2022 | 06-08-2022 | 3270
321 | PURULIA | Sarbari Piped Water Supply Scheme | SM/00590 |  |  | MVS | 161/PD | KOUSHIK CHATTERJEE | 01-02-2021 | 18-03-2021 | 413
322 | PURULIA | SINDHRI CHASMORE WATER SUPPLY SCHEME | SM/00851 | SM/10347 | Augmentation | MVS | 655/PD | SB CONSTRUCTION | 17-05-2023 | 16-07-2023 | 463
323 | PURULIA | SINDHRI CHASMORE WATER SUPPLY SCHEME | SM/00851 | SM/10347 | Augmentation | MVS | 852/PD | SADHAN GORAIN | 23-05-2022 | 07-07-2022 | 1404
324 | PURULIA | Sirkabad Piped Water Supply Scheme | SM/00314 | SM/09578 | Augmentation | MVS | 103/PD | KANTILAL SAO | 18-01-2022 | 19-03-2022 | 727
325 | PURULIA | Sirkabad Piped Water Supply Scheme | SM/00314 | SM/09578 | Augmentation | MVS | 102/PD | HIRAK KUMAR SAO | 18-01-2022 | 19-03-2022 | 332
326 | PURULIA | Sirkabad Piped Water Supply Scheme | SM/00314 | SM/09578 | Augmentation | MVS | 100/PD | HIRAK KUMAR SAO | 18-01-2022 | 04-03-2022 | 614
327 | PURULIA | Sirkabad Piped Water Supply Scheme | SM/00314 | SM/09578 | Augmentation | MVS | 313/PD | DEBAKI RANJAN SARKAR | 25-02-2022 | 11-04-2022 | 1118
328 | PURULIA | Sirkabad Piped Water Supply Scheme | SM/00314 | SM/09578 | Augmentation | MVS | 99/PD | ALOK KUMAR CHAKRABORTY | 18-01-2022 | 29-03-2022 | 649
329 | PURULIA | Sirkabad Piped Water Supply Scheme | SM/00314 | SM/09578 | Augmentation | MVS | 101/PD | SK MANIR | 18-01-2022 | 17-02-2022 | 100
330 | PURULIA | Sonathol Water Supply Scheme | SM/01671 | SM/09210 | Augmentation | MVS | 209/PD | M/S S & P CONSTRUCTION | 01-02-2022 | 18-03-2022 | 92
331 | PURULIA | Sonathol Water Supply Scheme | SM/01671 | SM/07838 | Retrofitting | MVS | 213/PD | KHAN ENTERPRISE | 08-02-2021 | 25-03-2021 | 536
332 | PURULIA | Sonathol Water Supply Scheme | SM/01671 | SM/09210 | Augmentation | MVS | 789/PD | MADHU SUDAN RAKSHIT | 05-05-2022 | 19-06-2022
333 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 |  | New | MVS | 1514/PD | SEKH ABBAS | 16-10-2023 | 30-11-2023
334 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 |  | New | MVS | 1795/PD | SEKH ABBAS | 08-12-2023 | 22-01-2024
335 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | SM/18528 |  | New | MVS | 2126/PD | TUMPA GORAIN | 05-12-2024 | 03-02-2025
336 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 |  | New | MVS | 2189/PD | M/S SAYAK BHATTACHARYA | 13-12-2024 | 11-02-2025 | 594
337 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | SM/18731 |  | New | MVS | 2126/PD | TUMPA GORAIN | 05-12-2024 | 03-02-2025
338 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 |  | New | MVS | 2189/PD | M/S SAYAK BHATTACHARYA | 13-12-2024 | 11-02-2025
339 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 |  | New | MVS | 2126/PD | TUMPA GORAIN | 05-12-2024 | 03-02-2025
340 | PURULIA | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | SM/18654 |  | New | MVS | 1496/PD | S PATHAK AND CO | 12-10-2023 | 26-11-2023
341 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/15936 | Augmentation | MVS | 319/PD | PRIYATOSH MUKHERJEE | 01-03-2024 | 30-04-2024 | 38
342 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/05832 |  | MVS | 538/PD | RAKSHIT ENTERPRISE | 12-04-2023 | 27-05-2023 | 35
343 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/15936 | Augmentation | MVS | 503/PD | MS D.PALIT AND CO. | 31-03-2023 | 15-05-2023 | 90
344 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/15936 | Augmentation | MVS | 537/PD | MOONLIGHT HOUSE | 12-04-2023 | 27-05-2023 | 32
345 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/15936 | Augmentation | MVS | 1393/PD | ANUP KUMAR SAHA | 01-09-2022 | 16-10-2022
346 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/05832 |  | MVS | 243/PD | ANUP KUMAR SAHA | 10-02-2021 | 26-04-2021 | 4230
347 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/05832 |  | MVS | 244/PD | SADHAN GORAIN | 10-02-2021 | 11-04-2021 | 1654
348 | PURULIA | Surface Water Supply Scheme for Manbazar-II Block (Part) | SM/03753 | SM/15936 | Augmentation | MVS | 538/PD | RAKSHIT ENTERPRISE | 12-04-2023 | 27-05-2023
349 | PURULIA | West Bengal Piped Water Supply Project (Purulia) | SM/04368 |  |  | MVS | 708/W-112/JICA/PMU/2013 | S.DUTTA | 06-12-2018 | 20-01-2019 | 11
Total | [10 empty] | 122028