## Issued Work Order (ALIPURDUAR)
Issued Work Order (ALIPURDUAR)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | ALIPURDUAR | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 |  | New | MVS | 2981/ALD | SOUVIK ROY PALADHI | 02-02-2023 | 01-08-2023 | 1378
2 | ALIPURDUAR | BALLALGURI PIPED WATER SUPPLY SCHEME | SM/14221 |  | New | MVS | 2980/ALD | DILIP MAHATO | 02-02-2023 | 01-08-2023 | 172
3 | ALIPURDUAR | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 |  | New | SVS | 2250/ALD | SAMIRON PODDER | 21-11-2022 | 20-05-2023 | 493
4 | ALIPURDUAR | Bandpani Tea Garden Areas Piped Water Supply Scheme. | SM/11483 |  | New | SVS | 1687/ALD | MITHUN DAS | 20-09-2022 | 18-01-2023 | 99
5 | ALIPURDUAR | BARIGURI PIPED WATER SUPPLY SCHEME | SM/13246 |  | New | MVS | 333/ALD | MESSRS A.B.G CONSTRUCTION | 16-05-2023 | 12-11-2023 | 538
6 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07126 | Retrofitting | SVS | 859/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 14-10-2020 | 13-11-2020 | 2
7 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07125 | Retrofitting | SVS | 1249/ALD | TAPAN CHANDA | 28-12-2020 | 26-02-2021 | 1
8 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07126 | Retrofitting | SVS | 1161/ALD | TAPAN CHANDA | 15-12-2020 | 13-02-2021
9 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07185 | Retrofitting | MVS | 911/ALD | TAPAN CHANDA | 16-10-2020 | 15-11-2020
10 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07123 | Retrofitting | MVS | 1162/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 15-12-2020 | 13-02-2021 | 493
11 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07123 | Retrofitting | MVS | 860/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 14-10-2020 | 13-11-2020 | 126
12 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07126 | Retrofitting | SVS | 2764/ALD | TAPAN CHANDA | 25-02-2022 | 26-04-2022 | 1001
13 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07123 | Retrofitting | MVS | 1575/ALD | TAPAN CHANDA | 22-11-2021 | 20-02-2022 | 585
14 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07123 | Retrofitting | MVS | 1320/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 05-10-2021 | 04-12-2021 | 997
15 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07122 | Retrofitting | MVS | 2763/ALD | TAPAN CHANDA | 25-02-2022 | 26-04-2022 | 1016
16 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07127 | Retrofitting | MVS | 1319/ALD | M/S SURAJIT DEY & CO | 05-10-2021 | 04-12-2021 | 522
17 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07185 | Retrofitting | MVS | 858/ALD | TAPAN CHANDA | 14-10-2020 | 13-11-2020 | 6
18 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07126 | Retrofitting | SVS | 912/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 16-10-2020 | 15-11-2020
19 | ALIPURDUAR | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | SM/07185 | Retrofitting | MVS | 1160/ALD | M/S SURAJIT DEY & CO | 15-12-2020 | 13-02-2021 | 742
20 | ALIPURDUAR | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 |  | New | SVS | 2184/ALD | D. K. & SONS | 06-10-2023 | 05-12-2023 | 497
21 | ALIPURDUAR | BEECH TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14214 |  | New | SVS | 3398/ALD | MAHENDRA CHHETRI | 16-03-2023 | 12-09-2023 | 1094
22 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 |  |  | MVS | 887/ALD | SREE MAA CONSTRUCTION | 03-09-2021 | 03-10-2021 | 140
23 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2614/ALD | HARIDAS GHOSH | 21-12-2022 | 04-02-2023 | 374
24 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2615/ALD | GOUTAM KUMAR DAS | 21-12-2022 | 04-02-2023 | 472
25 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2616/ALD | TAPASH KUMAR BHOWMICK | 21-12-2022 | 04-02-2023
26 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2627/ALD/ | SHIBA ENTERPRISE | 21-12-2022 | 19-02-2023 | 184
27 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2619/ALD | SREE MAA CONSTRUCTION | 21-12-2022 | 20-01-2023 | 139
28 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2631/ALD | DEBAJYOTI SUTRADHAR | 21-12-2022 | 19-02-2023 | 303
29 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2634/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 21-12-2022 | 19-02-2023 | 199
30 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2635/ALD | TAPASH DAS | 21-12-2022 | 19-02-2023 | 555
31 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2628/ALD/ | TAPASH KUMAR BHOWMICK | 21-12-2022 | 19-02-2023
32 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2630/ALD | HARIDAS GHOSH | 21-12-2022 | 19-02-2023 | 215
33 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2632/ALD | KAMALESH ROY | 21-12-2022 | 19-02-2023 | 400
34 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2633/ALD | DAS CONSTRUCTION | 21-12-2022 | 19-02-2023 | 497
35 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2621/ALD | DEBAJYOTI SUTRADHAR | 21-12-2022 | 19-02-2023
36 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 03/ALD | HARIDAS GHOSH | 04-04-2023 | 03-07-2023
37 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 |  |  | MVS | 888/ALD | SREE MAA CONSTRUCTION | 03-09-2021 | 03-10-2021 | 140
38 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2620/ALD | DEBAJYOTI SUTRADHAR | 21-12-2022 | 20-01-2023 | 140
39 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2629/ALD/ | MATRI ENTERPRISE | 21-12-2022 | 19-02-2023 | 393
40 | ALIPURDUAR | BHATIBARI WATER SUPPLY SCHEME | SM/00145 | SM/14096 | Augmentation | MVS | 2613/ALD | TAPASH KUMAR BHOWMICK | 21-12-2022 | 04-02-2023 | 833
41 | ALIPURDUAR | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 |  | New | SVS | 3193/ALD | S.G. CONSTRUCTION | 27-02-2023 | 26-08-2023 | 191
42 | ALIPURDUAR | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 |  | New | SVS | 1883/ALD | PRANAB GHOSH | 07-09-2023 | 07-10-2023 | 189
43 | ALIPURDUAR | BHATPARA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14212 |  | New | SVS | 2969/ALD | MAHENDRA CHHETRI | 31-01-2023 | 30-07-2023 | 1150
44 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 |  |  | MVS | 1767/ALD | HARIDAS GHOSH | 19-02-2021 | 20-04-2021
45 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 2141/ALD | HARIDAS GHOSH | 06-01-2022 | 05-02-2022 | 145
46 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 1840/ALD | HARI CONSTRUCTION | 10-12-2021 | 09-01-2022 | 106
47 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 1841/ALD | HARI CONSTRUCTION | 10-12-2021 | 09-01-2022 | 21
48 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 2382/ALD | HARIDAS GHOSH | 31-01-2022 | 01-05-2022 | 997
49 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 2140/ALD | HARIDAS GHOSH | 06-01-2022 | 05-02-2022 | 145
50 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 1842/ALD | HARIDAS GHOSH | 10-12-2021 | 09-01-2022 | 1
51 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 |  |  | MVS | 1313/ALD | HARI CONSTRUCTION | 05-10-2021 | 04-12-2021 | 756
52 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 |  |  | MVS | 723/ALD | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 22-09-2020 | 22-10-2020 | 1
53 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 | SM/09883 | Augmentation | SVS | 991/ALD | MANORAMA ENTERPRISE | 13-09-2021 | 13-10-2021 | 125
54 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 |  |  | MVS | 1585/ALD | HARIDAS GHOSH | 10-02-2021 | 11-04-2021
55 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 |  |  | MVS | 1462/ALD | HARI CONSTRUCTION | 25-01-2021 | 24-02-2021
56 | ALIPURDUAR | BHOLARDABARI WATER SUPPLY SCHEME | SM/00150 |  |  | MVS | 1586/ALD | HARIDAS GHOSH | 10-02-2021 | 11-04-2021
57 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 |  |  | MVS | 865/ALD | GOUTAM KUMAR DAS | 14-10-2020 | 13-11-2020 | 125
58 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | SM/09885 | Augmentation | MVS | 1605/ALD | GOUTAM KUMAR DAS | 22-11-2021 | 22-12-2021 | 134
59 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 |  |  | MVS | 1167/ALD | GOUTAM KUMAR DAS | 15-12-2020 | 13-02-2021 | 502
60 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 |  |  | MVS | 905/ALD | GOUTAM KUMAR DAS | 16-10-2020 | 15-11-2020 | 125
61 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | SM/09885 | Augmentation | MVS | 2381/ALD | DILIP MAHATO | 31-01-2022 | 01-04-2022 | 574
62 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | SM/09885 | Augmentation | MVS | 2379/ALD | DILIP MAHATO | 31-01-2022 | 01-05-2022 | 1070
63 | ALIPURDUAR | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | SM/09885 | Augmentation | MVS | 1606/ALD | GOUTAM KUMAR DAS | 22-11-2021 | 22-12-2021 | 145
64 | ALIPURDUAR | Bhutri Forest Piped Water Supply Scheme | SM/18156 |  | New | SVS | 94/ALD | FAUDA SINGH CHHETRI | 18-04-2023 | 16-08-2023 | 35
65 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 | SM/14233 | Augmentation | SVS | 1570/ALD | SOUVIK ROY PALADHI | 22-11-2021 | 21-01-2022 | 270
66 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 |  |  | MVS | 1453/ALD | PRAMESH LAMA | 25-01-2021 | 11-03-2021 | 134
67 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 |  |  | MVS | 1766/ALD | BILTU DAS | 19-02-2021 | 20-04-2021 | 1000
68 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 |  |  | MVS | 1452/ALD | GOUTAM KUMAR DAS | 25-01-2021 | 11-03-2021 | 195
69 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 |  |  | MVS | 1571/ALD | PRAMESH LAMA | 22-11-2021 | 21-01-2022 | 588
70 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 | SM/14233 | Augmentation | SVS | 2873/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 17-01-2023 | 03-03-2023 | 95
71 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 | SM/14233 | Augmentation | SVS | 2870/ALD | ANUP KUNDU CONSTRUCTION CO. | 17-01-2023 | 18-03-2023 | 890
72 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 | SM/14233 | Augmentation | SVS | 2872/ALD | DILIP MAHATO | 17-01-2023 | 18-03-2023 | 391
73 | ALIPURDUAR | BIRPARA WATR SUPPLY SCHEME | SM/00035 | SM/14233 | Augmentation | SVS | 2869/ALD | AMBITIOUS ENTERPRISE | 17-01-2023 | 18-03-2023 | 108
74 | ALIPURDUAR | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 |  | New | MVS | 2855/ALD | TAPASH KUMAR BHOWMICK | 17-01-2023 | 16-07-2023 | 1646
75 | ALIPURDUAR | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 |  | New | MVS | 1563/ALD | TAPASH KUMAR BHOWMICK | 23-08-2023 | 07-10-2023 | 147
76 | ALIPURDUAR | CHALNIPAK PIPED WATER SUPPLY SCHEME. | SM/15534 |  | New | MVS | 3156/ALD | SOUVIK ROY PALADHI | 22-02-2023 | 21-08-2023 | 783
77 | ALIPURDUAR | Chengmari Piped Water Supply Scheme | SM/18152 |  | New | MVS | 423/ALD | HARIDAS GHOSH | 24-05-2023 | 20-11-2023 | 675
78 | ALIPURDUAR | Chengmari Piped Water Supply Scheme | SM/18152 |  | New | MVS | 233/ALD | HARIDAS GHOSH | 04-05-2023 | 02-08-2023 | 361
79 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07059 | Retrofitting | MVS | 1169/ALD | SASANKA ROY | 15-12-2020 | 13-02-2021 | 151
80 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07176 | Retrofitting | SVS | 2311/ALD | AASHIRBAD ENTERPRISE | 25-01-2022 | 11-03-2022 | 44
81 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07176 | Retrofitting | SVS | 2303/ALD | AASHIRBAD ENTERPRISE | 25-01-2022 | 24-02-2022 | 130
82 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07176 | Retrofitting | SVS | 2754/ALD | KAJAL KUMAR DE | 24-02-2022 | 25-04-2022 | 998
83 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07176 | Retrofitting | SVS | 1378/ALD | M/S PALIT ENTERPRISE | 19-01-2021 | 05-03-2021 | 366
84 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07059 | Retrofitting | MVS | 870/ALD | SASANKA ROY | 14-10-2020 | 13-11-2020
85 | ALIPURDUAR | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | SM/07059 | Retrofitting | MVS | 907/ALD | SASANKA ROY | 16-10-2020 | 15-11-2020
86 | ALIPURDUAR | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 |  | New | SVS | 12/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 01-04-2022 | 30-07-2022 | 646
87 | ALIPURDUAR | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 |  | New | SVS | 672/ALD | ASHOK SAPKOTA | 06-03-2024 | 04-06-2024 | 150
88 | ALIPURDUAR | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 |  | New | SVS | 3393/ALD | DAS CONSTRUCTION | 16-03-2023 | 12-09-2023
89 | ALIPURDUAR | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13302 |  | New | SVS | 2921/ALD | BHAGWATI BHUJEL | 19-01-2023 | 19-05-2023
90 | ALIPURDUAR | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 |  | New | MVS | 2854/ALD | HARIDAS GHOSH | 17-01-2023 | 16-07-2023 | 994
91 | ALIPURDUAR | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 |  | New | MVS | 16/ALD | HARIDAS GHOSH | 01-04-2022 | 30-07-2022 | 897
92 | ALIPURDUAR | DAKSHIN PAITKAPARA PIPED WATER SUPPLY SCHEME | SM/10174 |  | New | MVS | 21/ALD | SOUVIK ROY PALADHI | 01-04-2022 | 30-07-2022 | 863
93 | ALIPURDUAR | DAKSHIN RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14217 |  | New | SVS | 3396/ALD | S.G. CONSTRUCTION | 16-03-2023 | 12-09-2023
94 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 876/ALD | M/S AMIT KUMAR GUPTA | 03-09-2021 | 02-11-2021 | 272
95 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 2236/ALD | M/S SIBU DEY AND CO | 14-01-2022 | 15-03-2022 | 291
96 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 977/ALD | M/S JHA CONSTRUCTION | 13-09-2021 | 12-11-2021 | 280
97 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 976/ALD | MADHAB SAHA | 13-09-2021 | 12-11-2021 | 63
98 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 2295/ALD | NARENDRA BHADANI. | 24-01-2022 | 25-03-2022 | 226
99 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 2664/ALD/ | M/S AMIT KUMAR GUPTA | 22-12-2022 | 22-03-2023 | 148
100 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 1493/ALD | MADHAB SAHA | 05-09-2022 | 20-10-2022 | 238
101 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 2294/ALD | SASANKA ROY | 24-01-2022 | 25-03-2022 | 273
102 | ALIPURDUAR | DAKSHIN SONARPUR WATER SUPPLY SCHEME | SM/00144 | SM/11970 | Augmentation | MVS | 877/ALD | M/S STAR INDIA CONSTRUCTION | 03-09-2021 | 02-11-2021 | 53
103 | ALIPURDUAR | DALGAON TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16823 |  | New | SVS | 3634/ALD | M/S MRITYUNJAY PAUL AND SONS | 31-03-2023 | 27-09-2023 | 405
104 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/07137 | Retrofitting | MVS | 1134/ALD | PARAMJYOTI ENTERPRISE | 10-12-2020 | 09-01-2021 | 125
105 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/18254 | Augmentation | MVS | 1995/ALD | SREE MAA CONSTRUCTION | 15-09-2023 | 14-11-2023 | 656
106 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/07137 | Retrofitting | MVS | 1178/ALD | M/S PALIT ENTERPRISE | 15-12-2020 | 13-02-2021 | 281
107 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/07137 | Retrofitting | MVS | 866/ALD | SANJIT SAHA | 14-10-2020 | 13-11-2020 | 125
108 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/07137 | Retrofitting | MVS | 1179/ALD | NARAYAN CHANDRA SAHA | 15-12-2020 | 13-02-2021
109 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/18254 | Augmentation | MVS | 970/ALD | MITHUN DAS | 12-07-2023 | 10-09-2023 | 661
110 | ALIPURDUAR | DALIMPUR WATER SUPPLY SCHEME | SM/00016 | SM/18254 | Augmentation | MVS | 966/ALD | TAPASH DAS | 12-07-2023 | 26-08-2023 | 120
111 | ALIPURDUAR | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | SM/07133 | Retrofitting | SVS | 630/ALD | M/S SURAJIT DEY & CO | 03-09-2020 | 02-12-2020 | 416
112 | ALIPURDUAR | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | SM/07133 | Retrofitting | SVS | 631/ALD | M/S SURAJIT DEY & CO | 03-09-2020 | 02-12-2020 | 804
113 | ALIPURDUAR | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | SM/11960 | Augmentation | MVS | 2661/ALD | SUDDHYA SING LAMA | 22-12-2022 | 20-06-2023 | 786
114 | ALIPURDUAR | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | SM/07132 | Retrofitting | SVS | 743/ALD | M/S SURAJIT DEY & CO | 23-09-2020 | 22-12-2020
115 | ALIPURDUAR | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | SM/07131 | Retrofitting | SVS | 634/ALD | DILIP MAHATO | 03-09-2020 | 02-12-2020 | 200
116 | ALIPURDUAR | DHANIRAMPUR PIPED WATER SUPPLY SCHEME | SM/15208 |  | New | MVS | 3636/ALD | DILIP MAHATO | 31-03-2023 | 27-09-2023 | 711
117 | ALIPURDUAR | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | SM/07191 | Retrofitting | SVS | 429/ALD | NARENDRA BHADANI. | 06-08-2020 | 04-11-2020
118 | ALIPURDUAR | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | SM/07191 | Retrofitting | SVS | 1954/ALD | CHANDAN KIRTONIA | 02-07-2024 | 30-09-2024 | 144
119 | ALIPURDUAR | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | SM/07191 | Retrofitting | SVS | 428/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 06-08-2020 | 04-11-2020
120 | ALIPURDUAR | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | SM/07130 | Retrofitting | SVS | 691/ALD | M/S SURAJIT DEY & CO | 16-09-2020 | 14-01-2021 | 205
121 | ALIPURDUAR | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | SM/07130 | Retrofitting | SVS | 693/ALD | M/S SURAJIT DEY & CO | 16-09-2020 | 14-01-2021 | 144
122 | ALIPURDUAR | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | SM/07130 | Retrofitting | SVS | 691/ALD | M/S SURAJIT DEY & CO | 16-09-2020 | 14-01-2021 | 121
123 | ALIPURDUAR | Dhumchipara Tea Garden Piped Water Supply Scheme | SM/04788 | SM/07130 | Retrofitting | SVS | 691/ALD | M/S SURAJIT DEY & CO | 16-09-2020 | 14-01-2021 | 107
124 | ALIPURDUAR | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | SM/07194 | Retrofitting | SVS | 434/ALD | MITHUN DAS | 06-08-2020 | 04-11-2020
125 | ALIPURDUAR | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | SM/07194 | Retrofitting | SVS | 433/ALD | MADHAB SAHA | 06-08-2020 | 04-11-2020
126 | ALIPURDUAR | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | SM/07194 | Retrofitting | SVS | 433/ALD | MADHAB SAHA | 06-08-2020 | 04-11-2020
127 | ALIPURDUAR | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | SM/07194 | Retrofitting | SVS | 434/ALD | MITHUN DAS | 06-08-2020 | 04-11-2020
128 | ALIPURDUAR | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | SM/07068 | Retrofitting | SVS | 1025/ALD | DILIP MAHATO | 18-11-2020 | 17-01-2021 | 939
129 | ALIPURDUAR | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | SM/07069 | Retrofitting | SVS | 1026/ALD | ASHIT KUMAR SINGHA | 18-11-2020 | 17-01-2021 | 515
130 | ALIPURDUAR | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | SM/07068 | Retrofitting | SVS | 2088/ALD | M/S SSB CONSTRUCTION CO. | 30-03-2020 | 28-06-2020 | 778
131 | ALIPURDUAR | Dimdima Tea Garden Area Piped Water Supply Scheme. | SM/06549 | SM/07069 | Retrofitting | SVS | 2092/ALD | GHOSH & SAHA CONSTRUCTION | 30-03-2020 | 28-06-2020 | 491
132 | ALIPURDUAR | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 |  | New | MVS | 2861/ALD | DILIP MAHATO | 17-01-2023 | 16-07-2023 | 1023
133 | ALIPURDUAR | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 |  | New | MVS | 2660/ALD | M/S DUTTA AND CO | 22-12-2022 | 21-04-2023 | 199
134 | ALIPURDUAR | ETHELBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13449 |  | New | MVS | 1878/ALD | NARENDRA BHADANI. | 07-09-2023 | 07-10-2023
135 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1248/ALD | BILTU DAS | 28-12-2020 | 26-02-2021 | 734
136 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1761/ALD | HARIDAS GHOSH | 19-02-2021 | 20-04-2021 | 882
137 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1254/ALD | HARIDAS GHOSH | 28-12-2020 | 26-02-2021 | 1102
138 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1805/ALD | DILIP MAHATO | 22-02-2021 | 23-04-2021 | 866
139 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1246/ALD | TAPASH KUMAR BHOWMICK | 28-12-2020 | 26-02-2021 | 795
140 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1758/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 19-02-2021 | 20-04-2021 | 1001
141 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1256/ALD | BILTU DAS | 28-12-2020 | 26-02-2021 | 1096
142 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1314/ALD | SOUVIK ROY PALADHI | 05-10-2021 | 04-12-2021 | 263
143 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1760/ALD | ASHIT KUMAR SINGHA | 19-02-2021 | 20-04-2021 | 973
144 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 979/ALD | MESSRS R N TRADERS | 13-09-2021 | 12-11-2021 | 498
145 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1257/ALD | BILTU DAS | 28-12-2020 | 26-02-2021 | 636
146 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1759/ALD | BILTU DAS | 19-02-2021 | 20-04-2021 | 134
147 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 1252/ALD | SOUVIK ROY PALADHI | 28-12-2020 | 26-02-2021 | 956
148 | ALIPURDUAR | FALAKATA WATER SUPPLY SCHEME | SM/00138 | SM/08080 | Retrofitting | MVS | 579/ALD | NARENDRA BHADANI. | 15-07-2021 | 29-08-2021 | 497
149 | ALIPURDUAR | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 |  | New | SVS | 3572/ALD | MADHAB SAHA | 27-03-2023 | 23-09-2023 | 273
150 | ALIPURDUAR | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 |  | New | SVS | 1888/ALD | MADHAB SAHA | 07-09-2023 | 07-10-2023 | 198
151 | ALIPURDUAR | GANGUTIA TEA GARDEN AREA PIPED WATER SUPPLY SHEME | SM/10180 |  | New | SVS | 13/ALD | SHREE RANISATI ENTERPRISE | 01-04-2022 | 30-07-2022 | 848
152 | ALIPURDUAR | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | SM/07197 | Retrofitting | SVS | 689/ALD | M/S SURAJIT DEY & CO | 16-09-2020 | 14-01-2021 | 200
153 | ALIPURDUAR | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | SM/07197 | Retrofitting | SVS | 689/ALD | M/S SURAJIT DEY & CO | 16-09-2020 | 14-01-2021 | 146
154 | ALIPURDUAR | GAROCHIRA BANDAPANI PIPED WATER SUPPLY SCHEME | SM/14216 |  | New | SVS | 2922/ALD | RATAN DUTTA | 19-01-2023 | 19-05-2023 | 109
155 | ALIPURDUAR | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 |  | New | MVS | 27/ALD | M/S DUTTA AND CO | 01-04-2022 | 30-07-2022 | 591
156 | ALIPURDUAR | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 |  | New | MVS | 26/ALD | ASHIT KUMAR SINGHA | 01-04-2022 | 30-07-2022 | 460
157 | ALIPURDUAR | GOPALPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10178 |  | New | MVS | 1875/ALD | NARENDRA BHADANI. | 07-09-2023 | 07-10-2023 | 184
158 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | SM/07184 | Retrofitting | SVS | 726/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 22-09-2020 | 22-10-2020
159 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | SM/07184 | Retrofitting | SVS | 1316/ALD | HARI CONSTRUCTION | 05-10-2021 | 19-11-2021 | 251
160 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | SM/07184 | Retrofitting | SVS | 1159/ALD | TAPASH KUMAR BHOWMICK | 15-12-2020 | 13-02-2021 | 429
161 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 |  |  | MVS | 1450/ALD | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 25-01-2021 | 11-03-2021 | 118
162 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 |  |  | MVS | 864/ALD | MATARA CONSTRUCTION CO | 14-10-2020 | 13-11-2020
163 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | SM/07182 | Retrofitting | MVS | 1851/ALD | GOUTAM KUMAR DAS | 13-12-2021 | 12-01-2022 | 146
164 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 |  |  | MVS | 1448/ALD | MATARA CONSTRUCTION CO | 25-01-2021 | 11-03-2021 | 112
165 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | SM/07182 | Retrofitting | MVS | 864/ALD | MATARA CONSTRUCTION CO | 14-10-2020 | 13-11-2020 | 3
166 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | SM/07182 | Retrofitting | MVS | 914/ALD | MATARA CONSTRUCTION CO | 16-10-2020 | 15-11-2020 | 1
167 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 |  |  | MVS | 914/ALD | MATARA CONSTRUCTION CO | 16-10-2020 | 15-11-2020
168 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | SM/07182 | Retrofitting | MVS | 2296/ALD | GOUTAM KUMAR DAS | 24-01-2022 | 25-03-2022 | 707
169 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | SM/07179 | Retrofitting | SVS | 1846/ALD | AASHIRBAD ENTERPRISE | 10-12-2021 | 09-01-2022 | 65
170 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | SM/07179 | Retrofitting | SVS | 1845/ALD | RATAN DUTTA | 10-12-2021 | 09-01-2022 | 141
171 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | SM/07179 | Retrofitting | SVS | 1303/ALD | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 05-10-2021 | 04-12-2021 | 1235
172 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | SM/07179 | Retrofitting | SVS | 1318/ALD | TAPASH KUMAR BHOWMICK | 05-10-2021 | 04-12-2021 | 719
173 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | SM/07178 | Retrofitting | SVS | 1158/ALD | TAPASH DAS | 15-12-2020 | 13-02-2021 | 102
174 | ALIPURDUAR | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | SM/07178 | Retrofitting | SVS | 722/ALD | TAPASH DAS | 22-09-2020 | 22-10-2020 | 184
175 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/07174 | Retrofitting | MVS | 728/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 22-09-2020 | 22-10-2020
176 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/07058 | Retrofitting | MVS | 2753/ALD | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 24-02-2022 | 25-04-2022 | 769
177 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/07174 | Retrofitting | MVS | 1283/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 05-01-2021 | 06-03-2021 | 436
178 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/10667 | Augmentation | MVS | 1560/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 23-08-2023 | 22-09-2023 | 58
179 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/07058 | Retrofitting | MVS | 2150/ALD | SHIB RATAN BHOWMIK | 06-01-2022 | 05-02-2022 | 144
180 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/10667 | Augmentation | MVS | 2603/ALD | SHYAMAL ROY | 04-12-2023 | 03-03-2024 | 66
181 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/07058 | Retrofitting | MVS | 2151/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 06-01-2022 | 05-02-2022 | 144
182 | ALIPURDUAR | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | SM/07174 | Retrofitting | MVS | 1137/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 10-12-2020 | 09-01-2021 | 75
183 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | SM/07187 | Retrofitting | MVS | 721/ALD | DAS CONSTRUCTION | 22-09-2020 | 22-10-2020 | 4
184 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | SM/07188 | Retrofitting | MVS | 1843/ALD | PROJIT HALDER | 10-12-2021 | 09-01-2022 | 142
185 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | SM/07187 | Retrofitting | MVS | 1250/ALD | GHOSH & SAHA CONSTRUCTION | 28-12-2020 | 26-02-2021 | 439
186 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | SM/07188 | Retrofitting | MVS | 2378/ALD | SHIBA ENTERPRISE | 31-01-2022 | 01-04-2022 | 129
187 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | SM/07187 | Retrofitting | MVS | 2377/ALD | MATRI ENTERPRISE | 31-01-2022 | 01-04-2022 | 460
188 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | SM/07188 | Retrofitting | MVS | 1844/ALD | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 10-12-2021 | 09-01-2022 | 85
189 | ALIPURDUAR | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | SM/10678 | Augmentation | MVS | 3198/ALD | BIJOY ROY | 27-02-2023 | 26-08-2023 | 474
190 | ALIPURDUAR | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 |  |  | MVS | 906/ALD | SASANKA ROY | 16-10-2020 | 15-11-2020 | 2
191 | ALIPURDUAR | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 |  |  | MVS | 1381/ALD | ASSOCIATE CONSTRUCTION COMPANY | 19-01-2021 | 05-03-2021 | 399
192 | ALIPURDUAR | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 |  |  | MVS | 1168/ALD | SASANKA ROY | 15-12-2020 | 13-02-2021 | 488
193 | ALIPURDUAR | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 |  |  | MVS | 869/ALD | SASANKA ROY | 14-10-2020 | 13-11-2020 | 40
194 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | SM/07136 | Retrofitting | MVS | 871/ALD | NARENDRA BHADANI. | 14-10-2020 | 13-11-2020
195 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | SM/07135 | Retrofitting | SVS | 1170/ALD | MITHUN DAS | 15-12-2020 | 13-02-2021
196 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | SM/07136 | Retrofitting | MVS | 1133/ALD | NARENDRA BHADANI. | 10-12-2020 | 09-01-2021 | 125
197 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 |  |  | MVS | 1181/ALD | SANJIT SAHA | 15-12-2020 | 13-02-2021 | 599
198 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | SM/07135 | Retrofitting | SVS | 1177/ALD | MATARA CONSTRUCTION CO | 15-12-2020 | 13-02-2021 | 546
199 | ALIPURDUAR | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | SM/07136 | Retrofitting | MVS | 1176/ALD | M/S SSB CONSTRUCTION CO. | 15-12-2020 | 13-02-2021 | 120
200 | ALIPURDUAR | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | SM/07177 | Retrofitting | SVS | 2765/ALD | NARENDRA BHADANI. | 25-02-2022 | 26-04-2022 | 693
201 | ALIPURDUAR | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | SM/07063 | Retrofitting | SVS | 978/ALD | HARIDAS GHOSH | 13-09-2021 | 12-11-2021 | 133
202 | ALIPURDUAR | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | SM/07063 | Retrofitting | SVS | 1279/ALD | MATRI ENTERPRISE | 05-01-2021 | 06-03-2021 | 500
203 | ALIPURDUAR | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | SM/07177 | Retrofitting | SVS | 910/ALD | M/S BHOWMICK CONSTRUCTION | 16-10-2020 | 15-11-2020
204 | ALIPURDUAR | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | SM/07063 | Retrofitting | SVS | 1175/ALD | TAPASH KUMAR BHOWMICK | 15-12-2020 | 13-02-2021
205 | ALIPURDUAR | Ground water based water supply scheme for Salsalabari and adjoining mouza | SM/04011 | SM/07063 | Retrofitting | SVS | 2115/ALD | MATRI ENTERPRISE | 05-01-2022 | 04-02-2022 | 145
206 | ALIPURDUAR | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | SM/07064 | Retrofitting | SVS | 2087/ALD | DILIP MAHATO | 30-03-2020 | 04-04-2020 | 196
207 | ALIPURDUAR | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | SM/07064 | Retrofitting | SVS | 1024/ALD | M/S SURAJIT DEY & CO | 18-11-2020 | 17-01-2021 | 78
208 | ALIPURDUAR | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | SM/07064 | Retrofitting | SVS | 1024/ALD | M/S SURAJIT DEY & CO | 18-11-2020 | 17-01-2021 | 187
209 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 | SM/08884 | Retrofitting | MVS | 2811/ALD | MAHENDRA CHHETRI | 28-02-2022 | 29-04-2022 | 994
210 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 | SM/08884 | Retrofitting | MVS | 2714/ALD | ASHIM KUMAR GHOSH | 23-02-2022 | 24-04-2022 | 997
211 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 | SM/08884 | Retrofitting | MVS | 2375/ALD | MADHAB SAHA | 31-01-2022 | 01-04-2022 | 698
212 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 |  |  | MVS | 1245/ALD | ASHIT KUMAR SINGHA | 28-12-2020 | 26-02-2021 | 3
213 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 |  |  | MVS | 1258/ALD | ASHIT KUMAR SINGHA | 29-12-2020 | 27-02-2021 | 721
214 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 |  |  | MVS | 582/ALD | M/S BHOWMICK CONSTRUCTION | 15-07-2021 | 14-08-2021 | 503
215 | ALIPURDUAR | HASIMARA AREAS WATER SUPPLY SCHEME | SM/00143 | SM/08884 | Retrofitting | MVS | 2376/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 31-01-2022 | 01-04-2022 | 529
216 | ALIPURDUAR | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 |  | New | MVS | 690/ALD | SASANKA ROY | 07-03-2024 | 05-06-2024 | 194
217 | ALIPURDUAR | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 |  | New | MVS | 1637/ALD | SASANKA ROY | 19-09-2022 | 18-11-2022 | 195
218 | ALIPURDUAR | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 |  | New | MVS | 1636/ALD | RATAN DUTTA | 19-09-2022 | 17-01-2023 | 396
219 | ALIPURDUAR | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME | SM/10776 |  | New | MVS | 605/ALD | M/S KAMAK ENGINEERS AND CO | 31-05-2022 | 30-06-2022 | 194
220 | ALIPURDUAR | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | SM/10169 | Augmentation | SVS | 1878/ALD | NARENDRA BHADANI. | 07-09-2023 | 07-10-2023
221 | ALIPURDUAR | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | SM/07129 | Retrofitting | SVS | 1753/ALD | MS DEYS CONSTRUCTION | 19-02-2021 | 05-04-2021 | 167
222 | ALIPURDUAR | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | SM/07129 | Retrofitting | SVS | 1334/ALD | BHAGWATI BHUJEL | 11-01-2021 | 10-02-2021 | 50
223 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/10156 | Augmentation | MVS | 24/ALD | AASHIRBAD ENTERPRISE | 01-04-2022 | 31-05-2022 | 165
224 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/07057 | Retrofitting | SVS | 2747/ALD | TAPASH DAS | 24-02-2022 | 25-04-2022 | 490
225 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/07057 | Retrofitting | SVS | 2748/ALD | KAMALESH ROY | 24-02-2022 | 25-04-2022 | 500
226 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/10156 | Augmentation | MVS | 2812/ALD | SOUVIK ROY PALADHI | 28-02-2022 | 29-04-2022 | 993
227 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/07057 | Retrofitting | SVS | 3191/ALD | AASHIRBAD ENTERPRISE | 28-03-2022 | 27-05-2022 | 134
228 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/07057 | Retrofitting | SVS | 867/ALD | PARAMJYOTI ENTERPRISE | 14-10-2020 | 13-11-2020
229 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/07057 | Retrofitting | SVS | 868/ALD | NARAYAN CHANDRA SAHA & SONS | 14-10-2020 | 13-11-2020
230 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/10156 | Augmentation | MVS | 411/ALD | SOUVIK ROY PALADHI | 11-05-2022 | 25-06-2022 | 294
231 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/07057 | Retrofitting | SVS | 1180/ALD | SANJIT SAHA | 15-12-2020 | 13-02-2021 | 486
232 | ALIPURDUAR | JATESWAR WATER SUPPLY SCHEME | SM/00023 | SM/10156 | Augmentation | MVS | 412/ALD | AASHIRBAD ENTERPRISE | 11-05-2022 | 25-06-2022 | 114
233 | ALIPURDUAR | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | SM/07195 | Retrofitting | SVS | 431/ALD | DAS ENTERPRISE | 06-08-2020 | 04-11-2020 | 75
234 | ALIPURDUAR | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | SM/07195 | Retrofitting | SVS | 432/ALD | DAS CONSTRUCTION | 06-08-2020 | 04-11-2020 | 401
235 | ALIPURDUAR | JAYANTI WATER SUPPLY SCHEME | SM/00034 | SM/07193 | Retrofitting | SVS | 1576/ALD | DEBAJYOTI SUTRADHAR | 22-11-2021 | 21-01-2022 | 200
236 | ALIPURDUAR | JAYANTI WATER SUPPLY SCHEME | SM/00034 | SM/07193 | Retrofitting | SVS | 975/ALD | GHOSH & SAHA CONSTRUCTION | 13-09-2021 | 13-10-2021 | 78
237 | ALIPURDUAR | JAYANTI WATER SUPPLY SCHEME | SM/00034 | SM/07193 | Retrofitting | SVS | 724/ALD | M/S BHOWMICK CONSTRUCTION | 22-09-2020 | 22-10-2020 | 150
238 | ALIPURDUAR | JAYANTI WATER SUPPLY SCHEME | SM/00034 | SM/07193 | Retrofitting | SVS | 1619/ALD | M/S BHOWMICK CONSTRUCTION | 23-11-2021 | 22-01-2022 | 259
239 | ALIPURDUAR | JAYANTI WATER SUPPLY SCHEME | SM/00034 | SM/07193 | Retrofitting | SVS | 916/ALD | M/S BHOWMICK CONSTRUCTION | 16-10-2020 | 15-11-2020 | 123
240 | ALIPURDUAR | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 |  | New | MVS | 2857/ALD | DILIP MAHATO | 17-01-2023 | 16-07-2023 | 963
241 | ALIPURDUAR | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | SM/07065 | Retrofitting | SVS | 2202/ALD | TAPASH KUMAR BHOWMICK | 11-01-2022 | 12-03-2022 | 68
242 | ALIPURDUAR | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | SM/07181 | Retrofitting | MVS | 1164/ALD | GHOSH & SAHA CONSTRUCTION | 15-12-2020 | 13-02-2021 | 439
243 | ALIPURDUAR | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | SM/07181 | Retrofitting | MVS | 862/ALD | DAS ENTERPRISE | 14-10-2020 | 13-11-2020 | 115
244 | ALIPURDUAR | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | SM/07181 | Retrofitting | MVS | 580/ALD | M/S BHOWMICK CONSTRUCTION | 15-07-2021 | 14-08-2021 | 152
245 | ALIPURDUAR | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 |  |  | MVS | 2240/ALD | KAMALESH ROY | 21-11-2022 | 20-01-2023 | 500
246 | ALIPURDUAR | KAIJALI BASTY WATER SUPPLY SCHEME | SM/00032 | SM/07181 | Retrofitting | MVS | 913/ALD | DAS ENTERPRISE | 16-10-2020 | 15-11-2020 | 133
247 | ALIPURDUAR | KALABERIA PIPED WATER SUPPLY SCHEME | SM/13306 |  | New | MVS | 3578/ALD | SASANKA ROY | 27-03-2023 | 23-09-2023 | 549
248 | ALIPURDUAR | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 |  | New | SVS | 1769/ALD | RAMESH SHARMA | 19-02-2021 | 20-04-2021 | 221
249 | ALIPURDUAR | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 |  | New | SVS | 3229/ALD. | SHREE RANISATI ENTERPRISE | 27-02-2023 | 27-06-2023 | 755
250 | ALIPURDUAR | KALCHINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/15482 |  | New | SVS | 1768/ALD | SUNDAR SING LAMA | 19-02-2021 | 20-04-2021 | 497
251 | ALIPURDUAR | KALCHINI WATER SUPPLY SCHEME | SM/00026 |  |  | MVS | 1243/ALD | SHYAM CHHETRI | 28-12-2020 | 26-02-2021
252 | ALIPURDUAR | KALCHINI WATER SUPPLY SCHEME | SM/00026 |  |  | MVS | 1769/ALD | RAMESH SHARMA | 19-02-2021 | 20-04-2021
253 | ALIPURDUAR | KALCHINI WATER SUPPLY SCHEME | SM/00026 |  |  | MVS | 1463/ALD | HARI CONSTRUCTION | 25-01-2021 | 24-02-2021
254 | ALIPURDUAR | KALCHINI WATER SUPPLY SCHEME | SM/00026 |  |  | MVS | 915/ALD | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16-10-2020 | 15-11-2020
255 | ALIPURDUAR | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 |  | New | SVS | 2239/ALD | TAPASH DAS | 21-11-2022 | 21-03-2023 | 620
256 | ALIPURDUAR | KARTIKA TEA GARDEN AREA PIPED WAATER SUPPLY SCHEME | SM/11991 |  | New | SVS | 2976/ALD | MAHENDRA CHHETRI | 02-02-2023 | 01-08-2023 | 494
257 | ALIPURDUAR | Khagenhat Piped Water Supply Scheme | SM/18151 |  | New | MVS | 2170/ALD | TAPASH DAS | 06-10-2023 | 05-12-2023 | 52
258 | ALIPURDUAR | Khagenhat Piped Water Supply Scheme | SM/18151 |  | New | MVS | 422/ALD | MADHAB SAHA | 24-05-2023 | 21-09-2023
259 | ALIPURDUAR | Khagenhat Piped Water Supply Scheme | SM/18151 |  | New | MVS | 258/ALD | DILIP MAHATO | 08-05-2023 | 04-11-2023 | 266
260 | ALIPURDUAR | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 |  | New | MVS | 2979/ALD | DILIP MAHATO | 02-02-2023 | 01-08-2023 | 479
261 | ALIPURDUAR | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 |  | New | MVS | 1852/ALD | TAPASH DAS | 04-09-2023 | 03-11-2023 | 499
262 | ALIPURDUAR | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 |  | New | MVS | 2235/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 21-11-2022 | 21-03-2023 | 195
263 | ALIPURDUAR | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 |  |  | MVS | 857/ALD | ASHIM KUMAR CHAKRABORTY | 14-10-2020 | 13-11-2020 | 116
264 | ALIPURDUAR | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | SM/11985 | Augmentation | MVS | 3000/ALD | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 06-02-2023 | 05-08-2023 | 1862
265 | ALIPURDUAR | KUMARGRAM WATER SUPPLY SCHEME | SM/00044 | SM/11985 | Augmentation | MVS | 1009/ALD | DILIP MAHATO | 15-07-2022 | 13-09-2022 | 420
266 | ALIPURDUAR | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 |  | New | SVS | 1305/ALD | HARIDAS GHOSH | 22-08-2022 | 20-12-2022 | 698
267 | ALIPURDUAR | KUMARGRAM TG AREA PIPED WATER SUPPLY SCHEME | SM/11482 |  | New | SVS | 1791/ALD | HARI CONSTRUCTION | 29-08-2023 | 28-10-2023 | 389
268 | ALIPURDUAR | LACHHIMANDABRI PIPED WATER SUPPLY SCHEME | SM/16819 |  | New | MVS | 1172/ALD | M/S T M CONSTRUCTION | 03-08-2023 | 30-01-2024
269 | ALIPURDUAR | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | SM/07138 | Retrofitting | SVS | 1807/ALD | GHOSH & SAHA CONSTRUCTION | 22-02-2021 | 23-04-2021 | 448
270 | ALIPURDUAR | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | SM/07066 | Retrofitting | MVS | 1757/ALD | MADHAB SAHA | 19-02-2021 | 20-04-2021
271 | ALIPURDUAR | LANKAPARA WATER SUPPLY SCHEME | SM/00892 |  |  | MVS | 744/ALD | M/S SURAJIT DEY & CO | 23-09-2020 | 22-12-2020 | 866
272 | ALIPURDUAR | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 |  | New | MVS | 23/ALD | DILIP MAHATO | 01-04-2022 | 30-07-2022
273 | ALIPURDUAR | MADARIHAT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10173 |  | New | MVS | 18/ALD | DILIP MAHATO | 01-04-2022 | 30-07-2022 | 930
274 | ALIPURDUAR | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | SM/07192 | Retrofitting | SVS | 880/ALD | SOUVIK ROY PALADHI | 03-09-2021 | 02-11-2021 | 584
275 | ALIPURDUAR | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | SM/07192 | Retrofitting | SVS | 798/ALD | TAPASH KUMAR BHOWMICK | 01-10-2020 | 30-11-2020
276 | ALIPURDUAR | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | SM/07192 | Retrofitting | SVS | 798/ALD | TAPASH KUMAR BHOWMICK | 01-10-2020 | 30-11-2020
277 | ALIPURDUAR | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | SM/07192 | Retrofitting | SVS | 2086/ALD | TAPASH KUMAR BHOWMICK | 30-03-2020
278 | ALIPURDUAR | MADHYA KAMAKHYAGURI PIPED WATER SUPPLY SCHEME | SM/15517 |  | New | MVS | 3155/ALD | GHOSH & SAHA CONSTRUCTION | 22-02-2023 | 21-08-2023 | 1029
279 | ALIPURDUAR | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 |  | New | MVS | 3575/ALD | DILIP MAHATO | 27-03-2023 | 23-09-2023 | 913
280 | ALIPURDUAR | MAIRADANGA PIPED WATER SUPPLY SCHEME | SM/15206 |  | New | MVS | 334/ALD | MESSRS A.B.G CONSTRUCTION | 16-05-2023 | 12-11-2023
281 | ALIPURDUAR | Makrapara W/S Scheme | SM/02173 | SM/07199 | Retrofitting | SVS | 697/ALD | DILIP MAHATO | 16-09-2020 | 14-01-2021 | 556
282 | ALIPURDUAR | Makrapara W/S Scheme | SM/02173 | SM/07199 | Retrofitting | SVS | 2897/ALD | DILIP MAHATO | 08-03-2022 | 07-05-2022 | 109
283 | ALIPURDUAR | MALSAGAON PIPED WATER SUPPLY SCHEME | SM/16818 |  | New | MVS | 1874/ALD | DILIP MAHATO | 07-09-2023 | 05-03-2024 | 1471
284 | ALIPURDUAR | MARAKHATA PIPED WATER SUPPLY SCHEME. | SM/13304 |  | New | MVS | 2863/ALD | HARIDAS GHOSH | 17-01-2023 | 16-07-2023 | 963
285 | ALIPURDUAR | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 |  | New | MVS | 22/ALD | TAPASH KUMAR BHOWMICK | 01-04-2022 | 30-07-2022 | 1261
286 | ALIPURDUAR | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 |  | New | MVS | 17/ALD | M/S SURAJIT DEY & CO | 01-04-2022 | 30-07-2022 | 660
287 | ALIPURDUAR | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 |  | New | SVS | 14/ALD | SHREE RANISATI ENTERPRISE | 01-04-2022 | 30-07-2022 | 447
288 | ALIPURDUAR | NARASINGPUR PIPED WATER SUPPLY SCHEME | SM/15758 |  | New | MVS | 1048/ALD | DILIP MAHATO | 20-07-2023 | 16-01-2024 | 1495
289 | ALIPURDUAR | NARTHALI WATER SUPPLY SCHEME | SM/00156 | SM/10154 | Augmentation | MVS | 2744/ALD | DAS CONSTRUCTION | 24-02-2022 | 25-04-2022 | 396
290 | ALIPURDUAR | NARTHALI WATER SUPPLY SCHEME | SM/00156 | SM/10154 | Augmentation | MVS | 2743/ALD | HARIDAS GHOSH | 24-02-2022 | 25-04-2022 | 928
291 | ALIPURDUAR | NARTHALI WATER SUPPLY SCHEME | SM/00156 | SM/10154 | Augmentation | MVS | 2742/ALD | MADHAB SAHA | 24-02-2022 | 25-04-2022 | 935
292 | ALIPURDUAR | NARTHALI WATER SUPPLY SCHEME | SM/00156 | SM/10154 | Augmentation | MVS | 2745/ALD | SASANKA ROY | 24-02-2022 | 25-04-2022 | 936
293 | ALIPURDUAR | NEPANIA WATER SCHEME (NORTH BANDAPARA TEA GARDEN) | SM/00039 | SM/11766 | Augmentation | SVS | 2489/ALD | BHAGWATI BHUJEL | 13-12-2022 | 12-04-2023 | 203
294 | ALIPURDUAR | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 |  | New | SVS | 1275/ALD | TAPASH KUMAR BHOWMICK | 17-08-2022 | 15-12-2022 | 297
295 | ALIPURDUAR | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 |  | New | SVS | 1307/ALD | MADHAB SAHA | 22-08-2022 | 20-12-2022 | 500
296 | ALIPURDUAR | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 |  | New | MVS | 1885/ALD | DEBAJYOTI SUTRADHAR | 07-09-2023 | 07-10-2023
297 | ALIPURDUAR | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 |  | New | MVS | 3571/ALD | DOOARS CONSTRUCTION COMPANY | 27-03-2023 | 23-09-2023 | 759
298 | ALIPURDUAR | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 |  | New | SVS | 1882/ALD | M/S A. B. ENTERPRISE | 07-09-2023 | 07-10-2023 | 192
299 | ALIPURDUAR | NIMTIJHORA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14215 |  | New | SVS | 3639/ALD | SAMIRON PODDER | 31-03-2023 | 27-09-2023 | 778
300 | ALIPURDUAR | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | SM/07190 | Retrofitting | SVS | 430/ALD | HARIDAS GHOSH | 06-08-2020 | 04-11-2020
301 | ALIPURDUAR | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | SM/07190 | Retrofitting | SVS | 430/ALD | HARIDAS GHOSH | 06-08-2020 | 04-11-2020
302 | ALIPURDUAR | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 |  | New | SVS | 3637/ALD | DEBAJYOTI SUTRADHAR | 31-03-2023 | 27-09-2023 | 209
303 | ALIPURDUAR | PAKRIGURI PIPED WAYER SUPPLY SCHEME. | SM/14223 |  | New | SVS | 1566/ALD | SREE MAA CONSTRUCTION | 23-08-2023 | 22-09-2023
304 | ALIPURDUAR | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 |  | New | SVS | 3505/ALD | TAPASH DAS | 23-03-2023 | 22-04-2023 | 47
305 | ALIPURDUAR | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 |  | New | SVS | 3397/ALD | SASANKA ROY | 16-03-2023 | 12-09-2023 | 752
306 | ALIPURDUAR | Parokata water supply scheme | SM/01378 | SM/09886 | Augmentation | MVS | 2116/ALD | SREE MAA CONSTRUCTION | 05-01-2022 | 04-02-2022 | 145
307 | ALIPURDUAR | Parokata water supply scheme | SM/01378 | SM/09886 | Augmentation | MVS | 2385/ALD | SOUVIK ROY PALADHI | 31-01-2022 | 01-04-2022 | 1614
308 | ALIPURDUAR | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 |  | New | MVS | 2862/ALD | M/S SSB CONSTRUCTION CO. | 17-01-2023 | 16-07-2023 | 817
309 | ALIPURDUAR | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 |  | New | MVS | 1590/ALD | ANKIT SARKAR | 25-08-2023 | 24-09-2023 | 49
310 | ALIPURDUAR | PASCHIM DEOGAON PIPED WATER SUPPLY SCHEME | SM/15207 |  | New | MVS | 1047/ALD | SOUVIK ROY PALADHI | 20-07-2023 | 16-01-2024
311 | ALIPURDUAR | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 |  | New | MVS | 2859/ALD | MAHENDRA CHHETRI | 17-01-2023 | 16-07-2023 | 1004
312 | ALIPURDUAR | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 |  | New | MVS | 2860/ALD | DILIP MAHATO | 17-01-2023 | 16-07-2023 | 490
313 | ALIPURDUAR | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | SM/07060 | Retrofitting | MVS | 1138/ALD | MADHAB SAHA | 10-12-2020 | 09-01-2021 | 143
314 | ALIPURDUAR | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | SM/07061 | Retrofitting | MVS | 1172/ALD | SOUVIK ROY PALADHI | 15-12-2020 | 13-02-2021 | 568
315 | ALIPURDUAR | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | SM/07060 | Retrofitting | MVS | 2766/ALD | TAPASH KUMAR BHOWMICK | 25-02-2022 | 26-04-2022 | 17
316 | ALIPURDUAR | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | SM/07061 | Retrofitting | MVS | 1171/ALD | SHIBA ENTERPRISE | 15-12-2020 | 13-02-2021 | 602
317 | ALIPURDUAR | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | SM/07061 | Retrofitting | MVS | 879/ALD | TAPASH KUMAR BHOWMICK | 03-09-2021 | 02-11-2021 | 966
318 | ALIPURDUAR | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | SM/07060 | Retrofitting | MVS | 1139/ALD | MADHAB SAHA | 10-12-2020 | 09-01-2021 | 104
319 | ALIPURDUAR | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 |  | New | MVS | 2977/ALD | DILIP MAHATO | 02-02-2023 | 01-08-2023 | 283
320 | ALIPURDUAR | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 |  | New | MVS | 2238/ALD | ASHOK SAPKOTA | 21-11-2022 | 21-03-2023 | 100
321 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2136/ALD | D. K. & SONS | 06-01-2022 | 05-02-2022 | 145
322 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 3623/ALD | D. K. & SONS | 30-03-2023 | 28-06-2023 | 743
323 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 3622/ALD | D. K. & SONS | 30-03-2023 | 29-05-2023
324 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1222/ALD | MAHENDRA CHHETRI | 10-08-2022 | 09-10-2022 | 994
325 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2374/ALD | AQUEDUCT PLASTICS PVT. LTD. | 31-01-2022 | 01-04-2022 | 934
326 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2137/ALD | D. K. & SONS | 06-01-2022 | 05-02-2022 | 145
327 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2154/ALD | MAHENDRA CHHETRI | 06-01-2022 | 05-02-2022 | 145
328 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2153/ALD | MAHENDRA CHHETRI | 06-01-2022 | 05-02-2022 | 144
329 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2152/ALD | D. K. & SONS | 06-01-2022 | 05-02-2022 | 145
330 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2373/ALD | AQUEDUCT PLASTICS PVT. LTD. | 31-01-2022 | 01-04-2022 | 711
331 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2204/ALD | DILIP MAHATO | 11-01-2022 | 12-03-2022 | 901
332 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 2203/ALD | MAHENDRA CHHETRI | 11-01-2022 | 12-03-2022 | 1000
333 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1449/ALD | MAHENDRA CHHETRI | 25-01-2021 | 11-03-2021 | 1101
334 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1765/ALD | MAHENDRA CHHETRI | 19-02-2021 | 20-04-2021 | 999
335 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1763ALD | AQUEDUCT PLASTICS PVT. LTD. | 19-02-2021 | 20-04-2021
336 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1451/ALD | AQUEDUCT PLASTICS PVT. LTD. | 25-01-2021 | 11-03-2021 | 1097
337 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 746/ALD | MAHENDRA CHHETRI | 12-03-2024 | 10-07-2024
338 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1762ALD | AQUEDUCT PLASTICS PVT. LTD. | 19-02-2021 | 20-04-2021 | 890
339 | ALIPURDUAR | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | SM/08080 | Retrofitting | MVS | 1764ALD | AQUEDUCT PLASTICS PVT. LTD. | 19-02-2021 | 20-04-2021 | 906
340 | ALIPURDUAR | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 |  | New | MVS | 3394/ALD | MESSRS A.B.G CONSTRUCTION | 16-03-2023 | 12-09-2023 | 781
341 | ALIPURDUAR | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 |  | New | MVS | 2858/ALD | SOUVIK ROY PALADHI | 17-01-2023 | 16-07-2023 | 871
342 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 |  |  | MVS | 1173/ALD | MADHAB SAHA | 15-12-2020 | 13-02-2021 | 249
343 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 |  |  | MVS | 908/ALD | SREE MAA CONSTRUCTION & CO. | 16-10-2020 | 15-11-2020
344 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 988/ALD | NEOGI ENTERPRISE | 15-07-2022 | 13-09-2022 | 181
345 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 995/ALD | DAS ENTERPRISE | 15-07-2022 | 13-09-2022 | 316
346 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 978/ALD | DILIP MAHATO | 15-07-2022 | 13-09-2022 | 1
347 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 997/ALD | M/S JHA CONSTRUCTION | 15-07-2022 | 13-09-2022 | 621
348 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 996/ALD | NARAYAN CHANDRA SAHA | 15-07-2022 | 13-09-2022 | 581
349 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 994/ALD | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 15-07-2022 | 13-09-2022 | 673
350 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 989/ALD | UTTAM KUMAR DUTTA | 15-07-2022 | 13-09-2022 | 170
351 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 982/ALD | DAS CONSTRUCTION | 15-07-2022 | 29-08-2022
352 | ALIPURDUAR | PURBA KANTHALBARI WATER SUPPLY SCHEME | SM/00153 | SM/11459 | Augmentation | MVS | 981/ALD | MAHENDRA CHHETRI | 15-07-2022 | 29-08-2022 | 270
353 | ALIPURDUAR | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 |  | New | MVS | 3577/ALD | HARIDAS GHOSH | 27-03-2023 | 23-09-2023 | 1169
354 | ALIPURDUAR | Purbba Majherdabri Tea Garden Area Piped Water Supply Scheme | SM/18157 |  | New | SVS | 406/ALD | DAS CONSTRUCTION | 22-05-2023 | 18-11-2023
355 | ALIPURDUAR | PURBBA NARATHALI PIPED WATER SUPPLY SCHEME. | SM/16537 |  | New | MVS | 3573ALD | MADHAB SAHA | 27-03-2023 | 23-09-2023 | 516
356 | ALIPURDUAR | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | SM/09884 | Augmentation | MVS | 2388/ALD | HARI CONSTRUCTION | 31-01-2022 | 01-04-2022 | 778
357 | ALIPURDUAR | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | SM/09884 | Augmentation | MVS | 1221/ALD | HARI CONSTRUCTION | 10-08-2022 | 09-10-2022 | 294
358 | ALIPURDUAR | PUTIMARI WATER SUPPLY SCHEME | SM/00017 | SM/09884 | Augmentation | MVS | 2291/ALD | HARI CONSTRUCTION | 24-01-2022 | 25-03-2022 | 1016
359 | ALIPURDUAR | PUTIMARI WATER SUPPLY SCHEME | SM/00017 |  |  | MVS | 725/ALD | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 22-09-2020 | 22-10-2020
360 | ALIPURDUAR | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | SM/07067 | Retrofitting | MVS | 1028/ALD | UMWELT ENGINEER PVT. LTD. | 18-11-2020 | 17-01-2021 | 924
361 | ALIPURDUAR | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | SM/07067 | Retrofitting | MVS | 1027/ALD | UMWELT ENGINEER PVT. LTD. | 18-11-2020 | 17-01-2021 | 1014
362 | ALIPURDUAR | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | SM/07067 | Retrofitting | MVS | 2201/ALD | SOUVIK ROY PALADHI | 11-01-2022 | 12-03-2022 | 961
363 | ALIPURDUAR | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | SM/07186 | Retrofitting | SVS | 2762/ALD | SOUVIK ROY PALADHI | 25-02-2022 | 26-04-2022 | 765
364 | ALIPURDUAR | Radharani Tea Garden Area Piped Water Supply Scheme | SM/06459 | SM/07186 | Retrofitting | SVS | 905/ALD | SOUVIK ROY PALADHI | 03-09-2021 | 18-10-2021 | 86
365 | ALIPURDUAR | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | SM/07196 | Retrofitting | SVS | 797/ALD | SOUVIK ROY PALADHI | 01-10-2020 | 30-11-2020
366 | ALIPURDUAR | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | SM/07196 | Retrofitting | SVS | 797/ALD | SOUVIK ROY PALADHI | 01-10-2020 | 30-11-2020 | 101
367 | ALIPURDUAR | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 |  | New | MVS | 3194/ALD | ASHIM KUMAR GHOSH | 27-02-2023 | 26-08-2023 | 819
368 | ALIPURDUAR | RAJABHAT TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14093 |  | New | MVS | 1884/ALD | PRITAM DAS | 07-09-2023 | 07-10-2023 | 211
369 | ALIPURDUAR | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14213 |  | New | SVS | 1171/ALD | M/S RADHASWAMI ENTERPRISE | 03-08-2023 | 30-01-2024 | 676
370 | ALIPURDUAR | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 |  | New | MVS | 2237/ALD | DAS CONSTRUCTION | 21-11-2022 | 21-03-2023 | 671
371 | ALIPURDUAR | RAYDAK TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12114 |  | New | MVS | 2978/ALD | CHINMOY BHATTACHARJEE | 02-02-2023 | 01-08-2023 | 361
372 | ALIPURDUAR | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | SM/12561 | Augmentation | MVS | 2658/ALD | HARIDAS GHOSH | 22-12-2022 | 21-04-2023 | 1297
373 | ALIPURDUAR | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | SM/12561 | Augmentation | MVS | 2500/ALD | TAPASH KUMAR BHOWMICK | 13-12-2022 | 12-04-2023 | 855
374 | ALIPURDUAR | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 |  |  | MVS | 727/ALD | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 22-09-2020 | 22-10-2020
375 | ALIPURDUAR | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | SM/12561 | Augmentation | MVS | 2501/ALD | MADHAB SAHA | 13-12-2022 | 12-04-2023 | 991
376 | ALIPURDUAR | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 |  | New | SVS | 1277/ALD | SOUVIK ROY PALADHI | 17-08-2022 | 15-12-2022 | 982
377 | ALIPURDUAR | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 |  | New | SVS | 1276/ALD | SOUVIK ROY PALADHI | 17-08-2022 | 15-12-2022 | 198
378 | ALIPURDUAR | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 |  | New | SVS | 1790/ALD | SOUVIK ROY PALADHI | 29-08-2023 | 28-10-2023 | 169
379 | ALIPURDUAR | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 |  | New | MVS | 1642/ALD | KAMALESH ROY | 19-09-2022 | 18-11-2022 | 299
380 | ALIPURDUAR | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 |  | New | MVS | 2657/ALD/ | DEBAJYOTI SUTRADHAR | 22-12-2022 | 21-04-2023 | 190
381 | ALIPURDUAR | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 |  | New | MVS | 1641/ALD | DAS CONSTRUCTION | 19-09-2022 | 18-11-2022 | 352
382 | ALIPURDUAR | SHRINATHPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11709 |  | New | MVS | 1640/ALD | TAPASH KUMAR BHOWMICK | 19-09-2022 | 18-11-2022
383 | ALIPURDUAR | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 |  | New | MVS | 15/ALD | BILTU DAS | 01-04-2022 | 30-07-2022 | 464
384 | ALIPURDUAR | SISHA JUMRHA PIPED WATER SUPPLY SCHEME | SM/12753 |  | New | MVS | 3576/ALD | DILIP MAHATO | 27-03-2023 | 23-09-2023 | 1090
385 | ALIPURDUAR | TASTI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/16822 |  | New | SVS | 975/ALD | MADHAB SAHA | 12-07-2023 | 08-01-2024
386 | ALIPURDUAR | TELIPARA PIPED WATER SUPPLY SCHEME. | SM/13303 |  | New | MVS | 3640/ALD | MATRI ENTERPRISE | 31-03-2023 | 27-09-2023 | 568
387 | ALIPURDUAR | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 |  | New | MVS | 1581/ALD | KAMALESH ROY | 24-08-2023 | 23-10-2023 | 80
388 | ALIPURDUAR | TORSHA FOREST PIPED WATER SUPPLY SCHEME | SM/14220 |  | New | MVS | 2919/ALD | KAMALESH ROY | 19-01-2023 | 19-05-2023 | 161
389 | ALIPURDUAR | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 |  | New | SVS | 1886/ALD | D. K. & SONS | 07-09-2023 | 07-10-2023
390 | ALIPURDUAR | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 |  | New | SVS | 283/ALD | MAHENDRA CHHETRI | 26-04-2022 | 23-09-2022
391 | ALIPURDUAR | Totopara Water Supply Scheme | SM/03080 | SM/07180 | Retrofitting | SVS | 745/ALD | PARESH CH GUHA | 23-09-2020 | 22-12-2020
392 | ALIPURDUAR | Totopara Water Supply Scheme | SM/03080 | SM/04771 |  | MVS | 745/ALD | PARESH CH GUHA | 23-09-2020 | 22-12-2020
393 | ALIPURDUAR | Totopara Water Supply Scheme | SM/03080 | SM/11765 | Augmentation | SVS | 2604/ALD | DULAL DAS | 04-12-2023 | 02-05-2024 | 109
394 | ALIPURDUAR | TOTPARA WATER SUPPLY SCHEME | SM/00148 |  |  | MVS | 1580/ALD | SASANKA ROY | 22-11-2021 | 21-01-2022 | 246
395 | ALIPURDUAR | TOTPARA WATER SUPPLY SCHEME | SM/00148 |  |  | MVS | 1579/ALD | NARENDRA BHADANI. | 22-11-2021 | 21-01-2022 | 240
396 | ALIPURDUAR | TOTPARA WATER SUPPLY SCHEME | SM/00148 | SM/10155 | Augmentation | SVS | 1852/ALD | HARI CONSTRUCTION | 13-12-2021 | 12-01-2022 | 132
397 | ALIPURDUAR | TOTPARA WATER SUPPLY SCHEME | SM/00148 |  |  | MVS | 1573/ALD | HARIDAS GHOSH | 22-11-2021 | 21-01-2022 | 517
398 | ALIPURDUAR | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 |  | New | MVS | 3574/ALD | TAPASH KUMAR BHOWMICK | 27-03-2023 | 23-09-2023 | 764
399 | ALIPURDUAR | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 |  | New | MVS | 3195/ALD | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 27-02-2023 | 26-08-2023 | 421
400 | ALIPURDUAR | TURTURI PIPED WATER SUPPLY SCHEME. | SM/14219 |  | New | MVS | 1571/ALD | TAPASH KUMAR BHOWMICK | 23-08-2023 | 07-10-2023
401 | ALIPURDUAR | UMACHARANPUR PIPED WATER SUPPLY SCHEME | SM/16114 |  | New | MVS | 1873/ALD | TAPASH KUMAR BHOWMICK | 07-09-2023 | 05-03-2024
402 | ALIPURDUAR | UTTAR DEOGAON PIPED WATER SUPPLY SCHEME | SM/16817 |  | New | MVS | 1046/ALD | DILIP MAHATO | 20-07-2023 | 16-01-2024 | 1041
403 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/07062 | Retrofitting | SVS | 1304/ALD | DULAL MAJUMDER | 05-10-2021 | 04-12-2021 | 997
404 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/07062 | Retrofitting | SVS | 1574/ALD | M/S PALIT ENTERPRISE | 22-11-2021 | 21-01-2022 | 229
405 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/10170 | Augmentation | SVS | 2564/ALD | DEBAJYOTI SUTRADHAR | 29-11-2023 | 27-02-2024 | 46
406 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/10170 | Augmentation | SVS | 1306/ALD | DILIP MAHATO | 22-08-2022 | 21-10-2022 | 181
407 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/07062 | Retrofitting | SVS | 1163/ALD | TAPASH DAS | 15-12-2020 | 13-02-2021 | 302
408 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/07062 | Retrofitting | SVS | 917/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 16-10-2020 | 15-11-2020 | 124
409 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/07062 | Retrofitting | SVS | 861/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 14-10-2020 | 13-11-2020 | 145
410 | ALIPURDUAR | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | SM/07062 | Retrofitting | SVS | 2289/ALD | GOUTAM KUMAR DAS | 24-01-2022 | 25-03-2022 | 429
411 | ALIPURDUAR | UTTAR LATABARI (NM) WATER SUPPLY SCHEME | SM/01021 |  |  | MVS | 1244/ALD | SHIB RATAN BHOWMIK | 28-12-2020 | 26-02-2021
412 | ALIPURDUAR | UTTAR LATABARI (NM) WATER SUPPLY SCHEME | SM/01021 | SM/10637 | Augmentation | SVS | 407/ALD | SHIB RATAN BHOWMIK | 11-05-2022 | 25-06-2022 | 286
413 | ALIPURDUAR | UTTAR LATABARI (NM) WATER SUPPLY SCHEME | SM/01021 |  |  | MVS | 915/ALD | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16-10-2020 | 15-11-2020 | 1
414 | ALIPURDUAR | UTTAR LATABARI (NM) WATER SUPPLY SCHEME | SM/01021 | SM/10637 | Augmentation | SVS | 406/ALD | ASHOK SAPKOTA | 11-05-2022 | 25-06-2022 | 624
415 | ALIPURDUAR | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 |  |  | MVS | 1831/ALD | RATAN DUTTA | 10-12-2021 | 09-01-2022 | 138
416 | ALIPURDUAR | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 | SM/08880 | Retrofitting | SVS | 2285/ALD | MAHENDRA CHHETRI | 21-01-2022 | 22-03-2022 | 258
417 | ALIPURDUAR | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 | SM/08880 | Retrofitting | SVS | 2284/ALD | DILIP MAHATO | 21-01-2022 | 22-03-2022 | 355
418 | ALIPURDUAR | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 |  |  | MVS | 1830/ALD | BHAGWATI BHUJEL | 10-12-2021 | 09-01-2022 | 145
419 | ALIPURDUAR | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 |  |  | MVS | 1806/ALD | DILIP MAHATO | 22-02-2021 | 23-04-2021 | 500
420 | ALIPURDUAR | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 |  |  | MVS | 1241/ALD | M/S SURAJIT DEY & CO | 27-09-2021 | 26-11-2021 | 429
421 | ALIPURDUAR | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | SM/10171 | Augmentation | MVS | 3002/ALD | M/S DUTTA AND CO | 15-03-2022 | 14-05-2022 | 464
422 | ALIPURDUAR | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 |  |  | MVS | 1287/ALD | TAPASH KUMAR BHOWMICK | 05-01-2021 | 06-03-2021
423 | ALIPURDUAR | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | SM/10171 | Augmentation | MVS | 2870/ALD | DILIP MAHATO | 07-03-2022 | 06-05-2022 | 731
424 | ALIPURDUAR | UTTAR MAJHERDABARI WATER SUPPLY SCHEME | SM/00152 | SM/10171 | Augmentation | MVS | 2872/ALD | MAHENDRA CHHETRI | 07-03-2022 | 06-05-2022 | 590
425 | ALIPURDUAR | UTTAR MAJID KHANA PIPED WATER SUPPLY SCHEME | SM/16538 |  | New | MVS | 3416/ALD | TAPASH KUMAR BHOWMICK | 17-03-2023 | 13-09-2023 | 981
426 | ALIPURDUAR | UTTAR MANDABARI PIPED WATER SUPPLY SCHEME | SM/16539 |  | New | MVS | 1113/ALD | MAHENDRA CHHETRI | 28-07-2023 | 24-01-2024 | 1201
427 | ALIPURDUAR | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 |  | New | MVS | 3570/ALD | SAMIRON PODDER | 27-03-2023 | 23-09-2023
428 | ALIPURDUAR | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | SM/08881 | Retrofitting | MVS | 1309/ALD | MITHUN DAS | 05-10-2021 | 04-12-2021 | 738
429 | ALIPURDUAR | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | SM/08881 | Retrofitting | MVS | 1577/ALD | ASHOK SAPKOTA | 22-11-2021 | 21-01-2022 | 375
430 | ALIPURDUAR | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | SM/08881 | Retrofitting | MVS | 1578/ALD | KAMALESH ROY | 22-11-2021 | 21-01-2022 | 376
431 | ALIPURDUAR | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | SM/11959 | Augmentation | MVS | 1492/ALD | MITHUN DAS | 05-09-2022 | 20-10-2022 | 238
432 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07175 | Retrofitting | SVS | 1157/ALD | DAS CONSTRUCTION | 15-12-2020 | 13-02-2021 | 749
433 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07121 | Retrofitting | SVS | 1308/ALD | DAS CONSTRUCTION | 05-10-2021 | 04-12-2021 | 349
434 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07121 | Retrofitting | SVS | 2118/ALD | DAS CONSTRUCTION | 05-01-2022 | 04-02-2022 | 144
435 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07175 | Retrofitting | SVS | 1135/ALD | KAMALESH ROY | 10-12-2020 | 09-01-2021
436 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07121 | Retrofitting | SVS | 2117/ALD | DAS CONSTRUCTION | 05-01-2022 | 04-02-2022 | 145
437 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07175 | Retrofitting | SVS | 720/ALD | KAMALESH ROY | 22-09-2020 | 22-10-2020
438 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07175 | Retrofitting | SVS | 2751/ALD | R.K.CONSTRUCTION | 24-02-2022 | 25-04-2022 | 549
439 | ALIPURDUAR | Water Supply Scheme for Birpara Mouzas | SM/03602 | SM/07121 | Retrofitting | SVS | 2200/ALD | DAS CONSTRUCTION | 11-01-2022 | 12-03-2022 | 496
440 | ALIPURDUAR | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | SM/08882 | Retrofitting | MVS | 2138/ALD | SASANKA ROY | 06-01-2022 | 05-02-2022 | 146
441 | ALIPURDUAR | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | SM/08882 | Retrofitting | MVS | 1305/ALD | SASANKA ROY | 05-10-2021 | 04-12-2021 | 399
442 | ALIPURDUAR | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 |  |  | MVS | 1174/ALD | TAPASH KUMAR BHOWMICK | 15-12-2020 | 13-02-2021 | 507
443 | ALIPURDUAR | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 |  |  | MVS | 909/ALD | SREE MAA CONSTRUCTION & CO. | 16-10-2020 | 15-11-2020 | 1
444 | ALIPURDUAR | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | SM/08882 | Retrofitting | MVS | 2139/ALD | SASANKA ROY | 06-01-2022 | 05-02-2022 | 74
445 | ALIPURDUAR | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | SM/08882 | Retrofitting | MVS | 2761/ALD | MATRI ENTERPRISE | 25-02-2022 | 26-04-2022 | 522
446 | ALIPURDUAR | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | SM/07198 | Retrofitting | SVS | 695/ALD | DILIP MAHATO | 16-09-2020 | 14-01-2021 | 236
447 | ALIPURDUAR | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | SM/07198 | Retrofitting | SVS | 695/ALD | DILIP MAHATO | 16-09-2020 | 14-01-2021
448 | ALIPURDUAR | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | SM/07134 | Retrofitting | SVS | 1166/ALD | AKANSHA COMMERCIAL PRIVATE LTD. | 15-12-2020 | 13-02-2021 | 585
449 | ALIPURDUAR | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | SM/07134 | Retrofitting | SVS | 1165/ALD | TAPAN CHANDA | 15-12-2020 | 13-02-2021 | 540
450 | ALIPURDUAR | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | SM/07124 | Retrofitting | SVS | 1253/ALD | GOUTAM KUMAR DAS | 28-12-2020 | 28-03-2021 | 369
451 | ALIPURDUAR | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | SM/07134 | Retrofitting | SVS | 1132/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 10-12-2020 | 09-01-2021 | 2
452 | ALIPURDUAR | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | SM/07134 | Retrofitting | SVS | 863/ALD | ASHIM KUMAR CHAKRABORTY | 14-10-2020 | 13-11-2020 | 97
453 | ALIPURDUAR | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | SM/07124 | Retrofitting | SVS | 1220/ALD | SREE MAA CONSTRUCTION | 10-08-2022 | 09-10-2022 | 199
454 | ALIPURDUAR | Water Supply Scheme for Salkumarhat Mouza | SM/01803 | SM/08883 | Retrofitting | SVS | 1242/ALD | KAMALESH ROY | 27-09-2021 | 26-11-2021 | 242
455 | ALIPURDUAR | Water Supply Scheme for Salkumarhat Mouza | SM/01803 | SM/08883 | Retrofitting | SVS | 1596/ALD | DEBABRATA DUTTA | 22-11-2021 | 22-12-2021 | 138
456 | ALIPURDUAR | Water Supply Scheme for Salkumarhat Mouza | SM/01803 | SM/08883 | Retrofitting | SVS | 1243/ALD | TAPASH DAS | 27-09-2021 | 26-11-2021 | 243
457 | ALIPURDUAR | Water Supply Scheme for Salkumarhat Mouza | SM/01803 | SM/08883 | Retrofitting | SVS | 1317/ALD | DILIP MAHATO | 05-10-2021 | 04-12-2021 | 598
458 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07128 | Retrofitting | SVS | 2292/ALD | DEBAJYOTI SUTRADHAR | 24-01-2022 | 25-03-2022 | 498
459 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/06652 |  | MVS | 1156/ALD | KAMALESH ROY | 15-12-2020 | 13-02-2021 | 200
460 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/06652 |  | MVS | 1136/ALD | KAMALESH ROY | 10-12-2020 | 09-01-2021
461 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07128 | Retrofitting | SVS | 2143/ALD | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 06-01-2022 | 05-02-2022 | 145
462 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07128 | Retrofitting | SVS | 2142/ALD | DEBAJYOTI SUTRADHAR | 06-01-2022 | 05-02-2022 | 120
463 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07128 | Retrofitting | SVS | 2750/ALD | AMBITIOUS ENTERPRISE | 24-02-2022 | 25-04-2022 | 244
464 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07189 | Retrofitting | MVS | 719/ALD | KAMALESH ROY | 22-09-2020 | 22-10-2020
465 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/06652 |  | MVS | 719/ALD | KAMALESH ROY | 22-09-2020 | 22-10-2020
466 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07189 | Retrofitting | MVS | 1156/ALD | KAMALESH ROY | 15-12-2020 | 13-02-2021 | 421
467 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/07189 | Retrofitting | MVS | 1136/ALD | KAMALESH ROY | 10-12-2020 | 09-01-2021
468 | ALIPURDUAR | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | SM/10676 | Augmentation | MVS | 675/ALD | TAPASH DAS | 06-03-2024 | 04-06-2024 | 111
Total | [10 empty] | 174281