## Issued Work Order (JHARGRAM)
Issued Work Order (JHARGRAM)
Sl. No. | District | Scheme | SM Code | Child SM Code | Scheme Type | Scheme coverage type | Work Order Memo Number | Agency | Work Order Issue Date | Work Order Completion Date | FHTC Provided
1 | JHARGRAM | Alampur Piped Water Supply Scheme | SM/05335 | SM/06831 | Retrofitting | MVS | 1398/MD | ASHIM KUMAR DEY | 26-11-2020 | 25-05-2021 | 639
2 | JHARGRAM | AMLACHATI AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12336 |  | New | MVS | 1415/JHD | M/S. D.K.H.CONSTRUCTION | 22-08-2023 | 20-11-2023 | 391
3 | JHARGRAM | ANANDAPUR AND ADJOINING MOUJAS PWSS | SM/17583 |  | New | MVS | 567/JHD | GOBINDA MAITY | 25-04-2023 | 01-12-2023 | 979
4 | JHARGRAM | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 |  | New | MVS | 567/JHD | GOBINDA MAITY | 25-04-2023 | 01-12-2023 | 948
5 | JHARGRAM | ANKRO AND ADJOINING MOUJAS PWSS | SM/12447 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 45
6 | JHARGRAM | BAHIR GRAM AND ADJOINING MOUJAS PWSS | SM/12441 | SM/17069 | Solarisation | SVS | 1954/JHD | SIBSANKAR CHOWDHURY | 22-11-2023 | 19-07-2024 | 437
7 | JHARGRAM | BAKRA AND ITS ADJOINING MOUJAS PWSS | SM/12390 |  | New | MVS | 443/JHD | GOBINDA MAITY | 23-03-2023 | 29-10-2023 | 1565
8 | JHARGRAM | BALISHIRA AND ADJOINING MOUJAS PWSS | SM/12388 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024
9 | JHARGRAM | BANDARBANI AND ADJONING MOUJAS PWSS | SM/12442 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 742
10 | JHARGRAM | BANKATI AND IT'S ADJOINING MOUJAS | SM/12351 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 753
11 | JHARGRAM | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 |  | New | MVS | 3015/JMD | CONCORD ENGINEERING | 20-10-2023 | 17-02-2024 | 34
12 | JHARGRAM | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 |  | New | MVS | 851/JHD | ASIS KUMAR SARANGI | 08-06-2023 | 05-12-2023 | 932
13 | JHARGRAM | BARASOL AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block. | SM/12324 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
14 | JHARGRAM | BELABERYA WATER SUPPLY SCHEME | SM/00776 | SM/09379 | Augmentation | MVS | 874/MD | SUBRATA DAS | 10-05-2022 | 06-11-2022 | 1212
15 | JHARGRAM | BELDA AND ADJOINING MOUJAS PWSS | SM/12451 |  | New | MVS | 368/JHD | M/S. D.K.H.CONSTRUCTION | 14-03-2023 | 10-09-2023 | 874
16 | JHARGRAM | BELIA AND ADJOINING MOUJAS PWSS | SM/12444 |  | New | MVS | 789/JHD | ASIS KUMAR SARANGI | 31-05-2023 | 27-11-2023 | 782
17 | JHARGRAM | BELPAHARI,SILDA AND ENROUTE VILLAGES WATER SUPPLY SCHEME | SM/00753 | SM/18428 | Augmentation | MVS | 1463/JHD | M/S A.R ENTERPRISE | 31-08-2023 | 27-02-2024 | 3423
18 | JHARGRAM | BHALUKASOL AND ADJOINING MOUJAS PWSS | SM/12391 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024 | 4644
19 | JHARGRAM | BHAMAN SANKRAIL AND ADJOINING MOUJAS PWSS | SM/12352 |  | New | MVS | 567/JHD | GOBINDA MAITY | 25-04-2023 | 01-12-2023 | 1073
20 | JHARGRAM | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 |  | New | MVS | 1865/JHD | R.CONSTRUCTION | 01-11-2023 | 30-01-2024 | 497
21 | JHARGRAM | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 |  | New | MVS | 1994/JHD | J.S.S. ENTERPRISE | 01-12-2023 | 29-02-2024 | 656
22 | JHARGRAM | Birkanar w/s scheme | SM/02707 | SM/09434 | Augmentation | MVS | 202/JSD | DEBASIS DATTA | 04-04-2022 | 25-04-2022 | 18
23 | JHARGRAM | Birkanar w/s scheme | SM/02707 | SM/06828 | Retrofitting | MVS | 1404/MD | DEBASIS DATTA | 26-11-2020 | 25-05-2021 | 81
24 | JHARGRAM | Birkanar w/s scheme | SM/02707 | SM/18012 | Augmentation | MVS | 606/JHD | DHUMKETU ENGINEERING PRIVATE LIMITED | 04-05-2023 | 03-07-2023 | 8
25 | JHARGRAM | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 |  | New | MVS | 1714/JHD | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 29-09-2023 | 27-01-2024 | 3
26 | JHARGRAM | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 |  | New | MVS | 1714/JHD | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 29-09-2023 | 27-01-2024
27 | JHARGRAM | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 |  | New | MVS | 1951/JHD | MONDAL PRECISION PRIVATE LIMITED | 22-11-2023 | 20-02-2024 | 37
28 | JHARGRAM | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 |  | New | MVS | 2303/JMD | CONCORD ENGINEERING | 14-08-2023 | 12-12-2023
29 | JHARGRAM | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 |  | New | MVS | 2304/JMD | CONCORD ENGINEERING | 14-08-2023 | 12-12-2023 | 226
30 | JHARGRAM | CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | SM/18746 |  | New | MVS | 3015/JMD | CONCORD ENGINEERING | 20-10-2023 | 17-02-2024
31 | JHARGRAM | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 |  | New | MVS | 2303/JMD | CONCORD ENGINEERING | 14-08-2023 | 12-12-2023 | 310
32 | JHARGRAM | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 |  | New | MVS | 1657/JHD | MONDAL PRECISION PRIVATE LIMITED | 19-09-2023 | 17-01-2024 | 87
33 | JHARGRAM | CHAMPASOL AND ADJOINING MOUJAS PWSS | SM/12387 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
34 | JHARGRAM | CHANDABILA AND ADJOINING MOPUJAS PWSS | SM/12435 |  | New | MVS | 1138/JHD | ASIS KUMAR SARANGI | 20-07-2023 | 16-01-2024 | 882
35 | JHARGRAM | Chandal Bundh Piped Water Supply Scheme | SM/05474 | SM/06832 | Retrofitting | MVS | 1416/MD | PROVAT KUMAR DE | 26-11-2020 | 25-05-2021 | 25
36 | JHARGRAM | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 |  | New | MVS | 861/JHD | ASIS KUMAR SARANGI | 08-06-2023 | 06-09-2023 | 2221
37 | JHARGRAM | CHENCHUR GERYA AND ADJOINING MOUJAS PWSS | SM/12445 |  | New | MVS | 791/JHD | PROVAT KUMAR DE | 31-05-2023 | 29-08-2023 | 709
38 | JHARGRAM | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | SM/12448 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
39 | JHARGRAM | CHHATINASOL WATER SUPPLY SCHEME | SM/00855 | SM/06830 | Retrofitting | MVS | 1401/MD | CHAKRABORTTI ENTERPRISE | 26-11-2020 | 25-05-2021 | 497
40 | JHARGRAM | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 |  | New | MVS | 2303/JMD | CONCORD ENGINEERING | 14-08-2023 | 12-12-2023 | 119
41 | JHARGRAM | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 |  | New | MVS | 1714/JHD | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 29-09-2023 | 27-01-2024
42 | JHARGRAM | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 |  | New | MVS | 567/JHD | GOBINDA MAITY | 25-04-2023 | 01-12-2023 | 1265
43 | JHARGRAM | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 |  | New | MVS | 3016/JMD | MONDAL PRECISION PRIVATE LIMITED | 20-10-2023 | 17-02-2024 | 343
44 | JHARGRAM | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 |  | New | MVS | 2304/JMD | CONCORD ENGINEERING | 14-08-2023 | 12-12-2023 | 74
45 | JHARGRAM | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 |  | New | MVS | 1209/JHD | SUNIL DULE | 26-07-2023 | 22-01-2024 | 589
46 | JHARGRAM | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 |  | New | MVS | 3016/JMD | MONDAL PRECISION PRIVATE LIMITED | 20-10-2023 | 17-02-2024 | 687
47 | JHARGRAM | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 |  | New | MVS | 1209/JHD | SUNIL DULE | 26-07-2023 | 22-01-2024
48 | JHARGRAM | DOHIJURI WATER SUPPLY SCHEME | SM/00777 | SM/10492 | Augmentation | MVS | 619/JHD | UTTAM KUMAR DAS | 25-11-2022 | 25-12-2022 | 1596
49 | JHARGRAM | DUMRI-NAKRASULI AND ADJOINING MOUJAS PWSS | SM/12359 |  | New | MVS | 444/JHD | MASUM ALI KHAN | 23-03-2023 | 09-10-2023 | 1250
50 | JHARGRAM | GAJPATHAR AND ADJOINING MOUJAS PWSS | SM/17590 |  | New | MVS | 1714/JHD | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 29-09-2023 | 27-01-2024 | 1
51 | JHARGRAM | GHORA PINCHA AND ADJOINING MOJAS PWSS | SM/12408 |  | New | MVS | 1097/JHD | ASIS KUMAR SARANGI | 14-07-2023 | 10-01-2024 | 944
52 | JHARGRAM | GIDIGHATI AND ADJOINING MOUJAS PWSS | SM/17926 |  | New | MVS | 1531/JHD | ASIS KUMAR SARANGI | 06-09-2023 | 04-01-2024 | 287
53 | JHARGRAM | GIDNI WATER SUPPLY SCHEME | SM/00440 | SM/09374 | Augmentation | MVS | 1221/JHD | NRIPENDRA NATH SINGHA | 30-05-2025 | 29-07-2025 | 7
54 | JHARGRAM | GIDNI WATER SUPPLY SCHEME | SM/00440 | SM/09374 | Augmentation | MVS | 432/MD | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 04-03-2022 | 02-06-2022 | 2324
55 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 |  | New | MVS | 1858/JHD | M/S BLUE BIRD | 31-10-2023 | 29-01-2024 | 928
56 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 1005
57 | JHARGRAM | GOBINDAPUR AND ADJOINING MOUJAS PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12329 |  | New | MVS | 443/JHD | GOBINDA MAITY | 23-03-2023 | 29-10-2023 | 815
58 | JHARGRAM | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 |  | New | MVS | 1401/JHD | M/S. D.K.H.CONSTRUCTION | 18-08-2023 | 16-11-2023 | 847
59 | JHARGRAM | GOHALMARA AND ADJOINING MOUJAS PWSS | SM/12340 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
60 | JHARGRAM | GOPIBALLAVPUR WATER SUPPLY SCHEME | SM/00765 | SM/10064 | Augmentation | MVS | 818/MD | GOBINDA MAITY | 29-04-2022 | 26-10-2022 | 4376
61 | JHARGRAM | GRAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/12725 |  | New | MVS | 1130/JHD | ASIS KUMAR SARANGI | 20-07-2023 | 16-01-2024 | 1401
62 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 453/MD | NRIPENDRA NATH SINGHA | 26-02-2021 | 13-03-2021 | 139
63 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/17950 | Augmentation | MVS | 473/JSD | SAURABH KAR | 16-05-2025 | 23-05-2025 | 8
64 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 603/JSD | PROVAT KUMAR DE | 09-02-2021 | 11-03-2021 | 6
65 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1223/MD | RAMENDRA NATH KAR | 29-07-2021 | 13-08-2021 | 179
66 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 621/JSD | S.B. TRADERS | 22-02-2021 | 24-03-2021 | 90
67 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 622/JSD | DHUMKETU ENGINEERING PRIVATE LIMITED | 22-02-2021 | 24-03-2021 | 5
68 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 623/JSD | BISHNU PADA NANDI | 22-02-2021 | 24-03-2021 | 181
69 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 627/JSD | ASSOCIATED ENGINEERS & TRADERS | 22-02-2021 | 24-03-2021 | 87
70 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 452/MD | NIRMAL DUTTA | 26-02-2021 | 13-03-2021 | 92
71 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 384/MD | SUNIL DULE | 25-02-2021 | 12-03-2021 | 125
72 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 385/MD | SUNIL DULE | 25-02-2021 | 12-03-2021 | 124
73 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 386/MD | SUNIL DULE | 25-02-2021 | 12-03-2021 | 96
74 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 388/MD | DEBABRATA DUTTA | 25-02-2021 | 12-03-2021 | 83
75 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1055/MD | ASIS KUMAR SARANGI | 02-07-2021 | 17-07-2021 | 186
76 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1056/MD | ASIS KUMAR SARANGI | 02-07-2021 | 17-07-2021 | 332
77 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 617/JSD | SRIMANTA KUMAR DE | 22-02-2021 | 24-03-2021 | 80
78 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 618/JSD | SRIMANTA KUMAR DE | 22-02-2021 | 24-03-2021 | 90
79 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 619/JSD | SRIMANTA KUMAR DE | 22-02-2021 | 24-03-2021 | 88
80 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 620/JSD | SUNIL DULE | 22-02-2021 | 24-03-2021 | 92
81 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 624/JSD | ASSOCIATED ENGINEERS & TRADERS | 22-02-2021 | 24-03-2021
82 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 625/JSD | THE TILES | 22-02-2021 | 24-03-2021 | 79
83 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 626/JSD | ASSOCIATED ENGINEERS & TRADERS | 22-02-2021 | 24-03-2021 | 92
84 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 628/JSD | ASSOCIATED ENGINEERS & TRADERS | 22-02-2021 | 24-03-2021 | 52
85 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 389/MD | J.S.S. ENTERPRISE | 25-02-2021 | 12-03-2021 | 91
86 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 390/MD | PROVAT KUMAR DE | 25-02-2021 | 12-03-2021 | 23
87 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1057/MD | ASIS KUMAR SARANGI | 02-07-2021 | 17-07-2021 | 63
88 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1064/MD | NIMAI LAL GURIA | 02-07-2021 | 17-07-2021 | 184
89 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 1224/MD | NIRMAL DUTTA | 29-07-2021 | 13-08-2021 | 97
90 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 824/MD | PROVAT KUMAR DE | 03-06-2021 | 18-06-2021 | 10
91 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1286/MD | SUNIL DULE | 09-08-2021 | 24-08-2021 | 126
92 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1286/MD | SUNIL DULE | 09-08-2021 | 24-08-2021 | 22
93 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1377/MD | SAIKAT DANDAPAT | 25-08-2021 | 09-09-2021
94 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 1378/MD | S.B. TRADERS | 25-08-2021 | 09-09-2021 | 143
95 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 1287/MD | GOUTAM PARIA | 09-08-2021 | 24-08-2021
96 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1287/MD | GOUTAM PARIA | 09-08-2021 | 24-08-2021 | 99
97 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1375/MD | A R ENTERPRISE | 25-08-2021 | 09-09-2021 | 95
98 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1212/MD | MAMPI ENTERPRISE | 28-07-2021 | 12-08-2021
99 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 1212/MD | MAMPI ENTERPRISE | 28-07-2021 | 12-08-2021 | 30
100 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 825/MD | PROVAT KUMAR DE | 03-06-2021 | 18-06-2021 | 185
101 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 825/MD | PROVAT KUMAR DE | 03-06-2021 | 18-06-2021
102 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1376/MD | SAIKAT DANDAPAT | 25-08-2021 | 09-09-2021 | 85
103 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 1211/MD | MAMPI ENTERPRISE | 28-07-2021 | 12-08-2021 | 221
104 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 1939/MD | DHUMKETU ENGINEERING PRIVATE LIMITED | 24-11-2021 | 09-12-2021 | 111
105 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 535/MD | RAMENDRA NATH KAR | 22-03-2022 | 06-04-2022 | 78
106 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 507/JSD | MANDAL ENTERPRISE | 13-09-2022 | 04-10-2022 | 24
107 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 1212/MD | MAMPI ENTERPRISE | 28-07-2021 | 12-08-2021 | 68
108 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 |  |  | MVS | 602/JSD | PROVAT KUMAR DE | 09-02-2021 | 11-03-2021 | 1
109 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 376/GPSD | ASHIS SHEE | 03-10-2023 | 23-10-2023 | 4
110 | JHARGRAM | Ground water based mini piped water supply scheme for provision of drinking water at different drought affected areas in 45 Nos. different locations | SM/06462 | SM/08029 | Retrofitting | MVS | 939/JSD | SAURABH KAR | 02-11-2023 | 23-11-2023 | 25
111 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I and Binpur-II in Jhargram District under Jhargram Division, PHE Dte. | SM/11476 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 559
112 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-I in Jhargram District under Jhargram Division, PHE Dte. | SM/11475 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 481
113 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Binpur-II, Gopiballavpur-I, Gopiballavpur-II and Jamboni in Jhargram District under Jhargram Division, PHE Dte. | SM/11477 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 205
114 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jamboni and Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11478 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 303
115 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram and Nayagram in Jhargram District under Jhargram Division, PHE Dte. | SM/11480 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 1057
116 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Jhargram in Jhargram District under Jhargram Division, PHE Dte. | SM/11479 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 831
117 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes (Maximum 100 Household) for Block Nayagram and Sankrail in Jhargram District under Jhargram Division, PHE Dte. | SM/11481 |  | New | MVS | 340/JHD | JHARGRAM SPV PRIVATE LIMITED | 09-03-2023 | 05-09-2023 | 401
118 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 125/JHD | MANDAL ENTERPRISE | 24-01-2024 | 09-03-2024 | 24
119 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 124/JHD | BRAJENDRANATH SENAPATI | 24-01-2024 | 24-03-2024 | 51
120 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 336/JHD | A R ENTERPRISE | 28-02-2024 | 29-03-2024 | 18
121 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 913/JHD | SAIKAT DANDAPAT | 08-07-2024 | 06-09-2024
122 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 3054/JHD | SUBHRANIL DAS | 20-12-2023 | 03-02-2024 | 14
123 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 44/JHD | M/S MILAN DATTA | 09-01-2024 | 08-02-2024 | 1
124 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 3105/JHD | DEBDATTA MANNA | 29-12-2023 | 28-01-2024 | 16
125 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 99/JHD | GANDHI MAHATA | 18-01-2024 | 17-02-2024 | 18
126 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 100/JHD | DIPAK ENTERPRISE | 18-01-2024 | 17-02-2024 | 15
127 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 81/JHD | SUBHAMAY DANDAPAT | 16-01-2024 | 15-02-2024 | 1
128 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1845/JHD | NIRMAL DUTTA | 31-10-2023 | 15-12-2023
129 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1853/JHD | NRIPENDRA NATH SINGHA | 31-10-2023 | 15-12-2023
130 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1718/JHD | SHIBAM ENTERPRIZES | 29-09-2023 | 28-11-2023 | 96
131 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1673/JHD | SANTOSH GHOSH | 21-09-2023 | 21-10-2023 | 19
132 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1667/JHD | M/S ANKITA CONSTRUCTION | 21-09-2023 | 21-10-2023 | 3
133 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1672/JHD | SAMIR PATRA | 21-09-2023 | 21-10-2023 | 7
134 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1675/JHD | ASHIS SHEE | 21-09-2023 | 21-10-2023 | 14
135 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1666/JHD | SAMIR PATRA | 21-09-2023 | 21-10-2023 | 9
136 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 1654/JHD | ENVOTECH INFRA SOLUTION | 15-09-2023 | 14-11-2023 | 48
137 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 154/JHD | KALYAN ADHIKARI | 30-01-2024 | 29-02-2024 | 12
138 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 101/JHD | BHOWMIK CONSTRUCTION | 18-01-2024 | 17-02-2024
139 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 438/JHD | S.R. ENTERPRISE | 14-03-2024 | 13-04-2024 | 19
140 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 436/JHD | TAPAS PAL | 14-03-2024 | 28-04-2024 | 20
141 | JHARGRAM | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 |  | New | MVS | 80/JHD | SAURABH KAR | 16-01-2024 | 15-02-2024 | 7
142 | JHARGRAM | Ground Water Based Piped Water Supply Scheme for Daha Munda (Nania Bad) | SM/04914 |  |  | MVS | 1281/MD | DIPAK KUMAR BAKLY | 16-10-2020 | 14-04-2021 | 2
143 | JHARGRAM | Ground Water Based Piped Water Supply Scheme for Daha Munda (Nania Bad) | SM/04914 |  |  | MVS | 1281/MD | DIPAK KUMAR BAKLY | 16-10-2020 | 14-04-2021 | 5
144 | JHARGRAM | Ground Water Based Piped Water Supply Scheme for Dhamro & its adj. mouzas | SM/04659 | SM/17959 | Augmentation | MVS | 1096/JHD | SAIKAT DANDAPAT | 14-07-2023 | 28-08-2023 | 131
145 | JHARGRAM | Ground Water Based Piped Water Supply Scheme for Dhamro & its adj. mouzas | SM/04659 |  |  | MVS | 1690/MD | SAIKAT DANDAPAT | 30-09-2021 | 15-10-2021 | 570
146 | JHARGRAM | Ground Water Based Piped Water Supply Scheme for Jhitka & its adj. mouzas | SM/04637 | SM/06828 | Retrofitting | MVS | 1582/MD | RAMENDRA NATH KAR | 11-12-2020 | 09-06-2021 | 78
147 | JHARGRAM | Ground water based piped water supply scheme for Sonarimara | SM/04956 |  |  | MVS | 1420/MD | BISHNU PADA NANDI | 26-11-2020 | 25-05-2021 | 1
148 | JHARGRAM | Ground water based piped water supply scheme for Sonarimara | SM/04956 |  |  | MVS | 448/MD. | BISHNU PADA NANDI | 26-02-2021 | 13-03-2021
149 | JHARGRAM | Ground water based piped water supply scheme for Sonarimara | SM/04956 |  |  | MVS | 1420/MD | BISHNU PADA NANDI | 26-11-2020 | 25-05-2021
150 | JHARGRAM | Ground water based piped water supply scheme for Sonarimara | SM/04956 |  |  | MVS | 885/JHD | SUTANU DE | 08-06-2023 | 07-08-2023 | 135
151 | JHARGRAM | HARDA AND ADJOINING MOUJAS PWSS | SM/12436 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 2072
152 | JHARGRAM | HARIPURBIRUA AND AJOINING MOUJAS PWSS | SM/12409 |  | New | MVS | 443/JHD | GOBINDA MAITY | 23-03-2023 | 29-10-2023 | 2146
153 | JHARGRAM | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 |  | New | MVS | 3015/JMD | CONCORD ENGINEERING | 20-10-2023 | 17-02-2024 | 431
154 | JHARGRAM | JAKUA AND ADJOINING MOUJAS PWSS | SM/12344 |  | New | MVS | 444/JHD | MASUM ALI KHAN | 23-03-2023 | 09-10-2023 | 432
155 | JHARGRAM | JANGALKHAS AND ADJOINING MOUJAS PWSS | SM/12775 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 904
156 | JHARGRAM | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 |  | New | MVS | 1657/JHD | MONDAL PRECISION PRIVATE LIMITED | 19-09-2023 | 17-01-2024 | 148
157 | JHARGRAM | KANKRIDAHI AND ADJOINING MOUJAS PWSS at Gopiballavpur I Block under Jhargram Division P.H.E. Dte. | SM/12330 |  | New | MVS | 1129/JHD | ASIS KUMAR SARANGI | 20-07-2023 | 16-01-2024 | 847
158 | JHARGRAM | Kantapahari w/s scheme | SM/02705 | SM/06828 | Retrofitting | MVS | 1405/MD | S.T. ENTERPRISE | 26-11-2020 | 25-05-2021
159 | JHARGRAM | Kantapahari w/s scheme | SM/02705 | SM/18002 | Augmentation | MVS | 652/JSD | SAMIR PATRA | 18-07-2023 | 17-08-2023 | 80
160 | JHARGRAM | Kantapahari w/s scheme | SM/02705 | SM/18002 | Augmentation | MVS | 671/JSD | GOURMOHAN DAS | 25-07-2023 | 24-08-2023 | 70
161 | JHARGRAM | KARKATASOL AND IT'S ADJOINING MOUJAS PWSS | SM/12524 |  | New | MVS | 443/JHD | GOBINDA MAITY | 23-03-2023 | 29-10-2023 | 1094
162 | JHARGRAM | KHAMARPARA AND ADJOINING MOUJAS PWSS | SM/12446 |  | New | MVS | 1207/JHD | SUNIL DULE | 26-07-2023 | 22-01-2024 | 893
163 | JHARGRAM | KHARIYARATA AND ADJOINING MOUJAS PWSS | SM/17592 |  | New | MVS | 1657/JHD | MONDAL PRECISION PRIVATE LIMITED | 19-09-2023 | 17-01-2024 | 353
164 | JHARGRAM | Khasjangal w/s scheme | SM/02706 | SM/06828 | Retrofitting | MVS | 1406/MD | SAIKAT DANDAPAT | 26-11-2020 | 25-05-2021 | 8
165 | JHARGRAM | Kuldiha Piped Water Supply Scheme. | SM/06540 | SM/09386 | Retrofitting | MVS | 225/JHD | GOBINDA MAITY | 16-02-2023 | 02-04-2023 | 438
166 | JHARGRAM | KULTIKRI WATER SUPPLY SCHEME | SM/01103 | SM/10491 | Augmentation | MVS | 373/JHD | SIBSANKAR CHOWDHURY | 18-10-2022 | 16-04-2023 | 1599
167 | JHARGRAM | Lakat w/s scheme | SM/02708 | SM/06828 | Retrofitting | MVS | 1583/MD | S.B. TRADERS | 11-12-2020 | 09-06-2021 | 2
168 | JHARGRAM | LALGARH WATER SUPPLY SCHEME | SM/00434 | SM/09373 | Augmentation | MVS | 875/MD | DULAL CHANDRA DAS | 10-05-2022 | 06-11-2022 | 1930
169 | JHARGRAM | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
170 | JHARGRAM | Manikpara W/s Scheme | SM/02015 | SM/10490 | Augmentation | MVS | 444/JHD | KOUSIK MONDAL | 14-03-2024 | 29-03-2024 | 312
171 | JHARGRAM | Manikpara W/s Scheme | SM/02015 | SM/10490 | Augmentation | MVS | 252/JHD | DIPAK KUMAR BAKLY | 06-09-2022 | 05-03-2023 | 1628
172 | JHARGRAM | Manikpara W/s Scheme | SM/02015 | SM/10490 | Augmentation | MVS | 332/JHD | DIPAK KUMAR BAKLY | 28-02-2024 | 14-03-2024 | 243
173 | JHARGRAM | METIAL AND ADJOINING MOUJAS PWSS | SM/12437 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
174 | JHARGRAM | MURABANI AND ADJOINING MOUJAS PWSS | SM/12440 |  | New | MVS | 1095/JHD | SAIKAT DANDAPAT | 14-07-2023 | 12-10-2023 | 455
175 | JHARGRAM | MURAKATI AND ADJOINING MOUJAS PWSS | SM/12339 | SM/17119 | Solarisation | SVS | 1954/JHD | SIBSANKAR CHOWDHURY | 22-11-2023 | 19-07-2024 | 492
176 | JHARGRAM | Naupara and adj. mouzas Water Supply Scheme | SM/02972 | SM/06831 | Retrofitting | MVS | 1412/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 18
177 | JHARGRAM | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 1564
178 | JHARGRAM | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 |  | New | MVS | 607/JHD | GOBINDA MAITY | 04-05-2023 | 10-12-2023 | 807
179 | JHARGRAM | ODALCHUHA WATER SUPPLY SCHEME | SM/00801 | SM/09375 | Augmentation | MVS | 177/MD | PROVAT KUMAR DE | 01-02-2022 | 18-03-2022 | 358
180 | JHARGRAM | PAKURIA WATER SUPPLY SCHEME | SM/00760 | SM/09377 | Augmentation | MVS | 179/MD | ASHIM KUMAR DEY | 01-02-2022 | 02-04-2022 | 512
181 | JHARGRAM | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 |  | New | MVS | 240/JHD | SUNIL DULE | 17-02-2023 | 16-08-2023 | 653
182 | JHARGRAM | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 |  | New | MVS | 883/JHD | PALCON | 08-06-2023 | 06-09-2023 | 70
183 | JHARGRAM | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 |  | New | MVS | 1325/JHD | DIVINE | 10-08-2023 | 08-11-2023 | 335
184 | JHARGRAM | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 |  | New | MVS | 646/JHD | SUNIL DULE | 11-05-2023 | 09-08-2023 | 390
185 | JHARGRAM | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 |  | New | MVS | 346/JHD | ASIS KUMAR SARANGI | 10-03-2023 | 06-09-2023 | 947
186 | JHARGRAM | PATHARNALA AND ADJOINING MOUJAS PWSS | SM/12527 |  | New | MVS | 371/JHD | SUNIL DULE | 14-03-2023 | 10-09-2023 | 972
187 | JHARGRAM | Piped Water Supply Scheme for Aulia Mouza | SM/03853 | SM/06829 | Retrofitting | MVS | 1410/MD | GOUTAM PARIA | 26-11-2020 | 25-05-2021
188 | JHARGRAM | Piped Water Supply Scheme for Bahadurpur Mouza | SM/03480 | SM/08173 | Retrofitting | SVS | 629/JSD | MA LAXMI ENTERPRISE | 22-02-2021 | 24-03-2021
189 | JHARGRAM | Piped Water Supply Scheme for Baliband Mouza | SM/03462 | SM/06832 | Retrofitting | MVS | 1589/MD | NIRMAL DUTTA | 11-12-2020 | 09-06-2021
190 | JHARGRAM | Piped Water Supply Scheme for Baliband Mouza | SM/03462 | SM/09385 | Retrofitting | MVS | 288/MD | NRIPENDRA NATH SINGHA | 15-02-2022 | 01-04-2022 | 154
191 | JHARGRAM | Piped Water Supply Scheme for Banshia Mouza | SM/03455 | SM/06830 | Retrofitting | MVS | 1411/MD | BISHNU PADA NANDI | 26-11-2020 | 25-05-2021
192 | JHARGRAM | Piped Water Supply Scheme for Banspahari mouza | SM/03815 | SM/09381 | Augmentation | SVS | 616/MD | SUNIL DULE | 04-04-2022 | 25-04-2022 | 103
193 | JHARGRAM | Piped Water Supply Scheme for Banspahari mouza | SM/03815 | SM/06829 | Retrofitting | MVS | 1409/MD | S.N ENTERPRISE | 26-11-2020 | 25-05-2021 | 6
194 | JHARGRAM | Piped Water Supply Scheme for Barabaria Mouza | SM/03456 | SM/07875 | Retrofitting | MVS | 587/JSD | BISHNU PADA NANDI | 01-02-2021 | 16-02-2021
195 | JHARGRAM | Piped Water Supply Scheme for Barajharia Mouza | SM/03458 | SM/06832 | Retrofitting | MVS | 1417/MD | PROVAT KUMAR DE | 26-11-2020 | 25-05-2021 | 19
196 | JHARGRAM | Piped Water Supply Scheme for Baratilaboni Mouza | SM/03472 | SM/07875 | Retrofitting | MVS | 580/JSD | J.S.S. ENTERPRISE | 01-02-2021 | 11-02-2021 | 1
197 | JHARGRAM | Piped Water Supply Scheme for Bhanga Bandh mouza | SM/03814 |  |  | MVS | 381/MD | SAIKAT DANDAPAT | 25-02-2021 | 12-03-2021 | 23
198 | JHARGRAM | Piped Water Supply Scheme for Bhangadali Mouza | SM/03464 | SM/07875 | Retrofitting | MVS | 581/JSD | SUNIL DULE | 01-02-2021 | 16-02-2021
199 | JHARGRAM | Piped Water Supply Scheme for Bhera Mouza | SM/03473 | SM/07875 | Retrofitting | MVS | 583/JSD | NIRMAL DUTTA | 01-02-2021 | 16-02-2021 | 35
200 | JHARGRAM | Piped Water Supply Scheme for Chhenpara Mouza | SM/03485 | SM/06832 | Retrofitting | MVS | 1588/MD | NRIPENDRA NATH SINGHA | 11-12-2020 | 09-06-2021 | 5
201 | JHARGRAM | Piped Water Supply Scheme for Chichira Mouza | SM/03459 | SM/09882 | Augmentation | SVS | 261/JRWS | SAUBHIK KUMAR NAG | 07-08-2024 | 06-10-2024 | 38
202 | JHARGRAM | Piped Water Supply Scheme for Chichira Mouza | SM/03459 | SM/06830 | Retrofitting | MVS | 1581/MD | SUNIL DULE | 11-12-2020 | 09-06-2021 | 400
203 | JHARGRAM | Piped Water Supply Scheme for Domsole mouza | SM/03817 | SM/13678 | Augmentation | MVS | 647/JHD | DEBASISH DOGRA | 01-12-2022 | 22-12-2022 | 144
204 | JHARGRAM | Piped Water Supply Scheme for Jamboni Mouza | SM/03457 | SM/06832 | Retrofitting | MVS | 1418/MD | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 26-11-2020 | 25-05-2021 | 10
205 | JHARGRAM | Piped Water Supply Scheme for Junsola Mouza | SM/03468 | SM/06831 | Retrofitting | MVS | 1413/MD | SATYA RANJAN DAS | 26-11-2020 | 25-05-2021 | 17
206 | JHARGRAM | Piped Water Supply Scheme for Junsola Mouza | SM/03468 | SM/18190 | Augmentation | SVS | 649/JSD | S.R. ENTERPRISE | 14-07-2023 | 13-08-2023 | 77
207 | JHARGRAM | Piped Water Supply Scheme for Kapgari Mouza | SM/03490 | SM/06832 | Retrofitting | MVS | 1415/MD | EVEREST CONSULTANT SERVICES | 26-11-2020 | 25-05-2021
208 | JHARGRAM | Piped Water Supply Scheme for Kechenda Mouza | SM/03467 |  |  | MVS | 424/JSD | J.S.S. ENTERPRISE | 30-12-2021 | 29-01-2022 | 63
209 | JHARGRAM | Piped Water Supply Scheme for Kechenda Mouza | SM/03467 | SM/06828 | Retrofitting | MVS | 1598/MD | DEBABRATA DUTTA | 14-12-2020 | 12-06-2021
210 | JHARGRAM | Piped Water Supply Scheme for Khamar mouza | SM/03816 | SM/09382 | Augmentation | SVS | 612/MD | M/S. SANKAR KUMAR NAG | 04-04-2022 | 25-04-2022 | 194
211 | JHARGRAM | Piped Water Supply Scheme for Khasjungle Mouza | SM/03474 |  |  | MVS | 1407/MD | M/S. SOMNATH | 26-11-2020 | 25-05-2021 | 66
212 | JHARGRAM | Piped Water Supply Scheme for Khasjungle Mouza | SM/03474 |  |  | MVS | 1407/MD | M/S. SOMNATH | 26-11-2020 | 25-05-2021 | 87
213 | JHARGRAM | Piped Water Supply Scheme for Khasjungle Mouza | SM/03474 | SM/06829 | Retrofitting | MVS | 1407/MD | M/S. SOMNATH | 26-11-2020 | 25-05-2021 | 14
214 | JHARGRAM | Piped Water Supply Scheme for Laudaha Mouza | SM/03465 |  |  | MVS | 1535/MD | S.T. ENTERPRISE | 13-09-2021 | 28-09-2021 | 6
215 | JHARGRAM | Piped Water Supply Scheme for Laudaha Mouza | SM/03465 | SM/08734 | Retrofitting | SVS | 1535/MD | S.T. ENTERPRISE | 13-09-2021 | 28-09-2021 | 540
216 | JHARGRAM | Piped Water Supply Scheme for Loagan Mouza | SM/03484 | SM/07875 | Retrofitting | MVS | 582/JSD | J.S.S. ENTERPRISE | 01-02-2021 | 03-03-2021
217 | JHARGRAM | Piped Water Supply Scheme for Lohamelya Mouza | SM/03479 |  |  | MVS | 1059/MD | NIMAI LAL GURIA | 02-07-2021 | 17-07-2021 | 157
218 | JHARGRAM | Piped Water Supply Scheme for Lohamelya Mouza | SM/03479 | SM/06832 | Retrofitting | MVS | 1414/MD | NIMAI LAL GURIA | 26-11-2020 | 25-05-2021
219 | JHARGRAM | Piped Water Supply Scheme for Lohamelya Mouza | SM/03479 |  |  | MVS | 1414/MD | NIMAI LAL GURIA | 26-11-2020 | 25-05-2021
220 | JHARGRAM | Piped Water Supply Scheme for Nakrasuli Mouza | SM/03482 | SM/06833 | Retrofitting | MVS | 1419/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 2
221 | JHARGRAM | Piped Water Supply Scheme for Netai & its Adjoining Mouzas | SM/03745 | SM/06829 | Retrofitting | MVS | 1584/MD | BIDYUT KUMAR SANTRA | 11-12-2020 | 09-06-2021 | 301
222 | JHARGRAM | Piped Water Supply Scheme for Pathardhara Mouza | SM/03488 | SM/07875 | Retrofitting | MVS | 588/JSD | DHUMKETU ENGINEERING PRIVATE LIMITED | 01-02-2021 | 16-02-2021 | 39
223 | JHARGRAM | Piped Water Supply Scheme for Pathardhara Mouza | SM/03488 |  |  | MVS | 588/JSD | DHUMKETU ENGINEERING PRIVATE LIMITED | 01-02-2021 | 16-02-2021 | 6
224 | JHARGRAM | Piped Water Supply Scheme for Pathardhara Mouza | SM/03488 | SM/10439 | Retrofitting | MVS | 201/JSD | DHUMKETU ENGINEERING PRIVATE LIMITED | 04-04-2022 | 25-04-2022 | 88
225 | JHARGRAM | Piped Water Supply Scheme for Pitanow Mouza | SM/03466 | SM/07875 | Retrofitting | MVS | 869/MD | AJITESH ACHARJEE | 10-05-2022 | 25-05-2022 | 111
226 | JHARGRAM | Piped Water Supply Scheme for Ragra Mouza | SM/03666 | SM/06833 | Retrofitting | MVS | 1402/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 39
227 | JHARGRAM | Piped Water Supply Scheme for Sankrail Mouza | SM/03475 |  |  | MVS | 878/MD | PULLOCK KUMAR GHOSH | 08-06-2021 | 23-06-2021 | 64
228 | JHARGRAM | Piped Water Supply Scheme for Sankrail Mouza | SM/03475 |  |  | MVS | 878/MD | PULLOCK KUMAR GHOSH | 08-06-2021 | 23-06-2021 | 50
229 | JHARGRAM | Piped Water Supply Scheme for Sasarah Mouza | SM/03469 |  |  | MVS | 1606/MD | SUNIL DULE | 17-09-2021 | 08-10-2021 | 854
230 | JHARGRAM | Piped Water Supply Scheme for Simulpal Mouza | SM/03478 | SM/06829 | Retrofitting | MVS | 1408/MD | GOUTAM RAY | 26-11-2020 | 25-05-2021 | 4
231 | JHARGRAM | PITHAPURA AND ADJOINING MOUJAS PWSS | SM/12355 | SM/18026 | Solarisation | SVS | 1564/JHD | I R CONSTRUCTION | 07-09-2023 | 06-12-2023 | 747
232 | JHARGRAM | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 |  | New | MVS | 858/JHD | SUNIL DULE | 08-06-2023 | 06-09-2023 | 1472
233 | JHARGRAM | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 1023
234 | JHARGRAM | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 |  | New | MVS | 1531/JHD | ASIS KUMAR SARANGI | 06-09-2023 | 04-01-2024 | 396
235 | JHARGRAM | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 |  | New | MVS | 607/JHD | GOBINDA MAITY | 04-05-2023 | 10-12-2023 | 1326
236 | JHARGRAM | Rain Water Harvesting Pond Based Piped Water Supply Scheme for Barasukjora & its adjoining mouzas | SM/03770 | SM/06835 | Retrofitting | MVS | 1400/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 608
237 | JHARGRAM | Rain Water Harvesting Pond Based Piped Water Supply Scheme for Barasukjora & its adjoining mouzas | SM/03770 | SM/06835 | Retrofitting | MVS | 1400/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 27
238 | JHARGRAM | Rain Water Harvesting Pond Based Piped Water Supply Scheme for Barasukjora & its adjoining mouzas | SM/03770 | SM/06834 | Retrofitting | MVS | 1077/JSD | SAIKAT DANDAPAT | 27-11-2024 | 11-12-2024 | 11
239 | JHARGRAM | Rain Water Harvesting Pond Based Piped Water Supply Scheme for Barasukjora & its adjoining mouzas | SM/03770 | SM/06834 | Retrofitting | MVS | 1399/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 275
240 | JHARGRAM | Rain Water Harvesting Pond Based Piped Water Supply Scheme for Barasukjora & its adjoining mouzas | SM/03770 | SM/06834 | Retrofitting | MVS | 1399/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 111
241 | JHARGRAM | Rain Water Harvesting Pond Based Piped Water Supply Scheme for Barasukjora & its adjoining mouzas | SM/03770 | SM/06834 | Retrofitting | MVS | 1076/JSD | SAIKAT DANDAPAT | 27-11-2024 | 11-12-2024 | 11
242 | JHARGRAM | Ramgarh w/s scheme | SM/02703 | SM/06827 | Retrofitting | MVS | 1403/MD | ASIS KUMAR SARANGI | 26-11-2020 | 25-05-2021 | 285
243 | JHARGRAM | Ramgarh w/s scheme | SM/02703 | SM/18014 | Augmentation | MVS | 647/JHD | SUNIL DULE | 11-05-2023 | 09-08-2023 | 13
244 | JHARGRAM | RAMPURA AND ADJOINING MOUJAS | SM/12880 |  | New | MVS | 607/JHD | GOBINDA MAITY | 04-05-2023 | 10-12-2023
245 | JHARGRAM | Rantua and adj. mouzas water supply scheme | SM/02971 | SM/09383 | Augmentation | MVS | 137/MD | SUNIL DULE | 27-01-2022 | 28-03-2022 | 2247
246 | JHARGRAM | RAUTARAPUR AND ADJOINING MOUJAS PWSS at Jhargram Block under Jhargram Division P.H.E. Dte. | SM/12333 |  | New | MVS | 1499/JHD | MONDAL ENTERPRISE | 05-09-2023 | 04-12-2023 | 963
247 | JHARGRAM | ROHINI RURAL PIPED WATER SUPPLY SCHEME | SM/01135 |  |  | MVS | 1526/MD | ASIS KUMAR SARANGI | 10-09-2021 | 09-11-2021 | 1935
248 | JHARGRAM | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 |  | New | MVS | 1110/JHD | M/S BLUE BIRD | 18-07-2023 | 16-10-2023 | 321
249 | JHARGRAM | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 |  | New | MVS | 1321/JHD | DHUMKETU ENGINEERING PRIVATE LIMITED | 10-08-2023 | 08-11-2023 | 475
250 | JHARGRAM | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 |  | New | MVS | 1111/JHD | A.R. ENTERPRISE | 18-07-2023 | 16-10-2023 | 416
251 | JHARGRAM | Satkuli Charar And It's Adjoining Moujas PWSS at Sankrail Block under Jhargram Division P.H.E. Dte. | SM/12334 |  | New | MVS | 607/JHD | GOBINDA MAITY | 04-05-2023 | 10-12-2023 | 436
252 | JHARGRAM | SHALUKA AND ADJOINING MOUJAS PWSS | SM/12520 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 650
253 | JHARGRAM | SHIYARBINDA AND ADJOINING MOUJAS PWSS | SM/17591 |  | New | MVS | 1531/JHD | ASIS KUMAR SARANGI | 06-09-2023 | 04-01-2024 | 218
254 | JHARGRAM | SIJUA AND ADJOINING MOUJAS PWSS | SM/12519 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 440
255 | JHARGRAM | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 2
256 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 345/JHD | NIMAI LAL GURIA | 28-09-2022 | 26-01-2023 | 106
257 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 618/JHD | DEBABRATA DUTTA | 25-11-2022 | 25-03-2023 | 37
258 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 346/JHD | BISHNU PADA NANDI | 28-09-2022 | 26-01-2023 | 81
259 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 876/MD | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 10-05-2022 | 06-11-2022 | 542
260 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 284/MD | SRIMANTA KUMAR DE | 15-02-2022 | 14-08-2022 | 346
261 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 347/JHD | M/S. SANKAR KUMAR NAG | 28-09-2022 | 26-01-2023 | 87
262 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 877/MD | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 10-05-2022 | 06-11-2022 | 613
263 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 455/JHD | ASSOCIATED ENGINEERS & TRADERS | 11-11-2022 | 11-03-2023 | 105
264 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 283/MD | M/S. D.K.H.CONSTRUCTION | 15-02-2022 | 14-08-2022 | 431
265 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 185/MD | GOBINDA MAITY | 01-02-2022 | 31-07-2022 | 378
266 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 189/MD | PROVAT KUMAR DE | 01-02-2022 | 31-07-2022 | 574
267 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 190/MD | SUJATA CONSTRUCTION | 01-02-2022 | 31-07-2022 | 282
268 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 172/MD | DIPAK KUMAR BAKLY | 01-02-2022 | 31-07-2022 | 520
269 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 186/MD | GOBINDA MAITY | 01-02-2022 | 31-07-2022 | 440
270 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 187/MD | GOBINDA MAITY | 01-02-2022 | 31-07-2022 | 672
271 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 193/MD | DIPAK KUMAR BAKLY | 01-02-2022 | 31-07-2022 | 455
272 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 196/MD | SUNIL DULE | 01-02-2022 | 31-07-2022 | 680
273 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 425/MD | RELIABLE SANITARY & PLUMBING CO. | 04-03-2022 | 31-08-2022
274 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 154/JSD | MANISHIKA CONSTRUCTION | 27-02-2024 | 05-03-2024
275 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 155/JSD | MANISHIKA CONSTRUCTION | 27-02-2024 | 05-03-2024
276 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 617/JHD | J.S.S. ENTERPRISE | 25-11-2022 | 25-03-2023 | 37
277 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 1988/JHD | ASHIS SHEE | 29-11-2023 | 29-12-2023 | 22
278 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 301/MD | ASIS KUMAR SARANGI | 15-02-2022 | 14-08-2022 | 1186
279 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 1333/JHD | BISHNU PADA NANDI | 10-08-2023 | 09-10-2023 | 104
280 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 1205/JHD | MANISHIKA CONSTRUCTION | 26-07-2023 | 24-09-2023 | 143
281 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 868/MD | SUBRATA DAS | 10-05-2022 | 06-11-2022 | 275
282 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 428/MD | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 04-03-2022 | 31-08-2022 | 292
283 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 431/MD | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 04-03-2022 | 31-08-2022 | 1
284 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 429/MD | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 04-03-2022 | 31-08-2022 | 172
285 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 430/MD | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 04-03-2022 | 31-08-2022 | 291
286 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 426/MD | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 04-03-2022 | 31-08-2022 | 217
287 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 427/MD | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 04-03-2022 | 31-08-2022 | 334
288 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 220/MD | CARBON SERVICES INDIA | 03-02-2022 | 02-08-2022 | 597
289 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 303/MD | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 15-02-2022 | 14-08-2022 | 255
290 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 198/MD | FIDERE MARINE SERVICES PVT. LTD. | 01-02-2022 | 31-07-2022 | 123
291 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 199/MD | FIDERE MARINE SERVICES PVT. LTD. | 01-02-2022 | 31-07-2022 | 532
292 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 194/MD | PALCON | 01-02-2022 | 31-07-2022 | 303
293 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 291/MD | NIRMAL DUTTA | 15-02-2022 | 14-08-2022 | 499
294 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 191/MD | FIDERE MARINE SERVICES PVT. LTD. | 01-02-2022 | 31-07-2022 | 305
295 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 216/MD | MAHAVIR PUMPS MFG. PVT. LTD. | 03-02-2022 | 02-08-2022 | 289
296 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 292/MD | BIDYUT KUMAR SANTRA | 15-02-2022 | 14-08-2022 | 496
297 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 217/MD | MAHAVIR PUMPS MFG. PVT. LTD. | 03-02-2022 | 02-08-2022 | 235
298 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 1013/MD | MONDAL PRECISION PRIVATE LIMITED | 27-05-2022 | 23-11-2022 | 240
299 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 1014/MD | MONDAL PRECISION PRIVATE LIMITED | 27-05-2022 | 23-11-2022 | 573
300 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 1015/MD | MONDAL PRECISION PRIVATE LIMITED | 27-05-2022 | 23-11-2022 | 599
301 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 197/MD | MAHAVIR PUMPS MFG. PVT. LTD. | 01-02-2022 | 31-07-2022 | 105
302 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 424/MD | MIDNAPUR PIPE CONCERN | 04-03-2022 | 31-08-2022 | 555
303 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 299/MD | SAIKAT DANDAPAT | 15-02-2022 | 14-08-2022 | 378
304 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 219/MD | SANYUKTA ENGINEERING PVT. LTD. | 03-02-2022 | 02-08-2022 | 282
305 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 305/MD | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 16-02-2022 | 15-08-2022 | 352
306 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 302/MD | LALIT BIHARI MAITY | 15-02-2022 | 14-08-2022 | 601
307 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 188/MD | SUNIL DULE | 01-02-2022 | 31-07-2022 | 380
308 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 276/JHD | DHUMKETU ENGINEERING PRIVATE LIMITED | 13-09-2022 | 11-01-2023 | 81
309 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 320/JHD | RAMENDRA NATH KAR | 21-09-2022 | 19-01-2023 | 83
310 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 218/MD | MAHAVIR PUMPS MFG. PVT. LTD. | 03-02-2022 | 02-08-2022 | 613
311 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 195/MD | KISHORE GHOSH | 28-12-2022 | 26-06-2023 | 618
312 | JHARGRAM | Stand Alone Units for Drought Like Situation Prone 8 Blocks of Jhargram District (Model Stand Alone Grid Power Operated Water Supply System for Habitations / Mouzas with 400 & More Population) under Mid-Term Plan of Master Plan. | SM/09915 |  | New | MVS | 874/MD | SUBRATA DAS | 10-05-2022 | 06-11-2022
313 | JHARGRAM | Sub-Surface Water Based Piped Water Supply Scheme for Nayagram Block (Part) | SM/05634 | SM/09384 | Retrofitting | MVS | 337/JHD | GOBINDA MAITY | 26-09-2022 | 25-11-2022 | 2531
314 | JHARGRAM | Sub-Surface Water Based Piped Water Supply Scheme for Nayagram Block (Part) | SM/05634 | SM/09384 | Retrofitting | MVS | 805/MD | GOBINDA MAITY | 28-04-2022 | 25-10-2022 | 40
315 | JHARGRAM | Sub-Surface Water Based Piped Water Supply Scheme for Nayagram Block (Part) | SM/05634 | SM/09384 | Retrofitting | MVS | 1871/JHD | GOBINDA MAITY | 01-11-2023 | 16-12-2023 | 648
316 | JHARGRAM | SUMITRAPUR AND ADJOINING MOJAS PWSS | SM/12528 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024 | 71
317 | JHARGRAM | TALPUKHURIA AND IT'S ADJOINING MOUJAS PWSS | SM/17932 |  | New | MVS | 1531/JHD | ASIS KUMAR SARANGI | 06-09-2023 | 04-01-2024 | 516
318 | JHARGRAM | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12449 |  | New | MVS | 1207/JHD | SUNIL DULE | 26-07-2023 | 22-01-2024
319 | JHARGRAM | THAKURPARA AND ADJOINING MOUJAS PWSS | SM/12453 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 1887
320 | JHARGRAM | TIAKITPUR ANAD AJOINING MOUJAS PWSS | SM/12349 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
321 | JHARGRAM | TILABANI AND ADJOINING MOUJAS PWSS | SM/12530 |  | New | MVS | 1113/JHD | M/S SWACH ENVIRONMENT PRIVATE LTD. | 18-07-2023 | 24-03-2024 | 1286
322 | JHARGRAM | TULIBAR AND ADJOINING MOUZAS PWSS | SM/17570 |  | New | MVS | 1138/JHD | ASIS KUMAR SARANGI | 20-07-2023 | 16-01-2024 | 770
323 | JHARGRAM | UPAR BAGHUASOL AND IT'S ADJOINING MOJAS PWSS | SM/12845 |  | New | MVS | 1727/JHD | ADITYA ARAV DEV CONS CO. PVT. LTD. | 30-09-2023 | 26-07-2024
324 | JHARGRAM | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 |  | New | MVS | 372/JHD | SUNIL DULE | 14-03-2023 | 10-09-2023 | 1271
Total | [10 empty] | 122715