## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dakshin Altagram Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | 51/JD | 08/01/2021 |  | UMWELT ENGINEER PRIVATE LIMITED | 38.7 | 33.23 | 1
2 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Maynatali Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | 310/JD | 26/02/2021 |  | Sanjit Saha | 22.93 | 0 | 1
3 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Paschim Mullickpara Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | 41/JD | 06/01/2021 |  | Balaji Uddyog | 36.46 | 15.26 | 1
4 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | SM/07303 | Retrofitting | Construction of Drain, Plinth Protection, Guard wall including Land Development at H/W site and stand posts for samsing T.G W/S/S under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | 1009/W/JSSD | 10/01/2022 |  | Subir Ghosh | 4.65 | 0 | 1
5 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHALAUNI T.G. Area piped Water Supply Scheme at Metiali Block under Jalpaiguri Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | 1092/JD | 15/10/2020 |  | BILTU DAS | 32.47 | 32.47 | 0
6 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme | SM/07303 | Retrofitting | Retrofitting work related to FHTC at Bhujaripara,Thakpara,Bhodapara,& Barakamat for Argigoralbari PWSS, under Jalpaiguri Division PHE Dte. |  |  | 324/RWS | 20/05/2021 |  | NARAYAN CHAKRABORTY | 4.61 | 4.61 | 0
Total | [12 empty] | 139.81 | 85.56 | 61.19