## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Special repairing of RCC Over Head Reservoir for Chamurchi Bazar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte.. | Assistant Engineer | Junior Engineer | 284/JD | 02/02/2022 |  | SUKES BASU MAJUMDAR | 8.29 | 8.32 | 1
2 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 313/DSD | 24/01/2022 |  | SAHA ENTERPRISE | 0.49 | 0.16 | 0
3 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 315/DSD | 25/01/2022 |  | SAHA ENTERPRISE | 0.49 | 0.49 | 0
4 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 327/DSD | 07/02/2022 |  | SAHA ENTERPRISE | 0.49 | 0.16 | 0
5 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 64/DSD | 23/05/2022 |  | M/S ROYAL ENTERPRISE | 0.71 | 0.49 | 0
6 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 346/DSD | 22/02/2022 |  | SAHA ENTERPRISE | 0.16 | 0.09 | 0
7 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1423/JD | 15/07/2022 |  | M/S A.B.G. CONSTRUCTION | 151.77 | 18.22 | 10
8 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Continuation order for the work of "Temporary Water Supply arrangement by Hiring of tanker for 15 days at Chamurchi Bazar P.W.S.S due to temporary lower down of water table of 2nd T/W located at Chunabhati T.G under Jalpaiguri Division P.H.E. Dte." (23.06.2022 to 07.07.2022) | Assistant Engineer | Junior Engineer | 1334/JD | 21/06/2022 |  | PARAMJYOTI ENTERPRISE | 4.85 | 0 | 1
9 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 29/DSD | 21/04/2022 |  | SAHA ENTERPRISE | 0.71 | 0.21 | 0
10 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | 152/DSD | 26/07/2022 |  | SUMON ELECTRICAL | 0.41 | 0.41 | 0
11 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | 183/DSD | 18/08/2022 |  | SUMON ELECTRICAL | 0.41 | 0.41 | 0
12 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TG PWSS, ZONE-I, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 1449/NMD | 21/12/2022 |  | SARKAR ELECTRIC | 26.26 | 26.26 | 100
13 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-III) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | 864/JD | 01/04/2022 |  | M/S. D.K. DEY & CO.. | 63.77 | 35.4 | 100
14 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Shifting of Rising main due to widening and Construction of New Culvert at Hatinala and other ancillary works related to the Rising main inside the Head works site of Chamurchi Bazar P.W.S.S. under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | 1807/JD | 14/09/2022 |  | RANA DEY | 3.57 | 3.56 | 0
15 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Resistivity Test for Four Nos.Tube Well for Chamurchi Tea Garden area Augmentation Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 142/JD | 18/01/2022 |  | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 0
16 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of rig approach road for the various zone of augmentation Chamurchi T.G.PWSS under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | 1500/JD | 27/07/2022 |  | PARAMJYOTI ENTERPRISE | 1.77 | 1.78 | 0
17 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Chamurchi T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | 1853/JD | 16/09/2022 |  | PARAMJYOTI ENTERPRISE | 4.65 | 4.78 | 0
18 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying of Individual D.I. Rising Main Including common manifold from 1st Tube Well to 2nd Tube Well and to Head Works site including internal connection of 1st and 2nd Tube Well site with Functional Household Tap Connection in connection with Jal Jeevan Mission under Augmentation of Chamurchi T.G. Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 627/JD | 13/03/2023 |  | SANKAR DAS | 47.49 | 18.8 | 50
19 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | 360/DSD | 02/03/2022 |  | SAHA ENTERPRISE | 0.16 | 0 | 100
20 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TG PWSS, ZONE-I, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 660/NMD | 31/05/2023 |  | SARKAR ELECTRIC | 0.91 | 0 | 90
21 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Sinking of two nos. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at Siv Mandir area of Chamurchi zone-II under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 802/JD. | 24/07/2023 |  | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 33.1 | 17.88 | 54
22 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Sinking of one no. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at chunavati chamurchi Zone-III under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 801/JD. | 24/07/2023 |  | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 16.55 | 16 | 80
23 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TEA GARDEN (CHAMURCHI BAZAR and CHAMURCHI FOREST BUSTY and LABOUR COLONY) PWSS, ZONE-II, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | 1380/NMD | 09/08/2023 |  | THE BANERJEE CONCERN | 26.24 | 0 | 40
24 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-I) udner Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | 967/JD | 20/04/2022 |  | NARAYAN CHANDRA SAHA | 85.51 | 47.43 | 100
25 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 300 Cu.M. R.C.C. Over Head Reservoir of 16 Mtr. Staging Height one No Pump House (5.40m x 3.60m) including Rising Main and Pump to Pump connection at zone - II of Chamurchi Tea Garden Area Augmentation P.W.S.S. udner Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 195/JD | 21/01/2022 |  | M/S KUNDAN TAMANG | 78.7 | 0 | 0
26 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 200 Cu.M. R.C.C. Over Head Reservoir of 16 Mtr. Staging Height one No Pump House (5.40m x 3.60m) and other related works at Zone - I of Chamurchi Tea Garden Area Augmentation P.W.S.S. udner Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1540/JD | 04/08/2022 |  | SAPTASWA SARKAR | 63.69 | 62.46 | 100
27 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Two nos Pump House with restoration of Sanitary Plumbing System including repairing of C.W.R. raising of valve chamber height and making of Cement Concrete Pathway at Chamurchi Forest Busty Head Works Site under Augmentation of Chamurchi T.G. Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1808/JD | 14/09/2022 |  | M/S KARMAKAR CONSTRACTION | 4.17 | 3.69 | 100
28 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Additional work in connection Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of CHAMURCHI TG (Z-I) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | 228/HQ/NMD | 15/09/2023 |  | SARKAR ELECTRIC | 1.44 | 0 | 100
29 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Providing Functional Household Tap Connection (Phase - II ) in connection with Jal Jeevan Mission for Augmentation of Chamurchi T.G. P.W.S.S (Zone -III) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1463/JD | 06/10/2023 |  | MALAY BHOWMIK | 27.18 | 0 | 50
30 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Banarhat block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | 1288/RWS | 28/11/2023 |  | SUKES BASU MAJUMDAR | 0.18 | 0 | 100
31 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of Two Nos Boundary Wall (at OHR site and alternate 1 st tube well Site) including construction of surface drain,making of pathway,Land development work,with supplying fitting fixing CIDF pipe,modification of pump house and constructionof rest rooms with construction of culvert along with scouring prevention work on the approach way including development of approach way with other allied works for the various site within the command area of augmentation of Chamurchi T.G. Area P.W.S.S.Zone - I under Jalpaiguri Division,P.H.E.D | Assistant Engineer | Junior Engineer | 1819/JD | 14/12/2023 |  | SAPTASWA SARKAR | 64.94 | 0 | 100
32 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer |  | 254/RS | 24/01/2024 |  | ELECTROSTEEL CASTINGS LIMITED | 31.65 | 0 | 2
33 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 257/RS | 24/01/2024 |  | JINDAL SAW LIMITED. | 137.78 | 0 | 50
34 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer 2 | 1982/JD | 03/01/2024 |  | APIKUL ALI | 0.88 | 0 | 30
35 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer 2 | 1983/JD | 03/01/2024 |  | RAKESH SARKAR | 0.88 | 0 | 30
36 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 3rd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer | Junior Engineer | 2303/JD | 07/02/2024 |  | DITIPRIYA CHOWDHURY | 4.9 | 0 | 100
37 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 2nd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement for at airtel site of Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer | Junior Engineer | 2304/JD | 07/02/2024 |  | MAA SHANTI BUILDERS | 4.9 | 0 | 100
38 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of different components i.e. Head Work Site Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement, Boundary wall and Laying rising Main at Shiv Mandir area of Chamurchi zone - II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 2330/JD | 08/02/2024 |  | M/S. SURYA I PVT. LTD COMPANY | 10.7 | 0 | 100
39 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of 300 Cu.M. R.C.C. Over Head Reservoir of 20 Mtr. Staging Height for zone - II of Augmentation of Chamurchi Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 2493/JD | 28/02/2024 |  | LOPCHAN ENTERPRISE | 90.95 | 0 | 100
40 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 15.07.2024 to 14.10.2024) | Assistant Engineer,HQ | Junior Engineer 2 | 561/JD | 03/07/2024 |  | APIKUL ALI | 0.44 | 0 | 0
41 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 2nd tube well site of Chamurchi Piped Water Supply Scheme (Zone-III, Chunabhati) of Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | 932/JD | 07/08/2024 |  | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 17.61 | 0 | 100
42 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHAMURCHI ZONE III, TW NO III (CHUNABHATI) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | 1638/NMD | 25/09/2024 |  | SARKAR ELECTRIC | 14.04 | 0 | 100
43 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Laying of rising main along with pump connection and allied works at Augmentation of Chamurchi Tea Garden Piped W/S Scheme (Zone-III) in connection with JJM at Banarhat Block, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 260/JSSD | 25/09/2024 |  | DITIPRIYA CHOWDHURY | 4.26 | 0 | 100
44 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Operation and Guarding of the Pumping Machinery for AUGMENTATION OF CHAMURCHI TEA GARDEN ( CHAMURCHI BAZAR and CHAMURCHI FOREST BUSTY and LABOUR COLONY) PWSS, ZONE-II, T/W NO: I, in the District of Jalpaiguri under NMD, PHE Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 1186/HQ/NMD | 30/05/2025 |  | THE BANERJEE CONCERN | 0.89 | 0 | 100
45 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Operation and Guarding of Pumping machinery at CHAMURCHI TEA GARDEN W/S SCHEME, Block : BANARHAT, in the district of JALPAIGURI | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 214/NMD | 22/01/2025 |  | SARKAR ELECTRIC | 7.06 | 0 | 100
46 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Operation and Guarding of Pumping machinery at CHAMURCHI (Chunabhati) W/S SCHEME, Block : BANARHAT, in the district of JALPAIGURI | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 211/NMD | 22/01/2025 |  | SARKAR ELECTRIC | 3.53 | 0 | 25
47 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply and Delivery of Standby Submersible pump for attending breakdown maintanance at ZONE- I , T/W no-II of CHAMURCHI T.G. W/S SCHEME in the district of Jalpaiguri under P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 1885/HQ/NMD | 18/11/2024 |  | SARKAR ELECTRIC | 0.79 | 0 | 100
48 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Construction of Boundary Wall at 3rd T/W site of Chamurchi Tea Garden Piped W/S scheme (Zone-II, Gumpha Line) along with pipeline repairing and other allied works in connection with JJM at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 2156/JD | 29/10/2025 |  | DITIPRIYA CHOWDHURY | 11.72 | 0 | 0
49 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Withdrawing , Reparing and lowering the pump motor set and allied works at ZONE-I, T/W no-II of CHAMURCHI T.G. W/S Scheme, in the district of jalpaiguri under NMD PHE Dte.. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 3034/HQ/NMD | 03/12/2025 |  | SARKAR ELECTRIC | 0.67 | 0 | 100
50 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Supply , Delivery & Installation of PLC for PLC Panel and allied works at Z- I , T/W NO I under CHAMURCHI TG water supply scheme in the district jalpaiguri under NMD ,PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 3040/HQ/NMD | 03/12/2025 |  | SARKAR ELECTRIC | 0.33 | 0 | 100
51 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Operation and Guarding of Pumping machinery at CHAMURCHI (Chunabhati) W/S SCHEME, Block : BANARHAT, in the district of JALPAIGURI | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 274/NMD | 30/01/2026 |  | SARKAR ELECTRIC | 0.87 | 0 | 0
52 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. | SM/08876 | Augmentation | Operation and Guarding of Pumping machinery at CHAMURCHI TEA GARDEN W/S SCHEME, Block : BANARHAT, in the district of JALPAIGURI | Assistant Engineer , Head Quarters , NMD | Junior Engineer | 277/NMD | 30/01/2026 |  | SARKAR ELECTRIC | 1.74 | 0 | 80
Total | [12 empty] | 1066.25 | 267.6 | 25.1