## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Implementation of BAJE BINDOLE and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer RSD | Junior Engineer, RSD | 1540/RD/PHE | 26/08/2022 |  | M/S MAA TARA CONSTRUCTION | 239.58 | 216.75 | 100
2 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Raiganj Division. |  |  | 4881/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Construction of OHR & other allied works of BAJE BINDOL and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | 587/RD/PHE | 24/02/2023 |  | M/S MAA TARA CONSTRUCTION BIRNAGAR | 157.71 | 47.44 | 85
4 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | 4003137386 | 18/04/2023 |  | W.B.S.E.D.C.LTD | 0.5 | 0.5 | 0
5 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | 4003132926 | 16/04/2023 |  | W.B.S.E.D.C.LTD | 0.55 | 0.55 | 0
6 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | 420/MLMD | 14/03/2023 |  | M/S. KUNDU CONSTRACTION | 10.89 | 10.8 | 100
7 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | 421/MLMD | 14/03/2023 |  | M/S PARIMAL DAS. | 10.92 | 10.84 | 100
8 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Making compound lighting arrangement with allied works at T/W no. I of Baje Bindole Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011708) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | 2240/MLMD | 18/07/2023 |  | MUKHERJEE ART CENTRE | 3.83 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2627/RS | 25/08/2023 |  | RASHMI METALIKS LIMITED | 1 | 0 | 10
10 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 257/RS | 24/01/2024 |  | JINDAL SAW LIMITED. | 17.26 | 0 | 50
11 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAJE BINDOL Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | 569/RD/PHE | 05/03/2024 |  | M/S MAA TARA CONSTRUCTION BIRNAGAR | 22.76 | 0 | 75
12 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Additional Pipe Line for Providing FHTC Baje Bindol Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District under Raiganj Division, P.H.E. Dte. (Phase-II) | Assistant Engineer RSD | Junior Engineer, RWS | 3014/RD/PHE | 03/10/2024 |  | M/S MAA TARA CONSTRUCTION | 54.09 | 0 | 60
13 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Trial Run For Baje Bindol PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | 538/RD/PHE | 12/02/2025 |  | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0
14 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at BAJE BINDOL W/S Scheme in the district of UTTAR DINAJPUR under MLMD, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | 435/MLMD | 22/01/2024 |  | M/S PARIMAL DAS. | 6.42 | 0 | 100
15 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at BAJE BINDOL W/S Scheme in the district of UTTAR DINAJPUR under MLMD, PHE Dte. | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | 53/MLMD | 03/01/2025 |  | M/S PARIMAL DAS. | 7.06 | 1.77 | 100
16 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | 58/RD/PHE | 03/01/2025 |  | TECHVISION | 0.2 | 0 | 83
17 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District | SM/11644 | New | Operation & Guarding of the Pumping Machinery (Automatic Operation) including all allied electro-mechanical components at Pump-House no I & II, of BAJE BINDO W/S Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-02,Junior Engineer-04 | 897/MLMD | 30/01/2026 |  | PADMA ENGINEERING CO. | 0.57 | 0 | 0
Total | [12 empty] | 534.21 | 288.65 | 54.03