## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Augmentation work of HEMTABAD ZONE-II Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal | Assistant Engineer RSD | Junior Engineer, RSD | 1548/RD/PHE | 26/08/2022 |  | UTTAM SAHA | 425.89 | 144.03 | 52
2 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Raiganj Division. |  |  | 4881/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | FHTC (Functional Household Tap Connection) for Hemtabad Zone-II Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | 2021/RD/PHE | 17/11/2022 |  | BHOLA PAUL | 64.54 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | 245/MLMD | 24/02/2023 |  | DAS CONSTRUCTION | 11.06 | 10.89 | 100
5 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Pump house for (5.4 x 3.6) at Head work site and(3.6x3.0) at 2nd Tubewell Site of Hemtabad Zone-II Water Supply Schemes Augmentation under Hemtabad Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | 389/RD/PHE | 07/02/2023 |  | M/S SANJIB BHATTACHARJEE SANJIB.RNJ@GMAIL.COM | 11.8 | 11.38 | 100
6 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. II (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | 4003083063 | 13/02/2023 |  | W.B.S.E.D.C.LTD | 0.54 | 0.54 | 0
7 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. I (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | 4003083051 | 13/02/2023 |  | W.B.S.E.D.C.LTD | 0.65 | 0.65 | 0
8 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | 729/RD/PHE | 15/03/2023 |  | Sovan Kumar Roy | 143.15 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | Assistant Engineer - I | Junior Engineer-07 | 1664/MLMD | 28/06/2023 |  | PABITRA MANDAL | 11.51 | 11.42 | 100
10 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2337/RS | 24/07/2023 |  | RASHMI METALIKS LIMITED | 92.72 | 0 | 2
11 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Hemtabad Water Supply Scheme, (Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | Assistant Engineer - I |  | 2657/MLMD | 10/08/2023 |  | MAA BHABOTARINE ENTERPRISE. | 9.02 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | 2953/MLMD | 28/12/2022 |  | BISWAS SUPPLIERS. | 10.94 | 0 | 0
13 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2555/RS | 17/08/2023 |  | JINDAL SAW LIMITED. | 13.49 | 0 | 15
14 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2627/RS | 25/08/2023 |  | RASHMI METALIKS LIMITED | 10.81 | 0 | 10
15 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation of Hemtabad Zone-II PWSS at Hemtabad Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | 2889/RD/PHE | 25/09/2024 |  | M/S SANJIB BHATTACHARJEE | 24.46 | 0 | 100
16 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | 737/RD/PHE | 12/03/2024 |  | HORIZEN | 0.18 | 0.18 | 100
17 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at HEMTABAD (ZONE-II) W/S Scheme in the district of UTTAR DINAJPUR under MLMD, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | 667/MLMD | 31/01/2024 |  | DAS CONSTRUCTION | 3.21 | 0 | 100
18 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at HEMTABAD (ZONE-II) W/S Scheme in the district of UTTAR DINAJPUR under MLMD, PHE Dte. | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | 253/MLMD | 13/01/2025 |  | DAS CONSTRUCTION | 7.06 | 3.55 | 100
19 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Continuation work-Operation & Guarding of the Pumping Machinery (Automatic Operation) including all allied electro- mechanical components at Pump-House no I of HEMTABAD (ZONE-II) W/S Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-07 | 4310/MLMD | 30/12/2024 |  | PABITRA MANDAL | 0.27 | 0 | 100
20 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at Pump House - I & II of HEMTABAD (ZONE-II) W/S Scheme in the district of UTTAR DINAJPUR under MLMD, PHE Dte. | Assistant Engineer - I | Junior Engineer-04 | 668/MLMD | 28/01/2026 |  | DAS CONSTRUCTION | 7.27 | 0 | 0
21 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. | SM/11727 | Augmentation | Supply & Delivery Standby Electro Mechanical components for existing PWSS in Hemtabad in the District of Uttar Dinajpur under Malda Mechanical Division, PHED. | Assistant Engineer - I | Junior Engineer-07 | 2201/MLMD | 21/08/2024 |  | BINA CONSTRUCTION | 0.72 | 0 | 100
Total | [12 empty] | 849.29 | 182.64 | 21.5