## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Formal work order for the work of Implementation of BHADAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 1996/MD | 17/05/2023 |  | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 336.77 | 321.92 | 85
2 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of BHADAR Piped Water Supply Scheme at Gaole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 2332/MD | 08/06/2023 |  | M/S KUNDU CONSTRUCTION | 87.98 | 80.55 | 90
3 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bhadar PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | 3004390642 | 16/08/2023 |  | W.B.S.E.D.C.LTD | 16.23 | 16.23 | 100
4 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2555/RS | 17/08/2023 |  | JINDAL SAW LIMITED. | 16.8 | 0 | 15
5 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Placing of diesel driven Car on hire basis for official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/07/2023 to 30/09/2023). | Mr. Arnab Giri, Assistant Engineer |  | 487/MD | 21/06/2023 |  | SUBHANKAR SINGH | 0.31 | 0.31 | 100
6 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhadar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014278) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | 3340/MLMD | 30/10/2023 |  | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 25.45 | 23.75 | 93
7 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Construction of Boundary Wall at Head Work site of Bhadar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 269/MD | 11/01/2024 |  | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 22.49 | 17.39 | 80
8 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Laying of Distribution Sysytem and Providing Functional Household Tap Connection (FHTC) of BHADAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 2928/MD | 10/06/2024 |  | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 55.17 | 27.8 | 50
9 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Construction of Boundary Wall at 2nd Tube Well Site of BHADAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | 2930/MD | 10/06/2024 |  | NANDAN ENTERPRISE | 6.73 | 0 | 70
10 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Continuation work-Continuation work-Operation & Guarding of the Pumping Machinery (Automatic Operation) including all allied electro- mechanical components at Pump-House no I of BHADAR W/S Scheme in the District of Malda under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-07 | 3478/MLMD | 30/10/2024 |  | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 0.81 | 0 | 100
11 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at BHADAR W/S Scheme in the district of MALDA under MLMD, PHE Dte. | Assistant Engineer - II | Junior Engineer-06 | 3649/MLMD | 29/08/2025 |  | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 3.63 | 0 | 0
12 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme | SM/12768 | New | Annual Operation Maintenance & Emergent repair of pipe line of distribution system & Rising main of BHADAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the District of Malda. {Period from 01/10/2025 to 30/09/2026}. | Sri Biswadip Sengupta, Assistant Engineer | Amit Karmakar, Junior Engineer | 5033/MD | 22/09/2025 |  | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 6.23 | 0 | 0
Total | [12 empty] | 578.59 | 487.93 | 84.33