## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | 364/JSD | 22/12/2021 |  | S.S.Infrastructure | 3.13 | 0 | 0
2 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-IV). | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | 127/JSD | 22/03/2022 |  | Moti Rahaman | 3.5 | 2.94 | 0
3 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-II). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | 128/JSD | 22/03/2022 |  | MURSHID ALOM | 3.87 | 3.83 | 90
4 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-I). | ASSISTANT ENGINEER |  | 121/JSD | 22/03/2022 |  | Dipayan Dey | 4.2 | 3.59 | 0
5 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I | SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-III). | ASSISTANT ENGINEER |  | 126/JSD | 22/03/2022 |  | Dipayan Dey | 3.73 | 3.53 | 0
Total | [12 empty] | 18.43 | 13.89 | 75.34