## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme | SM/07555 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rahatpur village and Rahatpur Habitation of Rahatpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-491/BWD/2020-21) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 4116/BWD | 16/10/2020 |  | DUBE ENTERPRISE | 4.87 | 4.87 | 1
2 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme | SM/07555 | Retrofitting | Extension of 63 mm dia UPVC pipeline to provide house connection to the beneficiaries of Rahatpur water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-B] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 139/KSD | 12/02/2021 |  | DUBE ENTERPRISE | 4.49 | 0 | 1
3 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme | SM/07555 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rahatpur village and Rahatpur habitation of Rahatpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-7A] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 4913./BWD | 08/12/2020 |  | DUBE ENTERPRISE | 4.31 | 0 | 1
Total | [12 empty] | 13.67 | 4.87 | 35.59