## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | 40/BWD | 05/01/2022 |  | PREMANANDA ROY BISWAS | 3.02 | 0 | 1
2 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Laying pipeline with FHTC for BALARAMPUR Water Supply Scheme at Matnasipur village (600 Nos) (from near rail gate to matnasipur) and rest portion FHTC work of Berugram village (46 Nos), Balarampur village (40 Nos), Nasipur village (45 Nos), Salimdanga village (15 Nos) within Jamalpur Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 1620/BWD | 21/03/2022 |  | M/S ASHA CONSTRUCTION | 7.5 | 0 | 100
3 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | AE(HQs),Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JE/RWS/JAMALPUR | 1454/BWD | 11/03/2022 |  | PREMANANDA ROY BISWAS | 2.5 | 0 | 1
4 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Jalpaiguri Division. |  | Junior Engineer | 3831/RS | 07/07/2022 |  | A.K.INDUSTRIES | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of BALARAMPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | 4887/BWD | 02/11/2022 |  | BIBHUTI SHAW | 10.07 | 0 | 100
6 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Balarampur Piped Water Supply Scheme at Balarampur (3 Nos Habitation), Berugram (3 Nos Habitation), Krishnapur (2 Nos Habitation) & Sadipur (3 Nos Habitation Part) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 66/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | 5009/BWD | 10/12/2020 |  | M/S ASHA CONSTRUCTION | 25.68 | 25.68 | 0
7 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block | SM/07776 | Retrofitting | Construction of temporary approach road for Boring machine and its accessories at 4th Tube Well site (due to low land) of Balarampur PWSS, Jamalpur Dev. Block Burdwan Sub-Division under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | 519/BSD | 13/03/2024 |  | BIBHUTI SHAW | 0.92 | 0 | 100
Total | [12 empty] | 49.68 | 25.68 | 51.68