## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Ukhra, Dafarpota, Dampal, Mmudpur, Narayanpur, Nowapara, Patuli, Tegachhi & Gachha (9nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | 3122/BWD | 02/06/2021 |  | SK ALIM | 212.45 | 53.87 | 1
2 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Harispur, Hatsiuri, Jajneswarpur, Jamalpur, Madhupur, Nakadaha, Nimdaha, Palasberia & Sarangpur (9nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | 3417/BWD | 25/06/2021 |  | ASHOK KUMAR GHOSH | 229.08 | 82.01 | 1
3 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Muragachha, Sardanga, Sihipara, Bagachra, Baragachhi, Belgachhi, Kumirpara, Lohachur, Atpara, Barea, Dhamas, Kamalapur & Kamalnagar (13nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | 3418/BWD | 25/06/2021 |  | MRITYUNJOY MUKHERJEE & CO. | 232.13 | 80.59 | 1
4 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Sajiara, Simla, Barapara, Bodhsah, Dubrajpur, Gobindapur, Isabpur, Kaibati, Khord Kaibati, Kubajpur, Kuksimla, Muksimpara, Sanghoshpara, Sumuria & Chhatni (15nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | 3230/BWD | 10/06/2021 |  | UNICON INDIA | 223.63 | 42.56 | 1
5 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Hapania, Kankhal, Khar Dattapara, Pathangram, Sontoshpur Pila & Uttar Srirampur (6nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | 3416/BWD | 25/06/2021 |  | M/S ASHA CONSTRUCTION | 146.22 | 0 | 1
6 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Majida, Rukuspur, Uttar Lakshmipur, Candipur, Gopipur, Kuturia & Mertala (7nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | 3393/BWD | 24/06/2021 |  | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 219.81 | 88.33 | 1
7 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at Surface Water Based w/s scheme for Arsenic affected areas of Purbasthali-II block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Part-A) and delivered to Barsul Divisional Store .[Part-3] | Assistant Engineer |  | 3836/BWD | 23/07/2021 |  | A.K. SIKDAR | 17.62 | 17.62 | 1
8 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Laying of 140 mm dia HDPE Pipe from Bardangamore to Khardattapara more (Node No- 289A -289- 286) of Zone-III under Surface Based W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | 84/KSD | 20/01/2022 |  | UNICON INDIA | 1.57 | 0 | 1
9 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purbasthali ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | 149/BWD | 07/01/2022 |  | G.S. CONSTRUCTION & CO. | 22.15 | 0 | 1
10 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Withdrawing of 110 mm dia HDPE Pipeline and relaying of 140 mm dia HDPE Pipe from Naomatha more to Bordanga more (Node No- 291 to 289-289A) under Surface Based W/S Scheme (Zone-III) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | 87/KSD | 21/01/2022 |  | UNICON INDIA | 1.57 | 0 | 1
11 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Sheet piling and others ancillary works to protect errosion of river bank protection area at raw water intake point of Kamalnagar WTP under Burdwan Division PHE Dte. | Assistant Engineer |  | 2015/BWD | 18/04/2022 |  | CONCORD ENGINEERING | 122.2 | 0 | 1
12 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Relaying of different dia UPVC pipeline at damaged portion as shown by Horizon of Zone-III of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-B] | Assistant Engineer |  | 148/KSD | 12/02/2021 |  | CHANCHAL PAL | 3.5 | 0 | 1
13 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Construction of wash out & over flow & drain for drain out of over flow water by 250 mm dia UPVC pipeline & soak well along with land development at Zone-I Head work site of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-C] | Assistant Engineer |  | 160/KSD | 19/02/2021 |  | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.1 | 0 | 1
14 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at surface water based water supply scheme for Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte.[Part-B] and delivered at Barsul Divisional store. | Assistant Engineer |  | 4476/BWD | 03/09/2021 |  | INDIA PIPE FITTING CO | 17.62 | 0 | 1
15 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali Piped Water Supply Scheme at Kasthashali Village (Kasthashali habitation) (Mouza) & Purbasthali village (Purbasthali habitation), Purbasthali-II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | 1328/BWD | 12/02/2021 |  | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.41 | 0 | 1
16 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Painting and renovation work of WTP Building, Boundary Wall, Truss Bridge etc. at Kamalnagar of Surface Water Based Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 5517/BWD | 14/12/2023 |  | SETH ENTERPRISE | 12.63 | 0 | 100
17 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Repairing and Renovation of Filter Bed, Main Boundary Gate, resetting of Paver Block Pathway, replacement of different damaged portion of doors/windows or any other structures & other related works for Kamalnagar WTP within Kalna Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 5510/BWD | 14/12/2023 |  | GHOSH BROTHERS | 47.97 | 0 | 5
18 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Biswarambha, Dhitpur, Doghori, Falea, Harishi & Moail, (6nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | AE(HQs) | J.E. 2 BURDWAN | 3121/BWD | 02/06/2021 |  | IJABUL SEKH | 205.05 | 91.62 | 0
19 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Extension of 75 mm dia UPVC pipeline of 300 mtr at Purbasthali ITI College (Zone-II) and 75 mm dia UPVC pipeline of 200 mtr at Lakshmipur from Nemai Ghosh's house at Ghoshpara to Sukumar Ghoshs house (Zone-I) & extension of 90 mm dia UPVC pipeline of 300 mtr from majida Khalpara Babu sk house to Hego Sks house and 90 mm dia UPVC pipeline of 180 mtr at Kuthipara more Anganwari Centre in Zone-I under surface based water supply scheme in the Arsenic affected areas of Purbasthali-II Block under Burdwan Division, PHE Dte. |  |  | 187/KSD | 23/03/2020 |  | M/S ASHA CONSTRUCTION | 3.26 | 0 | 0
20 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Painting & renovation work at Purbasthali raw water pumping station within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 4560/BWD | 16/10/2023 |  | CONCORD ENGINEERING | 6.53 | 0 | 100
21 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 2296/BWD | 20/06/2024 |  | M/S DATTA ENTERPRISE | 272.36 | 0 | 2
22 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | 3107/BWD | 12/08/2024 |  | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 30 | 0 | 80
23 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 608/BWD | 11/02/2025 |  | MANASH GHOSH | 0.28 | 0 | 51
24 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Work Order for "Restoration of Pipeline along with other ancillary work in connection with Retrofitting of Surface Water Based Piped Water Supply Scheme(SM/08030) for Zone III within Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 964/KSD | 31/07/2024 |  | IJABUL SEKH | 3.13 | 0 | 70
25 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block | SM/08030 | Retrofitting | Work Order for "Restoration of Pipeline along with other ancillary work in connection with Retrofitting of Surface Water Based Piped Water Supply Scheme(SM/08030) for Zone IV within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 965/KSD | 31/07/2024 |  | PARTHA PRATIM ACHARYA | 4.65 | 0 | 70
Total | [12 empty] | 2128.92 | 456.59 | 21.45