## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 0 | 0 | 100
2 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | 1004/BWD | 06/03/2023 |  | M/S TAPAS KUMAR CHAKRABORTY | 402.92 | 0 | 75
3 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work Order for "Supply of 1 (one) No. Diesel driven Motor cab (Inspection vehicle) on hire basis for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period for 3 (Three) Months]". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 1333/KSD | 28/08/2023 |  | PARTHA PRATIM ACHARYA | 0.92 | 0 | 100
4 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2631/RS | 25/08/2023 |  | RASHMI METALIKS LIMITED | 2.21 | 0 | 9
5 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Deara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 4060/CMD | 29/08/2023 |  | S.K. ENTERPRISE | 28.6 | 0 | 100
6 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | upply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admis | Assistant Engineer |  | 234/RS | 22/01/2024 |  | RASHMI METALIKS LIMITED | 38.05 | 0 | 5
7 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DEARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | 1979/KSD | 09/02/2024 |  | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 100
8 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 2398/CMD | 02/08/2024 |  | MS S G ENTERPRISE | 6.58 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for "Restoration of pipeline with other allied works at different places of Deara mouja under Deara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | 968/KSD | 31/07/2024 |  | M/S TAPAS KUMAR CHAKRABORTY | 2.35 | 0 | 100
10 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Providing Diesel generator set at Deara water supply scheme for Urgent FHTC connection under CMD P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 821/CMSD | 31/05/2024 |  | S.K. ENTERPRISE | 0.85 | 0 | 100
11 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Continuation Order-Providing Diesel generator set at DEARA Water supply scheme for Urgent FHTC connection under CMD PHE Dte. [W.E.F- 05.06.2024 TO 08.06.2024] | ASSISTANT ENGINEER | JUNIOR ENGINEER | 827/CMSD | 04/06/2024 |  | S.K. ENTERPRISE | 0.85 | 0 | 100
12 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Installation of Electrical items & allied works for Urgent FHTC for Deara PH 1 water supply scheme under CMD P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer | 822/CMSD | 31/05/2024 |  | S.K. ENTERPRISE | 0.64 | 0 | 100
13 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Installation of Electrical items & allied works for Urgent FHTC for Deara PH 2 water supply scheme under CMD P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer | 823/CMSD | 31/05/2024 |  | S.K. ENTERPRISE | 0.64 | 0 | 100
14 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Continuation Order-Providing Diesel generator set at DEARA Water Supply Scheme for Urgent FHTC connection under CMD PHE Dte [09/06/2024 to 12/06/2024] | ASSISTANT ENGINEER | Junior Engineer | 836/CMSD | 07/06/2024 |  | S.K. ENTERPRISE | 0.85 | 0 | 100
15 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 608/BWD | 11/02/2025 |  | MANASH GHOSH | 5 | 0 | 51
16 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for "Operation & Maintenance of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of DEARA PWSS within KALNA-1 BLOCK, KALNA-Sub-Division under Burdwan Division, PHE Dte. [Period for 01.07.2025 to 30.06.2026].". | Assistant Engineer |  | 1084/KSD | 01/07/2025 |  | SANJAY SK | 4.85 | 0 | 0
17 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for "Day to day Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of Deara PWSS under Kalna-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. [Period for Three Months ((For Trail Run only)] [Period 01.01.2025 to 31.03.2025]". | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | 2154/KSD | 31/12/2024 |  | SANJAY SK | 0.62 | 0 | 0
18 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for " Day to day Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of Deara PWSS under Kalna-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. [Period for Three Months ((For Operation only)] [Period 01.04.2025 to 30.06.2025]" | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | 455-1/KSD | 26/03/2025 |  | SANJAY SK | 0.63 | 0 | 0
19 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | CONTINUATION ORDER--Operation & Guarding of Pumping Machinery including all allied electro-mechanical components installed at DEARA PH 02 (Block-Kalna-I)water supply scheme, in the district of PurbaBardhaman Division, under CMD PHE Dte.[W.E.F-01.12.2024 TO 31.01.2025] | ASSISTANT ENGINEER | JUNIOR ENGINEER | 1383/CMSD | 29/11/2024 |  | S.K. ENTERPRISE | 0.6 | 0 | 0
20 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Operation & Guarding of pumping Machinery (Automatic Operation) including all allied electro-mechanical components installed at DEARA PH-02 (BLOCK-KALNA-1)w/s scheme in the district of Purba-Bardhaman Division under CMD PHE Dte. [w.e.f -01.09.2024 to 30.11.2024] | ASSISTANT ENGINEER | JUNIOR ENGINEER | 1121/CMSD | 29/08/2024 |  | S.K. ENTERPRISE | 0.88 | 0 | 0
21 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Operation and Guarding of pumping machinery (Automatic Operation)including all allied electro-mechanical components installed at DEARA of T.W. No. 1 & 2[Block - Kalna-I] W/SScheme in the District of Purba-Bardhaman Division, under CMD, PHE. Dte. [w.e.f - 01.02.2025 to 31.01.2026] | ASSISTANT ENGINEER | Junior Engineer | 461/CMD | 31/01/2025 |  | S.K. ENTERPRISE | 7.07 | 0 | 0
22 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Operation & Guarding of pumping Machinery (Automatic Operation) including all allied electro-mechanical components installed at DEARA PH-01 (BLOCK-KALNA-1)w/s scheme in the district of Purba-Bardhaman Division under CMD PHE Dte. [w.e.f -01.09.2024 to 30.11.2024] | ASSISTANT ENGINEER | JUNIOR ENGINEER | 1120/CMSD | 29/08/2024 |  | S.K. ENTERPRISE | 0.88 | 0 | 0
23 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | CONTINUATION ORDER- Operation and Guarding of pumping machinery including all allied eletrco-mechanical components installed at DEARA PH NO. 01 (BLOCK-KALNA -I) water supply scheme in the district of Purba-Bardhman Division under CMD,PHE,Dte. [W.E.F-01.12.2024 to 31.01.2025] | ASSISTANT ENGINEER | Junior Engineer | 1382/CMSD | 29/11/2024 |  | S.K. ENTERPRISE | 0.6 | 0 | 0
24 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for "Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of DEARA PWSS within KALNA-1 BLOCK, KALNA-Sub-Division under Burdwan Division, PHE Dte. [Period for 01.07.2025 to 30.06.2026].". | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | 1084/KSD | 01/07/2025 |  | SANJAY SK | 2.83 | 0 | 0
25 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at Deara W/S Scheme, P.H. No.-I [Block - Kalna-1] under CMD, P.H.E. Dte., Dist.- Purba Bardhaman(w.e.f. - 01.02.26 to 30.04.26) | ASSISTANT ENGINEER | Junior Engineer | 183/CMSD | 31/01/2026 |  | CHATTERJEE ENTERPRISE | 0.89 | 0 | 0
26 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Repairing of motor control unmanned panel and Voltage stabilizer at Deara water supply scheme, P.H. No.- II [Kalna-I, Block] under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | 1409/CMSD | 17/10/2025 |  | S.K. ENTERPRISE | 0.65 | 0 | 0
27 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at Deara W/S Scheme, P.H. No.-II [Block - Kalna-1] under CMD, P.H.E. Dte., Dist.- Purba Bardhaman(w.e.f. - 01.02.26 to 30.04.26) | ASSISTANT ENGINEER | Junior Engineer | 184/CMSD | 31/01/2026 |  | CHATTERJEE ENTERPRISE | 0.89 | 0 | 0
Total | [12 empty] | 512.51 | 0 | 0