## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | CHOTO RAMCHANDRAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | 3116/BWD | 19/07/2023 |  | KALPANA BUILDERS | 150.39 | 14 | 38
2 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhoto Ramchandrapur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | 4015/CMD | 29/08/2023 |  | JAL PRAVAHIKA PVT LTD | 27.77 | 0 | 48
3 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | 2405/CMD | 02/08/2024 |  | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 5.02 | 0 | 80
4 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Acceptance cum Formal Work Order for Balance works related sinking of Tube-wells at ARJURI village,PH,BW, LDS , Rising Mains, FHTCs,Road Restoration ,Land Development Etc. Construction of CHOTORAMCHANDRAPUR Piped Water Supply Scheme under Aushgram-II Block, of Durgapur Water supply Division, PHE Dte. | Assistant Engineer-I | Contractual Junior Engineer_3 | 1610/DWSD | 26/11/2024 |  | KALPANA BUILDERS | 78.66 | 0 | 0
5 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Continuation order for Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at CHOTO RAMCHANDRAPUR of Pump House No.-1 & 2 [Block ¿ Ausgram-II] W/S Scheme in the district of Purba-Bardhaman Division, under CMD, PHE. Dte.[w.e.f. - 01.02.25 to 28.02.25] | Driller In-Charge | Junior Engineer | 82-A/CMD | 22/01/2025 |  | JAL PRAVAHIKA PVT LTD | 0.56 | 0 | 0
6 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Operation and Guarding of pumping machinery (Automatic Operation)including all allied electro-mechanical components installed at Choto Ramchandrapur of Tube Well No. - 1 & 2 [Block - Ausgram-II] W/S Scheme in the district of Purba-Bardhaman Division, under CMD, PHE. Dte. | Driller In-Charge | JUNIOR ENGINEER | 563-B/CMD | 27/02/2025 |  | JAL PRAVAHIKA PVT LTD | 6.49 | 0 | 0
7 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Carrying out preventive as well as breakdown maintanance and repairing of chlorinator for ascertaining disinfection of different PWSS at Bhalki, Amrargarh, Chhora, Kalaijhuti & others w/s scheme (under Ausgram-II Block) under CMD, PHE Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | 660/DIC/BMSD(D) | 22/08/2025 |  | BABA MALLESHWAR ENTERPRISE. | 0.17 | 0 | 0
8 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Carrying out preventive and breakdown maintenance and repairing of chlorination system for ascertaining disinfection of different PWSS at Bhalki, Chhora& others w/s scheme (under Ausgram-II Block) under CMD, PHE Dte., Dist.- Purba Bardhaman. w.e.f 01/06/2025 to 31/07/2025 | Driller In-Charge | Junior Engineer | 336/DIC/BMSD(D) | 23/05/2025 |  | BABA MALLESHWAR ENTERPRISE. | 0.04 | 0 | 0
9 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14926 | New | Annual O and Mtc of distribution system ,rising main ,sluice valves including operation of sluice valves at Chhataramchandrapur PWSS under DWSD,PHE Dte (w.e.f 01.07.2025 to 30.06.2026) | Assistant Engineer-II ,Assistant Engineer-II (Newly Charge takenover) | Contractual Junior Engineer_3,JUNIOR ENGINEER-2 | 991/DWSD | 24/06/2025 |  | JOY GURU ENTERPRISE | 4.11 | 0 | 75
Total | [12 empty] | 273.2 | 14 | 5.12