## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Aligram Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | 4057/CMD | 29/08/2023 |  | EASTERN INDIA SALES & SERVICE | 27.78 | 0 | 48
2 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | 4581/BWD | 16/10/2023 |  | SAFECO ENTERPRISES | 205.85 | 0 | 60
3 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | upply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admis | Assistant Engineer |  | 234/RS | 22/01/2024 |  | RASHMI METALIKS LIMITED | 29.49 | 0 | 5
4 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2024 to 31.07.2024).(Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | 106/DWSD | 31/01/2024 |  | SUJIT ROY | 0.82 | 0 | 25
5 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Luxury Diesel Ambassadar Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2024 to 31.08.2024 (6 Months).(Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | 267/DWSD | 29/02/2024 |  | PRAMIT CHATTERJEE | 0.82 | 0 | 0
6 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.08.2024 to 31.01.2025).(Sl-01) | Assistant Engineer-II | JUNIOR ENGINEER-2 | 1079/DWSD | 30/07/2024 |  | SUJIT ROY | 0.82 | 0 | 0
7 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.09.2024 to 28.02.2025 (6 Months).(Sl-01) | Assistant Engineer-II | JUNIOR ENGINEER-2 | 1244/DWSD | 30/08/2024 |  | PRAMIT CHATTERJEE | 0.82 | 0 | 0
8 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.02.2024 to 29.02.2024). (SL-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | 186/DWSD | 15/02/2024 |  | PRAMIT CHATTERJEE | 0.05 | 0 | 100
9 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | 2764/CMD | 26/09/2024 |  | JAL PRAVAHIKA PVT LTD | 6.08 | 0 | 0
10 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2025 to 31.07.2025). | Assistant Engineer-II | JUNIOR ENGINEER-2 | 163/DWSD | 27/01/2025 |  | SUJIT ROY | 0.82 | 0 | 0
11 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | 340/DWSD | 27/02/2025 |  | PRAMIT CHATTERJEE | 0.41 | 0 | 0
12 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | 853/DWSD | 29/05/2025 |  | PRAMIT CHATTERJEE | 0.41 | 0 | 0
13 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Operation and Guarding of pumping machinery (Automatic Operation)including all allied electro-mechanical components installed at ALIGRAM PH - 1 W/S Scheme under Central Mechanical Division, PHE. Dte. [w.e.f ¿ 01.02.2025 to 28.02.2025] | Driller In-Charge | Junior Engineer | 63/DIC/BMSD(D) | 21/01/2025 |  | EASTERN INDIA SALES & SERVICE | 0.28 | 0 | 0
14 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at ALIGRAM of Pump House No.- 1 [Block- Ausgram-I] W/S Scheme in the district of Purba-Bardhaman Division, under CMD, PHE. Dte.[w.e.f. - 01.08.24 to 31.01.25] | Driller In-Charge | Junior Engineer | 2359/CMD | 31/07/2024 |  | EASTERN INDIA SALES & SERVICE | 1.77 | 0 | 0
15 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Operation and Guarding of pumping machinery (Automatic Operation)including all allied electro-mechanical components installed at Aligram of Tube Well No. - 1 & 2 [Block ¿ Ausgram-I] W/S Scheme in the district of Purba-Bardhaman Division, under CMD, PHE. Dte. | Driller In-Charge | Junior Engineer | 536-B/CMD | 20/02/2025 |  | EASTERN INDIA SALES & SERVICE | 6.5 | 0 | 0
16 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Operation & Maintenance of Distribution System ,Rising main, Sluice Valves, including operation of sluice valves of ALIGRAM PWSS under Durgapur Water Supply Division, PHE Dte. [Period for 01.08.2025 to 31.07.2026]. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,Junior Engineer_3 | 1219/DWSD | 31/07/2025 |  | RAJAT BARAN CHAND | 4.62 | 0 | 50
17 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Carrying out preventive as well as breakdown maintanance and repairing of chlorinator for ascertaining disinfection of different PWSS at Dignagar ,Koyrapur & others w/s scheme (under Ausgram-1 Block ) under CMD, PHE Dte., Dist.- Purba Bardhaman. w.e.f. 01/06/2025 to 30/06/2025 | Driller In-Charge | Junior Engineer | 337/DIC/BMSD(D) | 23/05/2025 |  | BABA MALLESHWAR ENTERPRISE. | 0.04 | 0 | 0
18 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-04) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | 1381/DWSD | 26/08/2025 |  | PRAMIT CHATTERJEE | 0.86 | 0 | 0
19 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Acceptance cum Formal Work Order for Supply of Sanitary articles with Others necessary office materials for Office of The Executive Engineer, Durgapur W/S Division, PHE, Dte. at Nababhat,Purba Bardhaman under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | 1210/DWSD | 23/08/2024 |  | GHOSH & ROY ENTERPRISE | 0.84 | 0 | 90
20 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Name of Work:- Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 16.09.2025 to 31.10.2025 (46 days) (Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1 | 1532/DWSD | 16/09/2025 |  | TKB ENTERPRISE | 0.22 | 0 | 0
21 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 16.09.2025 to 31.10.2025 (46 days) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1 | 1522/DWSD | 15/09/2025 |  | TKB ENTERPRISE | 0.22 | 0 | 0
22 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring charges of one no. Diesel driven Motor cabs (Luxury taxi) of mass emission standard like Bharat Stage ¿ II / BS ¿ III Purchased on or after 01/05/2008 with Diesel / LPG / CNG Engine, Motor cab/Maxi cab with engine capacity less than or equal to 2000 CC with West Bengal permit for the official use on the Office of the Executive Engineer, Durgapur W/S Division, PHE Dte including providing driver but excluding cost of diesel & Mobile as per terms & Condition and direction of the EIC (Rate should be including of pay and allowances and other char | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer_3 | 1236/DWSD | 01/08/2025 |  | M/S JOY | 0.14 | 0 | 0
23 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.11.2025 to 31.01.2026 (92 days) (Sl-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | 1772/DWSD | 31/10/2025 |  | TKB ENTERPRISE | 0.44 | 0 | 0
24 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.11.2025 to 31.01.2026 (92 days) (Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | 1773/DWSD | 31/10/2025 |  | TKB ENTERPRISE | 0.44 | 0 | 0
25 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of luxury Diesel Ambassador car use for inspection vehicle of JJM under office of the EE/DWSD/PHE Dte at Fagupur,Nababhat,Purba Bardhaman for the period from 01.09.2025 to 15.09.2025 | Assistant Engineer-I | JUNIOR ENGINEER-2 | 1427/DWSD | 29/08/2025 |  | PRAMIT CHATTERJEE | 0.07 | 0 | 0
26 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of luxury Diesel Ambassador car use for inspection vehicle of JJM under office of the EE/DWSD/PHE Dte at Fagupur,Nababhat,Purba Bardhaman for the period from 01.09.2025 to 15.09.2025 | Assistant Engineer-I | JUNIOR ENGINEER-2 | 1426/DWSD | 29/08/2025 |  | PRAMIT CHATTERJEE | 0.07 | 0 | 0
27 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Supply & fitting fixing of CHANGE OVER SWITCH at Tube well no.- I at Aligram w/s scheme, ( Block -Ausgram-I ) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | 588/DIC/BMSD(D) | 01/08/2025 |  | EASTERN INDIA SALES & SERVICE | 0.19 | 0 | 0
28 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Carrying out preventive as well as breakdown maintanance and repairing of chlorinator for ascertaining disinfection of different PWSS at Dignagar, Takipur & others w/s scheme (under Ausgram 1 Block) under CMD, PHE Dte., Dist.- Purba Bardhaman. w.e.f. 15/10/2025 to 14/11/2025 | Driller In-Charge | Junior Engineer | 675/DIC/BMSD(D) | 28/08/2025 |  | BABA MALLESHWAR ENTERPRISE. | 0.06 | 0 | 0
29 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Acceptance cum Formal Work Order for Annual Mtc. on contract (AMC) for computer Hardwares i.e. Printers, UPS, Monitors internet recharging, Keyboards, Mouse, Monitor, Mother Board, SMPS, DDR RAM etc and other related Hardwares peripherals in the office of the Executive Engineer, Durgapur W/S Division, PHE Dte | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | 1396/DWSD | 30/09/2024 |  | DIGITEK SOLUTIONS | 2.25 | 0 | 0
30 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the Assistant Engineer-I under office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.02.2026 to 31.07.2026 (6th months) (Sl-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,Junior Engineer_3 | 129/DWSD | 29/01/2026 |  | TKB ENTERPRISE | 0.86 | 0 | 0
31 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.02.2026 to 31.07.2026 (6th months) (Sl-01) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer_3 | 137/DWSD | 30/01/2026 |  | SIDDHARTH ENTERPRISE | 0.86 | 0 | 20
32 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Operation and Guarding of pumping machinery (Automatic Operation)including all allied electro-mechanical components installed at ALIGRAM [Block ¿ Ausgram-I] of TW No - 1 & 2 W/S Scheme in the district of Purba-Bardhaman Division, under CMD, PHE. Dte.[ w.e.f:-01.02.2026 to 31.01.2027] | Driller In-Charge | JUNIOR ENGINEER | 2505/CMD | 29/01/2026 |  | EASTERN INDIA SALES & SERVICE | 7.29 | 0 | 0
Total | [12 empty] | 302.2 | 0 | 0