## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 3957/BWD | 07/09/2023 |  | M/S B. NANDI | 242.77 | 0 | 20
2 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GAHAK Water Supply Scheme [ Block- PURBASTHALI -1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | 4192/CMD | 29/08/2023 |  | SOUNAK ENTERPRISE | 21.33 | 0 | 50
3 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | upply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admis | Assistant Engineer |  | 234/RS | 22/01/2024 |  | RASHMI METALIKS LIMITED | 15.53 | 0 | 5
4 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GAHAK PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 1017/KSD | 07/08/2024 |  | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
5 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 2979/CMD | 25/11/2024 |  | H.K. DAS & CO. | 6.91 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Operation & Guarding of Pumping Machinery under un-manned Operation at Gahak water supply scheme, P.H. No.-1 (Block- Purbasthali-I) under CMD, P.H.E. Dte. Dist.- Purba Bardhaman(w.e.f. - 01.08.2025 to 31.10.2025). | ASSISTANT ENGINEER | JUNIOR ENGINEER | 982/CMSD | 24/07/2025 |  | SOUNAK ENTERPRISE | 0.92 | 0 | 100
7 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | CONTINUATION ORDER-Operation and Guarding of Pumping machinery under un-manned operation at GHAHAK water supply scheme PH No. 01 Block-Purbasthali-I under CMD PHE Dte. [W.E.F-01.11.2025 TO 31.01.2026] | ASSISTANT ENGINEER | JUNIOR ENGINEER | 1426/CMSD | 29/10/2025 |  | SOUNAK ENTERPRISE | 0.92 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Operation and Guarding of pumping machinery (Automatic Operation) including all allied electro-mechanical components installed at GAHAK [Block - Purbasthali-I] of TW No - 1 W/S Scheme in the district of Purba-Bardhaman Division, under CMD, PHE. Dte. (w.e.f. -01/02/2026 to 31/01/2027) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 2588/CMD | 30/01/2026 |  | SOUNAK ENTERPRISE | 3.64 | 0 | 0
Total | [12 empty] | 292.67 | 0 | 0