## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-4A) with LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 3137/BWD | 20/07/2023 |  | SAKTI ENTERPRISE | 432.83 | 0 | 1
2 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 142/RS | 16/01/2024 |  | TATA METALIKS LTD | 26.68 | 0 | 4
3 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Work Order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV B) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." Sl-3 | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 2071/KSD | 29/02/2024 |  | APEX ENGINEERING | 2.53 | 0 | 100
4 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV A) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-5) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 2080/KSD | 29/02/2024 |  | APEX ENGINEERING | 2.27 | 0 | 100
5 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 2296/BWD | 20/06/2024 |  | M/S DATTA ENTERPRISE | 125.36 | 0 | 2
6 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | 608/BWD | 11/02/2025 |  | MANASH GHOSH | 265.4 | 0 | 51
Total | [12 empty] | 855.08 | 0 | 0