## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07447 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-I | 90/NAD-I | 22/01/2021 |  | APURBA MANDAL | 70.37 | 70.02 | 100
2 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07447 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. (Sl no.-02) Tender No. 229/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | 291/NAD-I | 04/02/2021 |  | CHANDAN ROY | 2.44 | 2.44 | 0
Total | [12 empty] | 72.8 | 72.46 | 99.52