## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Supply & delivery of ISI marked 50 mm. dia Galvanised Miled Steel Tube (Medium) conforming to IS: 1239 (Part-I)/2004 (sixth revision) with latest amendment under Rajarhat Store for the scheme of "Running Water Supply arrangement for Govt Institution (School/AWC/Health Centre) 225 nos in Durgapur CH-I, CH-II, Sanksahar, Bodre and Tardah GPS of Bhangar-I Block (CANNING PURBA A.C) of South 24 Pgs District under South 24 Pgs W/S Divn-I, PHE Dte (SM/10118) | Assistant Engineer |  | 4088/RS | 12/07/2022 |  | NEZONE TUBES LIMITED | 0 | 0 | 0
2 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Nadia Division. |  | Junior Engineer | 4893/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 12.44 | 0 | 0
3 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block ( Phase -A) in Nadia District under Nadia Division P.H.E. Dte. SLNo.7 | Assistant Engineer | Junior Engineer 3 | 894/ND | 19/02/2021 |  | ALOKE ENTERPRISE | 97.09 | 0 | 0
Total | [12 empty] | 109.53 | 0 | 0