## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08862 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | 1414/NAD-I | 08/11/2021 |  | JOY HIND TUBE WELLS | 44.57 | 44.25 | 100
2 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08862 | Retrofitting | Interconnection between 1st and 2nd Tubewell Rising Main at Chupria Zone-II W/S Scheme in Hanskhali block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | 2371/NAD-I | 06/10/2023 |  | BISWAS CONSTRUCTION | 14.67 | 0 | 100
3 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08862 | Retrofitting | Construction of AIRP capacity (92m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-II under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | 1119/NAD-I | 19/07/2024 |  | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 223.31 | 0 | 0
Total | [12 empty] | 282.54 | 44.25 | 15.66