## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Nadia Arsenic Division-I. |  | Junior Engineer | 1334/RS | 25/02/2022 |  | PUNAM KUMAR GUPTA | 42.25 | 0 | 0
2 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VI (BALIA) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | 429/NAD-I | 07/03/2022 |  | BIDYUT KUMAR | 87.82 | 81.95 | 100
3 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballavpur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | 514/NAD-I | 28/03/2022 |  | MANGES INDUSTRIAL CORPORATION | 125 | 111.93 | 100
4 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Supply & delivery of ISI marked 50 mm. dia Galvanised Miled Steel Tube (Medium) conforming to IS: 1239 (Part-I)/2004 (sixth revision) with latest amendment under Rajarhat Store for the scheme of "Running Water Supply arrangement for Govt Institution (School/AWC/Health Centre) 208 nos in Jainagar-I and Thakurpukur Mahestala Blocks of South 24 Pgs District under South 24 Pgs W/S Divn-I, PHE Dte (SM/10116) |  | Junior Engineer | 4090/RS | 12/07/2022 |  | UTKARSH INDIA LIMITED | 0 | 14.93 | 0
5 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Malda Division. |  | Junior Engineer | 4880/RS | 31/08/2022 |  | BALAJI TRADERS | 0 | 14.9 | 0
6 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl.No. 03) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | 965/NAD-I | 07/07/2022 |  | M/S K.P. CONSTRUCTION | 78.62 | 51.82 | 40
7 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House Darrappur Z-VIA under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | 1531/ NAD-I | 30/08/2022 |  | MAA LAXMI ENTERPRISE | 17.21 | 17.1 | 100
8 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Nadia Arsenic Division-I. |  |  | 5078/RS | 07/09/2022 |  | A.K.INDUSTRIES | 14.93 | 0 | 0
9 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Ballavpur Zone- VII under Surface (Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | 1964 / NAD-I | 14/10/2022 |  | D.C. RAKSHIT & SONS INDIA PVT LTD | 29.25 | 28.66 | 100
10 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of 550 cum capacity Over Head Reservoir, Boundary Wall, Switch Room and other allied works at Balia (Zone-VI) under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division ? I, P. H..E. Dte (SL NO. 04) | Assistant Engineer-II | Junior Engineer-IV | 1367/NAD-I | 12/05/2023 |  | M/S COSMOPOLITAN TRADERS | 23.55 | 21.53 | 100
11 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Retrofitting work at Lakshmipur and Srinagar under Ballavpur W/S Scheme in connection with augmentation of Ballavpur W/S Scheme under Chakdah (Part) W/S Scheme under JJM under NadiaArsenic Division-I, PHE Dte. (sl.no.18) | Assistant Engineer-II | Junior Engineer-I | 2243/NAD-I | 21/09/2023 |  | MANGES INDUSTRIAL CORPORATION | 9.54 | 9.45 | 100
12 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of different type road under Chanduria I ,Tatla I, Tatla II,Hingnara GP in connection with augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Block, by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. within Chakdah Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. | Assistant Engineer-II | Junior Engineer-IV | 132/NAD-I | 22/04/2025 |  | M/S DIPAK ENTERPRISE | 16.32 | 0 | 100
Total | [12 empty] | 444.49 | 352.26 | 79.25