## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Providing 2032 nos FHTC in Santoshpur, Teghari & Chandur villages of Santoshpur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1696/Hug | 17/12/2020 |  | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 0 | 66.59 | 0
2 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under North 24 PGS W/S. Division-I. |  |  | 4898/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 0 | 0
3 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | DEPOYMENT OF SECURITY GUARD |  |  | 825/HUG (T/N 373/HUG OF 2 | 31/03/2021 |  | P.B. ENTERPRISE (PINTU BHADURI) | 3.61 | 3.61 | 0
4 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | EMD/SD (WBPHE/EE/06/HUG/2018-19) Sl.4 |  |  | 1303/Hug | 14/08/2020 |  | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.64 | 0 | 0
5 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Sinking of tube-well by D.R. Rig method at SANTOSHPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 538/HUG | 20/02/2024 |  | ANIRUDDHA FARUQUE | 15.99 | 0 | 100
6 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of SANTOSHPUR PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | 4074/HUG | 19/12/2024 |  | RAJ CONSTRUCTION | 9.25 | 0 | 0
7 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Road restoration at Santoshpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 844/CHAN | 21/07/2025 |  | BIMAL KUMAR HALDER | 4.66 | 0 | 50
8 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Santoshpur W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 891/CHAN | 21/07/2025 |  | M/S RAJKUMAR KHAN | 4.97 | 0 | 100
9 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Repairing of pump house at 1St and 2nd TW site of Santoshpur PWSS under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 925/CHAN | 21/07/2025 |  | M/S RAJKUMAR KHAN | 4.33 | 0 | 25
10 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Repairing of boundary wall at old 1st tubewell site of Santoshpur PWSS Scheme under Chandannagar Sub-Division, PHE Dte | Assistant Engineer (Civil) |  | 1075/CHAN | 31/07/2025 |  | M/S RAJKUMAR KHAN | 4.18 | 0 | 0
11 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme | SM/07460 | Retrofitting | Installation of sluice valve for Santoshpur W/S Scheme under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1030/Chan | 31/07/2025 |  | M/S RAJKUMAR KHAN | 0.97 | 0 | 100
Total | [12 empty] | 52.6 | 70.2 | 133.45