## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of Lakshmipur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | 1995/Hug | 12/11/2021 |  | S. B. CONSTRUCTION | 0 | 0 | 100
2 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | 124/Hug | 19/01/2022 |  | SADHUKHAN ENTERPRISE | 3.79 | 0 | 100
3 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Providing 362nos F.H.T.C. in Lakshmipur &Barama Village of Lakshmipur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Goghat-I] |  |  | 392/Hug | 15/02/2021 |  | M/S T.K.B. CONSTRUCTION | 18.95 | 18.95 | 0
4 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Providing 477 nos F.H.T.C. in Dighara Village of Lakshmipur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] |  |  | 391/Hug | 15/02/2021 |  | DILIP KUMAR GHOSH | 13.44 | 13.44 | 0
5 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | DEPLOYMENT OF SECURITY GUARD |  |  | 821/HUG (T/N 48HUG OF 20- | 31/03/2021 |  | S.K. GHOSH | 3.22 | 3.22 | 0
6 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Providing 1122 nos F.H.T.C. in Haridaspur, Chapta & Shikhira Village of Chapta and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] |  |  | 383/Hug | 15/02/2021 |  | DAS ENTERPRISE (SAMIR DAS) | 0 | 0 | 50
Total | [12 empty] | 39.4 | 35.62 | 90.39