## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing1593 nos F.H.T.C. in Kanraria, Keshabchak,Mohanbati & Shibpur Village of Kulteghari and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Tarakeswar] | Assistant Engineer (Civil) | Junior Engineer (Civill) | 941/Hug | 06/05/2021 |  | M/S S.G. CONSTRUCTION | 0 | 34.67 | 100
2 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under North 24 PGS W/S. Division-I. |  |  | 4898/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 0 | 0
3 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Tullyan, Keshabchak, Kulteghari, Mohanbati Mouza in KULTEGHORI PWSS, Block Tarakeswar under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 2852/HUG | 16/12/2022 |  | S K ENTERPRISE | 14.97 | 0 | 100
4 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | 262/Hug | 03/02/2021 |  | K JAGADHATRY & CO | 0.16 | 0 | 0
5 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing 967 nos F.H.T.C. in Nachhipur & Tulyan Village of Kulteghari and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Tarakeswar] | Assistant Engineer (Civil) |  | 942/Hug | 06/05/2021 |  | M/S RAJKUMAR KHAN | 56.05 | 32.53 | 0
6 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing 1720 nos F.H.T.C. in Kashwara & Paunan village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] |  |  | 1681/Hug | 17/12/2020 |  | M/S S.G. CONSTRUCTION | 0.06 | 0 | 0
7 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Road restoration at Kultegori water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | 865/CHAN | 21/07/2025 |  | R.K. TRADERS | 4.79 | 0 | 90
8 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Road restoration at Kultegori water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | 866/CHAN | 21/07/2025 |  | JOY GURU ENTERPRISE | 4.89 | 0 | 50
9 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Road restoration at Kultegori water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | 864/CHAN | 22/07/2025 |  | TOTON MONDAL | 4.88 | 0 | 50
10 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Kulteghari W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 890/CHAN | 21/07/2025 |  | M/S RAJKUMAR KHAN | 4.97 | 0 | 100
11 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Repairing of boundary wall at old 1st tubewell site of Kulteghari PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 917/CHAN | 21/07/2025 |  | M/S RAJKUMAR KHAN | 4.17 | 0 | 0
12 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Repairing of pump house at 1St and 2nd TW site of Kulteghari PWSS under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 922/CHAN | 21/07/2025 |  | MAHABIR CONSTRUCTION | 4.39 | 0 | 100
Total | [12 empty] | 99.33 | 67.2 | 67.65