## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under North 24 PGS W/S. Division-I. |  |  | 4898/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 8.21 | 0
2 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Haripal Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | 270/Chan | 31/05/2022 |  | Srijan Ecological Upliftment Pvt. Ltd. | 2.83 | 2.84 | 0
3 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply & delivery of ISI marked 10 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] | Assistant Engineer |  | 4844/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 3.39 | 0
4 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Route Survey, Design Drawing & DPR Preparation of HARIPAL ZONE-II PWSS under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) |  | 275/Chan | 31/05/2022 |  | Srijan Ecological Upliftment Pvt. Ltd. | 3.45 | 3.21 | 0
5 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under New Town Kolkata W/S. Division-I. |  | Junior Engineer | 3858/RS | 07/07/2022 |  | ADITYA ENTERPRISE | 0 | 11.4 | 0
6 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Chak Ananta (Part) Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6 M X 3.0M )& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1563/HUG | 29/07/2022 |  | M/S R.M. CONSTRUCTION | 142.15 | 101.96 | 70
7 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply & delivery of ISI marked 12 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] |  |  | 4845/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 0 | 0
8 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1345/Hug | 29/06/2022 |  | SOUMYADIP DE | 110.86 | 35.86 | 99
9 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Balance work for special repairing of UPVC pipeline damaged due to construction of road with drain of PWD at Balarampur of Ashutosh G.P. under the command area of Haripal water supply scheme under Chandannagar Sub-Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | 337/CHAN | 12/07/2022 |  | Gour Kumar Das | 3.88 | 3.05 | 0
10 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS within Aminpur & Chandinagar (Part) Mouza at HARIPAL Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | 1347/Hug | 29/06/2022 |  | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 183.24 | 145.88 | 50
11 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) & Aminpur Mouza & Functional Household tap Connection, Construction of Boundary Wall & Switch Room at Proposed 2nd T.W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 2472/HUG | 18/11/2022 |  | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 157.64 | 142.45 | 100
12 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 2510/HUG | 22/11/2022 |  | SPG ENTERPRISES | 27.65 | 26.53 | 0
13 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Krishnapur, Chak Ananta(Part), Haripal, Chandinagar(Part), Kamar Chandi Mouza & Functional Household tap Connection, Rising Main at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1599/HUG | 04/08/2022 |  | ANALYTICA FOODTECH SERVICES PVT. LTD. | 193.1 | 161.04 | 100
14 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Haripal water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 840/ED | 14/02/2023 |  | DAS ENTERPRISE | 32.23 | 21.41 | 50
15 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) Mouza & Functional Household tap Connection, Rising Main, Construction of Boundary Wall & Switch Room at H/W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 426/HUG | 15/02/2023 |  | SOUMYADIP DE | 128.29 | 123.02 | 100
16 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | 1345/HUG | 29/06/2022 |  | Soumyadip De | 110.86 | 70.82 | 0
17 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 0 | 11.2 | 100
18 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 2499/HUG | 22/11/2022 |  | B.R SUPPLIERS | 13.81 | 0 | 100
19 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2337/RS | 24/07/2023 |  | RASHMI METALIKS LIMITED | 13.39 | 13.65 | 2
20 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Horizontal road crossing by trenchless method at Gopinagar More of Baidyabati- Tarakeswar Road (SH-12)and Haripal Station to Basudevpur More Road under Haripal (Zone-II) PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | 2830/HUG | 14/09/2023 |  | SOUMYADIP DE | 8.98 | 8.98 | 100
21 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of BANIDPUR PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1281/HUG | 04/05/2023 |  | AYUSH ENTERPRISE | 93.94 | 93.5 | 100
22 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Renovation of existing building at Haripal head work site for multipurpose use under CHANDANNAGAR Sub-Divn. of Hooghly Division, P.H.E. Dte. at Haripal head work site of Haripal (Zone - I) water supply scheme. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 3230/HUG | 03/11/2023 |  | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 10.53 | 0 | 100
23 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 1381/HMSD | 14/06/2023 |  | DEBASHISH GHOSH | 1.21 | 1.45 | 20
24 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | upply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admis | Assistant Engineer |  | 234/RS | 22/01/2024 |  | RASHMI METALIKS LIMITED | 70.24 | 0 | 5
25 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Gopinagar, Aminpur and Khamarchandi Village of Haripal Zone II and it's adjoining mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte [Block- Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | 820/HUG | 11/03/2024 |  | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 6.63 | 0 | 0
26 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under HARIPAL (PHASE-II) Block of Chandannagar Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 961/CHAN | 21/11/2024 |  | BIMAL KUMAR HALDER | 3 | 3 | 100
27 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under HARIPAL (PHASE-I) Block of Chandannagar Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 960/CHAN | 21/11/2024 |  | BIMAL KUMAR HALDER | 3.53 | 3.53 | 100
28 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Construction of approach road for Haripal Zone - II HWS at Mouza Gopinagar, JL no. 73, Dag No. 870, Khatian No. 1171 & 984 under Haripal PWSS under Chandannagar Sub- Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 3799/HUG | 26/11/2024 |  | SOUMYADIP DE | 4.19 | 4.19 | 100
29 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Balance Pipeline from Bharat Marbel to Basudebpur More under Haripal (Zone - II) Piped Water Supply Scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 649/HUG | 10/03/2025 |  | SOUMYADIP DE | 10.45 | 0 | 100
30 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - I W/S Scheme for the period 01.02.2025 to 31.03.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 118/Chan | 30/01/2025 |  | MODERN ENGINEERING CO. | 0.97 | 0.97 | 0
31 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 1st continuation work order for the work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - I W/S Scheme" for the period 01.04.2025 to 31.05.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 422/Chan | 28/03/2025 |  | MODERN ENGINEERING CO. | 0.97 | 0.97 | 0
32 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Haripal Zone1 W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 886/CHAN | 21/07/2025 |  | G.K ENTERPRISE (GOUR KUMAR DAS) | 4.82 | 0 | 100
33 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Construction of structural shed for storing Mechanical pumps and machineries at Haripal Zone-I OHR work site under Chandannagar Sub division within Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 898/CHAN | 21/07/2025 |  | JOY GURU ENTERPRISE | 4.88 | 0 | 0
34 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Bamboo Piling works beside the pond supporting DI Pipe and Road restoration at Chak Ananta village of Haripal Zone - I PWSS under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 878/CHAN | 21/07/2025 |  | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 1.45 | 0 | 100
35 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 3rd continuation of Operation & Maintenance of OHR, Laying Distribution System including Street Stand post, FHTC, Rising main & other essential components of HARIPAL, ENAYETPUR, KAMARKUNDU W/S Scheme for the period from 01/01/2025 to 31/01/2025 under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E.Dte. (Sl No.:- 12) | Assistant Engineer (Civil) | Junior Engineer (Civill) | 4192/HUG | 27/12/2024 |  | G.K ENTERPRISE (GOUR KUMAR DAS) | 1.96 | 0 | 0
36 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 2nd Continuation work order for work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - I W/S Scheme" for the period 01.06.2025 to 31.07.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 679/Chan | 29/05/2025 |  | MODERN ENGINEERING CO. | 0.97 | 0 | 0
37 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 2nd Continuation work order for the work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - II W/S Scheme" for the period 01.06.2025 to 31.07.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 680/Chan | 29/05/2025 |  | AMBIAN INFRASTRUCTURE (PARTNERSHIP) | 0.99 | 0 | 0
38 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 3rd Continuation work order for the work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - I W/S Scheme" for the period 01.08.2025 to 30.09.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1028/Chan | 30/07/2025 |  | MODERN ENGINEERING CO. | 0.97 | 0 | 0
39 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 1st continuation work order for the work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - II W/S Scheme" for the period 01.04.2025 to 31.05.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 426/Chan | 28/03/2025 |  | AMBIAN INFRASTRUCTURE (PARTNERSHIP) | 0.99 | 0 | 0
40 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 3rd Continuation work order for the work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - II W/S Scheme" for the period 01.08.2025 to 30.09.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1050/Chan | 31/07/2025 |  | AMBIAN INFRASTRUCTURE (PARTNERSHIP) | 0.99 | 0 | 0
41 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 4th Continuation work order for work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - I W/S Scheme" for the period 01.10.2025 to 16.11.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1468/Chan | 25/09/2025 |  | MODERN ENGINEERING CO. | 0.77 | 0 | 0
42 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | 4th Continuation work order for the work "Operation & Mtc of OHR, FHTC & Laying Distribution System including Street Stand Post, Rising Main & other essential components of Haripal Zone - II W/S Scheme" for the period 01.10.2025 to 16.11.2025 under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1469/Chan | 25/09/2025 |  | AMBIAN INFRASTRUCTURE (PARTNERSHIP) | 0.79 | 0 | 0
43 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL | SM/09982 | Augmentation | Providing F.H.T.C in leftout portion (Anantapur, Avirampur, Mosapur, Dignagar, Gabati mouzas) of Haripal water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 2832/HUG | 17/11/2025 |  | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 19.67 | 0 | 100
Total | [12 empty] | 1377.26 | 1002.49 | 72.79