## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Augmentation of BERABARI Water Supply Scheme with Construction of 600 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS(S-2) & Functional Household tap Connection within Chak Kalikabari, Beraberi, Jampukur, Madhusudanpur, Khaser Bheri & Khagragachhi Mouza, Switch room, Boundary wall, Rising Main, Repairing of existing Switch Rooms at Singur Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1383/Hug | 07/07/2022 |  | S & P ENTERPRISE | 461.01 | 460.96 | 50
2 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Barasat Arsenic Division. |  |  | 4897/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 2.71 | 0
3 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under North 24 PGS W/S. Division-I. |  |  | 4898/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 245.1 | 8.26 | 0
4 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 10 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] | Assistant Engineer |  | 4844/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 3.39 | 0
5 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Neroakhola W/S. & Mtc. Division. |  | Junior Engineer | 4877/RS | 31/08/2022 |  | BALAJI TRADERS | 0 | 17.19 | 0
6 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under New Town Kolkata W/S. Division-I. |  | Junior Engineer | 3858/RS | 07/07/2022 |  | ADITYA ENTERPRISE | 0 | 9.48 | 0
7 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 371/CMSD-II(D) | 29/07/2022 |  | C.M. Enterprise | 4.97 | 4.55 | 0
8 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-II, HARTIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | 370/CMSD-II(D) | 29/07/2022 |  | C.M. Enterprise | 2.93 | 2.75 | 0
9 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBEWELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 369/CMSD-II(D) | 28/07/2022 |  | C.M. Enterprise | 3.52 | 2.6 | 0
10 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | SUPPLY 7 DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKKS FOR CONSTRUCTION OF TUBE WELL aUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 372/CMSD-II(D) | 29/07/2022 |  | C.M. Enterprise | 3.52 | 2.62 | 0
11 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 12 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] |  |  | 4845/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 0 | 0
12 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 100 mm. dia Galvanised Miled Steel Tube (Medium) conforming to IS: 1239 (Part-I)/2004 (sixth revision) with latest amendment under Rajarhat Store for different scheme of South 24 Pgs District under South 24 Pgs W/S Divn-I, PHE Dte | Assistant Engineer |  | 4301/RS | 21/07/2022 |  | NEZONE TUBES LIMITED | 36.2 | 31.77 | 0
13 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITHJ OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 368/CMSD-II(D) | 28/07/2022 |  | C.M. Enterprise | 4.97 | 4.62 | 0
14 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | 367/CMSD-II(D) | 28/07/2022 |  | C.M. Enterprise | 2.93 | 2.78 | 0
15 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 1918/ED | 21/11/2022 |  | Glacier Engineering Co. | 10.67 | 10.38 | 0
16 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 98.79 | 28.28 | 100
17 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 375/CMSD-II (D) | 01/08/2022 |  | C.M. Enterprise | 4.97 | 4.7 | 0
18 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | PROVIDING DRILLINGCREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | 374/CMSD-II (D) | 01/08/2022 |  | C.M. Enterprise | 2.93 | 2.75 | 0
19 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 376/CMSD-II (D) | 01/08/2022 |  | C.M. Enterprise | 3.52 | 2.6 | 0
20 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 100 mm. dia Galvanised Miled Steel Tube (Medium) conforming to IS: 1239 (Part-I)/2004 (sixth revision) with latest amendment under Rajarhat Store for different W/S scheme vide scheme code SM/11285 against Burdwan Division | Assistant Engineer |  | 248/RS | 16/01/2023 |  | UTKARSH INDIA LIMITED | 78.7 | 78.7 | 0
21 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Day to day carriage of different materials(Like DI Pipes, DI Fittings, AC Pipes ,MSERW Pipes, GI Pipes, Ferrule,TMT Bar e.t.c) from Kalyani Stores under Resources Divn , P.H.E.Dte to different work sites in rural / urban areas in any area of West Bengal for the year 2022-2023. | Assistant Engineer |  | 475/RS | 07/02/2023 |  | CALCUTTA TRANSPORT AGENCY | 471.43 | 28.05 | 0
22 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply & delivery of ISI marked 100 mm. dia Galvanised Miled Steel Tube (Medium) conforming to IS: 1239 (Part-I)/2004 (sixth revision) with latest amendment under Rajarhat Store for different W/S scheme vide scheme code SM/11283 against Burdwan Division | Assistant Engineer |  | 250/RS | 16/01/2023 |  | UTKARSH INDIA LIMITED | 0 | 21.42 | 0
23 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Augmentation of BERABARI Water Supply Scheme with Laying Distribution System (S-1) & Functional Household Tap Connection at Baje Melia & Hijli Mouzas, Construction of Switch room at Proposed T.W Site, Boundary wall at Singur Block under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1583/HUG | 02/08/2022 |  | M/S BISWAS CONSTRUCTION | 246.26 | 204.24 | 50
24 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Route Survey, Design Drawing & DPR Preparation Beraberi PWSS under Chandannagar Sub Division , PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | 168/chan | 24/03/2022 |  | Srijan Ecological Upliftment Pvt. Ltd. | 4.17 | 4.13 | 0
25 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | CONTINUATION FOR HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. |  |  | 35/CMSD-II | 10/02/2023 |  | ASHUTOSH PAL | 0.29 | 0.29 | 0
26 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 1792/ED | 02/11/2022 |  | ALPHA ENTERPRISE | 10.67 | 10.38 | 99
27 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 1548/ED | 20/09/2022 |  | PERFECT AIRCONDITION | 9.66 | 9.4 | 99
28 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2502/RS | 10/08/2023 |  | ELECTROSTEEL CASTINGS LIMITED | 112.51 | 0 | 35
29 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2499/RS | 10/08/2023 |  | ELECTROSTEEL CASTINGS LIMITED | 0 | 118.13 | 80
30 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2631/RS | 25/08/2023 |  | RASHMI METALIKS LIMITED | 92.98 | 86.19 | 9
31 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5672/RS | 01/11/2022 |  | TATA METALIKS LTD | 103.46 | 0 | 100
32 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 142/RS | 16/01/2024 |  | TATA METALIKS LTD | 3.06 | 0 | 4
33 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BERABERI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 386/HUG | 08/02/2024 |  | BHATTACHARJEE CONSTRUCTION | 15.56 | 13.47 | 100
34 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. V, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | 338/ED | 21/02/2024 |  | DEY ENTERPRISE | 10.41 | 10.13 | 90
35 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 3379/HUG | 21/11/2023 |  | OSMAN SEKH | 16.05 | 15.97 | 100
36 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Providing connection in leftout portion of beraberi mouza under Beraberi water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. |  |  | 2341/HUG | 19/06/2024 |  | MAA TARA CONSTRUCTION | 31.82 | 0 | 0
37 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Horizontal Auger boring with water jet system including road restoration Work at Baje Melia & Hijli Mouzas under Beraberi Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly. |  |  | 3675/HUG | 13/11/2024 |  | M/S BISWAS CONSTRUCTION | 42.93 | 0 | 0
38 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Laying DI pipe and orther allied work for BERABERI PWSS UNDER singur block under chandannagar subdivision of of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 3618/HUG | 05/11/2024 |  | DAFFODIL | 72.7 | 0 | 80
39 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Special repairing to improve water supply at mouza madya-hijla , madhusudanpur , chak-kalikaburi under Beraberi W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 908/CHAN | 21/07/2025 |  | M/S BISWAS CONSTRUCTION | 4.91 | 0 | 100
40 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Special repairing to improve water supply at mouza Bajemilia ,beraberi , jampukur under Beraberi W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 899/CHAN | 21/07/2025 |  | M/S BISWAS CONSTRUCTION | 4.94 | 0 | 100
41 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI | SM/09984 | Augmentation | Construction of Adjacent two side boundary wall with gate, internal pathway & sanitary arrangement at Beraberi 2nd pump house in Bajemelia Mouza under singur Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 910/CHAN | 21/07/2025 |  | RITAM ENTERPRISE | 2.7 | 0 | 100
Total | [12 empty] | 2221.22 | 1202.89 | 54.15