## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admissi |  |  | 638/RS | 24/06/2020 |  | TATA METALIKS LTD | 0 | 0.05 | 0
2 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Siliguri W/S. Division. |  | Junior Engineer | 4878/RS | 31/08/2022 |  | BALAJI TRADERS | 0 | 30.75 | 0
3 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RAGHUNATHPUR(Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 01 | Assistant Engineer (Civil) |  | 1953/HUG | 07/09/2022 |  | Arun Seal and Co. | 23.79 | 23 | 0
4 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Reservoir of Capacity 1,36,200 litre of Raghunathpur & Damra Water Supply Scheme under Chinsurah Sub - Division of Hooghly Division, P.H.E. Dte. SL NO - 03 | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1906/HUG | 05/09/2022 |  | M/S SHIVAM UDYOG | 25.15 | 25.12 | 0
5 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RGHUNATHPUR(Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 02 | Assistant Engineer (Civil) |  | 1954/HUG | 07/09/2022 |  | Das Enterprise (SAMIR DAS) | 23.78 | 22.92 | 0
6 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Hooghly Division. |  | Junior Engineer | 5073/RS | 07/09/2022 |  | A.K.INDUSTRIES | 30.75 | 0 | 0
7 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | Driller In Charge | Junior Engineer | 289/CMSD-II (D) | 01/06/2022 |  | C.M. Enterprise | 0 | 4.73 | 0
8 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Augmentation of Raghunathpur (ZONE-I) with LDS, FHTC, Rising Main & Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 2172/HUG | 28/09/2022 |  | PRADIP KUMAR ADHYA | 433.19 | 235.24 | 55
9 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Augmentation of Raghunathpur (ZONE-II) with LDS, FHTC, Laying Rising Main & Interconnection with Distribution system at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | 1572/HUG | 01/08/2022 |  | DAS ENTERPRISE (SAMIR DAS) | 96.59 | 87.61 | 50
10 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | SUPPLY & DELIVERY CONSUMBLES SITE FOR CONSTRUCTION OF TUBE WELL AT RAGHUNATHPUR W/S SCH TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | 290/CMSD-II (D) | 01/06/2022 |  | C.M. Enterprise | 2.45 | 2.4 | 0
11 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | 288/CDD | 01/06/2022 |  | C.M. Enterprise | 3.07 | 2.9 | 0
12 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Preparation of DPR for Augmentation of Raghunathpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) |  | 129/CH | 17/02/2022 |  | Srijan Ecological Upliftment Pvt. Ltd. | 4.13 | 4.12 | 0
13 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Raghunathpur water supply scheme TW No I II III and IV, Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 855/ED | 14/02/2023 |  | D. K. ELECTRIC | 42.97 | 42.89 | 95
14 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | 444/HUG | 16/02/2023 |  | SHREEOM ENTERPRISE | 6.29 | 6.29 | 0
15 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 445/HUG | 16/02/2023 |  | DAS TRADING | 12.25 | 12.25 | 100
16 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | 1st Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.09.22 to 30.11.22 under Chinsurah Sub- Division P.H.E Dte. SL-15 | Assistant Engineer (Civil) |  | 1822/HUG | 31/08/2022 |  | M/S BISWAS CONSTRUCTION | 1.48 | 0 | 0
17 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.12.2022 to 31.12.2022 under Chinsurah Sub- Division P.H.E Dte. | Assistant Engineer (Civil) |  | 2593/HUG | 30/11/2022 |  | M/S BISWAS CONSTRUCTION | 0.49 | 0 | 0
18 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2337/RS | 24/07/2023 |  | RASHMI METALIKS LIMITED | 37.78 | 0 | 2
19 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Assistant Chief Engineer (M/E), PHE Dte. |  |  | 2382/HMSD | 27/12/2022 |  | BHOLA DEY | 1.11 | 1.11 | 1
20 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | 3rd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.01.23 to 31.08.22 under Chinsurah Sub- Division P.H.E Dte. SL-15 | Assistant Engineer (Civil) |  | 2974/HUG | 30/12/2022 |  | M/S BISWAS CONSTRUCTION | 3.96 | 0 | 0
21 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Day to day washing and cleaning of Administrative Building of Chinsurah Sub-Division Office, Supply and fitting, fixing of different items related to electrical and plumbing at the different units of the office premises of Chinsurah Sub-Division. P.H.E Dte. for the period of 12 (twelve) months. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 729/CH | 26/08/2022 |  | DAS ENTERPRISE (SAMIR DAS) | 1.99 | 0 | 0
22 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Crossing of Railway underpass with GI pipe and Replace and Relayling of DI pipe of Raghunathpur water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 757/Ch | 05/09/2022 |  | DAS ENTERPRISE (SAMIR DAS) | 1.13 | 0 | 0
23 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Dismantaling of old damaged Switch room at Ragunathpur 3rd Tube well site of Agumentation of Raghunathpur W/S Scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) |  | 690/CH | 27/07/2023 |  | SRI KRISHNA ENTERPRISE | 0.31 | 0.31 | 100
24 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2283/RS | 18/07/2023 |  | TATA METALIKS LTD | 0 | 17.69 | 45
25 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of RAGHUNATHPUR Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 3315/HUG | 10/11/2023 |  | DIBYENDU DHARA | 8.56 | 7.98 | 65
26 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | 4738/ED | 15/12/2023 |  | S. DUTTA | 0.12 | 0 | 90
27 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Shifting House Connection from existing main to new main and allied works from Bispara to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 532/CH | 14/06/2024 |  | R.K. TRADERS | 4.85 | 0 | 75
28 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Shifting House Connection from existing main to new main and allied works from Kuntighat More of Bispara of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 541/CH | 14/06/2024 |  | R.K. TRADERS | 4.84 | 0 | 75
29 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Shifting HDPE pipeline and allied works from Kuntighat to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 542/CH | 14/06/2024 |  | R.K. TRADERS | 3.15 | 0 | 75
30 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME | SM/11969 | Augmentation | Laying HDPE Pipeline From existing Distribution System for providing FHTC at Raghunathpur Z-II W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | 229/CH | 19/02/2025 |  | DAS ENTERPRISE (SAMIR DAS) | 4.46 | 0 | 50
Total | [12 empty] | 778.67 | 527.37 | 67.73