## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Repairing of Concrete Roads damaged due to Laying of Augmentation work of GHOSHPUR Water Supply Scheme under KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | 1102/HUG | 17/04/2023 |  | ARATI ENGINEERING | 18.55 | 0 | 0
2 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at GHOSHPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | 742/HUG | 15/03/2023 |  | MAYA CONSTRUCTION | 11.32 | 11.32 | 100
3 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | AUGMENTATION of GHOSHPUR Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-KHANAKUL-I, District:- Hooghly. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | 2414/HUG | 11/08/2023 |  | GHOSH BROTHERS | 333.22 | 233.14 | 80
4 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | AUGMENTATION of GHOSHPUR Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-KHANAKUL-I, District:- Hooghly. [AUGMENTATION SCHEME] | Assistant Engineer |  | 2037/HUG | 12/07/2023 |  | GHOSH BROTHERS | 333.22 | 0 | 0
5 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2631/RS | 25/08/2023 |  | RASHMI METALIKS LIMITED | 80.25 | 0 | 9
6 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghoshpur water supply scheme, T.W. No. I, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 335/ED | 21/02/2024 |  | DEY ENTERPRISE | 10.43 | 0 | 0
7 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | 1176/ED | 14/06/2024 |  | P.K. ENTERPRISE | 1.09 | 0 | 0
8 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Protection works and other allied works at Head Work Site of GHOSHPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte |  |  | 4056/HUG | 19/12/2024 |  | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 23.74 | 0 | 0
9 |  |  | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block |  |  | Protection works and other allied works at 3Nos. Proposed TubeWell Sites of Ghoshpur Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | 4053/HUG | 19/12/2024 |  | M/S KAUSAR CONSTRUCTION | 23.36 | 0 | 0
Total | [12 empty] | 835.17 | 244.46 | 29.27