## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOOGHLY | Hooghly Division | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | SM/18965 | Augmentation | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | 3312/HUG | 10/11/2023 |  | DILIP KUMAR GHOSH | 23.57 | 0 | 32
2 | HOOGHLY | Hooghly Division | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | SM/18965 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | 3476/HUG | 29/11/2023 |  | SPG ENTERPRISES | 35.15 | 12.28 | 20
3 | HOOGHLY | Hooghly Division | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | SM/18965 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of GOURHATI piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | 4525/ED | 23/11/2023 |  | UNIVERSAL ENTERPRISES | 21.49 | 0 | 0
4 | HOOGHLY | Hooghly Division | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block | SM/18965 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of GOURHATI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | 4084/HUG | 19/12/2024 |  | UNIQUE AGENCY | 11.23 | 0 | 98
Total | [12 empty] | 91.45 | 12.28 | 13.43