## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme | Assistant Engineer |  | 353/PD | 25/02/2021 |  | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 205.74 | 46.76 | 100
2 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of RCC Back Wash Reservoir of capacity 57.00 Cum at AT WTP Campus site of Marbel Lake W/S Scheme at Ajodhya Hill W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | Assistant Engineer |  | 640/PSD | 21/09/2021 |  | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 4.82 | 0 | 85
3 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Office Cum Godown at Ist Floor of Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer(HQ) | Junior Engineer | 538/PD | 01/04/2022 |  | BOSE CONSTRUCTION | 20.61 | 0 | 98
4 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Fencing on The Entry of Marble Lake under Marble Lake W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | 507/PSD | 12/08/2022 |  | ANUP KUMAR SAHA | 1 | 0 | 100
5 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Extension Of Distribution Line Near marble Lake road to Dulgubera and Laying of GI Pipe over Hatinada Khal Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | 509/PSD | 12/08/2022 |  | ANUP KUMAR SAHA | 4.75 | 0 | 100
6 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying Remaining Portion of distribution pipe Line due to shifting of OHR Location Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | 514/PSD | 12/08/2022 |  | ANUP KUMAR SAHA | 4.62 | 0 | 100
7 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-1) | Assistant Engineer |  | 1633/PD | 28/10/2022 |  | ANUP KUMAR SAHA | 4.25 | 0 | 75
8 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-2) | Assistant Engineer |  | 1634/PD | 28/10/2022 |  | ANUP KUMAR SAHA | 4.25 | 0 | 100
9 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of electro mechanical equipments submersible pump motor sets for raw water pump house, centrifugal pump motor sets for clear water pump house at Marble Lake piped water supply scheme , Block : Baghmundi, under Purulia Mechanical Division, P.H.E Dte.Dist : Purulia(Only trial Operation and Guarding part) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 354/PMD | 01/06/2022 |  | Combine Enterprises | 0.68 | 0 | 98
10 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of electro mechanical equipments submersible pump motor sets of Raw water pump house , centrifugal pump motor sets for Clear water pump house at Marble Lake piped water supply scheme , Block : Baghmundi under Purulia Mechanical Division PHE Dte. Dist : Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | 471/PMD | 28/07/2021 |  | COMBINE ENTERPRISES | 43.7 | 0 | 100
11 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of electro mechanical equipments submersible pump motor sets for Raw water pump house , centrifugal pump motor sets for Clear water pump house at Marble Lake piped water supply scheme, Block: Baghmundi under Purulia Mechanical Division PHE Dte.Dist : Purulia(Only trial Operation and Guarding part) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 516/PMD | 04/08/2022 |  | Combine Enterprises | 0.68 | 0 | 98
12 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of electro mechanical equipment's submersible pump motor sets for Raw water pump house , centrifugal pump motor sets for clear water pump house at Marble Lake piped water supply Scheme , Block Baghmundi , under Purulia Mechanical Division PHE Dte. Dist : Purulia (Only Trial operation and guarding part) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 239/PMD | 07/04/2022 |  | Combine Enterprises | 0.68 | 0 | 98
13 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of Voltage stabilizer ,valves, external illumination arrangement with allied works at Marble lake PWSS Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 307/PMD | 16/03/2023 |  | COMBINE ENTERPRISES | 13.17 | 0 | 60
14 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system and Construction of R.C.C. Elevated Reservoir, Capcaity 100 cum (Torch Type), Staging height 20 metre at Bhuinghora mouza for Marble Lake & its adjoing area W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | 1416/PD | 29/12/2020 |  | ANUP KUMAR SAHA | 178.29 | 58.68 | 0
15 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply and delivery of ISI marked Ductile Iron fitting (Bolted Collar, D.I. Pushing Bend, Tee, reducer, Spigot Tale Piece, Socket Tale Piece & other Specials) conforming to IS: 9523-2000 for push on joint / Flanged Joint / Mechanical Joint with externally and internally coated with Fusion Bonded Epoxy with necessary jointing material rubber gasket (IS 5382 1985) including transportation, loading, unloading and staking at site. Delivery is to be made in Kalyani Stores / Rajarhat Stores Sub-Division under resources Division P.H.E. Dte. |  |  | 772/RS | 19/04/2021 |  | KEJRIWAL CASTINGS LTD. | 0.51 | 0 | 0
16 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply and delivery of ISI marked Ductile Iron fitting (Bolted Collar, D.I. Pushing Bend, Tee, reducer, Spigot Tale Piece, Socket Tale Piece & other Specials) conforming to IS: 9523-2000 for push on joint / Flanged Joint / Mechanical Joint with externally and internally coated with Fusion Bonded Epoxy with necessary jointing material rubber gasket (IS 5382 1985) including transportation, loading, unloading and staking at site. Delivery is to be made in Kalyani Stores / Rajarhat Stores Sub-Division under resources Division P.H.E. Dte. |  |  | 771/RS | 19/04/2021 |  | ELECTROSTEEL CASTINGS LIMITED | 0.87 | 0 | 0
17 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply and delivery of ISI marked Ductile Iron fitting (Bolted Collar, D.I. Pushing Bend, Tee, reducer, Spigot Tale Piece, Socket Tale Piece & other Specials) conforming to IS: 9523-2000 for push on joint / Flanged Joint / Mechanical Joint with externally and internally coated with Fusion Bonded Epoxy with necessary jointing material rubber gasket (IS 5382 1985) including transportation, loading, unloading and staking at site. Delivery is to be made in Kalyani Stores / Rajarhat Stores Sub-Division under resources Division P.H.E. Dte. |  |  | 773/RS | 19/04/2021 |  | JINDAL SAW LIMITED. | 0.4 | 0 | 0
18 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.02.23 to 20.05.23] | Assistant Engineer | Junior Engineer | 245/PD | 20/02/2023 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
19 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.05.23 to 28.08.23] | Assistant Engineer | Junior Engineer | 678/PD | 17/05/2023 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
20 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 29.08.23 to 26.11.23] | Assistant Engineer | Junior Engineer | 1169/PD | 28/08/2023 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
21 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Allied Work of Construction of roof, slab, plaster etc. of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | 4675/PSD | 27/07/2023 |  | BOSE CONSTRUCTION | 0.88 | 0 | 100
22 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Parapet Wall of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | 4676/PSD | 27/07/2023 |  | BOSE CONSTRUCTION | 0.95 | 0 | 100
23 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of boundary wall for OHR campus at Bhuinghora mouza of Marbel Lake W/S Scheme at Ajodhya Hill under Purulia Division, PHE Dte. | Assistant Engineer |  | 1280/PD | 07/12/2020 |  | SHAYED NADEEM AHAMAD | 8.32 | 8.32 | 0
24 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of main drain at Baghmundi WTP Site under Piped Water Supply Scheme from Marble Lake under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | 892/PD | 07/05/2024 |  | ROY CONSTRUCTION | 2.32 | 0 | 100
25 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Arrangement of Pandel & other Miscellaneous works for infield training at Pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | 23/PMSD(Drilling) | 16/02/2024 |  | AMIT PATHAK | 0.54 | 0 | 100
26 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Arrangement of refreshment for infield training of pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | 24/PMSD(Drilling) | 16/02/2024 |  | AMIT PATHAK | 0.43 | 0 | 100
27 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying of Loop Line for the distribution System at different command area of Patuara, Ramjibanpur, Bhomorbera,Lawadih etc of Satra under Marble Lake W/S Scheme Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | 1500/PD | 27/08/2024 |  | SUBODH PRAMANIK | 27.42 | 0 | 80
28 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Allied works for construction of office cum Godown at Ajodhya under Marble Lake W/S Scheme Purulia Division, PHE Dte. (JJM) | Assistant Engineer(HQ) | Junior Engineer-1 | 1516/PD | 27/08/2024 |  | BOSE CONSTRUCTION | 11.59 | 0 | 100
29 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying HDPE distribution pipeline to cover the left out habitation of Ajodhya, Bagandih & Chatni mouza at Ajodhya Under Marble Lake W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | 1510/PD | 27/08/2024 |  | TUMPA GORAIN | 23.18 | 0 | 100
30 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of shed and other works at Manbhum Paridarshan Abas Campus under Marble Lake W/S Scheme Purulia Division, PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-1 | 1499/PD | 27/08/2024 |  | MAHARSHI BANERJEE | 5.61 | 0 | 100
31 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply and installation of PLC panel, Level transmitter with other allied work at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 1577/PMD | 14/11/2024 |  | SUBRATA DUTTA | 14.57 | 0 | 0
32 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. (For the period of 90 days) (w.e.f. 23.08.24 to 20.11.24) | Assistant Engineer | Junior Engineer-2 | 1473/PD | 21/08/2024 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
33 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. (For the period of 90 days) (w.e.f. 25.02.24 to 24.05.24) | Assistant Engineer | Junior Engineer-2 | 278A/PD | 20/02/2024 |  | ANUP KUMAR SAHA | 1.68 | 0 | 0
34 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. (For the period of 90 days) (w.e.f. 25.05.24 to 22.08.24) | Assistant Engineer | Junior Engineer-2 | 959A/PD | 22/05/2024 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
35 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. (For the period of 90 days) (w.e.f. 27.11.23 to 24.02.24) | Assistant Engineer | Junior Engineer-2 | 1681A/PD | 22/11/2023 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
36 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply and fitting fixing of Glow sign board and other electro-mechanical work at Marbel Lake water supply scheme under Purulia Mechanical Division, P.H.E. Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 378/PMSD(W/S) | 16/10/2023 |  | COMBINE ENTERPRISES | 0.95 | 0 | 0
37 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Operation & maintenance of 30Cum/HourCapacity Water Treatment Plant of Marble Lake & Its adjoining Mouza W/S Scheme at Ajodhya Hill of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. [For the period of 01.09.2024 to 31.08.2025] | Assistant Engineer | Junior Engineer-2 | 1640/PD | 30/08/2024 |  | ANUP KUMAR SAHA | 14.38 | 0 | 100
38 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Special repair work of pipe line at Marbel lake w/s Scheme under Purulia Division, PHE Dte. (Hilly Area) | Assistant Engineer(HQ) | Junior Engineer-1 | 168A/PD | 06/02/2025 |  | ANUP KUMAR SAHA | 0.97 | 0 | 100
39 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Operation and guarding of the pumping machinery and electrical installation at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. In the District of Purulia.(w.e.f. 01.03.2025 to 28.02.2026) | ASSISTANT ENGINEER | JUNIOR ENGINEER | 328/PMD | 27/02/2025 |  | COMBINE ENTERPRISES | 5.99 | 0 | 0
40 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation order for the work of O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte [For the period of 90 days] (w.e.f 20/05/2025-17/08/2025) | Assistant Engineer | Junior Engineer-2 | 894/PD | 19/05/2025 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
41 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte (For the period of 90 days) (w.e.f. 19.02.25 to 19.05.25) | Assistant Engineer | Junior Engineer-2 | 206/PD | 18/02/2025 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
42 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Operation and guarding of the pumping machinery and electrical installation at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. In the District of Purulia. (w.e.f. 01.11.2025 to 31.10.2026) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | 1638/PMD | 29/10/2025 |  | COMBINE ENTERPRISES | 6.2 | 0 | 0
43 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Repairing of 60 KVA Voltage stabilizer and other allied works at Marble lake Water Supply Scheme under Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | 391/PMSD(W/S) | 24/09/2025 |  | COMBINE ENTERPRISES | 0.76 | 0 | 0
44 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte (For the period of 90 days) (w.e.f. 21.11.24 to 18.02.25) | Assistant Engineer | Junior Engineer-2 | 1986A/PD | 19/11/2024 |  | ANUP KUMAR SAHA | 1.68 | 0 | 100
45 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Approch road & pathway alongwith other allide work at Bhuighora OHR Site under Marbel Lake Water Supply Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | 655/PD | 23/04/2025 |  | S.PATHAK & CO. | 18.32 | 0 | 70
46 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Withdrawing, Repairing and lowering of 7.5 HP Submersible pumping machinery and other allied works at Marble lake water supply scheme under Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | 434/PMSD(W/S) | 14/11/2025 |  | COMBINE ENTERPRISES | 0.32 | 0 | 0
Total | [12 empty] | 649.54 | 113.76 | 17.51