## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Shyampur-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu | JE/RWS/Shyampur II | 736/HD | 23/02/2023 |  | S.M. CONSTRUCTION | 3.83 | 0 | 100
2 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Kulgachia PWSS under Uluberia-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | 735/HD | 23/02/2023 |  | Deven Enterprise | 1.99 | 0 | 0
3 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Shyampur-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | 864/HD | 01/03/2023 |  | PRADIP KUMAR JATI | 9.13 | 0 | 100
4 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to various awangari within Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | 1102/HD | 17/03/2023 |  | LOKENATH ENTERPRISES | 2.78 | 0 | 100
5 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to various Schools within Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | 1103/HD | 17/03/2023 |  | LOKENATH ENTERPRISES | 6.65 | 0 | 100
6 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 180 mtr deep along with installation of 1.0 HP Submersible pump including making water supply plumbing arrangement at Kandua AWC & Kandua Primary School under Amta-I Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | 3103/AE/USD | 29/02/2024 |  | CHANDRANI ENTERPRISE | 1.84 | 0 | 100
7 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 201 mtr deep alongwith installation of 1.0 HP Sub mersible pump including making water supply plumbing arrangement at Solbaga Primary School under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | 783/AE/USD | 05/09/2024 |  | CHANDRANI ENTERPRISE | 2.48 | 0 | 100
8 | HOWRAH | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 201 mtr deep alongwith installation of 1.0 HP Sub mersible pump including making water supply plumbing arrangement at Dadpur AWC &DadpurPrimary School under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | 766/AE/USD | 04/09/2024 |  | CHANDRANI ENTERPRISE | 2.48 | 0 | 100
Total | [12 empty] | 31.18 | 0 | 0