## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Preparation of DPR for piped water supply scheme of Kumirmora PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | 255/HD | 07/02/2022 |  | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 0 | 0
2 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 0 | 0 | 100
3 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation) along with part Laying of Distribution and Providing Functional Household Tap Connection(FHTC)for Kumirmora Piped Water Supply scheme of Udayanarayanpur Block under Howrah Division P.H.E. Dte. in the District of Howrah. (Part-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | 2164/HD | 21/10/2022 |  | PRAVAT SARKAR | 194.98 | 0 | 60
4 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kumirmora PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | 2489/HD | 30/11/2022 |  | JYOTY SOLAR POWER | 27.45 | 0 | 0
5 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-B) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | 1988/HD | 26/09/2022 |  | TANMOY ROY CHOUDHURY | 88.86 | 0 | 60
6 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | 2810/HD | 21/12/2022 |  | SAMANTA BUILDERS | 8.5 | 0 | 100
7 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | 2807/HD | 21/12/2022 |  | CHINMOY SAMANTA | 8.5 | 0 | 100
8 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-C) | AE/RWS | JE/RWS/Udaynaryanpur | 1989/HD | 26/09/2022 |  | FARID UDDIN AHMED | 93.98 | 0 | 5
9 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Work Order for Raising main & Inter Connection with both tube wells of Kumirmora PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | 1922/HD | 08/05/2023 |  | LOKENATH ENTERPRISES | 5.34 | 0 | 70
10 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2502/RS | 10/08/2023 |  | ELECTROSTEEL CASTINGS LIMITED | 10.44 | 0 | 35
11 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2499/RS | 10/08/2023 |  | ELECTROSTEEL CASTINGS LIMITED | 0 | 0 | 80
12 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 3514/ED | 30/12/2022 |  | M/S S R ENTERPRISE | 20.38 | 0 | 90
13 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2283/RS | 18/07/2023 |  | TATA METALIKS LTD | 0 | 0 | 45
14 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Additional Laying of Distribution Pipe Lines and Providing Functional Household Tap Connection(FHTC) for leftout area of KUMIRMORA Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur | 4723/HD | 12/11/2024 |  | MISHRA ENTERPRISE | 48.16 | 0 | 85
15 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | 4813/HD | 19/11/2024 |  | HORIZEN | 0.7 | 0 | 70
16 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation & Maintenance of Uttar Manasri, Kumirmora, Bedhichandrapur, Gauranga Chak, Sonatala, Per Radhanagar and Khila Piped Water Supply Scheme (Block¿Udaynarayanpur) under RWS Howrah Sub Division of Howrah Division, PHE Dte. [For 365 days, w.e.f. 01/10/2024] | AE/RWS | je/blk/ulu1 | 4387/HD | 30/09/2024 |  | JAHANGIR ALAM | 6.99 | 0 | 0
17 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation and guarding of the pumping machinery at KUMIRMORA water supply scheme, Block - Udaynarayanpur, District ¿ Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 2801/ED | 30/12/2024 |  | M/S S.R. ENTERPRISE | 7.07 | 0 | 0
18 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation & Guarding of the pumping machinery at Kumirmora (UM) w/s scheme, P.H No. I, Block-Udaynarayanpur, District : Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 3981/HMSD | 21/08/2024 |  | M/S S.R. ENTERPRISE | 0.88 | 0 | 0
19 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation & guarding of pumping machinery at Kumirmora (UM) water supply scheme, P.H No.-II, Block-Udaynarayanpur, Dist.- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 6296/HMSD | 20/11/2024 |  | M/S S.R. ENTERPRISE | 0.3 | 0 | 0
20 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation & guarding of pumping machinery at Kumirmora (UM) water supply scheme, P.H No.-I, Block-Udaynarayanpur, Dist.- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 6295/HMSD | 20/11/2024 |  | M/S S.R. ENTERPRISE | 0.3 | 0 | 0
21 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Providing residual chlorine kits at different pump houses at Udaynarayanpur Block in the District Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 6092/HMSD | 06/11/2024 |  | M/S G P ENTERPRISE | 0.9 | 0 | 0
22 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation and guarding of the pumping machinery at KUMIRMORA water supply scheme, PH NO- I & II, Block - Udaynarayanpur, District ¿ Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 1556/ED | 25/08/2025 |  | APEX ENGINEERING & PROJECT CO. | 7.29 | 0 | 0
23 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Continuation order for Operation & Maintenance of Uttar Manasri, Kumirmora, Bedhichandrapur, Gauranga Chak, Sonatala, Per Radhanagar and Khila Piped Water Supply Scheme (Block Udaynarayanpur) under RWS Howrah Sub Division of Howrah Division, PHE Dte.[Period from 01/10/2025 to 31/12/2025] | AE/RWS | JE/RWS/Uluberia I | 3994/HD | 24/09/2025 |  | JAHANGIR ALAM | 2.06 | 0 | 100
24 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Withdrawing existing Submersible pumping machinery set and supply, delivery, lowering of higher head p/m set along column pipes to overcome drawdown situation at Kumirmora water supply scheme, Ph- II, Block- Udaynarayanpur, District-Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 2115/HMSD | 20/06/2025 |  | RADHARANI ENTERPRISE | 0.79 | 0 | 0
25 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation & Guarding of the pumping machinery at Kumirmora (UM) w/s scheme, P.H No. II, Block-Udaynarayanpur, District : Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | 3982/HMSD | 21/08/2024 |  | M/S S.R. ENTERPRISE | 0.88 | 0 | 0
26 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Continuation order for Operation & Maintenance of Uttar Manasri, Kumirmora, Bedhichandrapur, Gauranga Chak, Sonatala, Per Radhanagar and Khila Piped Water Supply Scheme (Block Udaynarayanpur) under RWS Howrah Sub Division of Howrah Division, PHE Dte. [Period from 01/01/2026 to 28/02/2026] | AE/RWS | JE/RWS/Uluberia I | 4735/HD | 31/12/2025 |  | JAHANGIR ALAM | 1.23 | 0 | 0
27 | HOWRAH | Howrah Division | Ground Water Based Piped Water Supply Scheme for Kumirmora Block- Udaynarayanpur, Dist-Howrah. | SM/11221 | New | Operation & Maintenance of Uttar Manasri, Kumirmora, Bedhichandrapur, Gauranga Chak,Sonatala,Per Radhanagar, Khila Piped Water Supply Scheme at Udaynarayanpur Block under RWS Howrah Sub-Division of Howrah Division, PHE Dte.(Period for O & M 365 days) | AE/RWS |  | 564/HD | 20/02/2026 |  | JAHANGIR ALAM | 8.54 | 0 | 0
Total | [12 empty] | 548.1 | 0 | 0