## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of MS Steel Plate Flooring in old intake of 34MGD at Dongaria in connection with Surface Water based Water Supply Scheme for Arsenic affected areas of South 24 Parganas in connection to destruction by 'Aumfun' |  |  | 1071/SWD-I | 08/10/2020 |  | DIAMOND ENTERPRISE | 5.9 | 11.78 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Water Supply and Ancillary works From the Source of BS-I to Begam pur High School of Zone-28 (BegamPur) Under Baruipur Block due to Cyclone "AMPHAN 2020 " under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. |  |  | 771/SWD-I | 14/08/2020 |  | M/S. GOUTAM ROY | 4.4 | 4.39 | 0
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Water Supply and Ancillary works from N.P.- 107-108 of Zone-28 of Baruipur Block due to Cyclone "AMPHAN 2020 " under Surface Water Based Water Supply Scheme for Arsenic Effected Areas of South 24 Paraganas Dist. |  |  | 743/SWD-I | 14/08/2020 |  | M/S. GOUTAM ROY | 4.76 | 4.76 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Re-construction of boundary wall of Zone-45, Mograhat-II block which is damaged due to Cyclone "AMPHAN 2020? under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | 851/SWD-I | 03/09/2020 |  | M/S. GOUTAM ROY | 12.13 | 11.52 | 0
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of worn out columns, Girders with allied components of old intake of 34MGD at Dongaria in connection with Surface Water based Water Supply Scheme for Arsenic affected areas of South 24 Parganas in connection to destruction by 'Aumfun' |  |  | 1072/ SWD-I | 08/10/2020 |  | M/S. S.S. ENTERPRISE | 25.67 | 2.05 | 0
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 63-62 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 590/SWD-I | 22/07/2020 |  | M/S. KUNDU CONSTRUCTION | 4.08 | 3.15 | 0
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of Boundary Wall affected due to cylone Amphan at Barijpur Zone - V, Mograhat-I Block, Dist.- S-24-Pgs. |  |  | 544/SWD-I | 22/07/2020 |  | J. ENTERPRISE | 3.31 | 6.62 | 0
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Bypass connection of Rising Main of 350 mm dia MS Pipeline inside PWD stackyard premises damaged due to Amphan cyclone at Zone 08 under Bishnupur-II Block in connection with Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24 Pgs. |  |  | 561/SWD-I | 22/07/2020 |  | SRIJON ENTERPRISE | 4.79 | 9.58 | 0
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of total Distribution system, Rising Main, Pipelines (CI/DI/AC/UPVC) of scheme from zone 1 under Budge Budge II with repairing of valve chambers and allied road restoration works under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 624/SWD-I | 30/07/2020 |  | SANJOY MIDDEY | 4.81 | 9.62 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Water Supply and Ancillary works from N.P.-014A-006-007-008-038A at Durga Pur of Zone-51 under Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 725/SWD-I | 14/08/2020 |  | RANADHIR SINHA | 4.25 | 8.5 | 0
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 61-55 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 586/SWD-I | 22/07/2019 |  | MS SARADA UDYOG | 3.62 | 7.25 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of total Distribution system, Rising Main, Pipelines (CI/DI/AC/UPVC) of scheme from zone 2 under Budge Budge II with repairing of valve chambers and allied road restoration works under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 625/SWD-I | 30/07/2020 |  | SANJOY MIDDEY | 2.66 | 5.33 | 0
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and protection of distribution pipeline damaged due to Amphan Cyclone of Zone-16 (Moudi Hospital road, Ali more, Daspara and other places) under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 560/SWD-I | 22/07/2020 |  | M/S RUNA ENTERPRISE | 4.81 | 9.63 | 0
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and repairing of the Water Supply and Ancillary works from N.P.-013-006 at Durga Pur of Zone-51 under Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 724/SWD-I | 14/08/2020 |  | RAJLAXMI CONSTRUCTION | 4.53 | 9.05 | 0
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of Boundary Wall in connection with Surface Water based Water Supply Scheme for Falta Mathurapur at 52 MGD WTP Premises in connection to destruction by 'AUMFUN' |  |  | 707/SWD-I | 12/08/2020 |  | M/S. S.S. ENTERPRISE | 18.81 | 18.81 | 0
16 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from N.P.- 040-041-042 & 042-035 Zone-25 of Baruipur block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 745/SWD-I | 14/08/2020 |  | LAKSHMI NARAYAN SAHOO | 4.2 | 8.39 | 0
17 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of total Distribution system, Rising Main, Pipelines (CI/DI/AC/UPVC) of scheme from zone 7 under Budge Budge II with repairing of valve chambers under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 628/SWD-I | 30/07/2020 |  | SNEHA CONSTRUCTION | 4.83 | 9.66 | 0
18 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of total Distribution system, Rising Main, Pipelines (CI/DI/AC/UPVC) of scheme from zone 5 & 6 under Budge Budge II with repairing of valve chambers under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 627/SWD-I | 30/07/2020 |  | SUKUMAR DEBNATH | 4.77 | 9.55 | 0
19 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Protection of 300 mm dia DI Rising Main affected due to cyclone Amphan at Chakbalibag (zone-18) by using bullah pilling under surface water based water supply scheme for arsenic affected areas of South 24-Pgs. Dist. |  |  | 552/SWD-I | 22/07/2020 |  | NIRMAL UDYOG | 1.61 | 3.22 | 0
20 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from N.P.- 122A-121-136, Zone-25 of Baruipur block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 748/SWD-I | 14/08/2020 |  | TOJO ENTERPRISE | 2.88 | 5.76 | 0
21 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of total Distribution system, Rising Main, Pipelines (CI/DI/AC/UPVC) of scheme from zone 3 & 4 under Budge Budge II with repairing of valve chambers under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 626/SWD-I | 30/07/2020 |  | S.M ENTERPRISE | 4.77 | 9.53 | 0
22 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of service road maintained by KMDA due to restoration of UPVC pipe line (90 mm & 110 mm) dia damaged due to super cyclone AMPHAN 2020 within Zone-25 of Baruipur block under "Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas district". |  |  | 1496/SWD-I | 30/12/2020 |  | LAKSHMI NARAYAN SAHOO | 1.21 | 2.42 | 0
23 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Tapan Baidya's House (N.P.-002) to Bimal Naskar's House (N.P.-002A) under Zone-26 (Bindakhali GP) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 754/SWD-I | 14/08/2020 |  | P S CONSTRUCTION | 3.11 | 6.21 | 0
24 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of Aluminium Doors and windows at 34MGD WTP premises and rain water pipe repair under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 631/SWD-I | 30/07/2020 |  | NIRMAL UDYOG | 3.73 | 7.46 | 0
25 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of Distribution line at Sonarpur, Alampur Muchipole, Mathorerpole , Malangadar with allied repair works under Budge Budge II with road restoration works at Dhancheberia and Dongaria More under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 629/SWD-I | 30/07/2020 |  | GOUTAM MAZUMDER | 4.84 | 9.67 | 0
26 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 65-07, 66-64 in Bhangor-I block Zone- 35 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 636/SWD-I | 30/07/2020 |  | S.C. ENTERPRISE | 4.38 | 8.76 | 0
27 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and protection of distribution pipeline damaged due to Amphan Cyclone of Zone-15 (Bagi and other places) under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 559/SWD-I | 22/07/2019 |  | M/S. FAIZUL HAQUE BISWAS | 4.7 | 9.4 | 0
28 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 8-9, 7-8, 63-68 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 587/SWD-I | 22/07/2020 |  | MS SARADA UDYOG | 4.05 | 8.09 | 0
29 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Installation of Contactless hand washing system with water storage tank at variuos places under SWSD-I,SWSD-II and Baruipur Sub Divn., under South 24-Pgs. Water Supply Divn.-I PHE Dte. (Total-10 Nos.) |  |  | 558/SWD-I | 22/07/2020 |  | NIKHIL SAMADDAR | 1.59 | 3.17 | 0
30 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Shib Tala (Dihi Madan Molla) to Notun Para (N.P.-052-053-055-056-058-060) under KMDA Zone-III (Horiharpur GP) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 758/SWD-I | 14/08/2020 |  | MONDAL CONSTRUCTION | 4.41 | 8.82 | 0
31 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and repairing of the Water Supply and Ancillary works from Monsa Tala More to Chatra More (N.P.-48-48A) under Zone-53 of Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 769/SWD-I | 14/08/2020 |  | SOMNATH ENTERPRISE | 4.51 | 9.01 | 0
32 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of pipeline affected due to Cyclone Amphan under zone 10 Surface Water Based Water Supply Scheme in the Arsenic affected areas of Bishnupur-II Block of South 24-Pargs. Dist. |  |  | 547/SWD-I | 22/07/2020 |  | A.G.S. ENTERPRISE | 0.44 | 0.87 | 0
33 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Over Head Reservoir (N.P.-023) to Nominchad High School (N.P.-003A) (Dhosa GP) of Zone-55, Joynagar-I Block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. (N.P- 003A-023) |  |  | 730/SWD-I | 14/08/2020 |  | I.B. ENTERPRISE | 2.47 | 4.94 | 0
34 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Over Head Reservoir (N.P.-003A) to Nominchad High School (N.P.-003) (Dhosa GP) of Zone-55, Joynagar-I Block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 731/SWD-I | 14/08/2020 |  | BAIDYA ENTERPRISE | 3.72 | 7.43 | 0
35 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of 34 MGD WTP infrastructure inclusive of two stores, Workshop Building, Administrative Building, clearing of WTP Premises (including uprooting, cutting stacking of trees), repair of leaks, damaged due to 'Amphan' under Surface water based water supply scheme for arsenic affected areas of South 24 Parganas. |  |  | 695/SWD-I | 10/08/2020 |  | M/S. S.S. ENTERPRISE | 9.14 | 18.28 | 0
36 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Protection of approach road affected due to cyclone Amphan and alied work at zone v (Barijpur) Block Mograhat-I for "Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, South-24 Pgs. under South 24-Pgs. Water Supply Divn.-I PHE Dte. |  |  | 545/SWD-I | 22/07/2020 |  | M/S. S.S. ENTERPRISE | 4.8 | 9.6 | 0
37 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 91-92, 65-64 in Bhangor-I block Zone- 35 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 637/SWD-I | 30/07/2020 |  | J.D. CONSTRUCTION | 4.62 | 9.23 | 0
38 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 9-10, 66-64 in Bhangor-I block Zone- 35 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 635/SWD-I | 30/07/2020 |  | J.D. CONSTRUCTION | 4.47 | 8.93 | 0
39 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from N.P.-003-004 at Durga Pur of Zone-51 under Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 726/SWD-I | 14/08/2020 |  | RANADHIR SINHA | 3.1 | 6.2 | 0
40 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and Ancillary works from N.P.-055-056-057 at Baharu of Zone-50 under Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 729/SWD-I | 14/08/2020 |  | RANADHIR SINHA | 4.54 | 9.08 | 0
41 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Protection of 250 mm dia pipe line affected due to cyclone Amphan near Jhajra School (zone-18) by using bullah pilling under surface water based water supply scheme for arsenic affected areas of South 24-Pgs. Dist. |  |  | 553/SWD-I | 22/07/2020 |  | NIRMAL UDYOG | 2.05 | 4.1 | 0
42 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 1-62 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 588/SWD-I | 22/07/2020 |  | SRIJON ENTERPRISE | 3.98 | 7.96 | 0
43 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Bypass connection of Rising Main of 350 mm dia MS Pipeline at Sanjua natun rasta more to replace the old pipeline damaged due to Amphan cyclone at Zone 08 under Bishnupur-II Block in connection with Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24 Pgs. |  |  | 562/SWD-I | 22/07/2020 |  | SRIJON ENTERPRISE | 3.87 | 7.73 | 0
44 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Protection work for laying of Rising Main of 350 mm dia MS Pipeline damaged due to Amphan cyclone at Zone 08 under Bishnupur-II Block in connection with Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24 Pgs. |  |  | 563/SWD-I | 22/07/2020 |  | SRIJON ENTERPRISE | 2.04 | 4.08 | 0
45 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 53-67 in Bhangor-I block Zone- 36 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 640/SWD-I | 30/07/2020 |  | M/S. JAYDEEP DASGUPTA | 4.75 | 9.49 | 0
46 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 51-52 in Bhangor-I block Zone- 36 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 641/SWD-I | 30/07/2020 |  | M/S. JAYDEEP DASGUPTA | 4.46 | 8.92 | 0
47 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Shib Tala Atghara Paschim Para (N.P.-336) to Najim Pur (N.P.-337) of Madarhaat Gram Panchayat under Baruipur KMDA Zone-III (Sultanpur) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 764/SWD-I | 14/08/2020 |  | NARAYAN ENTERPRISE | 1.24 | 2.49 | 0
48 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of Distribution line at Dhancheberia, Mathorerpole, Malangadar with allied repair works under Budge Budge II with road restoration works at Dhancheberia and Dongaria More under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 630/SWD-I | 30/07/2020 |  | NIRMAL UDYOG | 1.84 | 3.67 | 0
49 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Ramdhari Bridge (N.P.-126) to Bedotish Pramanik's House (N.P.-125) to Rehana Cycle Shop (N.P.-123) under Zone-27 (Ramdhari Mouza) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 761/SWD-I | 14/08/2020 |  | MAA LAXMI ENTERPRISE | 4.28 | 8.57 | 0
50 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 126-80, 114-115 under Sonarpur Block, Zone 30 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 585/SWD-I | 22/07/2020 |  | KAMALA ENTERPRISE | 4.21 | 8.42 | 0
51 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 47-51, 51-52 in Bhangor-I block Zone-36 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 639/SWD-I | 30/07/2020 |  | B R CONSTRUCTION | 4.48 | 8.97 | 0
52 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Salehpur School (N.P.-064) to Halder Para (N.P.-065) & Ramchandrapur Majhi Para (N.P.-056) to Pal Para (N.P.-057) under Zone-41 of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 760/SWD-I | 14/08/2020 |  | LAKSHMI NARAYAN SAHOO | 4.07 | 8.15 | 0
53 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from N.P.- 122A-122 of Baruipur block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [Zone-25] |  |  | 747/SWD-I | 14/08/2020 |  | M/S. JAYDEEP DASGUPTA | 4.32 | 8.65 | 0
54 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and repairing of the Supply and Ancillary works from Mansa Tala More to Chatra More to Bel Pukur Math (N.P.-48B-49-49B) under Zone-53 of Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 767/SWD-I | 14/08/2020 |  | SENGUPTA CONSTRUCTION | 4.56 | 9.12 | 0
55 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Monsa tala More To Chatra More to Bel Pukur Math (N.P.-49B-50-84 ) of Zone-53 , Joynagar-I Block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 738/SWD-I | 14/08/2020 |  | BAIDYA ENTERPRISE | 4.55 | 9.1 | 0
56 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of Temporary Boundary Wall in connection with Surface Water based Water Supply Scheme for Falta Mathurapur at 52 MGD WTP Premises in connection to destruction by 'Amphan'. |  |  | 696/SWD-I | 10/08/2020 |  | NIRMAL UDYOG | 5.63 | 10.99 | 0
57 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 2-3 under Sonarpur Block, Zone 30 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 581/SWD-I | 22/07/2020 |  | SUPER SKILL | 3.62 | 7.25 | 0
58 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in replace of old AC pipe line (non-repairable) at node point 51-65,51-52,52-53,52-62,61-62,60-61 of Zone 20 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 565/SWD-I | 22/07/2020 |  | SUNNY CONSTRUCTION | 4.74 | 9.48 | 0
59 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in replace of old AC pipe line (non-repairable) at node point 90-91-92 of Zone 20 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 567/SWD-I | 22/07/2020 |  | S.P. ENTERPRISE | 2 | 4.01 | 0
60 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Water Supply and Ancillary works from Panchanantala (N.P.- 14) to Goutam Mondal's House (N.P.- 20), Zone-49 under Joynagar block under due to Cyclone "Amphan 2020" Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. (N.P.- 17-18,17-19-20) |  |  | 732/SWD-I | 14/08/2020 |  | S.N. ENTERPRISE | 4.81 | 9.63 | 0
61 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and repairing of the Water Supply and Ancillary works from Goramandir to Kalyanpur GP Office (N.P.-46-48-49-97) under KMDA Zone-I of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 762/SWD-I | 14/08/2020 |  | MONDAL CONSTRUCTION | 4.67 | 9.35 | 0
62 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Mallick Pur Kaji Para More to Lichu Para (N.P.-50-53-52-51-95) and Hariharpur GP to Hati Para More (N.P.-47-97-94) under KMDA Zone-II of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 763/SWD-I | 14/08/2020 |  | MONDAL CONSTRUCTION | 1.31 | 2.63 | 0
63 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 110-102, 102-100 under Sonarpur Block, Zone 30 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 584/SWD-I | 22/07/2020 |  | NIRMAL UDYOG | 3.47 | 6.94 | 0
64 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of pipeline affected due to Cyclone Amphan under Zone-13 Surface Water Based Water Supply Scheme in the Arsenic affected areas of Bishnupur-II Block of South 24-Pargs. Dist. |  |  | 550/SWD-I | 22/07/2020 |  | A.G.S. ENTERPRISE | 1.06 | 2.11 | 0
65 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and repairing of the Supply and Ancillary works from Riu Das Para More to Damdama High School Math (N.P.-043-044-047) under Zone-54 of Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 768/SWD-I | 14/08/2020 |  | S.C. ENTERPRISE | 4.7 | 9.41 | 0
66 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of pipeline affected due to Cyclone Amphan under Zone 11 Surface Water Based Water Supply Scheme in the Arsenic affected areas of Bishnupur-II Block of South 24-Pargs. Dist. |  |  | 548/SWD-I | 22/07/2020 |  | A.G.S. ENTERPRISE | 3.61 | 7.23 | 0
67 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repairing of leakage, bursting of pipeline including supply of Sluice Valve and specials due to damages by cyclone Amphan and for day to day maintenance work under zone 10, 11, 12 & 13 under South 24 Pgs. W/S Sub-Divn-II of South 24 Pgs. W/S Divn-I PHE Dte. |  |  | 774/SWD-I | 14/08/2020 |  | A.G.S. ENTERPRISE | 2.07 | 4.14 | 0
68 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of pipeline with pilling work affected due to Cyclone Amphan in different places under Zone 11 Surface Water Based Water Supply Scheme in the Arsenic affected areas of Bishnupur-II Block of South 24-Pargs. Dist. |  |  | 568/SWD-I | 22/07/2020 |  | NATURAL RESOURCES CONSORTIUM | 1.59 | 3.17 | 0
69 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of pipeline affected due to Cyclone Amphan under Zone 12 Surface Water Based Water Supply Scheme in the Arsenic affected areas of Bishnupur-II Block of South 24-Pargs. Dist. |  |  | 549/SWD-I | 22/07/2020 |  | A.G.S. ENTERPRISE | 1.13 | 2.26 | 0
70 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Water Supply and Ancillary works from N.P.- A-B, B-21, 21-21A , Zone-52 under JOYNAGAR block under due to Cyclone "AMPHAN 2020 " Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. |  |  | 733/SWD-I | 14/08/2020 |  | S.N. ENTERPRISE | 4.2 | 8.41 | 0
71 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of UPVC pipelines at Uttar Raipur distribution Zone under Budge Budge-I under Surface Water Based Water Supply scheme for Arsenic affected areas of South 24-Pgns. district in connection to the destruction by Amphan. |  |  | 633/SWD-I | 30/07/2020 |  | M/S. S.S. ENTERPRISE | 4.29 | 8.34 | 0
72 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary Works from N.P.- 054-082,0-112-122, zone-25 of Baruipur block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 746/SWD-I | 14/08/2020 |  | LAKSHMI NARAYAN SAHOO | 4.35 | 8.7 | 0
73 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in replace of old AC pipeline (non-repairable) at node point 22 to 51 of Zone 20 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 566/SWD-I | 22/07/2020 |  | SUNNY CONSTRUCTION | 4.8 | 9.59 | 0
74 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line of 90mm, 110mm dia in place of old AC pipeline (non-repairable) at different node point of Zone 17 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 577/SWD-I | 22/07/2020 |  | M/S. S.S. ENTERPRISE | 4.38 | 8.75 | 0
75 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line of 90mm, 110mm, 125mm dia in place of old AC pipeline (non-repairable) at different node point of Zone 17 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 576/SWD-I | 22/07/2020 |  | M/S. S.S. ENTERPRISE | 4.75 | 9.5 | 0
76 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Kankar Bazar Paschim Para (N.P.-045) to Charagachia Primary School (N.P.-054) of Zone-46 under Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 721/SWD-I | 14/08/2020 |  | KAMALA ENTERPRISE | 4.38 | 8.75 | 0
77 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of pipeline affected due to Cyclone Amphan in between Node No. - 128-126, 126-127, 127-114, 114-113 under Zone 12 Surface Water Based Water Supply Scheme in the Arsenic affected areas of Bishnupur-II Block of South 24-Pargs. Dist. |  |  | 578/SWD-I | 22/07/2020 |  | M/S. TORSA ENTERPRISE | 2.57 | 5.13 | 0
78 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary Works from N.P.- 123-121, 121-122, 122-56, 56-55, 56-118 of Zone-44 of Magrahat-II Block due to Cyclone "AMPHAN"2020 Under Surface Water Based Water Supply Scheme for Arsenic Effected Areas of South 24 Paraganas Dist. |  |  | 716/SWD-I | 14/08/2020 |  | PROJECT AND MAINTENANCE | 4.69 | 9.38 | 0
79 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from N.P.-041-086-084-034-035-037-038-004 at Durga Pur of Zone-51 under Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district |  |  | 728/SWD-I | 14/08/2020 |  | M/S. KUNDU CONSTRUCTION | 4.8 | 9.6 | 0
80 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipeline (non-repairable) at node point 16-14-63,216-221,120-123 of Zone-08 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 571 /SWD-I | 22/07/2020 |  | SUKUMAR DEBNATH | 2.3 | 4.61 | 0
81 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Mamud Pur More (N.P.-028) to Budhopara Masjid (N.P.-014) & Khankar Bazar (N.P.-039) to Paschim Bazar (N.P.-045) of Zone-46 under Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. (N.P.-028-020-16,014-011,039-043-045) |  |  | 722/SWD-I | 14/08/2020 |  | KAMALA ENTERPRISE | 4.78 | 9.57 | 0
82 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipeline (non-repairable) at node point 120-121,107-108,30-31-33,133-143 of Zone-09 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 573/SWD-I | 22/07/2020 |  | ADRIK ENTERPRISE | 4.74 | 9.48 | 0
83 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipe line (non-repairable) from Khurir pole to Akulse more of Zone 08 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 580/SWD-I | 22/07/2020 |  | TOJO ENTERPRISE | 2.83 | 5.65 | 0
84 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Budhor Para (N.P.-008) to Khankar Bazar (N.P.-011) of Zone-46 under Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. (N.P- 008-009-011, 008-039) |  |  | 720/SWD-I | 14/08/2020 |  | KAMALA ENTERPRISE | 4.77 | 9.55 | 0
85 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipeline (non-repairable) at node point 53 to 54, 6 to 59 of Zone 17 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 574/SWD-I | 22/07/2020 |  | SUNNY CONSTRUCTION | 4.78 | 9.57 | 0
86 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 94-95, 76-95A, 19-26, 10-11, 11-12, 12-13, 94-230 in Sonarpur KMDA rural area, Zone-3 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 646/SWD-I | 30/07/2020 |  | PROJECT AND MAINTENANCE | 4.43 | 8.86 | 0
87 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Chandipur Bazer(N.P.-072) to Kazi Para (N.P.091) of Kalyan Pur Gram Panchayet under Zone-40 of Baruipur Block due to Cyclone "AMPHAN"2020 under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24 Pgs. District. (N.P.-072-075-077-080-082-085-087-089-090-091) |  |  | 751/SWD-I | 14/08/2020 |  | MANAS CHATTERJEE | 4.44 | 8.88 | 0
88 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Bidhyadhar Pur More (N.P.-039) to Hari Builder's (N.P.041) & Sikharballi-II GP Office (N.P.-030) to Kundarali FPS ( N.P.-031) And ratan Pur FPS (N.P.-083) to Kayem Molla's House (N.P.-084)of Sikharballi-II Gram Panchayet under Zone-40 of Baruipur Block due to Cyclone "AMPHAN"2020 under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24 Pgs. District. |  |  | 753/SWD-I | 14/08/2020 |  | MANAS CHATTERJEE | 4.32 | 8.64 | 0
89 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Pir Pukur F.P.S.(N.P.-043) to Indra Para Tematha More (N.P.-110) & Sikharballi-II GP Office(N.P.-030) to Mamud Pur More (N.P.-037) of Sikharballi-II Gram Panchayet under Zone-40 of Baruipur Block due to Cyclone "AMPHAN"2020 under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24 Pgs. District. |  |  | 752/SWD-I | 14/08/2020 |  | MANAS CHATTERJEE | 3.26 | 6.52 | 0
90 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Haldar Para Area (N.P.-060) to (N.P.-062) of Zone-47 under Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 718/SWD-I | 14/08/2020 |  | M/S. SUMAN ENTERPRISE | 4.71 | 9.43 | 0
91 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 114-115, 110-102 under Sonarpur Block, Zone 30 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 582/SWD-I | 22/07/2020 |  | NIRMAL UDYOG | 3.69 | 7.37 | 0
92 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from OHR site (N.P.-002) to Haldar Para (N.P.-045) of Zone-47 under Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. (N.P.-003-008; 045-046-054) |  |  | 719/SWD-I | 14/08/2020 |  | RAJLAXMI CONSTRUCTION | 3.96 | 7.93 | 0
93 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from N.P.- 62-23A of zone-43 of Baruipur Block Due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme for Arsenic Effected Areas of South 24 Paraganas |  |  | 749/SWD-I | 14/08/2020 |  | PROJECT AND MAINTENANCE | 4.75 | 9.5 | 0
94 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from N.P.- 23A-34A of zone-43 of Baruipur Block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme for Arsenic Effected Areas of South 24 Paraganas Dist |  |  | 750/SWD-I | 14/08/2020 |  | PROJECT AND MAINTENANCE | 4.69 | 9.38 | 0
95 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Re-construction of boundary wall of Zone-47 & 42, Mograhat-II block which is damaged due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 773/SWD-I | 14/08/2020 |  | RAJLAXMI CONSTRUCTION | 2.15 | 4.29 | 0
96 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Re-construction of boundary wall of Zone-29, Baruipur block which is damaged due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 772/SWD-I | 14/08/2020 |  | STAR ENTERPRISE | 3.23 | 6.46 | 0
97 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Water Supply System and other Ancillary works from Kamalpur to Nilmanikar High School (N.P.-36-54 & 54-60) of Zone-28 of Baruipur Block due to cyclone "AMPHAN-2020" under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 742/SWD-I | 14/08/2020 |  | STAR ENTERPRISE | 4.17 | 4.17 | 0
98 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from N.P. 96-64C-64-64A-64B under Zone-29 (Source BS-I) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 759/SWD-I | 14/08/2020 |  | STAR ENTERPRISE | 4.51 | 4.51 | 0
99 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from OHR site (N.P.-002) to Kesab Mondal's House (N.P.-007) under Zone-26 (Bindakhali GP) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 757/SWD-I | 14/08/2020 |  | KHAN ENTERPRISE | 4.81 | 4.81 | 0
100 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 219-220, 219-221, 221-222, 221-223, 394-395 in Sonarpur KMDA rural area, Zone-1 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 642/SWD-I | 30/07/2020 |  | STAR ENTERPRISE | 4.06 | 4.06 | 0
101 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of water supply system and other ancillary work node point- 90-82 in Bhangor-I block Zone-35 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 638/SWD-I | 30/07/2020 |  | SUPER SKILL | 4.09 | 8.19 | 0
102 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of water supply system and other ancillary work node point- 206-207, 276-285, 155-156, 207-208, 22-23-24, 25-26, 317-318, 319-320, 22-162, 23-161, 36-37, 37-38, 264-265, 265-266, 33-34, 34-35, 331-332 in Sonarpur KMDA rural area, Zone-2 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 645/SWD-I | 30/07/2020 |  | STAR ENTERPRISE | 4.35 | 4.35 | 0
103 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of water supply system and other ancillary work node point- 226-227, 226-228, 218-229, 229-230, 229-231, 231-232, 216-217, 217-218, 218-219 in Sonarpur KMDA rural area, Zone-1 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte. |  |  | 644/SWD-I | 30/07/2020 |  | STAR ENTERPRISE | 4.45 | 4.45 | 0
104 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Choudhury Shop (N.P.-015) to Gopal Haldar's House (N.P.-016) & Satyandra Asram (N.P.-017) to Bindakhali (N.P.-025) & Gopal Haldar's House (N.P.-016) to Satyandra Asram (N.P.-017) under Zone-26 (Bindakhali GP) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 756/SWD-I | 14/08/2020 |  | KHAN ENTERPRISE | 3.64 | 3.64 | 0
105 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Paruldah (N.P.-003) to Bimal Naskar's House (N.P.-002A) & Dakshin Para (N.P.-052) to Habul Bag's House (N.P.-053) under Zone-26 (Bindakhali GP) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 755/SWD-I | 14/08/2020 |  | KHAN ENTERPRISE | 3.05 | 3.05 | 0
106 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from 94-94A, 94A-95, 95-94B, 94A-96C &96-95, Zone-28 (Source BS-I) under Baruipur Block Due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. |  |  | 744/SWD-I | 14/08/2020 |  | M/S. GOUTAM ROY | 4.76 | 4.76 | 0
107 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Node Point 128-126, 124-123, 123-127, 124-125 of Zone-44 Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 717/SWD-I | 14/08/2020 |  | DIAMOND ENTERPRISE | 4.64 | 4.64 | 0
108 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from Node Point 135-84, 128-129, 104-105, 128A -128B of Zone-44 Mograhat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 715/SWD-I | 14/08/2020 |  | DIAMOND ENTERPRISE | 4.83 | 4.83 | 0
109 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Water Supply and Ancillary works from N.P.- 11-66, 66-25 of under Zone-28 of Magrahat-II Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 766/SWD-I | 14/08/2020 |  | DIAMOND ENTERPRISE | 4.66 | 4.66 | 0
110 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from N.P.-037-038 at Durga Pur of Zone-51 under Joynagar-I Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 727/SWD-I | 14/08/2020 |  | M/S. KUNDU CONSTRUCTION | 4.66 | 4.66 | 0
111 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of water supply system and other ancillary work node point- 221-223, 223-224, 223-225, 217-226, 216-234 in Sonarpur KMDA rural area, Zone-1 due to cyclone AMPHAN 2020 under South 24-Pgns Water Supply Division-I, PHE Dte |  |  | 643/SWD-I | 30/07/2020 |  | SRIJON ENTERPRISE | 3.99 | 3.99 | 0
112 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 1-62, 61-62 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 589/SWD-I | 22/07/2020 |  | M/S. SAMADDAR CONSTRUCTION | 3.72 | 3.72 | 0
113 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipe line (non-repairable) at node point 16-164,191-192,142-144 of Zone 08 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 570/SWD-I | 22/07/2020 |  | SUKUMAR DEBNATH | 1.29 | 1.29 | 0
114 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line of 90mm dia in place of old AC pipeline (non-repairable) at different node point of Zone-09 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 572/SWD-I | 22/07/2020 |  | SRIJON ENTERPRISE | 3.02 | 3.02 | 0
115 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipeline (non-repairable) at node point 9-245,146-97,93-98,6-197,9-207-208,10-145 of Zone-08 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 569/SWD-I | 20/07/2020 |  | SRIJON ENTERPRISE | 3.53 | 3.53 | 0
116 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from Begumpur Tapan Mondal House to Sagar Gayen House Via Oroncho School to Baidya Para,(Source BS-I) Zone-28 under Baruipur Block Due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. |  |  | 741/SWD-I | 14/08/2020 |  | M/S. GOUTAM ROY | 4.07 | 4.07 | 0
117 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Refurbishment of OHR Site of Zone-13A damaged due to Amphan Cyclone under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 551/SWD-I | 22/07/2020 |  | UNICON INDIA | 3.12 | 3.12 | 0
118 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Laying of new UPVC pipe line in place of old AC pipeline (non-repairable) at different node point of Zone 17 damaged due to Amphan cyclone under Surface Water Based Water Supply scheme of South 24-Pgs. W/S Sub-Divn.-II PHE Dte. |  |  | 575/SWD-I | 22/07/2020 |  | JAGANNATH ENTERPRISE | 4.77 | 4.77 | 0
119 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Special repair of 450mm to 150mm internal dia M.S./D.I. Rising Main connecting Nandaranpur, Atmarampur, Uttar Roypur, Betuabati, Buita, Jamalpur, Moukhali & Nischintipur OHR Zone and distribution zone of Uttar Roypur under Budge Budge I with repairing of valve chambers under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of South 24-Pgs. District in connection to the destruction by amphan on 20.05.2020 |  |  | 634/SWD-I | 03/07/2020 |  | M/S. S.S. ENTERPRISE | 1.42 | 1.42 | 0
120 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 61-55,63-62 under Sonarpur Block, Zone 33 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 591/SWD-I | 22/07/2020 |  | M/S. KUNDU CONSTRUCTION | 3.6 | 3.6 | 0
121 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Repair and Restoration of security guard room(2nos) at Zone-9 Head works site damaged due to Amphan cyclone under South 24-Pgs. Water Supply Sub-Divn.-II under South 24-Pgs. Water Supply Divn.-I PHE Dte. |  |  | 564/SWD-I | 22/07/2020 |  | SRIJON ENTERPRISE | 3.02 | 3.02 | 0
122 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Water Supply and Ancillary works From Node 35-37, 37-38 & 34-36 Zone-48 under MAGRAHAT-II block due to Cyclone "AMPHAN 2020 " under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. |  |  | 770/SWD-I | 14/08/2020 |  | DIAMOND ENTERPRISE | 4.59 | 4.59 | 0
123 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvenation and repairing of the Supply System and other Ancillary works from N.P. 63C-96B-342B-342A, 342B-342C under Zone-29 & KMDA Zone-III (Source BS-I) of Baruipur Block due to Cyclone 'Amphan' 2020 under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-Parganas district. |  |  | 765/SWD-I | 14/08/2020 |  | M/S. GOUTAM ROY | 4.63 | 4.63 | 0
124 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration and protection of distribution pipeline damaged due to Amphan Cyclone of Zone-16 (Moudi Dhankal, Khirishtala and other places) under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 579/SWD-I | 22/07/2020 |  | DIAMOND ENTERPRISE | 3.05 | 3.05 | 0
125 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Reparing of Pump House at Buita W/S Scheme, Rajibpur / Moukhali under Surface water based Mega Water supply scheme for Falta Mathurapur in connection to destruction by Aumphan on 20.05.2020 |  |  | 632/SWD-I | 30/07/2020 |  | M/S. S.S. ENTERPRISE | 2.62 | 2.62 | 0
126 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination, restoration and repairing of the water supply system and other ancillary works from Node Point 114-115 under Sonarpur Block, Zone 30 due to cyclone "AMPHAN" under South 24 Parganas Water Supply Division-I P.H.E. Dte. |  |  | 583/SWD-I | 22/07/2020 |  | M/S. S. D. CONSTRUCTION | 4.25 | 8.5 | 0
127 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of distribution pipeline damaged due to Amphan Cyclone of Zone-13A (From Joyrampur to Burosivtala) under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 556/SWD-I | 22/07/2020 |  | UNICON INDIA | 4.8 | 9.59 | 0
128 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of distribution pipeline damaged due to Amphan Cyclone of Zone-13A (near G.P. Pradhan's house & other 6 places) and other misc works like constn. of valve chamber, restoration of concrete road damaged due to repairing of pipeline under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 555/SWD-I | 22/07/2020 |  | NANDY UDYOG | 1.65 | 3.3 | 0
129 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Rejuvination and repairing of the Supply System and other Ancillary Works from 96-96C, 64B-64A-64, 64A-64C-96A-96C-64A, 64C-96 Zone-29 (source BS-I) under Baruipur Block due to Cyclone "AMPHAN"2020 under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | 740/SWD-I | 14/08/2020 |  | M/S. GOUTAM ROY | 4.76 | 4.76 | 0
130 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Reparing of Bagirathi Panchali inspection Bunglow damaged due to 'Amphan' under Surface water based water supply Scheme for arsenic affected areas of South 24 Parganas. |  |  | 694/SWD-I | 10/08/2020 |  | M/S. S.S. ENTERPRISE | 20.6 | 41.2 | 0
131 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Emergency restoration of Different damaged components for Pipe Water Supply Schemes at various zones under South 24 Parganas Water Supply Division-I, PHE Dte. Caused due to Super Cyclone AMPHAN on 20th May in the district of south 24 Parganas | SM/09020 | Disaster | Restoration of distribution pipeline damaged due to Amphan Cyclone of Zone-13A (Fakirpara) under South 24 Pgs W/S Sub Divn.-II, P.H.E. Dte. in connection with SWBPWSS in Arsenic Affected areas of South 24 Pgs. Dist. |  |  | 554/SWD-I | 22/07/2020 |  | UNICON INDIA | 4.8 | 9.6 | 0
Total | [12 empty] | 567.54 | 927.73 | 163.46