## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 6708/AD | 16/03/2022 |  | ALOK ENTERPRISE (A unit of Saket Trexim Pvt. Ltd.) | 341.37 | 249.16 | 86
2 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 600/AD | 28/04/2022 |  | M/S. S.S. ENTERPRISE | 537.16 | 351.97 | 73
3 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | 620/CSD | 06/08/2021 |  | INDRANIL DUTTA & ASSOCIATES | 4.28 | 4.28 | 100
4 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | 621/CSD | 06/08/2021 |  | INDRANIL DUTTA & ASSOCIATES | 3.2 | 3.2 | 100
5 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | 632/CSD | 10/08/2021 |  | INDRANIL DUTTA & ASSOCIATES | 3.92 | 3.93 | 100
6 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | 633/CSD | 10/08/2021 |  | INDRANIL DUTTA & ASSOCIATES | 3.53 | 3.53 | 100
7 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | 634/CSD | 10/08/2021 |  | INDRANIL DUTTA & ASSOCIATES | 2.35 | 1.73 | 100
8 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | 622/CSD | 06/08/2021 |  | INDRANIL DUTTA & ASSOCIATES | 1.57 | 0.99 | 100
9 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Day to day carriage of different materials(Like DI Pipes, DI Fittings, AC Pipes ,MSERW Pipes, GI Pipes, Ferrule,TMT Bar e.t.c) from Kalyani Stores under Resources Divn , P.H.E.Dte to different work sites in rural / urban areas in any area of West Bengal for the year 2022-2023. |  |  | 4796/RS | 25/08/2022 |  | DASGUPTA & CO. | 0 | 5.04 | 0
10 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Alipore Division. |  |  | 3854/RS | 07/07/2022 |  | ELECTRO ENTERPRISES | 12.3 | 0 | 0
11 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Raiganj Division.. |  | Junior Engineer | 5062/RS | 06/09/2022 |  | A.K.INDUSTRIES | 0 | 12.3 | 0
12 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 51.65 | 118.17 | 100
13 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Additional pipeline for FHTC work of Kalikatala W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 12591/AD | 13/03/2023 |  | M/S. S.S. ENTERPRISE | 90.52 | 0 | 100
14 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Day to day carriage of different materials(Like DI Pipes, DI Fittings, AC Pipes ,MSERW Pipes, GI Pipes, Ferrule,TMT Bar e.t.c) from Kalyani Stores under Resources Divn , P.H.E.Dte to different work sites in rural / urban areas in any area of West Bengal for the period of three months in the year 2022-2023 & 2023-2024. | Assistant Engineer |  | 1172/RS | 11/04/2023 |  | THE ENTERPRISE | 0 | 2.4 | 0
15 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Burdwan Division. | Assistant Engineer | Junior Engineer | 2618/RS | 24/08/2023 |  | PREETI ENTERPRISE | 0 | 1.36 | 100
16 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5672/RS | 01/11/2022 |  | TATA METALIKS LTD | 123.11 | 0 | 100
17 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (2500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalikatala (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub- Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 1548/AD | 17/07/2023 |  | M/S. S.S. ENTERPRISE | 177.08 | 0 | 30
18 | SOUTH 24 PARGANAS | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Kalikatala (Zone - I & II) of Canning-II Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone-II) (SM/10051) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | 4307/AD | 29/10/2024 |  | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 159.68 | 0 | 0
Total | [12 empty] | 1511.73 | 758.08 | 50.15