## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Construction of 02 (Two) nos. chlorination room at GOBINDAPUR of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD | JE-1 | 1410/SWD-I | 22/09/2022 |  | J H K ENTERPRISE | 11.01 | 0 | 100
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | 545/SMD | 21/02/2023 |  | DEBJYOTI BASU | 19.37 | 0 | 100
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Nadia Division. |  |  | 5077/RS | 07/09/2022 |  | A.K.INDUSTRIES | 0 | 9.3 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GOBINDAPUR PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010741] | AE BSD | JE-1 | 1685/SWD-I | 01/11/2022 |  | SIMPLEX DRILLING COMPANY | 42.98 | 36.72 | 100
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Preparation and submission of Detailed Project Report of GOBINDAPUR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | 1962/SWD-I | 21/01/2022 |  | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at GOBINDAPUR Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1510) | AE BSD | JE-1 | 1737/SWD-I | 10/08/2023 |  | TAAS ENTERPRISE | 511.22 | 262.75 | 80
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2501/RS | 10/08/2023 |  | ELECTROSTEEL CASTINGS LIMITED | 34.13 | 0 | 45
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2502/RS | 10/08/2023 |  | ELECTROSTEEL CASTINGS LIMITED | 0 | 35.84 | 35
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gobindapur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11280] | Assistant Engineer | Junior Engineer | 1520/SMSD | 18/11/2024 |  | DEBJYOTI BASU | 0.59 | 0 | 0
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Operation and guarding of the pumping machinery at PH No- 1 of Gobindapur W/S Scheme Jaynagar-I Block under south 24 pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | 274/SMSD | 25/02/2025 |  | DEBJYOTI BASU | 0.91 | 0 | 0
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gobindapur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11280] | Assistant Engineer | Junior Engineer | 18/SMSD | 06/01/2025 |  | DEBJYOTI BASU | 0.59 | 0 | 0
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Operation and guarding of the electric operated auto/ manual control pumping machinery at Dhosa, Paschim Chakpanchghora, Padmerhat, Mahismari, Gobindapur, Laxmi Narayanpur, Baharu, Punpo W/S Scheme of Jaynagar-I and Maipith W/S scheme of Kultali Block under South 24pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | 2845/SMD | 22/09/2025 |  | M/S. S.S. ENTERPRISE | 7.22 | 0 | 0
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Ground water based piped water supply scheme for Gobindapur PWSS, Under South 24-Pgns W/S Division-I, Block: Joynagar District South 24-Pgns. | SM/11280 | New | Washing cleaning of chlorine machine unit at different water supply scheme of Jaynagar-I and II and Mograhat-II Block under South-24Pgs Mechanical Division, PHE. Dte | Assistant Engineer | Junior Engineer | 2922/SMD | 25/09/2025 |  | SHIVAM ENTERPRISE | 0.1 | 0 | 0
Total | [12 empty] | 630.88 | 347.37 | 55.06