## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under South 24 PGS W/S. Division-I. |  | Junior Engineer | 2478/RS | 25/04/2022 |  | PREETI ENTERPRISE | 6.38 | 0 | 0
2 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for ALIPOREPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE2 | 915/SWD-I | 19/07/2022 |  | SIMPLEX DRILLING CO. | 14.18 | 13.06 | 100
3 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Tamluk Division. |  | Junior Engineer | 4887/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 6.38 | 0
4 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed ALIPORE PIPE WATER SUPPLY SCHEME Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 1038] | AE SWSD-II | JE2 | 1487/SWD-I | 28/09/2022 |  | MAA LAXMI ENTERPRISE | 119.84 | 57.85 | 90
5 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Preparation and submission of Detailed Project Report of "ALIPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | 458/SWD-I | 24/05/2022 |  | GEO SOLUTION | 2.51 | 2.5 | 100
6 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ALIPORE PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011230] | AE SWSD-II | JE2 | 2905/SWD-I | 14/02/2023 |  | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100
7 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for ALIPORE PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011230] | AE SWSD-II | JE2 | 3124/SWD-I | 24/02/2023 |  | CIVIL CONSULTANT | 15.88 | 0 | 100
8 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Alipore water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | 279/SMD | 01/02/2023 |  | NITESH MANAGEMENT | 26.52 | 0 | 40
9 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Development of low land and temporary aproach road for entering Tubewell site for proposed ALIPORE Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011230] | AE SWSD-II | JE2 | 3703/SWD-I | 30/03/2023 |  | SIMPLEX DRILLING COMPANY | 0.88 | 0.75 | 100
10 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | 1377/SWD-I | 12/07/2023 |  | CONCORD PROJECTS PVT. LTD. | 8.81 | 0 | 60
11 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Land Development at 1st Tubewell site under Alipore PWSS to accommodate FHTC in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011230] | AE SWSD-II |  | 1487/SWD-I | 19/07/2023 |  | MAA LAXMI ENTERPRISE | 2.97 | 2.97 | 100
12 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of ALIPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11493) (3rd Call) | AE SWSD-II | JE2 | 1498/SWD-I | 20/07/2023 |  | RAMASISH ENTERPRISE | 5.91 | 0 | 100
13 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2337/RS | 24/07/2023 |  | RASHMI METALIKS LIMITED | 26.86 | 0 | 2
14 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Laying rising main & additional pipeline for distribution system, construction of boundary walls for 1st & 2nd Tubewell sites and other allied works for proposed ground water based ALIPORE PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11493) | AE SWSD-II | JE2 | 2924/SWD-I | 25/06/2024 |  | MAA LAXMI ENTERPRISE | 67.93 | 0 | 0
15 | SOUTH 24 PARGANAS | South 24 Pgs. W/S Division - I | Proposed ground water based ALIPORE piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11493 | New | Operation and guarding of the electric operated auto/ manual control pumping machinery at Krishnarampur, Bakeswar, Bhandaria, Julpia & Alipore water supply scheme of Bishnupur-I Block under South 24pgs Mechanical Division, PHE Dte. | Assistant Engineer -II | Junior Engineer | 2936/SMD | 25/09/2025 |  | SINHA ELECTRICALS | 3.61 | 0 | 0
Total | [12 empty] | 303.88 | 85.11 | 28.01