## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for ERENDA piped water supply scheme at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tubewell site (Dag No. 391, Khatian No. 1321 , JL No. 132, Mouza- Noapara), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | 1441/SWD-I | 26/09/2022 |  | ABU TALEB MONDAL | 28.52 | 0 | 0
2 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Erenda water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | 300/SMD | 06/02/2023 |  | B.T.PROJECTS PVT.LTD. | 23 | 0 | 40
3 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ERENDA PWSS at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tube-well site (Dag No. 391 Khatian No. 1321, JL No. 132, Mouza- Noapara) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12043] | AE HQ-I |  | 3568/SWD-I | 22/03/2023 |  | ABUTALEB MONDAL | 3.13 | 0 | 0
4 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 3188] | AE HQ-II | JE-4 | 2002/SWD-I | 28/08/2023 |  | MAHMOOD ASSOCIATES PRIVATE LIMITED | 347.5 | 129.05 | 25
5 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi | Assistant Engineer | Junior Engineer | 2630/RS | 25/08/2023 |  | RASHMI METALIKS LIMITED | 4.7 | 0 | 2
6 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under South 24 PGS W/S. Division-I. | Assistant Engineer | Junior Engineer | 2704/RS | 31/08/2023 |  | ELECTRO ENTERPRISES | 0 | 4.52 | 100
7 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ERENDA PWSS of Bhangar-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010678] | AE HQ-II | JE-4 | 562/SWD-I | 31/01/2024 |  | TRAYEE DECORATOR | 15.88 | 13.05 | 100
8 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for ERENDA Piped Water Supply Scheme in BHANGAR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12043] | AE HQ-II | JE-4 | 1069/SWD-I | 04/03/2024 |  | ASHIM SHIL | 15.8 | 13.32 | 100
9 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12043) | AE HQ-I | JE-4 | 4465/SWD-I | 29/10/2024 |  | SUJIT KUMAR SHARMA | 10.53 | 0 | 100
10 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte. [WB092725] [SM/12043] [w.e.f. 01/12/2024 to 31/05/2025] | AE HQ-I | JE-4 | 4847/SWD-I | 28/11/2024 |  | GOPAL KUMAR JHA | 0.86 | 2.37 | 30
11 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte. [WB092725] [SM/12043] [w.e.f. 01/06/2025 to 30/11/2025] | AE HQ-I | JE-4 | 1367/SWD-I | 22/05/2025 |  | GOPAL KUMAR JHA | 0.87 | 0.4 | 18
12 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Improvement of outdoor Illumination arrangement with allied works at Erenda PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/12043) | Assistant Engineer | Junior Engineer | 1545/SMSD | 25/11/2024 |  | B.T.PROJECTS PVT.LTD. | 0.9 | 0 | 100
13 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Supply & Fixing main switch & Bus bar at Pump House no-1 of Erenda W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/12043) | Assistant Engineer | Junior Engineer | 1402/SMSD | 30/09/2024 |  | B.T.PROJECTS PVT.LTD. | 0.29 | 0 | 100
14 |  |  | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM |  |  | Operation and guarding of the electric operated auto/ manual control pumping machinery at Erenda, Bodra, Narayanpur and Padma Pukuria water supply scheme of Bhangar-I Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | 2852/SMD | 23/09/2025 |  | S.B.ENTERPRISE | 3.61 | 0 | 0
Total | [12 empty] | 455.59 | 162.72 | 35.72