## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Gopinathpur & its adjoining mouzas W/S Scheme (300 CuM) & (2) Khirinda & its adjoining mouzas W/S Scheme (400 CuM) within Pingla block in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division |  | 1476/MD | 25/07/2022 |  | JADAVPUR UNIVERSITY | 4.52 | 0 | 55
2 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Water sample testing and other works for construction of tube well (300mm x 200mm x 200 mtrs depth) by utilising departmental machineries for khirinda w/s scheme (TW-II), Pingla block under Paschim Midnapore Distrrict, CDD, PHE Dte. | Driller In Charge | Junior Engineer | 1723/CDD | 29/12/2022 |  | SANKAR PRASAD DUTTA & CO. | 10.21 | 0 | 0
3 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-II), PINGLA BLOCK, UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | 1722/CDD | 29/12/2022 |  | SANKAR PRASAD DUTTA & CO. | 5.6 | 0 | 0
4 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khirinda Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | 572/W/MMD | 20/03/2023 |  | DEY ENTERPRISE | 25.26 | 0 | 0
5 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-I), PINGLA BLOCK UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | 1720/CDD | 29/12/2022 |  | Universal Enterprises | 5.62 | 0 | 0
6 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | WATER SAMPLE TESTING AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHIRINDA W/S SCHEME (TW-I), PINGLA BLOCK UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | 1721/CDD | 29/12/2022 |  | Universal Enterprises | 10.23 | 0 | 0
7 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Hiring of Diesel driven motor cab(BS-III & Above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. Car No. WB-04H-5846. |  |  | 33/S&WSD | 23/03/2023 |  | ASHUTOSH DAS & CO | 0.14 | 0 | 100
8 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | 1069/W/MMD | 14/03/2024 |  | SWAPAN BANERJEE | 0.5 | 0 | 100
9 | PASCHIM MEDINIPUR | Midnapore Division | Khirinda Piped Water Supply Scheme. | SM/07393 | New | Construction of Pump House (PH-2), Boundary wall (2nd T/W Site) and Laying Rising main in between two tube wells with bypass line & interconnection work for Khirinda PWSS within Pingla block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | 1286/MD | 04/06/2025 |  | ARNAB PATRA | 16.37 | 0 | 40
Total | [12 empty] | 78.45 | 0 | 0