## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5672/RS | 01/11/2022 |  | TATA METALIKS LTD | 0 | 16.37 | 100
2 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | 1890/TD | 24/11/2022 |  | H. SAMANTA | 123.68 | 64.87 | 53
3 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Relaying Pipe Line of SARRANG PIPED WATER SUPPLY SCHEME due to Damaged by RIDF Road Construction, Block - Egra-I, District : Purba Medinipur. | Assistant Engineer | Junior Engineer | 2187/TD | 01/09/2023 |  | SATYABRATA BHAUMIK | 11.32 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Construction of approach road at H/W site & 2nd T/W site of Sarrang Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | 209/TD | 15/01/2025 |  | ASEMA ENTERPRISE | 1.95 | 0 | 0
Total | [12 empty] | 136.94 | 81.24 | 59.32