## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1440 nos) under JJM with allied work for Parihati PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub- Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | 1202/JHD | 26/07/2023 |  | SAIKAT DANDAPAT | 362.99 | 0 | 5
2 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | 1415/CDD | 21/09/2023 |  | JHARGRAM SPV PRIVATE LIMITED | 43.48 | 0 | 11
3 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Parihati and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division,Junior Engineer-III | 514/JRWS | 15/03/2024 |  | SANKAR KUMAR NAG | 4.82 | 0 | 0
4 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints admi |  |  | 1662/RS | 18/06/2024 |  | RASHMI METALIKS LIMITED | 12.79 | 0 | 20
5 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Supply and delivery of ISI marked Ductile Iron fittings(Bolted Collar, D.I. Pushing Bend, Tee, Reducer , Spigot Tale piece , socket Tale Piece & other Specials) conforming to IS: 9523-2000 for push on joint/ Flanged Joint / Mechanical Joint with externally and internally coated with Fusion Bonded Epoxy with necessary jointing material rubber gasket (IS 5382 1985) including transportation, loading, unloading and staking at site.Delivery is to be made in respective sites of Jhargram Division. |  |  | 1783/RS | 01/07/2024 |  | ELECTROSTEEL CASTINGS LIMITED | 0.56 | 0 | 10
6 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Supply and delivery of ISI marked Ductile Iron fittings(Bolted Collar, D.I. Pushing Bend, Tee, Reducer , Spigot Tale piece , socket Tale Piece & other Specials) conforming to IS: 9523-2000 for push on joint/ Flanged Joint / Mechanical Joint with externally and internally coated with Fusion Bonded Epoxy with necessary jointing material rubber gasket (IS 5382 1985) including transportation, loading, unloading and staking at site.Delivery is to be made in respective sites of Jhargram Division. |  |  | 2222/RS | 20/08/2024 |  | KEJRIWAL CASTINGS LTD. | 1.01 | 0 | 50
7 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Supply and delivery of ISI marked Ductile Iron fittings(Bolted Collar, D.I. Pushing Bend, Tee, Reducer , Spigot Tale piece , socket Tale Piece & other Specials) conforming to IS: 9523-2000 for push on joint/ Flanged Joint / Mechanical Joint with externally and internally coated with Fusion Bonded Epoxy with necessary jointing material rubber gasket (IS 5382 1985) including transportation, loading, unloading and staking at site.Delivery is to be made in respective sites of Jhargram Division. |  |  | 2807/RS | 06/11/2024 |  | JINDAL SAW LIMITED. | 0.61 | 0 | 10
8 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Jamboni GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | 367/JRWS | 03/10/2024 |  | PRINT PREVIEW | 0.5 | 0 | 100
9 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Operation and guarding of pumping Machinery (Automatic Operation) including all allied electro-mechanical components at Parihati mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 2317/JMD | 23/02/2024 |  | DEY ENTERPRISE | 1.61 | 0 | 100
10 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Parihati mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 6059/JMD | 12/08/2024 |  | DEY ENTERPRISE | 3.54 | 0 | 100
11 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Supply & delivery of standby pumping machineries at Parihati and adjacent water supply schemes in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | JE (M) | 97/W/AE/JMD | 21/04/2025 |  | CHAKRABORTY MINING & ENGINEERING | 0.8 | 0 | 0
12 | JHARGRAM | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Withdrawing of damaged Submersible pumping machinery and installation of same capacity departmentally supplied pump motor set with other allied works at Parihati mini piped water supply scheme of Jamboni block in the district of Jhargram under Jhargram Mechanical Division,P.H.E. DTE. | Assistant Engineer | JE (M) | 105/W/AE/JMD | 30/04/2025 |  | DEY ENTERPRISE | 0.12 | 0 | 100
Total | [12 empty] | 432.84 | 0 | 0