## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Providing UPVC materials including other drilling related works for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M) | 80/JMD | 03/01/2023 |  | DEBJYOTI BASU | 0.75 | 0 | 100
2 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Providing different manpower for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | 81/JMD | 03/01/2023 |  | DEBJYOTI BASU | 0.15 | 0 | 100
3 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | 01 nos I.E.P (size 10 cum/hr) with platfrom, with masonary drain of Chandabila W/S Scheme(under 45 nos Mini scheme) at Binpur-I Dev. Block under Jhargram Sub division within Jhargram Division ,PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | 1091/JHD | 14/07/2023 |  | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 9.9 | 4.36 | 95
4 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Natundihi W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | 2096/JMD | 03/08/2023 |  | RMD TRADING | 1.23 | 0 | 0
5 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Amlagura W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | 2101/JMD | 03/08/2023 |  | MONORANJAN DEY | 1.23 | 0 | 0
6 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no. II under JJM programme at Telidanga W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | 2100/JMD | 03/08/2023 |  | JAGANNATH ENTERPRISE | 1.23 | 0 | 0
7 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery, installation & commissioning of submersible pumping machinery and other Electro Mechanical accessories at replacement tube well no. II of Ruknimara mini piped W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | 2097/JMD | 03/08/2023 |  | SUJOY RANJAN BHOWMICK | 1 | 0 | 0
8 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Bhaliadiha W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | 2102/JMD | 03/08/2023 |  | DEBJYOTI BASU | 1.23 | 0 | 0
9 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Dakisole SSK W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | 2640/JMD | 29/08/2023 |  | BHABANI PRASAD MANNA | 1.23 | 0 | 0
10 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Sinking 2 nos rig bored tubewells(recplacement),reconstruction of boundary walls and interconnection pipelines from new tubewells to existing distribution pipe lines of Hatipata w/s scheme(under 45 Mini pwss) and Tapsia w/s scheme(under 45 Mini pwss). 4th Call (Ref: 1st Call eNIT_22 of 2022-23 , SL No.-3, and 2nd Call eNIT_08 of 2023-24, SL No.- 7, 3rd Call eNIT_13 of 2023-24, SL No.-3 ) | Assistant Engineer | Junior Engineer-III | 1040/JHD | 22/07/2024 |  | JAYANTA SAHOO | 13.13 | 10.95 | 90
11 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) by D.T.H. Method for Augmentation of Source of Dakaisole PWSS under 45 Mini PWSS at Binpur-II Block under Jhargram Sub-Division within Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | 738JSD | 02/08/2024 |  | BIDYUT KUMAR SANTRA | 4.05 | 0 | 0
12 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tube-well (Replacement) by D.T.H. Method for Augmentation of Source of Telidanga PWSS under 45 Mini PWSS at Binpur-II Block under Jhargram Sub-Division within Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | 737/JSD | 02/08/2024 |  | BIDYUT KUMAR SANTRA | 4.05 | 0 | 100
13 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | EXTENSION OF PIPELINE INCLUDING LEFTOUT FHTC UNDER JJM IN KUI MINI PWSS(OUT OF 45 NOS MINI PWSS) BLOCK - BINPUR-I WITHIN JHARGRAM SUB DIVISION UNDER JHARGRAM DIVISION PHE DTE. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | 473/JSD | 16/05/2025 |  | SAURABH KAR | 0.97 | 0 | 0
14 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Borjharia mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5760/JMD | 07/08/2024 |  | ECO ENTERPRISE | 3.54 | 1.41 | 0
15 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping Machinery (Automatic Operation) including all allied electro-mechanical components at Tube Well no. 1 of Bhaliaghati mini piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Driller-In-Charge | Junior Engineer | 2339/JMD | 23/02/2024 |  | CHAKRABORTY MINING & ENGINEERING | 1.61 | 0 | 0
16 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping Machinery (Automatic Operation) including all allied electro-mechanical components at Nayabasan mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | 2731/JMD | 29/02/2024 |  | PADMA ENGINEERING CO. | 1.61 | 0 | 0
17 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Tapsia mini piped water supply scheme in Jhargram District under Jhargram Mechanical Division PHE Dte. | Driller-In-Charge | Junior Engineer | 6479/JMD | 21/08/2024 |  | SOUMEN ELECTRIC | 3.54 | 0 | 0
18 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components installed at Chandabila Pry. School W/S Scheme at Binpur-II in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Driller-In-Charge | Junior Engineer | 6640/JMD | 22/08/2024 |  | M/S. EMMESS | 3.53 | 0 | 100
19 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Tube Well no. II of Bhalia Ghati mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 6115/JMD | 12/08/2024 |  | P.K. ENGINEERING | 3.53 | 0 | 0
20 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components installed at Pump House no. 1 of Radhanagar W/S Scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | JE (M) | 6608/JMD | 22/08/2024 |  | BEE GEE CONSTRUCTION | 3.53 | 0 | 100
21 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Aushpal mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 5727/JMD | 07/08/2024 |  | BUSR ENGINEERING | 3.54 | 0 | 100
22 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Kashafulia mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 5806/JMD | 07/08/2024 |  | DEBJYOTI BASU | 3.53 | 0 | 100
23 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components installed at Pump House no. 1 of Dehoganj W/S Scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Driller-In-Charge | Junior Engineer | 5777/JMD | 07/08/2024 |  | DEY ENTERPRISE | 3.54 | 0 | 0
24 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Bhaliadiha mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5749/JMD | 07/08/2024 |  | DEBJYOTI BASU | 3.53 | 0 | 0
25 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Bhaliaghati mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5750/JMD | 07/08/2024 |  | SUJOY RANJAN BHOWMICK | 3.53 | 0.89 | 0
26 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Bhurkundi (Near house of Kishore Mahata) mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5755/JMD | 07/08/2024 |  | RITESH ENTERPRISE | 3.54 | 0 | 0
27 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Chirakuti mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5771/JMD | 07/08/2024 |  | KAMAKHYA ENTERPRISE | 3.53 | 0 | 0
28 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Jamunasole mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 5793/JMD | 07/08/2024 |  | DEB KUMAR BASU | 3.53 | 0.89 | 100
29 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Kui mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 5813/JMD | 07/08/2024 |  | SHIVAM ENTERPRISE | 3.54 | 0.88 | 52
30 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Chandabilla mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 5761/JMD | 07/08/2024 |  | DEBJYOTI BASU | 3.53 | 0 | 100
31 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Chaulbata mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5767/JMD | 07/08/2024 |  | MENAKA ENTERPRISE | 3.54 | 0 | 0
32 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Mandar mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 6044/JMD | 12/08/2024 |  | MENAKA ENTERPRISE | 3.54 | 0 | 0
33 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Nayabasan mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 6051/JMD | 12/08/2024 |  | PADMA ENGINEERING CO. | 3.54 | 0 | 0
34 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Salpatra SSK mini piped water supply scheme in Jhargram District under Jhargram Mechanical Division PHE Dte. | Driller-In-Charge | Junior Engineer | 6077/JMD | 12/08/2024 |  | ABHIJIT BASU | 3.53 | 0.89 | 0
35 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components installed at Pump House no. 1 of Gharduar W/S Scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Driller-In-Charge | Junior Engineer | 5783/JMD | 07/08/2024 |  | MENAKA ENTERPRISE | 3.54 | 0 | 0
36 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Hatikadua mini piped water supply scheme in Jhargram District under Jhargram Mechanical Division PHE Dte. | Assistant Engineer | JE (M) | 5787/JMD | 07/08/2024 |  | SUJOY RANJAN BHOWMICK | 3.53 | 0 | 100
37 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Hatipata mini piped water supply scheme in Jhargram District under Jhargram Mechanical Division PHE Dte. | Driller-In-Charge | Junior Engineer | 5788/JMD | 07/08/2024 |  | DEBJYOTI BASU | 3.53 | 0 | 0
38 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Posro mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 6063/JMD | 12/08/2024 |  | CHAKRABORTY MINING & ENGINEERING | 3.54 | 0 | 100
39 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Raipal mini piped water supply scheme in Jhargram District under Jhargram Mechanical Division PHE Dte. | Driller-In-Charge | Junior Engineer | 6066/JMD | 12/08/2024 |  | M/S. EMMESS | 3.53 | 0 | 0
40 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Khanderpara mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 6174/JMD | 12/08/2024 |  | S.K. ENTERPRISE | 3.43 | 0 | 0
41 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Amlagura mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 5721/JMD | 07/08/2024 |  | MONORANJAN DEY | 3.54 | 0 | 33
42 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Pathardahar and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3041/JMD | 26/08/2025 |  | M/S. SAMRIDDHI ENTERPRISE | 3.65 | 0 | 0
43 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at jamunasol and adjacent 2 (two) nos. mini piped water supply schemes at Jamboni Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3050/JMD | 26/08/2025 |  | ABHIJIT BASU | 3.65 | 0 | 17
44 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bhaliaghati and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 2999/JMD | 25/08/2025 |  | SUJOY RANJAN BHOWMICK | 10.94 | 0 | 0
45 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Biriberia and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3031/JMD | 26/08/2025 |  | SUJOY RANJAN BHOWMICK | 7.29 | 0 | 0
46 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Amlasol and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3045/JMD | 26/08/2025 |  | DEBJYOTI BASU | 3.64 | 0 | 0
47 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Sankisol and adjacent 2 (two) nos. mini piped water supply schemes at Jamboni Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3052/JMD | 26/08/2025 |  | DEB KUMAR BASU | 3.65 | 0 | 17
48 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Amlakora and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3036/JMD | 26/08/2025 |  | S.S. GHORAI | 3.65 | 0 | 0
49 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Taldangra and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3043/JMD | 26/08/2025 |  | TAPAN BISWAS | 3.64 | 0 | 0
50 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Baraperia and adjacent 4 (four) nos. mini piped water supply schemes at Gopiballavpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3208/JMD | 27/08/2025 |  | SOUMEN ELECTRIC | 18.23 | 0 | 0
51 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Armah and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3199/JMD | 27/08/2025 |  | RUBY ENTERPRISE | 3.64 | 0 | 0
52 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Akrasole and adjacent 2 (two) nos. mini piped water supply schemes at Jhargram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3207/JMD | 27/08/2025 |  | MAA BHABOTARINE ENTERPRISE | 10.93 | 0 | 0
53 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Kadam Diha and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3190/JMD | 27/08/2025 |  | SOUMEN ELECTRIC | 3.65 | 0 | 0
54 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Nepura and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 3198/JMD | 27/08/2025 |  | SUBHAM ENTERPRISE | 3.65 | 0 | 0
55 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bakra and adjacent 2 (two) nos. mini piped water supply schemes at Gopiballavpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3201/JMD | 27/08/2025 |  | SUBHRA ENTERPRISE | 10.94 | 0 | 0
56 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Nakrasuli and adjacent 2 (two) nos. mini piped water supply schemes at Sankrail Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3203/JMD | 27/08/2025 |  | M/S. CHANDRANATH MUKHERJEE | 10.93 | 0 | 0
57 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Patina and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3194/JMD | 27/08/2025 |  | MAA BHABOTARINE ENTERPRISE | 3.64 | 0 | 0
58 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Amlagura and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3320/JMD | 28/08/2025 |  | MONORANJAN DEY | 10.94 | 0 | 0
59 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Nischinta and adjacent 2 (two) nos. mini piped water supply schemes at Sankrail Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3336/JMD | 28/08/2025 |  | M/S D.G.B. ENTERPRISE | 3.65 | 0 | 0
60 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Dubrajpur and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 3325/JMD | 28/08/2025 |  | M/S. EMMESS | 3.65 | 0 | 10
61 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Chandabila Pry. School and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 3327/JMD | 28/08/2025 |  | M/S. EMMESS | 10.94 | 0 | 10
62 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bhundurdahi and adjacent 2 (two) nos. mini piped water supply schemes at Gopiballavpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3331/JMD | 28/08/2025 |  | DEY ENTERPRISE | 3.65 | 0 | 0
63 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bansketia and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3319/JMD | 28/08/2025 |  | DEBJYOTI BASU | 3.64 | 0 | 0
64 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Sundraguri and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 3323/JMD | 28/08/2025 |  | ASHUTOSH DAS & CO. | 10.94 | 0 | 0
65 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Benachapra and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 3326/JMD | 28/08/2025 |  | MONORANJAN DEY | 3.65 | 0 | 0
66 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Phul Berya and adjacent 2 (two) nos. mini piped water supply schemes at Jamboni Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3340/JMD | 28/08/2025 |  | DEB KUMAR BASU | 3.65 | 0 | 17
67 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Andhari Sol and adjacent 2 (two) nos. mini piped water supply schemes at Jhargram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3346/JMD | 28/08/2025 |  | DEBJYOTI BASU | 3.64 | 0 | 20
68 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Gharduar and adjacent 2 (two) nos. mini piped water supply schemes at Gopiballavpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3334/JMD | 28/08/2025 |  | PADMA ENGINEERING CO. | 10.93 | 0 | 0
69 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Dubrajpur and adjacent 2 (two) nos. mini piped water supply schemes at Jhargram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE4 | 3345/JMD | 28/08/2025 |  | DEB KUMAR BASU | 3.65 | 0 | 20
70 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Narcha and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3328/JMD | 28/08/2025 |  | ASSOCIATED ELECTRICAL CO. | 3.65 | 0 | 20
71 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Kui and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3322/JMD | 28/08/2025 |  | GOSWAMI TRANSPORT & ENGINEERING WORKS | 10.94 | 0 | 20
72 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Nuasai and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3463/JMD | 29/08/2025 |  | M/S. NABIN GOPAL SENGUPTA | 3.65 | 0 | 0
73 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bhararu and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3466/JMD | 29/08/2025 |  | RISHAV ENTERPRISE | 3.65 | 0 | 0
74 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Hijli and adjacent 2 (two) nos. mini piped water supply schemes at Jamboni Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3469/JMD | 29/08/2025 |  | DIPALI CONSTRUCTION | 3.64 | 0 | 0
75 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bhalaidiha and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3465/JMD | 29/08/2025 |  | RMD TRADING | 10.94 | 0 | 0
76 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Sankarbani and adjacent 4 (four) nos. mini piped water supply schemes at Jhargram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 3476/JMD | 29/08/2025 |  | JAGANNATH ENTERPRISE | 7.29 | 0 | 0
77 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Bangora and adjacent 2 (two) nos. mini piped water supply schemes at Gopiballavpur-II Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3467/JMD | 29/08/2025 |  | MASSK ENGINEERING WORKS | 10.94 | 0 | 0
78 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Tilaboni and adjacent 2 (two) nos. mini piped water supply schemes at Binpur-I Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 3522/JMD | 29/08/2025 |  | N S TRADING | 3.65 | 0 | 0
79 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Kalmapukuria and adjacent 2 (two) nos. mini piped water supply schemes at Nayagram Block under Jhargram Mechanical Division, P.H.E. Dte. in the district of Jhargram. | Driller-In-Charge | Junior Engineer | 3464/JMD | 29/08/2025 |  | A.S. ENTERPRISE | 3.64 | 0 | 0
80 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of pumping machineries (Automatic Operation) including all allied electro-mechanical components at Tube Well no. I of Antapati mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 6095/JMD | 12/08/2024 |  | MENAKA ENTERPRISE | 3.54 | 0 | 100
81 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply delivery of Direct on line (DOL) starters for Salpatra & other piped water supply schemes of Jhargram district under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | 63/W/MMSD(D) | 30/04/2025 |  | ABHIJIT BASU | 0.93 | 0 | 0
82 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Replacement of existing damaged voltage stabilizer with departmentally supplied 10 KVA oil cooled single phase voltage stabilizer and supply of different type electrical equipments including wiring system for Sankhara pry. School stand alone mini water supply scheme of Binpur -I block and Chatra stand alone mini water supply scheme in Garmeta-II block under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | 107/W/AE/JMD | 30/04/2025 |  | SHOVAN KUMAR DAS | 0.49 | 0 | 100
83 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Operation and guarding of Pumping Machineries (Automatic Operation) including all allied electro-mechanical components at Balarampur mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 5732/JMD | 07/08/2024 |  | INDRANI ENTERPRISE | 3.54 | 0 | 50
84 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity pump motor set & washing development of tubewell with other allied works at Khasjungle & its adjacent mini piped water supply scheme of Nayagram block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 237/W/MMSD(D) | 28/08/2025 |  | SHIBA DURGA ENTERPRISE | 0.84 | 0 | 0
85 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, delivery & installation of Submersible pumping machinery and other Electro Mechanical accessories at replacement T/W no-2 of Hatipata mini piped water supply scheme of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | 7/W/MMSD(D) | 10/01/2025 |  | JOYGURU ENTERPRISE | 0.97 | 0 | 0
86 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Modification of existing disinfection arrangement by supplying & fitting fixing of loft tank , necessary pipe fitting etc. at Armah & adjacent three nos. w/s schemes in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | Junior Engineer | 19/W/AE/JMD | 29/01/2025 |  | SUBHRA ENTERPRISE | 0.99 | 0 | 100
87 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Withdrawing the existing submersible pumping machinery and washing development with other allied works at Tilaboni and adjacent two (2) water supply schemes in Binpur-I Block of Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M) | 161/W/AE/JMD | 25/06/2025 |  | MONORANJAN DEY | 0.92 | 0 | 60
88 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, Delivery and Installation of Automatic plunger type chlorinator having flow rate of 0-100 LPH and maximum pressure of 10 kgf/cm2 coupled with 0.5 hp single phase motor at Ruknimara mini water supply scheme of Nayagram block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 107/W/MMSD(D) | 16/05/2025 |  | SOUMEN ELECTRIC | 0.81 | 0 | 100
89 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Withdrawing the existing submersible pump motor set for washing development & subsequently yield testing and lowering the pump-motor sets at Posro mini piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | 178,/W/AE/JMD | 01/10/2024 |  | CHAKRABORTY MINING & ENGINEERING | 0.26 | 0 | 100
90 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply & delivery of standby pumping machineries at tube well no. 1 of Barajharia and adjacent water supply schemes of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 102/W/MMSD(D) | 16/05/2025 |  | GOENKA ENTERPRISE | 0.8 | 0 | 0
91 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Dismantling the existing damaged voltage stabilizer & installation of departmentally supplied Single phase 10 KVA oil cooled type voltage stabilizer with other allied works at Dehoganj mini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | 216/W/MMSD(D) | 06/08/2025 |  | SHOVAN KUMAR DAS | 0.3 | 0 | 0
92 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, Delivery and Installation of Automatic plunger type chlorinator having flow rate of 0-100 LPH and maximum pressure of 10 kgf/cm2 coupled with 0.5 hp three phase motor at Nota piped water supply scheme of Gopiballavpur-II block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 244/W/MMSD(D) | 08/09/2025 |  | B. P. TRADING CORPORATION | 0.81 | 0 | 0
93 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Surging of existing Tubewells and other allied electromechanical works at Gokurbar mini in Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 69./W/MMSD(D) | 04/03/2024 |  | M/S SIMARR | 0.66 | 0 | 0
94 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Continuation work order for Operation and guarding of pumping Machinery (Automatic Operation) including all allied electro-mechanical components at Kashafulia mini piped water supply scheme under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | 2622./JMD | 28/08/2023 |  | DEBJYOTI BASU | 1.42 | 0 | 100
95 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Supply, Delivery and Installation of Automatic plunger type chlorinator having flow rate of 0-100 LPH and maximum pressure of 10 kgf/cm2 coupled with 0.5 hp single phase motor at Barajharia ICDS water supply scheme of Nayagram block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 168/W/MMSD(D) | 30/06/2025 |  | MAHALAKSHMI ENTERPRISE | 0.81 | 0 | 0
96 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Repairing & rejuvenation of electro-mechanical accessories for Sundraguri mini piped W/S scheme at Binpur-I block under Jhargram Mechanical Division, PHE. Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer | 1100/JMD | 26/05/2025 |  | S.S. GHORAI | 3.52 | 0 | 100
97 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity pump motor set with other allied works at Bhalaidiha mini piped water supply scheme of Binpur-II block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 691/W/MMSD(D) | 10/12/2024 |  | DEBJYOTI BASU | 0.18 | 0 | 0
98 | JHARGRAM | Jhargram Division | Retrofitting(PHASE-II) to accommodate FHTC under JJM in 45 Nos. Mini (part) ( Telidanga, Dakaisole, Amlagora, Natundihi, Bhelaidiha, Hatipada, Tapsia, Chandabila) PWSS at different left out vulnerable drought affected areas in different Blocks in Jhargram | SM/17950 | Augmentation | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity pump motor set with other allied works at Amlagura & adjacent W/S scheme of Binpur-II block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | 266/W/MMSD(D) | 14/10/2025 |  | YUVAN CONSTRUCTION | 0.99 | 0 | 0
Total | [12 empty] | 398.5 | 20.26 | 5.09