## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Nadia Arsenic Division-II. |  |  | 4895/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 14.26 | 0
2 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Barasat Division. |  |  | 4896/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 245.1 | 2.78 | 0
3 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply & delivery of ISI marked 10 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] | Assistant Engineer |  | 4844/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 196 | 0 | 0
4 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Bamunara piped W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | 1242/DWSD | 18/08/2022 |  | AHS R INFRA PRIVATE LIMITED | 14.76 | 13.36 | 0
5 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply & delivery of ISI marked 12 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] |  |  | 4845/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 1.27 | 0
6 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and allied works construction 400 M3 OHR with 20 mtr staging height including soil investigation and construction of pump house (5.40 m X 3.60 m) with sanitary and water supply arrangement and construction of pump house (3.60X3.00 m) with FHTC for Bamunara piped water Supply scheme under DWSD ,PHE Dte (NS) |  |  | 1438/DWSD | 13/10/2022 |  | HANNAN BUILDERS PVT. LTD. | 658.55 | 455.75 | 100
7 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm | Assistant Engineer |  | 5673/RS | 01/11/2022 |  | JINDAL SAW LIMITED. | 0 | 10.99 | 0
8 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 13.79 | 0 | 100
9 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5672/RS | 01/11/2022 |  | TATA METALIKS LTD | 19.67 | 7.53 | 100
10 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Bistupur ,Bamunara piped W/s Scheme under DWSD, PHE Dte |  |  | 526/DWSD | 29/03/2023 |  | Measure Land | 8.11 | 7.62 | 0
11 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Supply & Installation of Submersible Pumping Machinery, Voltages Stabilizer , Chlorination system and internal House wiring for Tube well for Tube well no:- 1 & 2 at Bamunara water supply scheme under CMD PHE Dte, Dist: Paschim Bardhaman. | Driller In-Charge | Junior Engineer | 1656/CMD | 06/04/2023 |  | D.K. ELECTRIC | 22.77 | 22.04 | 100
12 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Repairing and Overhauling of Voltage Stabilizer at Bamunara P/H No.-2 , Jatgaria, P/H No.-01, Kanksa Zone-II/D, P/H No.-1, under Kanksa Block, Paschim Bardhaman, under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | 1267/AE-II/AMD | 09/07/2025 |  | SINHA ELECTRICALS | 0.84 | 0 | 100
13 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery under unmanned operation at Bamunara water supply scheme T.W. No-1, Block: Kanksa ,Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 2163/AMD | 15/12/2023 |  | PESTCO INDIA | 3.21 | 0 | 100
14 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery under unmanned operation at Bamunara water supply scheme T.W. No-2, Block: Kanksa ,Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 2165/AMD | 15/12/2023 |  | PESTCO INDIA | 3.21 | 0 | 100
15 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Continuation order for Operation and Guarding arrangement of Pumping Machinery under unmanned operation at Bamunara water supply scheme T.W. No-2, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 2025/AMD | 04/12/2024 |  | PESTCO INDIA | 0.62 | 0 | 100
16 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water Supply Scheme P.H No-01, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3 | 427/AMD | 20/02/2025 |  | PESTCO INDIA | 3.53 | 0 | 100
17 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Continuation order for Operation and Guarding arrangement of Pumping Machinery under unmanned operation at Bamunara water supply scheme T.W. No-1, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 2045/AMD | 04/12/2024 |  | PESTCO INDIA | 0.62 | 0 | 100
18 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water Supply Scheme P.H No-02, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3 | 428/AMD | 20/02/2025 |  | PESTCO INDIA | 3.53 | 0 | 100
19 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Repairing and Overhauling of Voltage Stabilizer at Kanksa Zone-II/C, TW No.-03, Bamunara, TW No.-02 under Kanksa Block, Paschim Bardhaman, under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3 | 1365/AE-II/AMD | 24/07/2025 |  | SINHA ELECTRICALS | 0.88 | 0 | 100
20 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Repairing and Overhauling of Voltage Stabilizer at Basudha, TW No.-01 & 02, Bamunara, TW No.-01, under Kanksa Block, Paschim Bardhaman, under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3 | 1952/AE-II/AMD | 09/12/2025 |  | SINHA ELECTRICALS | 0.83 | 0 | 100
21 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water supply scheme P.H No-02, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1 | 305/AMD | 19/02/2026 |  | PESTCO INDIA | 3.64 | 0 | 0
22 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water supply scheme P.H No-04, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1 | 344/AMD | 20/02/2026 |  | M/S SAJAHAN CHOWDHURY | 3.62 | 0 | 0
23 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water supply scheme P.H No-03, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1 | 343/AMD | 20/02/2026 |  | M/S SAJAHAN CHOWDHURY | 3.62 | 0 | 0
24 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water supply scheme P.H No-05, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1 | 345/AMD | 20/02/2026 |  | M/S SAJAHAN CHOWDHURY | 3.62 | 0 | 0
25 | PASCHIM BARDHAMAN | RCFA Division I | BAMUNARA PIPED WATER SUPPLY SCHEME. | SM/11227 | New | Operation and Guarding arrangement of Pumping Machinery at Bamunara water supply scheme P.H No-01, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-1 | 304/AMD | 19/02/2026 |  | PESTCO INDIA | 3.64 | 0 | 0
Total | [12 empty] | 1214.16 | 535.6 | 44.11