## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Physical Progress %
1 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & delivery of ISI marked 10 mm dia Nominal size with Leaded tin Bronze Ferrule conforming to IS: 2692:1989 consisting component of Body, Plug, Cap, Water Plate & Nut, Resilient Washer and Copper Washer for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply within West Bengal and delivery will be made in Rajarhat/Kalyani stores under Resources Division for different Water supply Scheme situated under Barasat Division. |  |  | 4896/RS | 31/08/2022 |  | PUNAM KUMAR GUPTA | 0 | 0 | 0
2 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & delivery of ISI marked 10 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] | Assistant Engineer |  | 4844/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 0 | 0
3 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Shyambazar piped W/s Scheme under DWSD ,PHE Dte (SL-01) |  |  | 1233/DWSD | 17/08/2022 |  | M/S. D. Palit & Co. | 14.76 | 0 | 0
4 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & delivery of ISI marked 12 mm dia High strength deformed steel bar(TMT) conformin to IS:1786:2008 Latest of Fe 500D (Killed steel) at Rajarhat Store under Resources Division PHE Dte.[Type of steel: Killled, Producer Type: Primary Producer, Type of Raw Material: virgin] |  |  | 4845/RS | 29/08/2022 |  | SHAKAMBHARI ISPAT & POWER LTD | 0 | 0 | 0
5 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm | Assistant Engineer |  | 5673/RS | 01/11/2022 |  | JINDAL SAW LIMITED. | 0 | 0 | 0
6 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5671/RS | 01/11/2022 |  | ELECTROSTEEL CASTINGS LIMITED | 7.71 | 0 | 100
7 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Shyambazar ,Telipara piped W/s Scheme under DWSD, PHE Dte |  |  | 527/DWSD | 29/03/2023 |  | Measure Land | 5 | 0 | 0
8 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply and delivery of ISI Marked Centrifugally Cast (Spun) Ductile iron Pressure Pipes for Water with Socket & Spigot ends conforming to IS:8329/2000(latest amendment) in standard length of 5.5 M/6.00M suitable for push on joint (rubber gasket jointing) with Cement Mortar Lining inside the pipes and outside zinc coating with finished layer of Bituminous coating/ Synthetic resin (Blue/Red Epoxy) compatible with zinc coating (Class K-9 & Class K-7) along with supply of EPDM Quality of Rubber Gasket as per IS:5382/1985, for each of the joints adm |  |  | 5672/RS | 01/11/2022 |  | TATA METALIKS LTD | 0 | 0 | 100
9 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Formal order for the work of laying distribution system ,rising main construction of 150 M3 with 20 mtr staging height including soil investigation construction of Pump house (5.4X3.6 m) with sanitary and Water supply arrangement and construction of pump house (3.6X3.00 mtr) for Shyambazar W/s Scheme under DWSD ,PHE Dte (New Scheme) |  |  | 1648/DWSD | 02/12/2022 |  | DUTTA ENTERPRISE | 213.72 | 0 | 100
10 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | 1580/CMD | 04/04/2023 |  | A.S. ENTERPRISE | 9.3 | 0 | 100
11 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. |  |  | 1579/CMD | 04/04/2023 |  | MS DAS ELECTRIC CO | 9.3 | 0 | 100
12 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply and delivery of Standby Column Pipe at various Piped Water Supply Scheme, under Kanksa Block, Dist - Paschim Bardhaman under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | 1263/AE-II/AMD | 09/07/2025 |  | ANANYA CONSTRUCTION | 0.98 | 0 | 0
13 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Operation and Guarding arrangement of Pumping Machinery under unmanned operation at Shambazar water supply scheme T.W. No-2, Block: Kanksa ,Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 2166/AMD | 15/12/2023 |  | HINDUSTHAN CONSULTANT FIRM | 3.21 | 0 | 100
14 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Operation & Guarding arrangement of Pumping Machinery Under un-manned operation at Shyambazar Water supply scheme, T.W. No.-1, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E.Dte. | Assistant Engineer-II | Junior Engineer-3 | 444/AMD | 29/02/2024 |  | MITRA ENTERPRISE | 2.92 | 0 | 100
15 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Continuation order for Operation & Guarding arrangement of Pumping Machinery Under un-manned operation at Shyambazar Water supply scheme, T.W. No.-1, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E.Dte. | Assistant Engineer-II | Junior Engineer-3 | 90/AMD | 27/01/2025 |  | MITRA ENTERPRISE | 0.25 | 0 | 100
16 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Continuation order for Operation and Guarding arrangement of Pumping Machinery under unmanned operation at Shambazar water supply scheme T.W. No-2, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 1895/AMD | 13/11/2024 |  | HINDUSTHAN CONSULTANT FIRM | 0.62 | 0 | 100
17 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Operation & Guarding arrangement of Pumping Machinery at Shyambazar Water Supply Scheme, P.H No.-2, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | 434/AMD | 20/02/2025 |  | HINDUSTHAN CONSULTANT FIRM | 3.53 | 0 | 16
18 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Operation & Guarding arrangement of Pumping Machinery at Shyambazar Water Supply Scheme, P.H No.-01, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | 423/AMD | 20/02/2025 |  | MITRA ENTERPRISE | 3.51 | 0 | 16
19 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Erection work and painting of existing pole including allied work of Shyambazar, TW No.-01,under Block-Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | 1369/AE-II/AMD | 24/07/2025 |  | M/S JIT ENTERPRISE | 0.61 | 0 | 100
20 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Supply Delivery and Installation of electrical componants at starter panel and other allied works at Shyambazar Piped Water Supply Scheme, TW No.-02, Block- Kanksa, Dist- Paschim Bardhaman, Under AMD P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | 645/AE-II/AMD | 21/03/2025 |  | HINDUSTHAN CONSULTANT FIRM | 0.3 | 0 | 100
21 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Lowering of column pipe including withdrawing, lowring and other allied works at Shyambazar, TW No.-02, under Block - Kanksa, Dist - Paschim Bardhaman under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | 1951/AE-II/AMD | 09/12/2025 |  | HINDUSTHAN CONSULTANT FIRM | 0.3 | 0 | 100
22 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Lowering of column pipe including withdrawing, lowring and other allied works at Shyambazar, TW No.-01, under Block - Kanksa, Dist - Paschim Bardhaman under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-3 | 1959/AE-II/AMD | 10/12/2025 |  | MITRA ENTERPRISE | 0.34 | 0 | 100
23 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Operation & Guarding arrangement of Pumping Machinery at Shyambazar Water Supply Scheme, P.H No.-2, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E.Dte. | Assistant Engineer-II | Junior Engineer-2 | 358/AMD | 20/02/2026 |  | HINDUSTHAN CONSULTANT FIRM | 3.64 | 0 | 0
24 | PASCHIM BARDHAMAN | RCFA Division I | Shyambazar Piped water Supply Scheme | SM/11228 | New | Operation & Guarding arrangement of Pumping Machinery at Shyambazar Water supply scheme, P.H No.-01, Block: Kanksa, Dist: Paschim Bardhaman under Asansol Mechanical Division, P.H.E.Dte. | Assistant Engineer-II | Junior Engineer-2 | 357/AMD | 20/02/2026 |  | MITRA ENTERPRISE | 3.6 | 0 | 0
Total | [12 empty] | 283.59 | 0 | 0