## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | TSM/009821 | SM/10209 | Augmentation | 16/12/2021 | 2450 | 489.84 | Yes | 489.84 | 06/03/2025 | 11/09/2024 | 27 | 611.21 | MVS
2 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008332 | SM/09699 | Augmentation | 19/08/2021 | 1185 | 323.86 | Yes | 323.86 | 23/08/2023 | 17/03/2025 | 21 | 335.38 | MVS
3 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to Angadnwadi centre (189 nos),Health Care Faciliteis & other s Public Institution under Durgapur W/s Division, PHE Dte flor Kanksa & Durgapur-Faridpur block of Paschim Bardhaman | TSM/009648 | SM/10372 | Anganwadi | 27/01/2022 | 0 | 835.05 | Yes | 835.05 |  | 11/05/2021 | 41 | 941.32 | MVS
4 | PASCHIM BARDHAMAN | Durgapur W/S Division | KOTALPUKUR PIPED WATER SUPPLY SCHEME | TSM/009500 | SM/10996 | New | 17/02/2022 | 173 | 54.17 | Yes | 54.17 | 22/06/2022 | 17/05/2022 | 2 | 53.22 | MVS
5 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme | TSM/006587 | SM/07547 | Retrofitting | 04/12/2020 | 880 | 41.6 | Yes | 41.6 | 13/04/2023 | 27/06/2022 | 2 | 7.95 | MVS
6 | PASCHIM BARDHAMAN | Durgapur W/S Division | GARADAHA PIPED WATER SUPPLY SCHEME. | TSM/009280 | SM/11934 | New | 17/02/2022 | 171 | 51.33 | Yes | 51.33 | 04/01/2023 | 15/03/2023 | 2 | 44.26 | MVS
7 | PURBA BARDHAMAN | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME | TSM/015705 | SM/13494 | New | 09/09/2022 | 1630 | 642.77 | Yes | 642.77 | 01/03/2024 | 26/11/2024 | 11 | 556.8 | MVS
8 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | TSM/015271 | SM/13328 | New | 09/09/2022 | 3034 | 995.39 | Yes | 995.39 | 01/03/2024 | 30/08/2024 | 15 | 2256.46 | MVS
9 | PURBA BARDHAMAN | Durgapur W/S Division | PICHKURI PIPED WATER SUPPLY SCHEME | TSM/015273 | SM/13330 | New | 09/09/2022 | 1793 | 703.65 | Yes | 703.65 | 16/01/2025 | 17/03/2025 | 9 | 528.82 | MVS
10 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | TSM/007685 | SM/08710 | Retrofitting | 19/02/2021 | 4223 | 268.29 | Yes | 268.29 | 16/02/2024 | 29/08/2024 | 21 | 234.04 | MVS
11 | PURBA BARDHAMAN | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | TSM/017813 | SM/18313 | New | 28/12/2022 | 4076 | 2374.1 | Yes | 2374.1 | 03/12/2024 | 17/04/2025 | 21 | 3829.71 | MVS
12 | PURBA BARDHAMAN | Durgapur W/S Division | MOHANPUR PIPED WATER SUPPLY SCHEME | TSM/016268 | SM/18242 | New | 26/09/2022 | 2788 | 1333.72 | Yes | 1333.72 | 02/12/2024 | 08/01/2025 | 13 | 1498.05 | MVS
13 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME | TSM/017787 | SM/18478 | New | 16/11/2022 | 9074 | 4015.02 | Yes | 4015.02 | 03/12/2024 | 27/03/2025 | 12 | 2800.75 | MVS
14 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | TSM/006680 | SM/07829 | Retrofitting | 04/12/2020 | 4100 | 239.55 | Yes | 239.55 | 16/02/2024 | 17/03/2025 | 21 | 133.78 | MVS
15 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008335 | SM/09714 | Augmentation | 19/08/2021 | 2485 | 754.02 | Yes | 754.02 | 27/12/2023 | 28/04/2025 | 15 | 709.09 | MVS
16 | PASCHIM BARDHAMAN | Durgapur W/S Division | Providing running water supply to schools(121 nos) under Durgapur W/S Division,Kanksa amd Durgapur-Faridpur block,Dist-Paschim Bardhaman | TSM/009643 | SM/10373 | School | 27/01/2022 | 0 | 391.11 | Yes | 391.11 |  | 21/04/2022 | 32 | 388.67 | MVS
17 | PASCHIM BARDHAMAN | Durgapur W/S Division | BANAGRAM PIPED WATER SUPPLY SCHEME | TSM/009278 | SM/11223 | New | 17/02/2022 | 112 | 34.78 | Yes | 34.78 | 04/01/2023 | 18/05/2022 | 1 | 22.78 | MVS
18 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) | TSM/009488 | SM/11454 | Augmentation | 17/02/2022 | 12405 | 2799.63 | Yes | 2799.63 | 17/03/2025 | 14/06/2024 | 47 | 2697.35 | MVS
19 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC under Durgapur W/s Division, PHE Dte. | TSM/006401 | SM/07519 | Retrofitting | 04/12/2020 | 1880 | 97.53 | Yes | 97.53 | 04/01/2023 | 14/11/2024 | 20 | 148.02 | MVS
20 | PURBA BARDHAMAN | Durgapur W/S Division | Karatia Piped Water Supply Scheme | TSM/015260 | SM/13397 | New | 09/09/2022 | 2002 | 839.41 | Yes | 839.41 | 16/01/2025 | 17/03/2025 | 9 | 658.35 | MVS
21 | PURBA BARDHAMAN | Durgapur W/S Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | TSM/015699 | SM/13466 | New | 09/09/2022 | 503 | 313.2 | Yes | 313.2 | 31/07/2024 | 26/09/2024 | 10 | 233.01 | MVS
22 | PURBA BARDHAMAN | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME | TSM/016604 | SM/14974 | New | 26/09/2022 | 2132 | 981.92 | Yes | 981.92 | 21/06/2024 | 06/06/2024 | 13 | 956.05 | MVS
23 | PURBA BARDHAMAN | Durgapur W/S Division | LOAPUR PIPED WATER SUPPLY SCHEME | TSM/016509 | SM/18323 | New | 26/09/2022 | 3508 | 1466.39 | Yes | 1466.39 | 03/10/2024 | 25/11/2024 | 9 | 1238.8 | MVS
24 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TILAKCHANDRAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020579 | SM/18886 | Augmentation | 10/03/2023 | 1888 | 350.95 | Yes | 350.95 | 06/03/2025 | 29/02/2024 | 6 | 291.89 | MVS
25 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BIRUDIHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017278 | SM/18824 | Augmentation | 28/12/2022 | 1916 | 860 | Yes | 860 | 17/01/2025 | 16/03/2024 | 8 | 606.86 | MVS
26 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme | TSM/006204 | SM/06964 | Retrofitting | 25/09/2020 | 1798 | 99.26 | Yes | 99.26 | 07/11/2023 | 24/08/2023 | 9 | 175.73 | MVS
27 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme | TSM/006589 | SM/07548 | Retrofitting | 04/12/2020 | 1903 | 89.96 | Yes | 89.96 | 16/03/2023 | 18/04/2023 | 7 | 105.77 | MVS
28 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | TSM/009032 | SM/10203 | Augmentation | 16/12/2021 | 0 | 943.11 | Yes | 943.11 | 17/01/2025 | 20/05/2024 | 42 | 884.39 | MVS
29 | PURBA BARDHAMAN | Durgapur W/S Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | TSM/009277 | SM/10055 | Retrofitting | 16/12/2021 | 1771 | 114.87 | Yes | 114.87 | 16/02/2024 | 06/06/2024 | 2 | 64.84 | MVS
30 | PASCHIM BARDHAMAN | Durgapur W/S Division | Telipara Piped Water Supply Scheme. | TSM/004035 | SM/10311 | New | 16/12/2021 | 870 | 389.8 | Yes | 389.8 | 17/03/2025 | 17/03/2023 | 15 | 445.62 | MVS
31 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | TSM/009659 | SM/10211 | Augmentation | 16/12/2021 | 3815 | 811.61 | Yes | 811.61 | 06/03/2025 | 24/07/2024 | 30 | 927.19 | MVS
32 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF RCFA (PART III) ZONE II PIPED WATER SUPPLY SCHEME (Complying JJM) . | TSM/009489 | SM/12726 | Augmentation | 17/02/2022 | 13807 | 2832.34 | Yes | 2832.34 | 17/03/2025 | 06/09/2024 | 70 | 2737.45 | MVS
33 | PASCHIM BARDHAMAN | Durgapur W/S Division | JATGARIA PIPED WATER SUPPLY SCHEME. | TSM/009285 | SM/11933 | New | 17/02/2022 | 762 | 275.4 | Yes | 275.4 | 29/07/2024 | 08/06/2023 | 7 | 240.33 | MVS
34 | PURBA BARDHAMAN | Durgapur W/S Division | JALKANDAR PIPED WATER SUPPLY SCHEME | TSM/016585 | SM/14953 | New | 26/09/2022 | 2122 | 969.12 | Yes | 969.12 | 16/01/2025 | 26/11/2024 | 13 | 291.01 | MVS
35 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Maheshpur,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-A) | TSM/011035 | SM/13879 | New | 26/09/2022 | 68 | 42.44 | Yes | 42.44 | 07/09/2022 |  | 0 | 0 | MVS
36 | PURBA BARDHAMAN | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME | TSM/016522 | SM/14929 | New | 26/09/2022 | 1131 | 395.09 | Yes | 395.09 | 31/07/2024 | 26/09/2024 | 11 | 302.25 | MVS
37 | PURBA BARDHAMAN | Durgapur W/S Division | BHEDIA PIPED WATER SUPPLY SCHEME | TSM/017145 | SM/14748 | New | 30/09/2022 | 1543 | 699.32 | Yes | 699.32 | 01/03/2024 | 26/11/2024 | 8 | 572.95 | MVS
38 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KOTALPUKUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017286 | SM/15663 | Augmentation | 16/11/2022 | 574 | 227.43 | Yes | 227.43 | 28/11/2024 | 17/03/2023 | 6 | 180.57 | MVS
39 | PURBA BARDHAMAN | Durgapur W/S Division | PANDUK PIPED WATER SUPPLY SCHEME | TSM/016569 | SM/18445 | New | 26/09/2022 | 3269 | 1188.77 | Yes | 1188.77 | 01/03/2024 | 11/02/2025 | 10 | 1036.96 | MVS
40 | PASCHIM BARDHAMAN | Durgapur W/S Division | DANDESHWAR PIPED WATER SUPPLY SCHEME. | TSM/009556 | SM/11282 | New | 16/03/2022 | 703 | 254.22 | Yes | 254.22 | 24/11/2022 | 01/06/2023 | 8 | 212.1 | MVS
41 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block | TSM/006679 | SM/07807 | Retrofitting | 04/12/2020 | 1017 | 62.17 | Yes | 62.17 | 16/03/2023 | 30/06/2022 | 7 | 86.66 | MVS
42 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | TSM/007675 | SM/08705 | Retrofitting | 19/02/2021 | 2137 | 119.29 | Yes | 119.29 | 16/02/2024 | 27/11/2024 | 4 | 99.3 | MVS
43 | PURBA BARDHAMAN | Durgapur W/S Division | BHUYERA PIPED WATER SUPPLY SCHEME | TSM/016618 | SM/13948 | New | 26/09/2022 | 1330 | 678.07 | Yes | 678.07 | 01/03/2024 | 10/08/2023 | 7 | 1037.08 | MVS
44 | PURBA BARDHAMAN | Durgapur W/S Division | BHOTA PIPED WATER SUPPLY SCHEME | TSM/015701 | SM/13293 | New | 09/09/2022 | 799 | 378.17 | Yes | 378.17 | 01/03/2024 | 26/11/2024 | 12 | 958.33 | MVS
45 | PURBA BARDHAMAN | Durgapur W/S Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME | TSM/016502 | SM/14954 | New | 26/09/2022 | 491 | 294.41 | Yes | 294.41 | 01/03/2024 | 26/11/2024 | 8 | 198.75 | MVS
46 | PURBA BARDHAMAN | Durgapur W/S Division | KHANDARI PIPED WATER SUPPLY SCHEME | TSM/015263 | SM/13396 | New | 09/09/2022 | 2173 | 977.81 | Yes | 977.81 | 01/10/2024 | 10/12/2024 | 9 | 162.02 | MVS
47 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground water based mini piped W/s Scheme (Max 100 House Hold)for Gourangapur Village,Panchayet-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD,PHE Dte (Part-D) | TSM/014846 | SM/13863 | New | 26/09/2022 | 25 | 34.64 | Yes | 34.64 | 07/09/2022 |  | 0 | 0 | MVS
48 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground Water based Mini piped W/S Scheme (Maximum 100 House hold)for Banagram Village,GP-Bankati,Block-Kanksa,Dist-Paschim Bardhaman under DWSD ,PHE Dte (Part-E) | TSM/014844 | SM/13866 | New | 26/09/2022 | 99 | 47.8 | Yes | 47.8 | 07/09/2022 |  | 0 | 0 | MVS
49 | PURBA BARDHAMAN | Durgapur W/S Division | MARO PIPED WATER SUPPLY SCHEME | TSM/017784 | SM/15579 | New | 28/12/2022 | 238 | 237.76 | Yes | 237.76 | 06/03/2024 | 01/06/2023 | 7 | 211.27 | MVS
50 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | TSM/016564 | SM/14927 | New | 26/09/2022 | 1088 | 503.42 | Yes | 503.42 | 01/03/2024 | 30/07/2024 | 14 | 101.08 | MVS
51 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR TELIPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017281 | SM/16250 | Augmentation | 28/12/2022 | 1006 | 638.71 | Yes | 638.71 | 01/02/2024 | 11/05/2023 | 12 | 547.83 | MVS
52 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017220 | SM/15639 | Augmentation | 16/11/2022 | 1738 | 989.75 | Yes | 989.75 | 17/03/2025 | 24/07/2024 | 11 | 843.28 | MVS
53 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BANAGRAM PART, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017275 | SM/16903 | Augmentation | 28/12/2022 | 171 | 64.9 | Yes | 64.9 | 01/02/2024 | 18/05/2023 | 4 | 60.39 | MVS
54 | PURBA BARDHAMAN | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME | TSM/017795 | SM/18446 | New | 28/12/2022 | 5643 | 2589.76 | Yes | 2589.76 | 03/12/2024 | 09/01/2025 | 15 | 3136.32 | MVS
55 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BAMUNARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017310 | SM/18467 | Augmentation | 16/11/2022 | 2662 | 1401.03 | Yes | 1401.03 | 30/08/2024 | 02/09/2024 | 20 | 1365.36 | MVS
56 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BISTUPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/018199 | SM/18469 | Augmentation | 16/11/2022 | 3740 | 2403.3 | Yes | 2403.3 | 17/03/2025 | 19/06/2024 | 38 | 1683.37 | MVS
57 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | TSM/006413 | SM/07518 | Retrofitting | 04/12/2020 | 0 | 96.32 | Yes | 96.32 | 22/06/2022 | 24/05/2021 | 15 | 114.54 | MVS
58 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | TSM/006683 | SM/07869 | Retrofitting | 04/12/2020 | 1976 | 109.48 | Yes | 109.48 | 23/10/2024 | 06/06/2024 | 7 | 156.81 | MVS
59 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | TSM/006672 | SM/07824 | Retrofitting | 04/12/2020 | 1830 | 117.09 | Yes | 117.09 |  | 23/08/2024 | 8 | 120.47 | MVS
60 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-D) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | TSM/009822 | SM/10210 | Augmentation | 16/12/2021 | 3113 | 780.77 | Yes | 780.77 | 25/06/2024 | 18/05/2022 | 32 | 871.79 | MVS
61 | PASCHIM BARDHAMAN | Durgapur W/S Division | Shyambazar Piped water Supply Scheme | TSM/010261 | SM/11228 | New | 16/03/2022 | 882 | 309.98 | Yes | 309.98 | 25/06/2024 | 15/03/2023 | 9 | 282.35 | MVS
62 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | TSM/005580 | SM/07391 | Retrofitting | 28/08/2020 | 36446 | 1841 | Yes | 1841 |  | 29/04/2021 | 150 | 1988.62 | MVS
63 | PURBA BARDHAMAN | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME | TSM/016543 | SM/13966 | New | 26/09/2022 | 1821 | 849.7 | Yes | 849.7 | 06/12/2024 | 02/08/2024 | 12 | 339.82 | MVS
64 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jemua piped W/S scheme for providing FHTC under Durgapur W/s Division, PHE Dte (Mouza-Jemua(JL-80,Paranganj(JL_79) of Jemua Gram Panchayat,Block-Durgapur-Faridpur,Dist-Paschmi Bardhaman. | TSM/011036 | SM/13685 | Retrofitting | 09/09/2022 | 1404 | 137.13 | Yes | 137.13 | 01/05/2023 | 03/05/2023 | 12 | 150.38 | MVS
65 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground water based mini piped water supply scheme (Max 100 House Hold) for Kotalpukur ,G.P-Bankati,Block-Kanksa ,Dist-Paschim Bardhaman under Durgapur W/S Division,PHE Dte (Part-F) | TSM/014871 | SM/13861 | New | 26/09/2022 | 60 | 41.75 | Yes | 41.75 | 07/09/2022 | 01/08/2022 | 1 | 275.32 | MVS
66 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Kendula ,G.P-Pratabpur,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-C) | TSM/014848 | SM/13864 | New | 26/09/2022 | 53 | 40.28 | Yes | 40.28 | 07/09/2022 |  | 0 | 0 | MVS
67 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | TSM/016537 | SM/14926 | New | 26/09/2022 | 546 | 315.46 | Yes | 315.46 | 01/03/2024 | 26/11/2024 | 10 | 293.33 | MVS
68 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017279 | SM/16901 | Augmentation | 28/12/2022 | 769 | 340.79 | Yes | 340.79 | 17/03/2025 | 24/05/2023 | 4 | 297.89 | MVS
69 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARKILLA KHEROBARI, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017285 | SM/15659 | Augmentation | 16/11/2022 | 350 | 157.71 | Yes | 157.71 | 01/02/2024 | 15/05/2023 | 3 | 114.87 | MVS
70 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JEMUA, UNDER DURGAPUR W/S DIVISION , BLOCK : DURGAPUR FARIDPUR, DISTRICT : PASCHIM BARDDHAMAN | TSM/020574 | SM/18890 | Augmentation | 10/03/2023 | 1657 | 219.38 | Yes | 219.38 | 12/03/2024 | 11/04/2023 | 3 | 124.41 | MVS
71 | PURBA BARDHAMAN | Durgapur W/S Division | BARADOBA PIPED WATER SUPPLY SCHEME | TSM/017790 | SM/18230 | New | 28/12/2022 | 216 | 215.86 | Yes | 215.86 | 01/03/2024 | 26/11/2024 | 10 | 185.76 | MVS
72 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-I) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman(WB) | TSM/009656 | SM/10208 | Augmentation | 16/12/2021 | 2538 | 700.46 | Yes | 700.46 | 17/03/2025 | 15/03/2023 | 48 | 810.85 | MVS
73 | PASCHIM BARDHAMAN | Durgapur W/S Division | GARKILLA KHEROBARI PIPED WATER SUPPLY SCHEME. | TSM/009281 | SM/10998 | New | 17/02/2022 | 126 | 41.17 | Yes | 41.17 | 22/06/2022 | 15/03/2023 | 2 | 31.64 | MVS
74 | PASCHIM BARDHAMAN | Durgapur W/S Division | BAMUNARA PIPED WATER SUPPLY SCHEME. | TSM/009558 | SM/11227 | New | 16/03/2022 | 1540 | 44.3 | Yes | 773.34 | 28/02/2025 | 24/07/2023 | 8 | 772.78 | MVS
75 | PURBA BARDHAMAN | Durgapur W/S Division | KALYANPUR PIPED WATER SUPPLY SCHEME | TSM/016514 | SM/13939 | New | 26/09/2022 | 2206 | 820.46 | Yes | 820.46 | 01/08/2024 | 02/01/2025 | 13 | 1752.73 | MVS
76 | PURBA BARDHAMAN | Durgapur W/S Division | DHARALA PIPED WATER SUPPLY SCHEME | TSM/017149 | SM/14056 | New | 30/09/2022 | 713 | 347.99 | Yes | 347.99 | 01/03/2024 | 26/11/2024 | 11 | 252.48 | MVS
77 | PURBA BARDHAMAN | Durgapur W/S Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | TSM/016584 | SM/14071 | New | 26/09/2022 | 1303 | 667.05 | Yes | 667.05 | 01/03/2024 | 25/11/2024 | 9 | 551.17 | MVS
78 | PURBA BARDHAMAN | Durgapur W/S Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | TSM/016266 | SM/14074 | New | 26/09/2022 | 2233 | 908.14 | Yes | 908.14 | 05/09/2024 | 25/04/2023 | 5 | 108.83 | MVS
79 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | TSM/007678 | SM/08708 | Retrofitting | 19/02/2021 | 1804 | 112.85 | Yes | 112.85 | 26/07/2024 | 02/05/2022 | 6 | 92.54 | MVS
80 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008333 | SM/09712 | Augmentation | 19/08/2021 | 4237 | 732.87 | Yes | 732.87 | 01/08/2024 | 25/03/2025 | 20 | 938.57 | MVS
81 | PASCHIM BARDHAMAN | Durgapur W/S Division | Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman under Durgapur Water Supply Scheme. | TSM/018322 | SM/15666 | New | 16/11/2022 | 2454 | 905.76 | Yes | 905.76 | 04/03/2025 | 15/03/2024 | 18 | 851.64 | MVS
82 | PURBA BARDHAMAN | Durgapur W/S Division | BAHADURPUR PIPED WATER SUPPLY SCHEME | TSM/015696 | SM/13504 | New | 09/09/2022 | 936 | 420.97 | Yes | 420.97 | 01/03/2024 | 02/01/2025 | 9 | 307.07 | MVS
83 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground water based mini piped water supply scheme (Max 100 House Hold) for Pathardiha,GP-Gopalpur,Block -Kanksa,Dist-Paschim Bardhaman under Durgapur W/s Division,PHE Dte (Part-G) | TSM/014872 | SM/18745 | New | 26/09/2022 | 0 | 39.36 | Yes | 39.36 | 07/09/2022 |  | 0 | 0 | MVS
84 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JATGARIA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017244 | SM/18825 | Augmentation | 28/12/2022 | 683 | 306.19 | Yes | 306.19 | 30/08/2024 | 12/11/2024 | 6 | 280.49 | MVS
85 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block | TSM/006685 | SM/07781 | Retrofitting | 04/12/2020 | 1810 | 103.35 | Yes | 103.35 | 22/08/2022 | 01/06/2023 | 8 | 63.72 | MVS
86 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | TSM/008334 | SM/09713 | Augmentation | 19/08/2021 | 2306 | 594.6 | Yes | 594.6 | 16/02/2024 | 06/06/2024 | 13 | 542.51 | MVS
87 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-B) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Bardhaman (WB) | TSM/009820 | SM/10212 | Augmentation | 16/12/2021 | 2984 | 663.97 | Yes | 663.97 | 17/03/2025 | 24/07/2023 | 24 | 691.29 | MVS
88 | PASCHIM BARDHAMAN | Durgapur W/S Division | DHOBARU PIPED WATER SUPPLY SCHEME | TSM/009279 | SM/10999 | New | 17/02/2022 | 197 | 57.63 | Yes | 57.63 | 22/06/2022 | 17/03/2023 | 2 | 49.46 | MVS
89 | PASCHIM BARDHAMAN | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | TSM/008345 | SM/09875 | Augmentation | 19/08/2021 | 0 | 1310.24 | Yes | 1310.24 | 17/03/2025 | 11/04/2023 | 54 | 1360.33 | MVS
90 | PASCHIM BARDHAMAN | Durgapur W/S Division | NAPARA PIPED WATER SUPPLY SCHEME. | TSM/009283 | SM/11932 | New | 17/02/2022 | 2252 | 657.52 | Yes | 657.52 | 17/03/2025 | 29/02/2024 | 9 | 564.04 | MVS
91 | PASCHIM BARDHAMAN | Durgapur W/S Division | AMLAJORA PIPED WATER SUPPLY SCHEME | TSM/009286 | SM/11937 | New | 17/02/2022 | 1738 | 529.96 | Yes | 529.96 | 17/03/2025 | 24/07/2023 | 9 | 510.5 | MVS
92 | PURBA BARDHAMAN | Durgapur W/S Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | TSM/016555 | SM/14073 | New | 26/09/2022 | 2189 | 853.72 | Yes | 853.72 | 01/03/2024 | 10/01/2025 | 7 | 158.26 | MVS
93 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR GARADAHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017283 | SM/16900 | Augmentation | 28/12/2022 | 252 | 98.83 | Yes | 98.83 | 03/10/2024 | 15/05/2023 | 4 | 116.8 | MVS
94 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DHOBARU, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017277 | SM/16902 | Augmentation | 28/12/2022 | 262 | 94.57 | Yes | 94.57 | 01/02/2024 | 31/01/2024 | 4 | 122.06 | MVS
95 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NAPARA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMA | TSM/017221 | SM/15657 | Augmentation | 16/11/2022 | 2092 | 929.97 | Yes | 929.97 | 06/03/2025 | 29/10/2024 | 15 | 901.19 | MVS
96 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR KANCHANPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020575 | SM/18888 | Augmentation | 10/03/2023 | 0 | 175.3 | Yes | 175.3 | 06/03/2025 | 13/12/2024 | 4 | 65.6 | MVS
97 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR SHYAMBAZAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/017280 | SM/18826 | Augmentation | 28/12/2022 | 1034 | 460.11 | Yes | 460.11 | 17/01/2025 | 27/08/2024 | 6 | 355.37 | MVS
98 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR BASUDHA, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020573 | SM/18877 | Augmentation | 10/03/2023 | 1986 | 313.27 | Yes | 313.27 | 17/03/2025 | 30/09/2024 | 6 | 261.17 | MVS
99 | PASCHIM BARDHAMAN | Durgapur W/S Division | RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | TSM/018422 | SM/18417 | New | 28/12/2022 | 2776 | 2340.61 | Yes | 2340.61 | 03/03/2025 | 15/03/2024 | 24 | 2295.76 | MVS
100 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block | TSM/021381 | SM/18679 | New | 10/03/2023 | 7647 | 4311.81 | Yes | 4311.81 | 03/12/2024 | 09/01/2025 | 11 | 3042.83 | MVS
101 | PURBA BARDHAMAN | Durgapur W/S Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME | TSM/015738 | SM/18408 | New | 09/09/2022 | 3278 | 1068.22 | Yes | 1068.22 | 28/11/2024 | 11/02/2025 | 8 | 1030.9 | MVS
102 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | TSM/006698 | SM/08034 | Retrofitting | 04/12/2020 | 8364 | 615.56 | Yes | 1126.08 | 22/07/2024 | 31/12/2024 | 42 | 1021.71 | MVS
103 | PASCHIM BARDHAMAN | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | TSM/006407 | SM/07524 | Retrofitting | 04/12/2020 | 1686 | 86.82 | Yes | 86.82 | 22/06/2022 | 29/04/2021 | 16 | 72.94 | MVS
104 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | TSM/006677 | SM/07808 | Retrofitting | 04/12/2020 | 1383 | 89.76 | Yes | 89.76 | 23/08/2023 | 06/06/2024 | 7 | 97.88 | MVS
105 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | TSM/006675 | SM/07809 | Retrofitting | 04/12/2020 | 1133 | 69.73 | Yes | 69.73 | 20/07/2023 | 18/04/2023 | 7 | 72.17 | MVS
106 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | TSM/006674 | SM/07810 | Retrofitting | 04/12/2020 | 1398 | 83.84 | Yes | 83.84 | 22/07/2024 | 03/12/2024 | 4 | 97.94 | MVS
107 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | TSM/006588 | SM/07817 | Retrofitting | 04/12/2020 | 2806 | 132.65 | Yes | 132.65 | 16/02/2024 | 05/06/2024 | 5 | 130.82 | MVS
108 | PASCHIM BARDHAMAN | Durgapur W/S Division | Extension of PWSS to 3 nos. Sourceless Schools located within the command area of the PWS. | TSM/007440 | SM/09242 | School | 19/02/2021 | 0 | 10.72 | Yes | 10.72 |  | 01/02/2022 | 7 | 11.77 | MVS
109 | PASCHIM BARDHAMAN | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | TSM/005153 | SM/08877 | New | 04/12/2020 | 4127 | 23.94 | Yes | 1167.42 | 17/03/2025 | 10/05/2022 | 34 | 1305.92 | MVS
110 | PASCHIM BARDHAMAN | Durgapur W/S Division | BIRUDIHA PIPED WATER SUPPLY SCHEME | TSM/009284 | SM/11224 | New | 17/02/2022 | 1697 | 633.08 | Yes | 633.08 | 01/02/2024 | 01/06/2023 | 6 | 593.53 | MVS
111 | PURBA BARDHAMAN | Durgapur W/S Division | SILUT PIPED WATER SUPPLY SCHEME | TSM/016560 | SM/13903 | New | 26/09/2022 | 2432 | 894.4 | Yes | 894.4 | 01/03/2024 | 17/03/2025 | 8 | 627.31 | MVS
112 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block | TSM/006682 | SM/07870 | Retrofitting | 04/12/2020 | 2688 | 157.93 | Yes | 157.93 | 22/07/2024 | 05/04/2023 | 3 | 121.32 | MVS
113 | PURBA BARDHAMAN | Durgapur W/S Division | SHIBADA PIPED WATER SUPPLY SCHEME | TSM/015707 | SM/13492 | New | 09/09/2022 | 1282 | 617.18 | Yes | 617.18 | 16/01/2025 | 10/12/2024 | 11 | 421.48 | MVS
114 | PURBA BARDHAMAN | Durgapur W/S Division | SONAIAIMA Purba Piped Water Supply Scheme | TSM/015270 | SM/13326 | New | 09/09/2022 | 1416 | 633.06 | Yes | 633.06 | 01/03/2024 | 22/01/2025 | 14 | 667.42 | MVS
115 | PURBA BARDHAMAN | Durgapur W/S Division | DIGHA PIPED WATER SUPPLY SCHEME | TSM/016527 | SM/13938 | New | 26/09/2022 | 1556 | 809.82 | Yes | 809.82 | 01/03/2024 | 21/11/2024 | 11 | 788.79 | MVS
116 | PURBA BARDHAMAN | Durgapur W/S Division | BELGRAM PIPED WATER SUPPLY SCHEME | TSM/016265 | SM/14018 | New | 26/09/2022 | 2093 | 931.79 | Yes | 931.79 | 01/03/2024 | 21/05/2024 | 7 | 1398.93 | MVS
117 | PURBA BARDHAMAN | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | TSM/016545 | SM/14072 | New | 26/09/2022 | 1821 | 962.8 | Yes | 962.8 | 01/03/2024 | 03/10/2024 | 12 | 937.65 | MVS
118 | PURBA BARDHAMAN | Durgapur W/S Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME | TSM/017152 | SM/14060 | New | 30/09/2022 | 1177 | 551.85 | Yes | 551.85 | 01/03/2024 | 17/02/2025 | 8 | 477.93 | MVS
119 | PASCHIM BARDHAMAN | Durgapur W/S Division | Ground water based Mini piped W/s Scheme (Maximum 100 House Holds) for Bhadrapur ,G.P-Loudoha,Block-Durgapur-Faridpur Dist-Paschim Bardhaman under Durgapur W/s Division, PHE Dte (Part-B) | TSM/014849 | SM/13862 | New | 26/09/2022 | 20 | 33.6 | Yes | 33.6 | 07/09/2022 |  | 0 | 0 | MVS
120 | PURBA BARDHAMAN | Durgapur W/S Division | AUSGRAM PIPED WATER SUPPLY SCHEME | TSM/016287 | SM/14905 | New | 26/09/2022 | 2264 | 951.12 | Yes | 951.12 | 01/03/2024 | 10/12/2024 | 11 | 161.47 | MVS
121 | PASCHIM BARDHAMAN | Durgapur W/S Division | PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM | TSM/018376 | SM/16249 | New | 28/12/2022 | 943 | 579.21 | Yes | 579.21 | 30/08/2024 | 01/12/2023 | 27 | 583.11 | MVS
122 | PURBA BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | TSM/019285 | SM/15176 | Augmentation | 16/11/2022 | 1200 | 217.82 | Yes | 217.82 | 06/08/2024 | 16/07/2024 | 5 | 169.44 | MVS
123 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME | TSM/017785 | SM/18344 | New | 16/11/2022 | 12334 | 4972.51 | Yes | 4972.51 | 03/12/2024 | 04/02/2025 | 20 | 4968.21 | MVS
124 | PASCHIM BARDHAMAN | Durgapur W/S Division | AUGMENTATION OF SUB SURFACE WATER BASED WATER SUPPLY SCHEME FOR KRISHNAPUR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | TSM/020576 | SM/18887 | Augmentation | 10/03/2023 | 1377 | 220.53 | Yes | 220.53 | 17/03/2025 | 10/12/2024 | 5 | 80.48 | MVS
125 | PURBA BARDHAMAN | Durgapur W/S Division | Sanko Piped Water Supply Scheme | TSM/015698 | SM/18407 | New | 09/09/2022 | 3620 | 1448.91 | Yes | 1448.91 | 01/10/2024 | 28/01/2025 | 9 | 1327.7 | MVS
126 | PASCHIM BARDHAMAN | Durgapur W/S Division | Supply and Delivery of Chemicals, Consumbles, Glassware etc. required for smooth running of Laudoha Sub-District laboratory. | TSM/005391 | SM/06638 | Support | 05/11/2019 | 0 | 4.1 | Yes | 4.1 |  | 08/10/2020 | 2 | 3.77 | MVS
127 | PASCHIM BARDHAMAN | Durgapur W/S Division | Operation charges of 2 Two) Nos Sub-District Laboratories under Durgapur Water Supply Division,PHE Dte ,Dist-Paschim Bardhaman related to Water quality monitoring and surveillance programme under Jal jeevan Mission. | TSM/016338 | SM/13908 | Support | 26/09/2022 | 0 | 8.54 | Yes | 8.54 |  | 31/01/2023 | 1 | 1.09 | MVS
Total | [7 empty] | 286417 | 83936.26 |  | 86319.3 |  |  | 1715 | 80790.55