## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | TSM/005481 | SM/07764 | New | 17/07/2020 | 2122 | 759.01 | Yes | 759.01 | 14/01/2025 | 01/04/2022 | 33 | 851.65 | MVS
2 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme | TSM/008386 | SM/09218 | Augmentation | 08/09/2021 | 1849 | 128.6 | Yes | 128.6 | 26/06/2025 | 22/04/2024 | 10 | 80.81 | MVS
3 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009806 | SM/10224 | School | 16/12/2021 | 0 | 920.88 | Yes | 920.88 | 05/09/2023 | 07/04/2022 | 8 | 1548.37 | MVS
4 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | TSM/009800 | SM/10250 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 14/03/2023 | 31/01/2022 | 21 | 773.89 | MVS
5 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme | TSM/010889 | SM/15936 | Augmentation | 28/12/2022 | 3421 | 999.41 | Yes | 999.41 | 09/04/2025 | 10/11/2023 | 12 | 968.51 | MVS
6 | PURULIA | Purulia Division | Left out Mouzas of Barabazar pipe water supply scheme | TSM/011442 | SM/18319 | New | 25/04/2022 | 14878 | 6135.38 | Yes | 6135.38 | 13/07/2023 | 12/07/2022 | 27 | 7255.27 | MVS
7 | PURULIA | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. | TSM/012987 | SM/18915 | Augmentation | 10/03/2023 | 0 | 666.74 | Yes | 666.74 | 18/03/2025 | 16/10/2023 | 27 | 550.77 | MVS
8 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006312 | SM/06940 | Retrofitting | 25/09/2020 | 1849 | 96.09 | Yes | 96.09 |  | 01/12/2020 | 10 | 175.68 | MVS
9 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006316 | SM/06941 | Retrofitting | 25/09/2020 | 1112 | 68.58 | Yes | 68.58 | 05/09/2024 | 01/12/2020 | 11 | 184.19 | MVS
10 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006757 | SM/07836 | Retrofitting | 04/12/2020 | 1072 | 91.65 | Yes | 91.65 |  | 15/01/2021 | 6 | 99.64 | MVS
11 | PURULIA | Purulia Division | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006761 | SM/07840 | Retrofitting | 04/12/2020 | 171 | 10.75 | Yes | 10.75 | 05/09/2024 | 06/07/2021 | 2 | 21.84 | MVS
12 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006311 | SM/07566 | Retrofitting | 25/09/2020 | 3763 | 244.44 | Yes | 244.44 |  | 01/02/2021 | 18 | 257.17 | MVS
13 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC | TSM/009010 | SM/09577 | Augmentation | 08/10/2021 | 3531 | 791.71 | Yes | 791.71 | 09/04/2025 | 22/12/2022 | 37 | 972.64 | MVS
14 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | TSM/009009 | SM/09579 | Augmentation | 08/10/2021 | 1450 | 463.03 | Yes | 463.03 | 26/06/2025 | 18/01/2023 | 33 | 572.7 | MVS
15 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. | TSM/009008 | SM/09580 | Augmentation | 08/10/2021 | 860 | 504.47 | Yes | 504.47 | 09/04/2025 | 26/07/2023 | 45 | 527.36 | MVS
16 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008384 | SM/10048 | Augmentation | 08/09/2021 | 4501 | 1477.06 | Yes | 1477.06 | 08/05/2025 | 14/07/2023 | 40 | 1553.18 | MVS
17 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme | TSM/010923 | SM/10544 | Augmentation | 16/03/2022 | 0 | 317.07 | Yes | 317.07 | 07/02/2025 | 18/06/2024 | 13 | 355.47 | MVS
18 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009794 | SM/10278 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 06/12/2022 | 19/04/2022 | 9 | 592.38 | MVS
19 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009792 | SM/10277 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 05/07/2022 | 02/05/2022 | 8 | 977.08 | MVS
20 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009788 | SM/10286 | Anganwadi | 16/12/2021 | 0 | 921.04 | Yes | 921.04 | 05/07/2022 | 05/05/2022 | 20 | 1515.28 | MVS
21 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009803 | SM/10229 | School | 16/12/2021 | 0 | 889.17 | Yes | 889.17 |  | 08/04/2022 | 6 | 915.1 | MVS
22 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme | TSM/009011 | SM/10721 | Augmentation | 08/10/2021 | 4178 | 1045.37 | Yes | 1045.37 | 28/08/2024 | 05/05/2022 | 31 | 1107.32 | MVS
23 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) | TSM/009004 | SM/10722 | Augmentation | 08/10/2021 | 7881 | 2195.7 | Yes | 2195.7 | 14/01/2025 | 02/01/2023 | 64 | 2148.33 | MVS
24 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009797 | SM/10249 | Anganwadi | 16/12/2021 | 0 | 783.7 | Yes | 783.7 | 23/11/2022 | 02/05/2022 | 15 | 618.74 | MVS
25 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006313 | SM/06942 | Retrofitting | 25/09/2020 | 1241 | 86.91 | Yes | 86.91 |  | 09/04/2024 | 8 | 109.85 | MVS
26 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS | TSM/016045 | SM/14460 | Augmentation | 26/09/2022 | 2424 | 660.04 | Yes | 660.04 | 14/01/2025 | 18/08/2023 | 16 | 639.1 | MVS
27 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. | TSM/005223 | SM/08718 | Anganwadi | 05/11/2019 | 1105 | 552.02 | Yes | 552.02 | 19/07/2023 | 11/09/2024 | 30 | 964.85 | MVS
28 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006759 | SM/07838 | Retrofitting | 04/12/2020 | 1218 | 73.08 | Yes | 73.08 |  | 08/02/2021 | 5 | 143.87 | MVS
29 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006308 | SM/07564 | Retrofitting | 25/09/2020 | 2672 | 128.34 | Yes | 128.34 |  | 27/08/2021 | 37 | 169.03 | MVS
30 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme | TSM/008387 | SM/09038 | Augmentation | 08/09/2021 | 3823 | 389.21 | Yes | 389.21 | 28/10/2024 | 12/04/2023 | 32 | 362.44 | MVS
31 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006315 | SM/08584 | Retrofitting | 25/09/2020 | 2623 | 474.74 | Yes | 474.74 | 27/01/2023 | 12/04/2023 | 12 | 558.3 | MVS
32 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009810 | SM/10225 | School | 16/12/2021 | 0 | 848.34 | Yes | 848.34 | 05/09/2023 | 02/05/2022 | 9 | 836.33 | MVS
33 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) | TSM/009015 | SM/10718 | Augmentation | 08/10/2021 | 6702 | 1670.03 | Yes | 1670.03 | 08/05/2025 | 07/08/2023 | 41 | 1628.46 | MVS
34 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS | TSM/019805 | SM/15040 | Augmentation | 16/11/2022 | 0 | 396.97 | Yes | 396.97 | 09/04/2025 | 25/07/2024 | 6 | 395.98 | MVS
35 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS | TSM/019807 | SM/15041 | Augmentation | 16/11/2022 | 0 | 298.83 | Yes | 298.83 | 28/08/2024 | 10/04/2023 | 8 | 278.85 | MVS
36 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme | TSM/008398 | SM/09211 | Augmentation | 08/09/2021 | 988 | 167.09 | Yes | 167.09 | 07/02/2025 | 27/08/2024 | 22 | 210.68 | MVS
37 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. | TSM/009743 | SM/10227 | School | 16/12/2021 | 0 | 943.72 | Yes | 943.72 | 05/09/2023 | 06/04/2022 | 13 | 1686.12 | MVS
38 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II | TSM/016015 | SM/18641 | New | 30/09/2022 | 0 | 60986.55 | Yes | 60986.55 | 09/04/2025 | 07/05/2024 | 42 | 30184.23 | MVS
39 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008379 | SM/09578 | Augmentation | 08/10/2021 | 4309 | 785.53 | Yes | 785.53 | 28/08/2024 | 27/07/2023 | 35 | 1030.57 | MVS
40 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme | TSM/008395 | SM/09212 | Augmentation | 08/09/2021 | 768 | 354.91 | Yes | 354.91 | 28/08/2024 | 05/01/2022 | 21 | 477.57 | MVS
41 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008390 | SM/09216 | Augmentation | 08/09/2021 | 1140 | 424.22 | Yes | 424.22 | 09/04/2025 | 02/01/2023 | 29 | 480.07 | MVS
42 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC | TSM/008389 | SM/09217 | Augmentation | 08/09/2021 | 271 | 386.08 | Yes | 386.08 | 28/10/2024 | 30/06/2023 | 31 | 451.04 | MVS
43 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | TSM/009002 | SM/09582 | Augmentation | 08/10/2021 | 237 | 203.85 | Yes | 203.85 | 14/01/2025 | 12/04/2023 | 22 | 257.82 | MVS
44 | PURULIA | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. | TSM/009000 | SM/09583 | Augmentation | 08/10/2021 | 1857 | 103.56 | Yes | 103.56 | 09/04/2025 | 17/01/2022 | 18 | 113.18 | MVS
45 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009785 | SM/10282 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 12/08/2022 | 09/01/2023 | 39 | 1187.32 | MVS
46 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/009014 | SM/10198 | Augmentation | 22/11/2021 | 4421 | 1455.54 | Yes | 1455.54 | 07/02/2025 | 23/02/2023 | 50 | 1739.32 | MVS
47 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009793 | SM/10279 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 23/11/2022 | 02/05/2022 | 16 | 1128.76 | MVS
48 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008461 | SM/10395 | Augmentation | 27/01/2022 | 5991 | 1949.9 | Yes | 1949.9 | 09/04/2025 | 17/05/2023 | 48 | 1573.26 | MVS
49 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009812 | SM/10230 | School | 16/12/2021 | 0 | 902.6 | Yes | 902.6 | 05/09/2023 | 20/04/2022 | 10 | 1232.73 | MVS
50 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. | TSM/009801 | SM/10251 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 02/12/2022 | 16/12/2022 | 27 | 1134.68 | MVS
51 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. | TSM/009791 | SM/10255 | Anganwadi | 16/12/2021 | 0 | 824.09 | Yes | 824.09 | 05/09/2023 | 10/08/2023 | 23 | 923.04 | MVS
52 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B | TSM/016037 | SM/14024 | Augmentation | 26/09/2022 | 3031 | 782.25 | Yes | 782.25 | 09/04/2025 | 20/04/2023 | 24 | 766.51 | MVS
53 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss | TSM/019808 | SM/15039 | Augmentation | 16/11/2022 | 0 | 512.38 | Yes | 512.38 | 24/01/2025 | 26/06/2024 | 11 | 397.29 | MVS
54 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia | TSM/008462 | SM/10045 | Augmentation | 08/09/2021 | 47 | 1577.26 | Yes | 1577.26 | 07/03/2025 | 22/12/2022 | 35 | 1691.26 | MVS
55 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B | TSM/016040 | SM/18306 | Augmentation | 26/09/2022 | 4471 | 1014.74 | Yes | 1014.74 | 28/11/2024 | 04/08/2023 | 11 | 963.47 | MVS
56 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III | TSM/018257 | SM/18653 | New | 16/11/2022 | 0 | 16409.28 | Yes | 16409.28 | 26/06/2025 | 07/05/2024 | 56 | 5803.33 | MVS
57 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006307 | SM/07563 | Retrofitting | 25/09/2020 | 5324 | 185.57 | Yes | 185.57 |  | 29/12/2020 | 8 | 289.58 | MVS
58 | PURULIA | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006762 | SM/07841 | Retrofitting | 04/12/2020 | 1864 | 120.54 | Yes | 120.54 |  | 02/08/2022 | 4 | 74.71 | MVS
59 | PURULIA | Purulia Division | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006309 | SM/07565 | Retrofitting | 25/09/2020 | 2058 | 159.92 | Yes | 159.92 |  | 10/02/2021 | 2 | 220.85 | MVS
60 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008391 | SM/09036 | Augmentation | 08/09/2021 | 2888 | 965.77 | Yes | 965.77 | 09/04/2025 | 02/01/2023 | 47 | 1056.15 | MVS
61 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. | TSM/008880 | SM/10257 | School | 16/12/2021 | 0 | 605.24 | Yes | 605.24 |  | 16/03/2022 | 5 | 430.97 | MVS
62 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009786 | SM/10283 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 22/08/2022 | 31/03/2023 | 22 | 1283.37 | MVS
63 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009789 | SM/10275 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 24/03/2023 | 02/05/2022 | 31 | 992.22 | MVS
64 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. | TSM/009003 | SM/10723 | Augmentation | 08/10/2021 | 8268 | 2091.4 | Yes | 2091.4 | 09/04/2025 | 05/12/2022 | 69 | 3111.58 | MVS
65 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. | TSM/009782 | SM/10252 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 22/08/2022 | 19/04/2022 | 16 | 1080.51 | MVS
66 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009795 | SM/10254 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 24/03/2023 | 17/05/2022 | 23 | 1282.32 | MVS
67 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme | TSM/008385 | SM/09213 | Augmentation | 08/09/2021 | 1241 | 195.46 | Yes | 195.46 | 26/09/2024 | 17/10/2023 | 24 | 163.07 | MVS
68 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII | TSM/016044 | SM/14023 | Augmentation | 26/09/2022 | 3400 | 721.23 | Yes | 721.23 | 26/06/2025 | 12/04/2023 | 12 | 632.19 | MVS
69 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS | TSM/016080 | SM/14459 | Augmentation | 26/09/2022 | 658 | 363.94 | Yes | 363.94 | 09/04/2025 | 08/08/2023 | 16 | 386.24 | MVS
70 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMANDIHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MANBAZAR-I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013873 | SM/14251 | New | 26/09/2022 | 22 | 29.24 | Yes | 29.24 | 09/04/2025 | 24/02/2023 | 1 | 4.69 | MVS
71 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006760 | SM/07839 | Retrofitting | 04/12/2020 | 2932 | 175.07 | Yes | 175.07 |  | 01/02/2021 | 12 | 224.13 | MVS
72 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR ANKDUAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER JAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013718 | SM/16091 | New | 28/12/2022 | 97 | 37.39 | Yes | 37.39 | 02/08/2022 | 24/02/2023 | 1 | 2.97 | MVS
73 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008388 | SM/09037 | Augmentation | 08/09/2021 | 2031 | 684.31 | Yes | 684.31 | 14/01/2025 | 17/05/2023 | 43 | 760.96 | MVS
74 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. | TSM/009005 | SM/09581 | Augmentation | 08/10/2021 | 81 | 288.49 | Yes | 288.49 | 14/01/2025 | 26/07/2023 | 45 | 334.98 | MVS
75 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme | TSM/008394 | SM/10047 | Augmentation | 08/09/2021 | 4032 | 1088.37 | Yes | 1088.37 | 07/02/2025 | 26/07/2023 | 31 | 1008.7 | MVS
76 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009783 | SM/10281 | Anganwadi | 16/12/2021 | 0 | 872.57 | Yes | 872.57 | 05/09/2023 | 17/05/2022 | 14 | 997.48 | MVS
77 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. | TSM/009799 | SM/10274 | Anganwadi | 16/12/2021 | 0 | 824.09 | Yes | 824.09 |  | 02/05/2022 | 11 | 957.84 | MVS
78 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. | TSM/009790 | SM/10276 | Anganwadi | 16/12/2021 | 0 | 880.65 | Yes | 880.65 | 05/09/2023 | 26/06/2023 | 31 | 1643.66 | MVS
79 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009796 | SM/10280 | Anganwadi | 16/12/2021 | 0 | 912.96 | Yes | 912.96 | 22/08/2022 | 31/03/2023 | 27 | 1204.09 | MVS
80 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme | TSM/008399 | SM/11453 | Augmentation | 16/03/2022 | 6896 | 2367.56 | Yes | 2367.56 | 09/04/2025 | 26/07/2023 | 45 | 2158.07 | MVS
81 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A | TSM/016038 | SM/14025 | Augmentation | 26/09/2022 | 2868 | 538.41 | Yes | 538.41 | 10/02/2025 | 22/05/2023 | 8 | 509.83 | MVS
82 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMNI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ARSHA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013556 | SM/16570 | New | 30/09/2022 | 50 | 30.31 | Yes | 30.31 |  | 10/02/2023 | 1 | 3.07 | MVS
83 | PURULIA | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) | TSM/012586 | SM/18528 | New | 20/05/2022 | 286151 | 27591.27 | Yes | 27591.27 | 09/04/2025 | 18/03/2024 | 7 | 36723.1 | MVS
84 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) | TSM/017881 | SM/18654 | New | 16/11/2022 | 0 | 65922.47 | Yes | 65922.47 | 26/06/2025 | 28/08/2024 | 277 | 61877 | MVS
85 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009804 | SM/10223 | School | 16/12/2021 | 0 | 830.21 | Yes | 830.21 | 01/08/2022 | 26/04/2024 | 14 | 858.34 | MVS
86 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | TSM/005788 | SM/06826 | Augmentation | 28/08/2020 | 473 | 81.48 | Yes | 81.48 |  | 22/04/2022 | 9 | 155.37 | MVS
87 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006314 | SM/07567 | Retrofitting | 25/09/2020 | 3823 | 168.98 | Yes | 168.98 | 27/01/2023 | 13/01/2021 | 25 | 145.57 | MVS
88 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme | TSM/008393 | SM/09214 | Augmentation | 08/09/2021 | 2672 | 463.76 | Yes | 463.76 | 09/04/2025 | 08/03/2024 | 44 | 549.17 | MVS
89 | PURULIA | Purulia Division | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) | TSM/008046 | SM/09028 | School | 19/08/2021 | 0 | 33.33 | Yes | 33.33 |  | 02/05/2022 | 2 | 22.21 | MVS
90 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009784 | SM/10284 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 |  | 29/03/2022 | 8 | 641.43 | MVS
91 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008455 | SM/10347 | Augmentation | 27/01/2022 | 3104 | 940.26 | Yes | 940.26 | 07/02/2025 | 17/05/2023 | 24 | 801.62 | MVS
92 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme | TSM/008396 | SM/09943 | Augmentation | 22/11/2021 | 800 | 371.08 | Yes | 371.08 | 14/01/2025 | 14/06/2023 | 29 | 425.93 | MVS
93 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. | TSM/009798 | SM/10285 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 24/03/2023 | 02/05/2022 | 35 | 753.27 | MVS
94 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) | TSM/009013 | SM/10719 | Augmentation | 08/10/2021 | 5016 | 1569.58 | Yes | 1569.58 | 07/02/2025 | 09/12/2022 | 31 | 1602.07 | MVS
95 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009787 | SM/10253 | Anganwadi | 16/12/2021 | 0 | 937.2 | Yes | 937.2 | 21/02/2023 | 24/03/2022 | 16 | 743.15 | MVS
96 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A | TSM/016041 | SM/14022 | Augmentation | 26/09/2022 | 3393 | 559.47 | Yes | 559.47 | 10/02/2025 | 11/04/2023 | 13 | 532.59 | MVS
97 | PURULIA | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS | TSM/019806 | SM/15336 | Augmentation | 28/12/2022 | 0 | 363.16 | Yes | 363.16 | 28/08/2024 | 19/07/2023 | 4 | 314.03 | MVS
98 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B | TSM/016042 | SM/16379 | Augmentation | 16/11/2022 | 1951 | 814.73 | Yes | 814.73 | 22/01/2025 | 11/04/2023 | 13 | 768.92 | MVS
99 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. | TSM/009744 | SM/10228 | School | 16/12/2021 | 0 | 889.14 | Yes | 889.14 | 05/09/2023 | 12/04/2022 | 5 | 1104.99 | MVS
100 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB | TSM/016036 | SM/18250 | Augmentation | 26/09/2022 | 3798 | 1077.99 | Yes | 1077.99 | 14/01/2025 | 06/05/2025 | 18 | 546.57 | MVS
101 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) | TSM/011448 | SM/18333 | New | 20/05/2022 | 74419 | 10279.85 | Yes | 10279.85 | 11/09/2024 | 17/06/2025 | 6 | 32269.6 | MVS
102 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) | TSM/015985 | SM/18731 | New | 10/03/2023 | 0 | 161758.31 | Yes | 161758.31 | 09/04/2025 | 29/10/2024 | 176 | 96144.59 | MVS
103 | PURULIA | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006310 | SM/06939 | Retrofitting | 25/09/2020 | 1259 | 81.16 | Yes | 81.16 |  | 29/12/2020 | 4 | 151.68 | MVS
104 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | TSM/006758 | SM/07837 | Retrofitting | 04/12/2020 | 1801 | 224.29 | Yes | 224.29 | 09/04/2025 | 17/05/2023 | 12 | 173.6 | MVS
105 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008431 | SM/09209 | Augmentation | 08/09/2021 | 2359 | 590.04 | Yes | 590.04 | 14/01/2025 | 23/02/2023 | 29 | 594.28 | MVS
106 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme | TSM/008397 | SM/09210 | Augmentation | 08/09/2021 | 1218 | 401.87 | Yes | 401.87 | 09/04/2025 | 17/05/2023 | 20 | 490.61 | MVS
107 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008392 | SM/09215 | Augmentation | 08/09/2021 | 2135 | 514.62 | Yes | 514.62 | 07/02/2025 | 12/04/2023 | 30 | 787.82 | MVS
108 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) | TSM/008456 | SM/10046 | Augmentation | 08/09/2021 | 13173 | 2330.93 | Yes | 2330.93 | 09/04/2025 | 14/05/2024 | 54 | 2355.76 | MVS
109 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009805 | SM/10222 | School | 16/12/2021 | 0 | 825.62 | Yes | 825.62 |  | 08/04/2022 | 5 | 695.16 | MVS
110 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. | TSM/009746 | SM/10226 | School | 16/12/2021 | 0 | 843.81 | Yes | 843.81 | 05/09/2023 | 25/04/2022 | 5 | 846.57 | MVS
111 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC | TSM/009012 | SM/10720 | Augmentation | 08/10/2021 | 3650 | 1231.07 | Yes | 1231.07 | 07/02/2025 | 07/05/2024 | 33 | 1105.86 | MVS
112 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. | TSM/009811 | SM/10256 | School | 16/12/2021 | 0 | 771.24 | Yes | 771.24 | 19/01/2024 | 20/04/2022 | 6 | 778.19 | MVS
113 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II | TSM/016035 | SM/14669 | Augmentation | 26/09/2022 | 0 | 969.41 | Yes | 969.41 | 09/04/2025 | 10/04/2023 | 22 | 800.79 | MVS
114 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B | TSM/016039 | SM/14670 | Augmentation | 26/09/2022 | 3183 | 984.33 | Yes | 984.33 | 14/01/2025 | 07/05/2024 | 16 | 954.47 | MVS
115 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | TSM/013606 | SM/15380 | New | 26/09/2022 | 44 | 32.84 | Yes | 32.84 |  | 08/02/2023 | 1 | 4.83 | MVS
116 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project | TSM/017383 | SM/18779 | Augmentation | 30/09/2022 | 1038 | 4685.1 | Yes | 4685.1 | 26/06/2025 | 07/04/2025 | 57 | 3818.04 | MVS
117 | PURULIA | Purulia Division | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purulia District. | TSM/008138 | SM/09027 | Support | 19/08/2021 | 0 | 437.58 | Yes | 437.58 |  |  | 0 | 0 | MVS
118 | PURULIA | Purulia Division | Supply of Chemicals & Consumables Glass Wares etc. required for smooth running of 17 NOS laboratories located at different blocks of Purulia District under Purulia Division, PHE Dte. | TSM/023287 | SM/19265 | Support | 09/03/2024 | 0 | 372.4 | Yes | 372.4 |  |  | 0 | 0 | MVS
119 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission | TSM/007271 | SM/08682 | Support | 10/02/2021 | 0 | 34.33 | Yes | 34.33 | 16/10/2023 | 18/08/2021 | 7 | 31.66 | MVS
120 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | TSM/017570 | SM/14143 | Support | 30/09/2022 | 0 | 95.58 | Yes | 95.58 | 05/02/2024 | 05/05/2023 | 34 | 204.78 | MVS
121 | PURULIA | Purulia Division | Engagement of a Third Party Inspection (TPI) of the Materials, Machineries and Equipments for Civil, Mechanical, Electrical & Instrumentation for different Water Supply Projects under Jal Jeevan Mission (JJM) in the district of Purulia. | TSM/023732 | SM/19367 | Support | 22/10/2024 | 0 | 126.49 | Yes | 126.49 |  |  | 0 | 0 | MVS
122 | PURULIA | Purulia Division | Water sample collection charges by engagement of agency at different blocks of Purulia District under Purulia Division, PHE Dte. | TSM/023062 | SM/19291 | Support | 09/03/2024 | 0 | 784.73 | Yes | 784.73 |  |  | 0 | 0 | MVS
123 | PURULIA | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. | TSM/015261 | SM/17197 | Support | 28/12/2022 | 0 | 82.63 | Yes | 82.63 | 05/09/2024 | 26/06/2023 | 4 | 16.27 | MVS
124 | PURULIA | Purulia Division | Honorarium of Asha Workers & Self Help group in connection with FTK testing at different blocks of Purulia District under Purulia Division, PHE Dte. | TSM/023064 | SM/19290 | Support | 09/03/2024 | 0 | 321.19 | Yes | 321.19 |  |  | 0 | 0 | MVS
125 | PURULIA | Purulia Division | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission | TSM/017571 | SM/17411 | Support | 30/09/2022 | 0 | 78.13 | Yes | 78.13 |  |  | 0 | 0 | MVS
126 | PURULIA | Purulia Division | Supply, Delivery, Installation of Computer & Peripheral including CCTV for the official use under the office of The Executive Engineer & Different Sub-Division offices including all Water Test Laboratories in Purulia District under Purulia Division, PHE D | TSM/023065 |  | Support | 22/10/2024 | 0 | 99.96 | No | 0 |  |  | 0 | 0 | MVS
127 | PURULIA | Purulia Division | Operational charges of 17 nos PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | TSM/023377 | SM/19324 | Support | 22/10/2024 | 0 | 144.85 | Yes | 144.85 |  |  | 0 | 0 | MVS
128 | * | Purulia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. | TSM/011104 |  | Support | 30/03/2022 | 0 | 113.46 | No | 0 |  |  | 0 | 0 | MVS
129 | PURULIA | Purulia Division | Procurement of Chemicals, Consumables, Glass wares etc. including annual maintenance contract (AMC) of Laboratories. | TSM/005387 | SM/06620 | Support | 05/11/2019 | 0 | 75.01 | Yes | 75.01 |  |  | 0 | 0 | MVS
130 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | TSM/021973 | SM/19090 | Support | 17/08/2023 | 0 | 155.07 | Yes | 155.07 | 18/12/2023 | 25/04/2024 | 44 | 149.31 | MVS
131 | PURULIA | Purulia Division | Supply of Chemicals & Consumables Glass Wares etc. required for smooth running of 17 NOS Laboratories located at different blocks of Purulia District under Purulia Division, PHE Dte. | TSM/023063 | SM/19266 | Support | 09/03/2024 | 0 | 223.97 | Yes | 223.97 |  |  | 0 | 0 | MVS
Total | [7 empty] | 562147 | 432540.84 |  | 432327.41 |  |  | 2981 | 355896.13