## D4- Work Order Tracking
D4- Work Order Tracking (Rs. in Lakh)
Sl No. | District | Division | Scheme | TSM Code | SM Code | Scheme Type | SLSSC date | FHTC Involved | Estimated Cost | AAFS Status | AAFS Cost | Date of first Tender issue | Date of first Work order | No. of Work Orders issued | Work Value | Scheme coverage type
1 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. | TSM/009476 | SM/10774 | Retrofitting | 27/01/2022 | 59 | 18.12 | Yes | 18.12 |  | 26/05/2022 | 3 | 17.26 | MVS
2 | KALIMPONG | Neorakhola W/S Mnt. Division | Detail Project Report on Extension of pipeline by way of Retrofitting of Neorakhola Piped water Scheme to provide Functional Household Tap Connection to the remaining households of en-route villages of the Scheme in Kalimpong Block I-II , under Kalimpong | TSM/010474 | SM/10512 | Retrofitting | 17/02/2022 | 677 | 504.2 | Yes | 504.2 |  | 13/04/2022 | 6 | 503.28 | MVS
3 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Kolbong | TSM/009508 | SM/10834 | New | 17/02/2022 | 107 | 104.23 | Yes | 104.23 | 12/10/2023 | 31/05/2023 | 6 | 84.53 | MVS
4 | DARJEELING | Neorakhola W/S Mnt. Division | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. | TSM/010475 | SM/10622 | Disaster | 16/03/2022 | 0 | 480.8 | Yes | 480.8 |  | 13/04/2022 | 4 | 347.68 | MVS
5 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Kolbong Forest Village under Lava Gitbeong G.P. Kalimpong Block-II, in the District of Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009886 | SM/10623 | New | 16/03/2022 | 28 | 41.4 | Yes | 41.4 |  | 25/05/2022 | 1 | 38.82 | MVS
6 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. | TSM/011122 | SM/11394 | Retrofitting | 30/03/2022 | 1395 | 199.28 | Yes | 199.28 |  | 12/07/2022 | 3 | 184.59 | MVS
7 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011222 | SM/12366 | New | 30/03/2022 | 1358 | 1129.94 | Yes | 1129.94 |  | 05/05/2025 | 5 | 1125 | MVS
8 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA | TSM/009860 | SM/10798 | New | 17/02/2022 | 233 | 226.19 | Yes | 226.19 |  | 05/08/2022 | 2 | 118.28 | MVS
9 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA | TSM/009853 | SM/10805 | New | 17/02/2022 | 588 | 123.11 | Yes | 123.11 |  | 25/11/2022 | 2 | 79.07 | MVS
10 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | TSM/009851 | SM/10807 | New | 17/02/2022 | 754 | 103.62 | Yes | 103.62 |  | 26/05/2022 | 3 | 64.48 | MVS
11 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA | TSM/009855 | SM/10803 | New | 17/02/2022 | 588 | 91.97 | Yes | 91.97 |  | 26/05/2022 | 3 | 61.51 | MVS
12 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA | TSM/009844 | SM/10828 | New | 17/02/2022 | 303 | 117.73 | Yes | 117.73 |  | 30/06/2022 | 4 | 82.9 | MVS
13 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM PHENTO SOURCE TO DUKA | TSM/009637 | SM/10748 | New | 17/02/2022 | 143 | 165.77 | Yes | 165.77 |  | 25/05/2022 | 1 | 155.54 | MVS
14 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM KHARKHOLA TO SARDAR AND LOWER TOP LINE | TSM/009636 | SM/10749 | New | 17/02/2022 | 105 | 105.72 | Yes | 105.72 |  | 25/05/2022 | 1 | 102.55 | MVS
15 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. | TSM/009602 | SM/11317 | Retrofitting | 17/02/2022 | 142 | 12.12 | Yes | 12.12 |  | 30/06/2022 | 2 | 10.99 | MVS
16 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-1 BLOCK, UNDER KALIMPONG DISTRICT | TSM/012581 | SM/12180 | New | 20/05/2022 | 295 | 520.75 | Yes | 520.75 |  | 18/10/2022 | 1 | 400.34 | MVS
17 | KALIMPONG | Neorakhola W/S Mnt. Division | SURFACE WATER BASED PARINAGAR KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010477 | SM/11313 | New | 16/03/2022 | 462 | 829.3 | Yes | 829.3 | 04/09/2024 | 12/07/2022 | 2 | 757.66 | MVS
18 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS | TSM/012041 | SM/11855 | New | 20/05/2022 | 228 | 408.25 | Yes | 408.25 |  | 19/09/2023 | 2 | 372.52 | MVS
19 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KASHONE KHASMAHAL (PART) UNDER KASHONE G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/012505 | SM/12630 | New | 20/05/2022 | 530 | 939.41 | Yes | 939.41 |  | 13/06/2025 | 3 | 934.94 | MVS
20 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012579 | SM/11943 | New | 20/05/2022 | 385 | 212.19 | Yes | 212.19 | 07/03/2024 | 18/06/2024 | 3 | 222.66 | MVS
21 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAIL PROJECT REPORT OF Dr. GRAHAM'S HOME (PART) PIPED WATER SUPPLY SCHEME (PWSS) UNDER DR. GRAHAM'S HOME G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/012503 | SM/11955 | New | 20/05/2022 | 221 | 242.62 | Yes | 242.62 |  | 04/11/2022 | 1 | 229.27 | MVS
22 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009536 | SM/11344 | New | 16/03/2022 | 120 | 32.23 | Yes | 32.23 |  | 20/01/2024 | 4 | 40.4 | MVS
23 | KALIMPONG | Neorakhola W/S Mnt. Division | PAREN FOREST PIPED WATER SUPPLY SCHEME | TSM/011674 | SM/13609 | New | 05/07/2022 | 46 | 133.18 | Yes | 133.18 | 23/12/2022 | 17/07/2023 | 2 | 92.71 | MVS
24 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 192 numbers of school under Darjeeling Pulbazar Block in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte | TSM/010216 | SM/11356 | School | 16/03/2022 | 0 | 638.99 | Yes | 638.99 |  | 12/07/2022 | 1 | 620.25 | MVS
25 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 42 Numbers of school in Kalimpong Block -I under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte | TSM/010217 | SM/11358 | School | 16/03/2022 | 0 | 182.6 | Yes | 182.6 |  | 12/07/2022 | 1 | 177.33 | MVS
26 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 79 Numbers of Anganwadi Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/010191 | SM/11364 | Anganwadi | 16/03/2022 | 0 | 398.55 | Yes | 398.55 |  | 12/07/2022 | 2 | 393.8 | MVS
27 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | TSM/010271 | SM/11365 | Health Center | 16/03/2022 | 0 | 38.03 | Yes | 38.03 |  | 12/07/2022 | 7 | 23.69 | MVS
28 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Rohini Tea Garden | TSM/011593 | SM/11938 | New | 25/04/2022 | 614 | 408.51 | Yes | 408.51 | 29/12/2022 | 28/04/2023 | 3 | 334.16 | MVS
29 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL (PART), BLOCK : KALIMPONG - II, DISTRICT : Kalimpong | TSM/012583 | SM/13605 | New | 20/05/2022 | 991 | 419.43 | Yes | 419.43 | 24/01/2023 | 04/05/2023 | 5 | 402.28 | MVS
30 | KALIMPONG | Neorakhola W/S Mnt. Division | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG | TSM/017451 | SM/16230 | New | 28/12/2022 | 1068 | 921.36 | Yes | 921.36 | 03/09/2024 | 29/05/2023 | 3 | 919.45 | MVS
31 | DARJEELING | Neorakhola W/S Mnt. Division | LATPANICHAR PIPED WATER SUPPLY SCHEME | TSM/018164 | SM/16162 | New | 28/12/2022 | 172 | 268.11 | Yes | 268.11 | 08/02/2023 | 24/09/2024 | 3 | 243.86 | MVS
32 | DARJEELING | Neorakhola W/S Mnt. Division | LODHAMA PIPED WATER SUPPLY SCHEME. | TSM/018972 | SM/15872 | New | 28/12/2022 | 45 | 178.54 | Yes | 178.54 | 01/02/2023 | 27/04/2023 | 2 | 157.85 | MVS
33 | DARJEELING | Neorakhola W/S Mnt. Division | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme | TSM/018086 | SM/16142 | New | 28/12/2022 | 711 | 334.74 | Yes | 334.74 | 27/04/2023 | 19/07/2023 | 1 | 4.38 | MVS
34 | DARJEELING | Neorakhola W/S Mnt. Division | PANIGHATA Piped Water Supply Scheme | TSM/018071 | SM/16144 | New | 28/12/2022 | 1222 | 363.69 | Yes | 363.69 | 26/09/2024 | 28/01/2024 | 6 | 360.95 | MVS
35 | DARJEELING | Neorakhola W/S Mnt. Division | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME | TSM/016186 | SM/15894 | New | 28/12/2022 | 259 | 295.85 | Yes | 295.85 | 10/02/2023 | 28/04/2023 | 2 | 251.87 | MVS
36 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Sevok Hill Forest area under Kurseong Block. | TSM/020258 | SM/15895 | New | 28/12/2022 | 598 | 496.03 | Yes | 496.03 | 25/04/2023 | 03/09/2024 | 4 | 225.67 | MVS
37 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/015162 | SM/16352 | New | 22/08/2022 | 715 | 705.57 | Yes | 705.57 | 02/12/2022 | 12/05/2023 | 1 | 4.4 | MVS
38 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ALOOBARI PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012886 | SM/16629 | New | 26/09/2022 | 333 | 610.28 | Yes | 610.28 | 02/12/2022 | 28/04/2023 | 2 | 579.52 | MVS
39 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR D I F UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015687 | SM/15642 | New | 09/09/2022 | 314 | 211.63 | Yes | 211.63 | 08/12/2022 | 26/09/2024 | 2 | 106.66 | MVS
40 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) UNDER GITDUBLING G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | TSM/012819 | SM/15644 | New | 09/09/2022 | 538 | 650.72 | Yes | 650.72 | 24/01/2023 | 10/05/2023 | 2 | 628.78 | MVS
41 | DARJEELING | Neorakhola W/S Mnt. Division | SUKNA PIPED WATER SUPPLY SCHEME | TSM/017746 | SM/15653 | New | 30/09/2022 | 402 | 304.63 | Yes | 304.63 | 29/12/2022 | 08/07/2024 | 3 | 258.41 | MVS
42 | DARJEELING | Neorakhola W/S Mnt. Division | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. | TSM/018033 | SM/15878 | New | 28/12/2022 | 384 | 277.07 | Yes | 277.07 | 08/02/2023 | 28/04/2023 | 4 | 268.22 | MVS
43 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013037 | SM/18282 | New | 22/08/2022 | 1124 | 1545.44 | Yes | 1545.44 | 22/02/2023 | 18/07/2023 | 2 | 1481.43 | MVS
44 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/016207 | SM/18633 | New | 26/09/2022 | 1243 | 1443.98 | Yes | 1443.98 | 02/12/2022 | 26/02/2024 | 5 | 1433.61 | MVS
45 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING | TSM/016300 | SM/18635 | New | 26/09/2022 | 1938 | 1907.13 | Yes | 1907.13 | 30/11/2022 | 26/02/2024 | 4 | 1902.08 | MVS
46 | DARJEELING | Neorakhola W/S Mnt. Division | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS | TSM/016195 | SM/18724 | New | 28/12/2022 | 1347 | 1783.75 | Yes | 1783.75 | 27/04/2023 | 19/12/2024 | 3 | 1780.02 | MVS
47 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL (PART) UNDER DUNGRA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015695 | SM/18247 | New | 28/12/2022 | 946 | 1350.54 | Yes | 1350.54 | 12/12/2023 | 18/07/2023 | 2 | 1232.78 | MVS
48 | DARJEELING | Neorakhola W/S Mnt. Division | MAHAL DIRAM TEA GARDEN PWSS | TSM/011323 | SM/13623 | New | 22/08/2022 | 166 | 230.73 | Yes | 230.73 | 12/12/2022 | 28/02/2023 | 3 | 215.95 | MVS
49 | DARJEELING | Neorakhola W/S Mnt. Division | KANKIBONG PWSS | TSM/019208 | SM/18992 | New | 28/12/2022 | 672 | 836.23 | Yes | 836.23 | 01/02/2023 | 17/10/2023 | 1 | 785.44 | MVS
50 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | TSM/011753 | SM/18820 | New | 20/05/2022 | 1170 | 2125.19 | Yes | 2125.19 | 22/02/2023 | 05/05/2025 | 4 | 2116.86 | MVS
51 | DARJEELING | Neorakhola W/S Mnt. Division | DARJEELING PULBAZAR PUMPING-II PWSS | TSM/019546 | SM/18659 | New | 28/12/2022 | 2169 | 8823.99 | Yes | 8823.99 | 28/11/2023 | 01/08/2024 | 9 | 8214.91 | MVS
52 | DARJEELING | Neorakhola W/S Mnt. Division | DARJEELING PULBAZAR PUMPING-III PWSS | TSM/019593 | SM/18792 | New | 28/12/2022 | 1620 | 7379.87 | Yes | 7379.87 | 05/02/2024 | 11/09/2024 | 5 | 6757.3 | MVS
53 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division | TSM/009296 | SM/10765 | Retrofitting | 27/01/2022 | 136 | 18 | Yes | 18 |  | 26/05/2022 | 3 | 18.59 | MVS
54 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield | TSM/009472 | SM/10772 | Retrofitting | 27/01/2022 | 96 | 15.76 | Yes | 15.76 |  | 24/05/2022 | 3 | 14.32 | MVS
55 | DARJEELING | Neorakhola W/S Mnt. Division | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. | TSM/010473 | SM/10789 | New | 16/03/2022 | 105 | 100.65 | Yes | 100.65 |  | 27/07/2023 | 3 | 201.32 | MVS
56 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED SURFACE WATER BASED KANKE BONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010480 | SM/10791 | New | 16/03/2022 | 373 | 470.31 | Yes | 470.31 |  | 30/06/2022 | 1 | 448.31 | MVS
57 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Rissium forest Village under Santook GP in Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009875 | SM/10602 | New | 16/03/2022 | 27 | 25.25 | Yes | 25.25 |  | 26/05/2022 | 1 | 21.57 | MVS
58 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM KHANI KHOLA TO CHUKIM | TSM/009629 | SM/10753 | New | 17/02/2022 | 122 | 138.36 | Yes | 138.36 |  | 25/05/2022 | 1 | 134.25 | MVS
59 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) | TSM/011138 | SM/11378 | Retrofitting | 30/03/2022 | 0 | 40.64 | Yes | 40.64 |  | 12/07/2022 | 3 | 36.64 | MVS
60 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) | TSM/011137 | SM/11379 | Retrofitting | 30/03/2022 | 78 | 23.39 | Yes | 23.39 |  | 12/07/2022 | 4 | 19.91 | MVS
61 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | TSM/011133 | SM/11389 | Retrofitting | 30/03/2022 | 63 | 15.54 | Yes | 15.54 |  | 12/07/2022 | 4 | 13.37 | MVS
62 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | TSM/009847 | SM/10825 | New | 17/02/2022 | 165 | 118.57 | Yes | 118.57 | 28/02/2023 | 30/06/2022 | 2 | 90.47 | MVS
63 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM BHADRA JHORA TO CHOTTA SURUK | TSM/009642 | SM/10747 | New | 17/02/2022 | 135 | 72.57 | Yes | 72.57 |  | 30/06/2022 | 1 | 70.29 | MVS
64 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAIL PROJECT REPORT OF LOWER DARA GAON AND UPPER & LOWER GAIRI GAON PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/011284 | SM/11579 | New | 30/03/2022 | 249 | 312.68 | Yes | 312.68 |  | 14/10/2022 | 1 | 306.11 | MVS
65 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney ( North shibkhola habitation ) under Kurseong Sub-Division PHED, GTA. | TSM/009606 | SM/11314 | Retrofitting | 17/02/2022 | 125 | 10.67 | Yes | 10.67 |  | 30/06/2022 | 2 | 10.05 | MVS
66 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation)under Kurseong Sub-Division PHED, GTA. | TSM/009594 | SM/11325 | Retrofitting | 17/02/2022 | 120 | 10.69 | Yes | 10.69 |  | 30/06/2022 | 2 | 10.08 | MVS
67 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Malotar Tea Estate under Kurseong-Sub Division, PHED, GTA | TSM/010590 | SM/11329 | Retrofitting | 17/02/2022 | 156 | 19.72 | Yes | 19.72 |  | 30/06/2022 | 2 | 18.8 | MVS
68 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. | TSM/009302 | SM/11300 | Retrofitting | 27/01/2022 | 55 | 20.83 | Yes | 20.83 |  | 30/06/2022 | 2 | 19.29 | MVS
69 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Krishi kunj | TSM/009481 | SM/11308 | Retrofitting | 27/01/2022 | 27 | 5.7 | Yes | 5.7 |  | 30/06/2022 | 1 | 5.52 | MVS
70 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Chota Tingling | TSM/009480 | SM/11309 | Retrofitting | 27/01/2022 | 60 | 8.98 | Yes | 8.98 |  | 30/06/2022 | 1 | 7.72 | MVS
71 | KALIMPONG | Neorakhola W/S Mnt. Division | PURBA KABI GAON GRAVITY BASED PIPE WATER SUPPLY SCHEME | TSM/009677 | SM/11312 | New | 16/03/2022 | 98 | 100.81 | Yes | 100.81 |  | 30/06/2022 | 1 | 96.46 | MVS
72 | DARJEELING | Neorakhola W/S Mnt. Division | Singla Tea Garden water supply scheme. | TSM/009506 | SM/11339 | New | 17/02/2022 | 746 | 384.26 | Yes | 384.26 |  | 09/04/2025 | 4 | 377.71 | MVS
73 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | TSM/012508 | SM/11889 | New | 20/05/2022 | 308 | 319.88 | Yes | 319.88 | 24/04/2023 | 24/09/2024 | 5 | 310.76 | MVS
74 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of Drinking water from spring water source for 13 Numbers Health care Facilities in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. | TSM/010264 | SM/11368 | Health Center | 16/03/2022 | 0 | 54.35 | Yes | 54.35 |  | 12/07/2022 | 1 | 49.48 | MVS
75 | KALIMPONG | Neorakhola W/S Mnt. Division | LOLAY KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | TSM/012584 | SM/13603 | New | 20/05/2022 | 664 | 341.66 | Yes | 341.66 | 23/11/2023 | 01/02/2023 | 2 | 330.92 | MVS
76 | KALIMPONG | Neorakhola W/S Mnt. Division | GODAK BUSTY PIPED WATER SUPPLY SCHEME. | TSM/011867 | SM/13608 | New | 05/07/2022 | 136 | 356.95 | Yes | 356.95 |  | 24/07/2023 | 1 | 350.72 | MVS
77 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014807 | SM/13617 | New | 22/08/2022 | 240 | 442.25 | Yes | 442.25 | 14/10/2022 | 13/06/2025 | 3 | 433.45 | MVS
78 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011759 | SM/11953 | New | 20/05/2022 | 527 | 768.51 | Yes | 768.51 |  | 05/05/2025 | 5 | 766.68 | MVS
79 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 27 numbers school, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong | TSM/010268 | SM/11357 | School | 16/03/2022 | 0 | 142.95 | Yes | 142.95 |  | 12/07/2022 | 1 | 136.95 | MVS
80 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 49 Numbers of school in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/010187 | SM/11359 | School | 16/03/2022 | 0 | 261.22 | Yes | 261.22 |  | 12/07/2022 | 2 | 259.81 | MVS
81 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 48 Nos of Aganwadi under Gorubathan Block, in the District of Kalimpong under Neorakhola water supply Division, kalimpong PHE Directorate. | TSM/010274 | SM/11363 | Anganwadi | 16/03/2022 | 0 | 241.95 | Yes | 241.95 |  | 12/07/2022 | 1 | 232.03 | MVS
82 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012883 | SM/13956 | New | 22/08/2022 | 455 | 517.62 | Yes | 517.62 | 02/12/2022 | 09/12/2024 | 5 | 517.33 | MVS
83 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/013035 | SM/14528 | New | 22/08/2022 | 790 | 1138.22 | Yes | 1138.22 | 30/11/2022 | 17/02/2024 | 3 | 1061.88 | MVS
84 | KALIMPONG | Neorakhola W/S Mnt. Division | TODAY TANGTA KHASMAHAL PWSS | TSM/014294 | SM/14171 | New | 22/08/2022 | 970 | 1635.15 | Yes | 1635.15 | 23/11/2023 | 28/04/2023 | 6 | 1600.9 | MVS
85 | DARJEELING | Neorakhola W/S Mnt. Division | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME | TSM/016084 | SM/16159 | New | 28/12/2022 | 55 | 307.56 | Yes | 307.56 | 08/02/2023 | 05/06/2023 | 2 | 288.35 | MVS
86 | DARJEELING | Neorakhola W/S Mnt. Division | RIMBICK Piped Water Supply Scheme | TSM/019197 | SM/16123 | New | 28/12/2022 | 450 | 716.55 | Yes | 716.55 | 08/02/2023 | 12/07/2023 | 2 | 702.35 | MVS
87 | DARJEELING | Neorakhola W/S Mnt. Division | CHAINPURAY PIPED WATER SUPPLY SCHEME | TSM/017539 | SM/15881 | New | 28/12/2022 | 105 | 82.28 | Yes | 82.28 | 08/02/2023 | 12/07/2023 | 2 | 81.11 | MVS
88 | DARJEELING | Neorakhola W/S Mnt. Division | MAJUA PIPED WATER SUPPLY SCHEME. | TSM/018191 | SM/15874 | New | 28/12/2022 | 175 | 301.04 | Yes | 301.04 | 08/02/2023 | 28/04/2023 | 3 | 285.02 | MVS
89 | DARJEELING | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013036 | SM/16533 | New | 22/08/2022 | 936 | 1182.41 | Yes | 1182.41 | 30/11/2022 | 28/04/2023 | 3 | 1179.72 | MVS
90 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) | TSM/014159 | SM/16386 | New | 30/09/2022 | 329 | 669.48 | Yes | 669.48 | 02/12/2022 | 03/03/2023 | 2 | 661.54 | MVS
91 | KALIMPONG | Neorakhola W/S Mnt. Division | PAGRAN BONG KHASMAHAL PWSS | TSM/015516 | SM/16854 | New | 28/12/2022 | 187 | 473.77 | Yes | 473.77 | 23/11/2023 | 12/07/2023 | 2 | 389.25 | MVS
92 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/017453 | SM/16145 | New | 28/12/2022 | 346 | 442.66 | Yes | 442.66 | 11/02/2023 | 09/06/2025 | 3 | 434.26 | MVS
93 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG-II DISTRICT:KALIMPONG | TSM/012818 | SM/15645 | New | 09/09/2022 | 651 | 973.41 | Yes | 973.41 | 12/12/2022 | 10/05/2023 | 2 | 943.34 | MVS
94 | DARJEELING | Neorakhola W/S Mnt. Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME | TSM/017747 | SM/15647 | New | 30/09/2022 | 1036 | 656.45 | Yes | 656.45 | 29/11/2023 | 08/07/2024 | 4 | 509.76 | MVS
95 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) UNDER DALAPCHAND G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017321 | SM/16649 | New | 28/12/2022 | 351 | 437.66 | Yes | 437.66 | 01/02/2023 | 28/04/2023 | 2 | 380.94 | MVS
96 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MARIA KHASMAHAL (PART) (UPPER RABEK) UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014813 | SM/13616 | New | 22/08/2022 | 123 | 268.04 | Yes | 268.04 | 08/12/2022 | 16/01/2024 | 3 | 254.47 | MVS
97 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR ICHA KHASMAHAL PWSS, BLOCK: -KALIMPONG-I, DISTRICT: KALIMPONG | TSM/012509 | SM/18322 | New | 20/05/2022 | 1196 | 1040.03 | Yes | 1040.03 |  | 18/07/2023 | 4 | 928 | MVS
98 | DARJEELING | Neorakhola W/S Mnt. Division | PESHOK TEA GARDEN PWSS | TSM/016194 | SM/18728 | New | 28/12/2022 | 1000 | 1054.98 | Yes | 1054.98 | 17/07/2023 | 05/05/2025 | 4 | 1050.24 | MVS
99 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection under JSP Programme for PWS scheme at Kataray forest Busty | TSM/009305 | SM/11302 | Retrofitting | 27/01/2022 | 56 | 9.52 | Yes | 9.52 |  | 30/06/2022 | 1 | 7.66 | MVS
100 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANGMAKHUM KHAS MAHAL (Part) PWSS,BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | TSM/011800 | SM/14193 | New | 20/05/2022 | 724 | 701.2 | Yes | 701.2 | 12/12/2022 | 26/05/2023 | 2 | 649.45 | MVS
101 | DARJEELING | Neorakhola W/S Mnt. Division | DARJEELING-PULBAZAR PUMPING-I PWSS | TSM/019601 | SM/18827 | New | 28/12/2022 | 3658 | 17368.24 | Yes | 17368.24 | 28/11/2023 | 03/09/2024 | 4 | 15905.62 | MVS
102 | KALIMPONG | Neorakhola W/S Mnt. Division | Providing piped water Supply Scheme for Fourteen 14 Nos of villages (part) under Kalimpong Block-I & Kalimpong Block-II in the district of Kalimpong under Neorakhola water Supply & Maintenance Division PHE Dte. | TSM/020226 | SM/18443 | New | 28/12/2022 | 3512 | 3488.92 | Yes | 3488.92 | 13/06/2024 | 18/06/2024 | 20 | 2985.96 | MVS
103 | KALIMPONG | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR SANGSER KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | TSM/013034 | SM/19176 | New | 22/08/2022 | 1749 | 2560.38 | Yes | 2560.38 | 28/02/2023 | 03/04/2025 | 6 | 2038.85 | MVS
104 | KALIMPONG | Neorakhola W/S Mnt. Division | Retrofitting of Neorakhola piped water supply scheme to provide Functional Household Tap Connection to the enroute villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme | TSM/007291 | SM/08693 | Retrofitting | 10/02/2021 | 1000 | 99.42 | Yes | 99.42 |  | 06/09/2021 | 4 | 105.67 | MVS
105 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA UNDER BHALUKHOP G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009661 | SM/10704 | New | 17/02/2022 | 226 | 338.99 | Yes | 338.99 |  | 05/08/2022 | 1 | 327.77 | MVS
106 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Paiengoan forest Village under Santook GP in Kalimpong Block-II in the district of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009880 | SM/10625 | New | 16/03/2022 | 62 | 49.5 | Yes | 49.5 |  | 26/05/2022 | 2 | 47.98 | MVS
107 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA | TSM/011214 | SM/11396 | New | 30/03/2022 | 106 | 234.66 | Yes | 234.66 |  | 09/04/2025 | 3 | 224.72 | MVS
108 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED SURFACE WATER BASED SAMALBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010478 | SM/10792 | New | 16/03/2022 | 457 | 606.74 | Yes | 606.74 |  | 12/07/2022 | 1 | 583.66 | MVS
109 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source of school (31 nos) under Mirik Block in the District of Darjeeling under Neorakhola water supply & Mtc Division, P.H.E Dte. | TSM/009893 | SM/10784 | School | 27/01/2022 | 0 | 102.1 | Yes | 102.1 |  | 26/05/2022 | 1 | 94.19 | MVS
110 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA | TSM/009846 | SM/10826 | New | 17/02/2022 | 448 | 178.67 | Yes | 178.67 |  | 05/08/2022 | 2 | 97.9 | MVS
111 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA | TSM/009845 | SM/10827 | New | 17/02/2022 | 283 | 213.75 | Yes | 213.75 | 28/02/2023 | 26/05/2022 | 2 | 126.58 | MVS
112 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Thulung Gaon | TSM/009512 | SM/10830 | New | 17/02/2022 | 107 | 78.67 | Yes | 78.67 |  | 26/05/2022 | 2 | 76.53 | MVS
113 | KALIMPONG | Neorakhola W/S Mnt. Division | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | TSM/010201 | SM/10820 | New | 16/03/2022 | 48 | 47.33 | Yes | 47.33 |  | 03/02/2023 | 1 | 2.13 | MVS
114 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Pokhriabong Busty 5 No. | TSM/009510 | SM/10832 | New | 17/02/2022 | 85 | 98.99 | Yes | 98.99 |  | 26/05/2022 | 4 | 87.49 | MVS
115 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM MANDIR KHOLA TO TANYANG | TSM/009633 | SM/10751 | New | 17/02/2022 | 195 | 214.24 | Yes | 214.24 |  | 26/05/2022 | 1 | 211.87 | MVS
116 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAIL PROJECT REPORT OF SURUK KHASMAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/011291 | SM/11578 | New | 30/03/2022 | 296 | 393.32 | Yes | 393.32 |  | 01/10/2024 | 2 | 374.22 | MVS
117 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. | TSM/009604 | SM/11315 | Retrofitting | 17/02/2022 | 108 | 21.28 | Yes | 21.28 |  | 30/06/2022 | 2 | 20.51 | MVS
118 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Rajbari under Kurseong-Sub Division, PHED, GTA | TSM/010589 | SM/11328 | Retrofitting | 17/02/2022 | 220 | 27.54 | Yes | 27.54 |  | 30/06/2022 | 2 | 23.48 | MVS
119 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM DALDALEY JHORA TO PASSABONG | TSM/009638 | SM/11342 | New | 17/02/2022 | 65 | 100.52 | Yes | 100.52 |  | 30/06/2022 | 1 | 96 | MVS
120 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012587 | SM/11942 | New | 20/05/2022 | 286 | 233.67 | Yes | 233.67 |  | 28/05/2025 | 3 | 230.5 | MVS
121 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | TSM/010190 | SM/11369 | Health Center | 16/03/2022 | 0 | 17.3 | Yes | 17.3 |  | 12/07/2022 | 3 | 14.55 | MVS
122 | KALIMPONG | Neorakhola W/S Mnt. Division | SUNTALAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/010972 | SM/11377 | New | 30/03/2022 | 55 | 89.16 | Yes | 89.16 |  | 21/02/2024 | 2 | 92.09 | MVS
123 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 07 (Seven) Numbers of Gram Panchayat office in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/010188 | SM/11372 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 16/03/2022 | 7 | 43.43 | Yes | 43.43 |  | 12/07/2022 | 1 | 42.17 | MVS
124 | DARJEELING | Neorakhola W/S Mnt. Division | Augmentation of source and provding FHTC at Bijanbari Bazaar | TSM/009478 | SM/11375 | Augmentation | 17/02/2022 | 50 | 42.06 | Yes | 42.06 | 24/04/2023 | 30/06/2022 | 1 | 35.85 | MVS
125 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Goethals Siding and Upper Kharay Busty with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009523 | SM/11352 | New | 16/03/2022 | 110 | 32.24 | Yes | 32.24 |  | 28/09/2022 | 1 | 31.04 | MVS
126 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Aganwadi Centers in Block- Mirik, under the District of Darjeeling ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/010192 | SM/11361 | Anganwadi | 16/03/2022 | 0 | 106.1 | Yes | 106.1 |  | 05/08/2022 | 1 | 97.78 | MVS
127 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED WATER SUPPLY SCHEME FOR PUDDUNG KHAS MAHAL PWSS,BLOCK : KALIMPONG - I, DISTRICT : KALIMPONG | TSM/011686 | SM/13606 | New | 20/05/2022 | 692 | 427.72 | Yes | 427.72 | 10/05/2023 | 24/07/2023 | 1 | 345.67 | MVS
128 | KALIMPONG | Neorakhola W/S Mnt. Division | SAKAM FOREST & DARJILING HILLDOARS TEA GARDEN PWSS | TSM/014292 | SM/13953 | New | 22/08/2022 | 663 | 882.37 | Yes | 882.37 | 08/12/2022 | 09/02/2023 | 3 | 882.57 | MVS
129 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS | TSM/012040 | SM/14418 | New | 20/05/2022 | 1100 | 1660.67 | Yes | 1660.67 | 30/11/2022 | 29/04/2025 | 4 | 1645.75 | MVS
130 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012881 | SM/14530 | New | 22/08/2022 | 1488 | 1651.09 | Yes | 1651.09 | 22/02/2023 | 05/05/2025 | 3 | 1632.57 | MVS
131 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS | TSM/012043 | SM/15224 | New | 20/05/2022 | 910 | 2098.08 | Yes | 2098.08 | 26/04/2023 | 12/07/2023 | 2 | 2052.67 | MVS
132 | KALIMPONG | Neorakhola W/S Mnt. Division | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | TSM/016058 | SM/15554 | New | 26/09/2022 | 278 | 248.56 | Yes | 248.56 | 24/01/2023 | 03/03/2023 | 2 | 196.17 | MVS
133 | DARJEELING | Neorakhola W/S Mnt. Division | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) | TSM/016192 | SM/15892 | New | 28/12/2022 | 133 | 161.01 | Yes | 161.01 | 08/02/2023 | 28/04/2023 | 2 | 156.08 | MVS
134 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017497 | SM/16512 | New | 28/12/2022 | 136 | 160.61 | Yes | 160.61 | 01/02/2023 | 28/04/2023 | 3 | 158.43 | MVS
135 | DARJEELING | Neorakhola W/S Mnt. Division | DANGIA PIPED WATER SUPPLY SCHEME | TSM/018175 | SM/15896 | New | 28/12/2022 | 484 | 524.85 | Yes | 524.85 | 08/02/2023 | 04/05/2023 | 5 | 508.53 | MVS
136 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015694 | SM/15641 | New | 09/09/2022 | 275 | 214.02 | Yes | 214.02 | 28/10/2022 | 28/02/2023 | 2 | 204.68 | MVS
137 | DARJEELING | Neorakhola W/S Mnt. Division | MAHANADI FOREST PIPED WATER SUPPLY SCHEME. | TSM/018153 | SM/15875 | New | 28/12/2022 | 158 | 217.84 | Yes | 217.84 | 19/06/2024 |  | 0 | 0 | MVS
138 | DARJEELING | Neorakhola W/S Mnt. Division | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/018126 | SM/15876 | New | 28/12/2022 | 1198 | 790.03 | Yes | 790.03 | 12/03/2024 | 18/06/2024 | 3 | 757.82 | MVS
139 | DARJEELING | Neorakhola W/S Mnt. Division | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. | TSM/018101 | SM/15877 | New | 28/12/2022 | 35 | 150.95 | Yes | 150.95 | 08/02/2023 | 15/05/2023 | 3 | 133.5 | MVS
140 | DARJEELING | Neorakhola W/S Mnt. Division | BARBATIA KHASMAHAL PWSS | TSM/018689 | SM/18189 | New | 28/12/2022 | 147 | 404.81 | Yes | 404.81 | 11/02/2023 | 04/05/2023 | 2 | 195.53 | MVS
141 | DARJEELING | Neorakhola W/S Mnt. Division | GINGLAM & GIELIE TEA GARDEN PWSS | TSM/018144 | SM/18721 | New | 28/12/2022 | 908 | 1070.75 | Yes | 1070.75 | 12/03/2024 | 18/06/2024 | 3 | 1069.21 | MVS
142 | DARJEELING | Neorakhola W/S Mnt. Division | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | TSM/010228 | SM/10817 | New | 16/03/2022 | 989 | 379.09 | Yes | 379.09 |  | 02/11/2023 | 4 | 724.02 | MVS
143 | DARJEELING | Neorakhola W/S Mnt. Division | RONGCHONG AND LABDA PWSS | TSM/018103 | SM/18729 | New | 28/12/2022 | 594 | 1302.23 | Yes | 1302.23 | 27/04/2023 | 08/07/2024 | 3 | 1298.98 | MVS
144 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra | TSM/009299 | SM/10561 | Retrofitting | 27/01/2022 | 111 | 16.73 | Yes | 16.73 |  | 10/05/2022 | 2 | 14.47 | MVS
145 | DARJEELING | Neorakhola W/S Mnt. Division | SITTONG KHASMAHAL PWSS | TSM/016146 | SM/18336 | New | 28/12/2022 | 635 | 1082.47 | Yes | 1082.47 | 17/05/2023 | 28/05/2025 | 2 | 1044.2 | MVS
146 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Gitangay under Kurseong-Sub Division, PHED, GTA | TSM/010598 | SM/11337 | Retrofitting | 17/02/2022 | 72 | 14.29 | Yes | 14.29 |  | 30/06/2022 | 2 | 12.31 | MVS
147 | KALIMPONG | Neorakhola W/S Mnt. Division | Retrofitting for FHTC & Improvement of piped water supply scheme for Pedong Bazar & adjoining areas in connection with (JJM & Jal swapno) | TSM/006925 | SM/07872 | Retrofitting | 04/12/2020 | 625 | 72.63 | Yes | 72.63 | 08/01/2024 | 12/10/2020 | 5 | 74.42 | MVS
148 | KALIMPONG | Neorakhola W/S Mnt. Division | Extension of piped water supply scheme to Upper Pedong Lower Goan (St George Primary School) Anganwadi Centre under Pedong G.P and Pagang Gumtaline Anganwadi Centre under Paiyong G.P under Kalimpong lock-II, located within the commanding area of PWSS for | TSM/008121 | SM/09019 | Anganwadi | 19/08/2021 | 0 | 8.21 | Yes | 8.21 |  |  | 0 | 0 | MVS
149 | KALIMPONG | Neorakhola W/S Mnt. Division | Augmentation of Neorakhola Water Supply Scheme for extending FHTC Facility to the enroute habitations under Kalimpong Block-I & Block-II under Neorakhola W/S & Mtc Division ,PHE Dte., Kalimpong | TSM/008351 | SM/10052 | Augmentation | 15/09/2021 | 0 | 4402.74 | Yes | 4402.74 |  | 13/04/2022 | 25 | 1939.94 | MVS
150 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Bokhim khasmahal & paygang khasmahal (PC) under Gitdabling G.P. Kalimpong Blick-II in the District of Kalimpong in connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009883 | SM/10562 | New | 16/03/2022 | 67 | 132.05 | Yes | 132.05 |  | 24/05/2022 | 1 | 126.49 | MVS
151 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION | TSM/009651 | SM/10744 | New | 17/02/2022 | 405 | 225.47 | Yes | 225.47 |  | 25/05/2022 | 1 | 222.09 | MVS
152 | DARJEELING | Neorakhola W/S Mnt. Division | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M | TSM/009891 | SM/10687 | School | 27/01/2022 | 0 | 379.94 | Yes | 379.94 |  | 06/05/2022 | 4 | 540.21 | MVS
153 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. | TSM/009507 | SM/10835 | New | 17/02/2022 | 242 | 218.24 | Yes | 218.24 | 24/04/2023 | 03/08/2023 | 5 | 208.69 | MVS
154 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Noam forest Village under Pokhriabong GP in Gorubathan Block in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009878 | SM/10603 | New | 16/03/2022 | 55 | 41.32 | Yes | 41.32 |  | 26/05/2022 | 2 | 44.53 | MVS
155 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II | TSM/011131 | SM/11383 | Retrofitting | 30/03/2022 | 315 | 65.26 | Yes | 65.26 |  | 28/09/2022 | 3 | 64.2 | MVS
156 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. | TSM/011128 | SM/11385 | Retrofitting | 30/03/2022 | 170 | 47.07 | Yes | 47.07 |  | 12/07/2022 | 3 | 42.2 | MVS
157 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | TSM/011127 | SM/11386 | Retrofitting | 30/03/2022 | 474 | 122.75 | Yes | 122.75 |  | 12/07/2022 | 4 | 123.12 | MVS
158 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | TSM/011126 | SM/11387 | Retrofitting | 30/03/2022 | 145 | 31.49 | Yes | 31.49 |  | 11/05/2023 | 2 | 30.32 | MVS
159 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA | TSM/009856 | SM/10802 | New | 17/02/2022 | 3231 | 228.59 | Yes | 228.59 |  | 01/11/2023 | 3 | 354.6 | MVS
160 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 8 12 AND KHOTILINE UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009667 | SM/10696 | New | 17/02/2022 | 135 | 115.09 | Yes | 115.09 |  | 25/05/2022 | 2 | 107.89 | MVS
161 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009665 | SM/10697 | New | 17/02/2022 | 100 | 126.09 | Yes | 126.09 |  | 01/08/2022 | 1 | 120.9 | MVS
162 | KALIMPONG | Neorakhola W/S Mnt. Division | Augmentation of Lolaygoan Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission (JJM) under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009871 | SM/10705 | Augmentation | 27/01/2022 | 105 | 99.21 | Yes | 99.21 |  | 13/04/2022 | 1 | 95.54 | MVS
163 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | TSM/009890 | SM/10814 | School | 27/01/2022 | 0 | 263.53 | Yes | 263.53 |  | 01/08/2024 | 12 | 8.97 | MVS
164 | DARJEELING | Neorakhola W/S Mnt. Division | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | TSM/010227 | SM/10818 | New | 16/03/2022 | 684 | 299.8 | Yes | 299.8 |  | 02/11/2023 | 6 | 15.22 | MVS
165 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram Tea Estate ( Dilaram Bazar habitation ) under Kurseong Sub-Division PHED, GTA. | TSM/009601 | SM/11318 | Retrofitting | 17/02/2022 | 65 | 7.31 | Yes | 7.31 |  | 30/06/2022 | 2 | 6.36 | MVS
166 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. | TSM/009598 | SM/11321 | Retrofitting | 17/02/2022 | 193 | 17.13 | Yes | 17.13 |  | 30/06/2022 | 2 | 15.7 | MVS
167 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div | TSM/009596 | SM/11323 | Retrofitting | 17/02/2022 | 270 | 22.61 | Yes | 22.61 |  | 30/06/2022 | 2 | 21.71 | MVS
168 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA | TSM/010588 | SM/11327 | Retrofitting | 17/02/2022 | 135 | 15.46 | Yes | 15.46 |  | 30/06/2022 | 2 | 13.42 | MVS
169 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SINGI KAHSMAHAL PWSS IN KALIMPONG-I BLOCK | TSM/012042 | SM/12181 | New | 20/05/2022 | 514 | 695.67 | Yes | 695.67 |  | 17/10/2023 | 2 | 662.05 | MVS
170 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Bagmara Busty under Kurseong-Sub Division, PHED, GTA | TSM/010596 | SM/11335 | Retrofitting | 17/02/2022 | 58 | 12.77 | Yes | 12.77 |  | 05/08/2022 | 2 | 9.52 | MVS
171 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for 14th Mile and Pagla Jhora Busty under Kurseong-Sub Division, PHED, GTA | TSM/010597 | SM/11336 | Retrofitting | 17/02/2022 | 102 | 13.82 | Yes | 13.82 |  | 30/06/2022 | 2 | 11.49 | MVS
172 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011758 | SM/11954 | New | 20/05/2022 | 215 | 333.26 | Yes | 333.26 |  | 18/10/2022 | 3 | 321.5 | MVS
173 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 02 numbers of Health centers, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division, PHE Directorate kalimpong. | TSM/010270 | SM/11367 | Health Center | 16/03/2022 | 0 | 15 | Yes | 15 |  | 26/05/2022 | 4 | 12.27 | MVS
174 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009525 | SM/11351 | New | 16/03/2022 | 35 | 18.6 | Yes | 18.6 |  | 12/07/2022 | 3 | 19.78 | MVS
175 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | TSM/011757 | SM/12128 | New | 20/05/2022 | 759 | 990.4 | Yes | 990.4 |  | 30/03/2023 | 4 | 993.32 | MVS
176 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 87 Nos of School under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong. | TSM/010272 | SM/11355 | School | 16/03/2022 | 202 | 273.3 | Yes | 273.3 |  | 12/07/2022 | 1 | 232.24 | MVS
177 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 101 Nos of Aganwadi under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, kalimpong PHE Directorate | TSM/010273 | SM/11360 | Anganwadi | 16/03/2022 | 0 | 397.94 | Yes | 397.94 |  | 12/07/2022 | 1 | 310.44 | MVS
178 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source for 16 Numbers of Aganwadi Centers in Block- Kurseong, under the District of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte,. | TSM/010189 | SM/11362 | Anganwadi | 16/03/2022 | 0 | 38.79 | Yes | 38.79 |  | 12/07/2022 | 1 | 37.03 | MVS
179 | KALIMPONG | Neorakhola W/S Mnt. Division | UPPER FAGU PIPED WATER SUPPLY SCHEME. | TSM/012803 | SM/13954 | New | 22/08/2022 | 924 | 819.76 | Yes | 819.76 | 22/02/2024 | 18/07/2023 | 2 | 807.55 | MVS
180 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012887 | SM/13957 | New | 22/08/2022 | 175 | 451.2 | Yes | 451.2 | 02/12/2022 | 20/01/2023 | 2 | 391.94 | MVS
181 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013038 | SM/13958 | New | 22/08/2022 | 170 | 330.4 | Yes | 330.4 |  | 23/12/2022 | 2 | 307.43 | MVS
182 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. | TSM/012820 | SM/12983 | New | 20/05/2022 | 1341 | 1217.59 | Yes | 1217.59 | 02/12/2022 | 08/07/2024 | 5 | 1222.2 | MVS
183 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017393 | SM/15042 | New | 30/09/2022 | 161 | 213.24 | Yes | 213.24 | 02/12/2022 | 09/02/2023 | 3 | 196.09 | MVS
184 | KALIMPONG | Neorakhola W/S Mnt. Division | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER KALIMPONG G.P, BLOCK:-KALIMPONG-I, DISTRICT:-KALIMPONG | TSM/017437 | SM/16231 | New | 28/12/2022 | 1175 | 944.04 | Yes | 944.04 | 01/02/2023 | 26/05/2023 | 2 | 855.25 | MVS
185 | DARJEELING | Neorakhola W/S Mnt. Division | TUKDAH FOREST PIPED WATER SUPPLY SCHEME | TSM/017294 | SM/16157 | New | 28/12/2022 | 125 | 112.01 | Yes | 112.01 | 08/02/2023 | 24/09/2024 | 2 | 7.77 | MVS
186 | DARJEELING | Neorakhola W/S Mnt. Division | KOLBONG KHASMAHAL PWSS | TSM/014695 | SM/15840 | New | 09/09/2022 | 143 | 214.49 | Yes | 214.49 | 24/01/2023 | 04/05/2023 | 2 | 213.09 | MVS
187 | DARJEELING | Neorakhola W/S Mnt. Division | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. | TSM/016115 | SM/15909 | New | 28/12/2022 | 120 | 304.67 | Yes | 304.67 | 08/02/2023 | 05/06/2023 | 2 | 279.12 | MVS
188 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Maharani Tea Garden | TSM/012916 | SM/16474 | New | 30/09/2022 | 488 | 465.91 | Yes | 465.91 | 25/11/2022 | 05/05/2025 | 3 | 459.74 | MVS
189 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017347 | SM/16514 | New | 28/12/2022 | 538 | 896.34 | Yes | 896.34 | 01/02/2023 | 05/06/2023 | 2 | 879.3 | MVS
190 | DARJEELING | Neorakhola W/S Mnt. Division | BIJANBARI PIPED WATER SUPPLY SCHEME. | TSM/019202 | SM/15869 | New | 28/12/2022 | 298 | 357.73 | Yes | 357.73 | 01/02/2023 | 27/04/2023 | 2 | 340.98 | MVS
191 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017366 | SM/16234 | New | 28/12/2022 | 47 | 55.28 | Yes | 55.28 | 01/02/2023 | 12/07/2023 | 2 | 52.88 | MVS
192 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHASMAHAL (PART) UNDER KAGAY G.P, BLOCK:KALIMPONG - II, DISTRICT:KALIMPONG | TSM/013305 | SM/15643 | New | 09/09/2022 | 169 | 300.21 | Yes | 300.21 |  | 28/02/2023 | 2 | 284.6 | MVS
193 | DARJEELING | Neorakhola W/S Mnt. Division | SINGALILA FOREST PWSS | TSM/019228 | SM/16771 | New | 28/12/2022 | 76 | 398.31 | Yes | 398.31 | 01/02/2023 | 27/04/2023 | 4 | 394.84 | MVS
194 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAIL PROJECT REPORT OF PALLA KHASMAHAL PIPED WATER SUPPLY SCHEME (PWSS) UNDER LOLAY G.P, BLOCK:-KALIMPONG-II, P.S:-KALIMPONG, DISTRICT:KALIMPONG | TSM/011490 | SM/15646 | New | 09/09/2022 | 171 | 226.84 | Yes | 226.84 | 02/12/2022 | 03/09/2024 | 4 | 228.92 | MVS
195 | KALIMPONG | Neorakhola W/S Mnt. Division | DALINGKOT FOREST & DALINGMA KHASMAHAL PWSS | TSM/013403 | SM/19112 | New | 15/07/2022 | 784 | 1414.95 | Yes | 1414.95 | 14/12/2022 | 03/01/2024 | 3 | 1408.44 | MVS
196 | KALIMPONG | Neorakhola W/S Mnt. Division | RANGO FOREST PWSS | TSM/013119 | SM/18823 | New | 15/07/2022 | 1892 | 1664.29 | Yes | 1664.29 | 24/01/2023 | 21/09/2023 | 2 | 1661.53 | MVS
197 | DARJEELING | Neorakhola W/S Mnt. Division | HUM TUKDAH KHASMAHAL PWSS | TSM/018171 | SM/18316 | New | 28/12/2022 | 1616 | 1456.69 | Yes | 1456.69 | 11/02/2023 | 16/04/2025 | 3 | 228.9 | MVS
198 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM KAMZER KHOLA TO LOWER LOLAY | TSM/009628 | SM/10754 | New | 17/02/2022 | 160 | 176.39 | Yes | 176.39 |  | 26/05/2022 | 1 | 174.61 | MVS
199 | KALIMPONG | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL PWSS IN KALIMPONG II BLOCK UNDER KALIMPONG DISTRICT. | TSM/012889 | SM/18589 | New | 28/12/2022 | 1130 | 1104.14 | Yes | 1104.14 | 11/02/2023 |  | 0 | 0 | MVS
200 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth | TSM/009297 | SM/10766 | Retrofitting | 27/01/2022 | 35 | 7.21 | Yes | 7.21 |  | 25/05/2022 | 2 | 6.44 | MVS
201 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM KHARKHOLA TO LOWER REON | TSM/009617 | SM/10756 | New | 17/02/2022 | 102 | 105.07 | Yes | 105.07 |  | 25/05/2022 | 1 | 101.69 | MVS
202 | DARJEELING | Neorakhola W/S Mnt. Division | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING | TSM/010472 | SM/10788 | New | 16/03/2022 | 1310 | 244.94 | Yes | 244.94 |  | 08/07/2024 | 9 | 252.93 | MVS
203 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009662 | SM/10695 | New | 17/02/2022 | 136 | 138.07 | Yes | 138.07 |  | 26/05/2022 | 1 | 133.86 | MVS
204 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TO BURMAIK UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009654 | SM/10699 | New | 17/02/2022 | 350 | 152.76 | Yes | 152.76 |  | 25/05/2022 | 1 | 147.75 | MVS
205 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme For Jhepi & Gurdung. | TSM/009509 | SM/10833 | New | 17/02/2022 | 309 | 318.71 | Yes | 318.71 | 24/04/2023 | 30/06/2022 | 4 | 308.84 | MVS
206 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision of Drinking water from spring water source to sourceless schools under different Blocks viz Mirik,Kurseong,Darjeeling-Pulbazar,Jorebunglow-Sukhiapokhri & Rangli-Rangliot in the District of Darjeeling Under Neorakhola Wate | TSM/009457 | SM/10239 | School | 16/12/2021 | 0 | 389.69 | Yes | 389.69 |  | 28/02/2022 | 2 | 229.2 | MVS
207 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar | TSM/011134 | SM/11382 | Retrofitting | 30/03/2022 | 250 | 54.99 | Yes | 54.99 |  | 12/07/2022 | 2 | 50.37 | MVS
208 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) | TSM/009473 | SM/10773 | Retrofitting | 27/01/2022 | 139 | 21.6 | Yes | 21.6 |  | 24/05/2022 | 3 | 19.92 | MVS
209 | DARJEELING | Neorakhola W/S Mnt. Division | Creation of gravity based provision of drinking water from spring water source of anganwadi(119 nos) centers under Darjeeling pulbazar block in the district of Darjeeling under Neorakhola water supply & maintenance division, P.H.E. Directorate | TSM/009892 | SM/10796 | Anganwadi | 27/01/2022 | 0 | 429.36 | Yes | 429.36 |  | 06/05/2022 | 1 | 334.99 | MVS
210 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER SANGSEY G.P BLOCK-II, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009650 | SM/10702 | New | 17/02/2022 | 131 | 113.56 | Yes | 113.56 |  | 13/05/2022 | 1 | 100.81 | MVS
211 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA | TSM/009848 | SM/10810 | New | 17/02/2022 | 233 | 151.73 | Yes | 151.73 |  | 26/05/2022 | 1 | 83.04 | MVS
212 | DARJEELING | Neorakhola W/S Mnt. Division | Nipania Piped water Supply Scheme. | TSM/010842 | SM/10815 | New | 16/03/2022 | 1314 | 461.01 | Yes | 461.01 |  | 02/11/2023 | 5 | 1013.55 | MVS
213 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional household tap connection with pipeline retrofitting for PWS scheme at Lingsaybong, Lodhuma-II | TSM/009471 | SM/10822 | Retrofitting | 27/01/2022 | 28 | 19.74 | Yes | 19.74 |  | 26/05/2022 | 2 | 16.77 | MVS
214 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY | TSM/009632 | SM/10752 | New | 17/02/2022 | 72 | 75.91 | Yes | 75.91 |  | 30/06/2022 | 1 | 73.59 | MVS
215 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011754 | SM/12179 | New | 20/05/2022 | 447 | 663.63 | Yes | 663.63 |  | 05/05/2025 | 3 | 659.3 | MVS
216 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis | TSM/009597 | SM/11322 | Retrofitting | 17/02/2022 | 174 | 14.74 | Yes | 14.74 |  | 30/06/2022 | 2 | 13.04 | MVS
217 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Kalimati Busty under Kurseong-Sub Division, PHED, GTA | TSM/010591 | SM/11330 | Retrofitting | 17/02/2022 | 56 | 13.49 | Yes | 13.49 |  | 30/06/2022 | 2 | 12.48 | MVS
218 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional households Tap connection under JSP Programme for PWS Scheme Soureni Bazar | TSM/009309 | SM/11306 | Retrofitting | 27/01/2022 | 166 | 23.6 | Yes | 23.6 |  | 30/06/2022 | 1 | 22.21 | MVS
219 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution networks retrofitting under JSP Programme for PWS Scheme for Chowandhura | TSM/009303 | SM/11311 | Retrofitting | 27/01/2022 | 41 | 11.81 | Yes | 11.81 |  | 30/06/2022 | 1 | 11.04 | MVS
220 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM SAWRENI KHOLA TO NIM BUSTY | TSM/009666 | SM/11340 | New | 17/02/2022 | 280 | 220.09 | Yes | 220.09 |  | 30/06/2022 | 1 | 174.02 | MVS
221 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM DEORALI KHOLA TO PAKANG | TSM/009653 | SM/11341 | New | 17/02/2022 | 150 | 117.19 | Yes | 117.19 |  | 30/06/2022 | 1 | 113.45 | MVS
222 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING | TSM/011927 | SM/11856 | New | 20/05/2022 | 100 | 290.75 | Yes | 290.75 | 26/05/2023 | 12/07/2023 | 3 | 287.72 | MVS
223 | DARJEELING | Neorakhola W/S Mnt. Division | Augmentation of source for lower Takbia | TSM/009479 | SM/11374 | Augmentation | 17/02/2022 | 0 | 28.05 | Yes | 28.05 |  | 30/08/2024 | 2 | 24.72 | MVS
224 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011831 | SM/11891 | New | 20/05/2022 | 759 | 865.61 | Yes | 865.61 |  | 29/09/2022 | 3 | 860.97 | MVS
225 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009535 | SM/11345 | New | 16/03/2022 | 52 | 24.77 | Yes | 24.77 |  | 12/07/2022 | 2 | 23.93 | MVS
226 | KALIMPONG | Neorakhola W/S Mnt. Division | AMBEOK TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/012753 | SM/13610 | New | 15/07/2022 | 309 | 260.67 | Yes | 260.67 |  | 20/01/2023 | 2 | 257.62 | MVS
227 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR TURZUM FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/014805 | SM/13621 | New | 22/08/2022 | 124 | 236.28 | Yes | 236.28 | 14/10/2022 | 28/11/2024 | 4 | 255.69 | MVS
228 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FORPROPOSED GRAVETY BASED & PUMPING BASEDPIPED WATER SUPPLY SCHEME FOR BONGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT: Kalimpong | TSM/011801 | SM/13604 | New | 20/05/2022 | 1015 | 564.2 | Yes | 564.2 |  | 21/02/2024 | 6 | 567.85 | MVS
229 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/015166 | SM/14529 | New | 22/08/2022 | 2710 | 2347.04 | Yes | 2347.04 | 02/01/2025 | 30/07/2024 | 6 | 2063.47 | MVS
230 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | TSM/014847 | SM/14532 | New | 22/08/2022 | 1060 | 1462.38 | Yes | 1462.38 | 24/02/2023 | 29/05/2023 | 3 | 1408.05 | MVS
231 | KALIMPONG | Neorakhola W/S Mnt. Division | PANKHASARI KHASMAHAL PWSS | TSM/014359 | SM/14170 | New | 22/08/2022 | 666 | 1201.07 | Yes | 1201.07 | 23/11/2023 | 06/02/2023 | 2 | 1197.7 | MVS
232 | DARJEELING | Neorakhola W/S Mnt. Division | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME | TSM/014898 | SM/16160 | New | 28/12/2022 | 196 | 237.91 | Yes | 237.91 | 08/02/2023 | 28/04/2023 | 2 | 197.63 | MVS
233 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/017463 | SM/15884 | New | 28/12/2022 | 644 | 710.16 | Yes | 710.16 | 11/02/2023 | 29/04/2025 | 3 | 1025.89 | MVS
234 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/015717 | SM/15640 | New | 09/09/2022 | 685 | 497.43 | Yes | 497.43 | 02/12/2022 | 28/08/2024 | 5 | 487.78 | MVS
235 | DARJEELING | Neorakhola W/S Mnt. Division | GOKE PIPED WATER SUPPLY SCHEME. | TSM/018207 | SM/15873 | New | 28/12/2022 | 1083 | 932.73 | Yes | 932.73 | 26/09/2024 | 17/12/2024 | 3 | 912.65 | MVS
236 | DARJEELING | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013286 | SM/16534 | New | 22/08/2022 | 389 | 1531.5 | Yes | 1531.5 | 22/02/2023 | 09/04/2025 | 2 | 94.02 | MVS
237 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District | TSM/014857 | SM/16535 | New | 22/08/2022 | 1196 | 1055.89 | Yes | 1055.89 | 30/11/2022 | 27/04/2023 | 2 | 1047.97 | MVS
238 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL (PART) UNDER KAGEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | TSM/017340 | SM/16235 | New | 28/12/2022 | 199 | 233.82 | Yes | 233.82 | 01/02/2023 | 12/07/2023 | 2 | 209.91 | MVS
239 | DARJEELING | Neorakhola W/S Mnt. Division | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. | TSM/015037 | SM/16238 | New | 28/12/2022 | 43 | 133.16 | Yes | 133.16 | 08/02/2023 | 17/07/2023 | 2 | 129 | MVS
240 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT | TSM/016292 | SM/16627 | New | 26/09/2022 | 854 | 954.9 | Yes | 954.9 | 02/12/2022 | 29/04/2025 | 3 | 944.22 | MVS
241 | DARJEELING | Neorakhola W/S Mnt. Division | MAHANADI FOREST PIPED WATER SUPPLY SCHEME | TSM/017745 | SM/15648 | New | 30/09/2022 | 191 | 230 | Yes | 230 | 25/04/2023 | 08/07/2024 | 2 | 173.05 | MVS
242 | DARJEELING | Neorakhola W/S Mnt. Division | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/017741 | SM/15655 | New | 30/09/2022 | 697 | 743.37 | Yes | 743.37 | 23/12/2022 | 07/06/2024 | 3 | 733.47 | MVS
243 | DARJEELING | Neorakhola W/S Mnt. Division | SAMALBONG PWSS | TSM/017243 | SM/18722 | New | 28/12/2022 | 544 | 1305.89 | Yes | 1305.89 | 09/02/2023 | 29/04/2025 | 2 | 101.82 | MVS
244 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS | TSM/012053 | SM/11854 | New | 20/05/2022 | 716 | 942.58 | Yes | 942.58 |  | 29/09/2022 | 3 | 935.51 | MVS
245 | KALIMPONG | Neorakhola W/S Mnt. Division | PATEN GODAK KHASMAHAL PWSS | TSM/013333 | SM/18255 | New | 15/07/2022 | 874 | 1128.06 | Yes | 1128.06 |  | 17/07/2023 | 2 | 1121.68 | MVS
246 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/018540 | SM/18601 | New | 28/12/2022 | 2294 | 2696.35 | Yes | 2696.35 | 26/09/2024 | 03/08/2023 | 2 | 2575.57 | MVS
247 | DARJEELING | Neorakhola W/S Mnt. Division | DAWAIPANI & TUKDAH TEA GARDEN PWSS | TSM/018050 | SM/18752 | New | 28/12/2022 | 1324 | 1141.66 | Yes | 1141.66 | 08/02/2023 | 05/05/2025 | 2 | 138.71 | MVS
248 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retroffting for Piped water supply scheme at Ramam Forest Village | TSM/009295 | SM/10764 | Retrofitting | 27/01/2022 | 60 | 21.15 | Yes | 21.15 |  | 24/05/2022 | 2 | 20.72 | MVS
249 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta | TSM/009301 | SM/10768 | Retrofitting | 27/01/2022 | 127 | 25.05 | Yes | 25.05 |  | 24/05/2022 | 2 | 25.02 | MVS
250 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting for Piped water supply scheme at Upper Lamagoan | TSM/009097 | SM/10769 | Retrofitting | 27/01/2022 | 76 | 22.77 | Yes | 22.77 |  | 25/05/2022 | 2 | 19.02 | MVS
251 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village | TSM/009469 | SM/10770 | Retrofitting | 27/01/2022 | 39 | 21.64 | Yes | 21.64 |  | 24/05/2022 | 2 | 16.98 | MVS
252 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM PAREN KHOLA TO RANGPO DIVISON | TSM/009645 | SM/10746 | New | 17/02/2022 | 205 | 194.83 | Yes | 194.83 |  | 25/05/2022 | 2 | 191.35 | MVS
253 | DARJEELING | Neorakhola W/S Mnt. Division | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. | TSM/010476 | SM/10790 | New | 16/03/2022 | 129 | 100.33 | Yes | 100.33 |  | 27/07/2023 | 2 | 1.9 | MVS
254 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER KALIMPONG GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009635 | SM/10700 | New | 17/02/2022 | 242 | 173.31 | Yes | 173.31 |  | 24/05/2022 | 1 | 164.25 | MVS
255 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM SETHI KHOLA TO UPPER KHANI UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009626 | SM/10701 | New | 17/02/2022 | 90 | 114.57 | Yes | 114.57 |  | 30/06/2022 | 1 | 104.88 | MVS
256 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Daragoan Lekharga. | TSM/009505 | SM/10836 | New | 17/02/2022 | 84 | 67.94 | Yes | 67.94 |  | 03/07/2025 | 4 | 66.02 | MVS
257 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal jeewan Mission/Jal swapno Mission for balance household at Fatingtar | TSM/011130 | SM/11384 | Retrofitting | 30/03/2022 | 95 | 27.28 | Yes | 27.28 |  | 27/07/2023 | 1 | 25.37 | MVS
258 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar | TSM/011124 | SM/11392 | Retrofitting | 30/03/2022 | 950 | 180.91 | Yes | 180.91 |  | 12/07/2022 | 3 | 162.31 | MVS
259 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011215 | SM/11395 | New | 30/03/2022 | 360 | 306.47 | Yes | 306.47 |  | 04/05/2023 | 2 | 268.66 | MVS
260 | DARJEELING | Neorakhola W/S Mnt. Division | Choongtoong & Lizahill Tea Garden water supply scheme | TSM/009503 | SM/12269 | New | 17/02/2022 | 2635 | 1242.31 | Yes | 1242.31 |  | 31/08/2023 | 4 | 1237.7 | MVS
261 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA | TSM/009854 | SM/10804 | New | 17/02/2022 | 588 | 123.59 | Yes | 123.59 |  | 23/12/2022 | 2 | 76.49 | MVS
262 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA | TSM/009849 | SM/10809 | New | 17/02/2022 | 99 | 115.19 | Yes | 115.19 |  | 10/01/2023 | 2 | 67.61 | MVS
263 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Singbuli factory gaon | TSM/009511 | SM/10831 | New | 17/02/2022 | 211 | 77.24 | Yes | 77.24 |  | 26/05/2022 | 2 | 64.49 | MVS
264 | DARJEELING | Neorakhola W/S Mnt. Division | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | TSM/010207 | SM/10819 | New | 16/03/2022 | 298 | 150.71 | Yes | 150.71 |  | 27/07/2023 | 3 | 0.27 | MVS
265 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011755 | SM/12178 | New | 20/05/2022 | 285 | 595.74 | Yes | 595.74 |  | 14/10/2022 | 3 | 590.98 | MVS
266 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | TSM/009595 | SM/11324 | Retrofitting | 17/02/2022 | 425 | 36.13 | Yes | 36.13 |  | 30/06/2022 | 2 | 30.3 | MVS
267 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail | TSM/009308 | SM/11305 | Retrofitting | 27/01/2022 | 60 | 14.68 | Yes | 14.68 |  | 30/06/2022 | 2 | 13.58 | MVS
268 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Bada kothi | TSM/009482 | SM/11310 | Retrofitting | 27/01/2022 | 37 | 4.51 | Yes | 4.51 |  | 30/06/2022 | 1 | 3.78 | MVS
269 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA | TSM/010592 | SM/11331 | Retrofitting | 17/02/2022 | 310 | 31.31 | Yes | 31.31 |  | 30/06/2022 | 2 | 28.31 | MVS
270 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sivitar under Kurseong-Sub Division, PHED, GTA | TSM/010594 | SM/11333 | Retrofitting | 17/02/2022 | 110 | 26.69 | Yes | 26.69 |  | 30/06/2022 | 2 | 24.69 | MVS
271 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Singtam Tea Garden | TSM/009502 | SM/11338 | New | 17/02/2022 | 485 | 176.87 | Yes | 176.87 | 24/01/2023 | 12/07/2023 | 2 | 176.08 | MVS
272 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based provision of Drinking water from spring water source for 12 Numbers of Gram panchayat Buildings in Kalimpong Block- I under the District of kalimpong , under Neorakhola water supply Division, kalimpong PHE Dte. | TSM/010266 | SM/11371 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 16/03/2022 | 12 | 39.73 | Yes | 39.73 |  | 12/07/2022 | 1 | 39.26 | MVS
273 | KALIMPONG | Neorakhola W/S Mnt. Division | BINDU PIPED WATER SUPPLY SCHEME | TSM/013475 | SM/13622 | New | 22/08/2022 | 174 | 130.17 | Yes | 130.17 |  | 20/01/2023 | 2 | 123.46 | MVS
274 | KALIMPONG | Neorakhola W/S Mnt. Division | SURUK PIPED WATER SUPPLY SCHEME | TSM/012709 | SM/13607 | New | 05/07/2022 | 338 | 643.2 | Yes | 643.2 | 08/12/2022 | 09/02/2023 | 3 | 640.68 | MVS
275 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009534 | SM/11346 | New | 16/03/2022 | 45 | 21.35 | Yes | 21.35 |  | 12/07/2022 | 2 | 20.32 | MVS
276 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009527 | SM/11349 | New | 16/03/2022 | 175 | 79.79 | Yes | 79.79 | 03/03/2022 | 23/08/2023 | 2 | 78.19 | MVS
277 | KALIMPONG | Neorakhola W/S Mnt. Division | SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. | TSM/013023 | SM/13613 | New | 15/07/2022 | 303 | 351.35 | Yes | 351.35 | 24/01/2023 | 23/08/2023 | 3 | 359.16 | MVS
278 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. | TSM/012507 | SM/11952 | New | 20/05/2022 | 898 | 884.34 | Yes | 884.34 |  | 03/11/2022 | 3 | 884.41 | MVS
279 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | TSM/010269 | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 16/03/2022 | 6 | 28.59 | Yes | 28.59 |  | 12/07/2022 | 6 | 23.59 | MVS
280 | KALIMPONG | Neorakhola W/S Mnt. Division | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | TSM/011843 | SM/13612 | New | 15/07/2022 | 245 | 290.97 | Yes | 290.97 | 19/10/2022 | 05/06/2023 | 2 | 280.71 | MVS
281 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/017375 | SM/16233 | New | 28/12/2022 | 700 | 963.91 | Yes | 963.91 | 01/02/2023 | 13/06/2025 | 3 | 954.63 | MVS
282 | DARJEELING | Neorakhola W/S Mnt. Division | PANTHABARI FOREST Piped Water Supply Scheme | TSM/018085 | SM/16143 | New | 28/12/2022 | 134 | 142.59 | Yes | 142.59 | 11/02/2023 | 12/01/2024 | 4 | 94.5 | MVS
283 | DARJEELING | Neorakhola W/S Mnt. Division | HATTA PIPED WATER SUPPLY SCHEME. | TSM/017468 | SM/15883 | New | 28/12/2022 | 134 | 329.63 | Yes | 329.63 | 08/02/2023 | 05/06/2023 | 2 | 279.65 | MVS
284 | DARJEELING | Neorakhola W/S Mnt. Division | MANEDARA PIPED WATER SUPPLY SCHEME. | TSM/017455 | SM/15885 | New | 28/12/2022 | 347 | 485.98 | Yes | 485.98 | 12/03/2024 | 18/06/2024 | 3 | 448.77 | MVS
285 | DARJEELING | Neorakhola W/S Mnt. Division | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme | TSM/014789 | SM/16385 | New | 09/09/2022 | 445 | 556.38 | Yes | 556.38 | 16/02/2024 | 12/07/2023 | 2 | 533.79 | MVS
286 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/016235 | SM/16628 | New | 26/09/2022 | 643 | 870.77 | Yes | 870.77 | 02/12/2022 | 23/03/2024 | 3 | 852.87 | MVS
287 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (GUNAWAR) (PART) | TSM/014157 | SM/15649 | New | 30/09/2022 | 348 | 611 | Yes | 611 | 17/07/2023 | 17/10/2023 | 1 | 605.39 | MVS
288 | KALIMPONG | Neorakhola W/S Mnt. Division | NIM KHASMAHAL & PHASINTING KHASMAL PWSS | TSM/011586 | SM/18415 | New | 05/07/2022 | 475 | 1069.7 | Yes | 1069.7 | 24/01/2023 | 17/08/2023 | 2 | 957.24 | MVS
289 | DARJEELING | Neorakhola W/S Mnt. Division | BADAMTAM TEA GARDEN PWSS | TSM/018945 | SM/18725 | New | 28/12/2022 | 986 | 1124.76 | Yes | 1124.76 | 12/12/2023 | 05/06/2025 | 4 | 1123.59 | MVS
290 | DARJEELING | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/016215 | SM/18317 | New | 26/09/2022 | 955 | 1246.59 | Yes | 1246.59 | 26/09/2024 | 26/02/2024 | 5 | 1226.06 | MVS
291 | DARJEELING | Neorakhola W/S Mnt. Division | LEBONG & MINERAL TEA GARDEN PWSS | TSM/019193 | SM/18726 | New | 28/12/2022 | 1242 | 1123.93 | Yes | 1123.93 | 12/03/2024 | 18/06/2024 | 4 | 1122.53 | MVS
292 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANGARJUNG TEA GARDEN & OTHER 3 VILLAGES PWSS(MVS),BLOCK: JORE BUNGALOW-SUKHIAPOKHRI,DISTRICT: DARJEELING | TSM/021465 | SM/19177 | New | 10/03/2023 | 6430 | 9214.38 | Yes | 9214.38 | 06/02/2024 | 09/09/2024 | 1 | 8505.63 | MVS
293 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division | TSM/009298 | SM/10767 | Retrofitting | 27/01/2022 | 130 | 16.01 | Yes | 16.01 |  | 24/05/2022 | 2 | 14.84 | MVS
294 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village | TSM/009470 | SM/10771 | Retrofitting | 27/01/2022 | 23 | 14.21 | Yes | 14.21 |  | 24/05/2022 | 4 | 14.18 | MVS
295 | KALIMPONG | Neorakhola W/S Mnt. Division | Proposed surface water based Nabgaon Khasmahal PWSS to accommodate FHTC in Kalimpong-I Block within Kalimpong District under Neorakhola W/S & Mtc Division P.H.E Dte. | TSM/010521 | SM/10787 | New | 16/03/2022 | 613 | 975.33 | Yes | 975.33 | 22/07/2024 | 29/11/2024 | 2 | 957.22 | MVS
296 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM DHOBI KHOLA TO LOWER DALEP | TSM/009627 | SM/10755 | New | 17/02/2022 | 160 | 201.1 | Yes | 201.1 |  | 25/05/2022 | 1 | 199.1 | MVS
297 | KALIMPONG | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source to sourceless schoolsunder Kalimpong Block I , Kalimpong Block II &Gorubathan Block in the District of Kalimpong Under Neorakhola water Suppply & Mtc. Division ,Kalimpong PHE Dte | TSM/009316 | SM/10214 | School | 16/12/2021 | 0 | 753.18 | Yes | 753.18 |  | 28/02/2022 | 10 | 798.32 | MVS
298 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for chumang forest under Gitdabling G.P Kalimpong Block-II, Dist- Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009885 | SM/10599 | New | 16/03/2022 | 28 | 67.06 | Yes | 67.06 |  | 26/05/2022 | 1 | 64.02 | MVS
299 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Dalapchand slip reserve forest Village under Dalapchand GP in Kalimpong Block II in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009877 | SM/10601 | New | 16/03/2022 | 10 | 9.66 | Yes | 9.66 |  | 26/05/2022 | 2 | 9.48 | MVS
300 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Paren forest Village under Paten Godak GP in Gorubathan Block in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009881 | SM/10576 | New | 16/03/2022 | 45 | 49.14 | Yes | 49.14 |  | 09/11/2023 | 2 | 52.38 | MVS
301 | KALIMPONG | Neorakhola W/S Mnt. Division | Chunabhatti Bazar D.I.F & Lish Forest Piped Water Supply Scheme. | TSM/010520 | SM/10729 | New | 16/03/2022 | 197 | 136.35 | Yes | 136.35 | 09/11/2023 | 21/12/2022 | 5 | 115.17 | MVS
302 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Icha forest Village under Sangsey GP Kalimpong Block-II, in the District of Kalimpong in connecion with implementation under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009876 | SM/10624 | New | 16/03/2022 | 42 | 40.13 | Yes | 40.13 |  | 25/05/2022 | 1 | 38.89 | MVS
303 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection under Jal Jeewan mission / Jal sapno Programme from existing scheme at 3rd mile , Simkuna | TSM/011136 | SM/11380 | Retrofitting | 30/03/2022 | 45 | 10.66 | Yes | 10.66 |  | 12/07/2022 | 2 | 9.57 | MVS
304 | DARJEELING | Neorakhola W/S Mnt. Division | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | TSM/011135 | SM/11381 | Retrofitting | 30/03/2022 | 520 | 76.94 | Yes | 76.94 | 24/04/2023 | 12/07/2022 | 4 | 76.68 | MVS
305 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under Jal Jeewan Mission/ Jal Swapno Programme at New Fallodi Tea Garden ( Mandir Goan) | TSM/011140 | SM/11390 | Retrofitting | 30/03/2022 | 45 | 10.66 | Yes | 10.66 |  | 12/07/2022 | 1 | 9.11 | MVS
306 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA | TSM/011216 | SM/11399 | New | 30/03/2022 | 446 | 562.88 | Yes | 562.88 |  | 04/05/2023 | 3 | 503.52 | MVS
307 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED SURFACE WATER BASED NIMBONG KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010482 | SM/10793 | New | 16/03/2022 | 342 | 731.44 | Yes | 731.44 | 23/11/2023 | 27/05/2025 | 3 | 724.32 | MVS
308 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA | TSM/009858 | SM/10800 | New | 17/02/2022 | 233 | 143.69 | Yes | 143.69 |  | 09/04/2025 | 3 | 106.71 | MVS
309 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA | TSM/009857 | SM/10801 | New | 17/02/2022 | 233 | 163.3 | Yes | 163.3 |  | 05/08/2022 | 2 | 100.88 | MVS
310 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P BLOCK-I, KALIMPONG UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009652 | SM/10703 | New | 17/02/2022 | 407 | 286.37 | Yes | 286.37 |  | 09/04/2025 | 2 | 285.38 | MVS
311 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Mangber forest Village under Teesta GP in Kalimpong Block-I in connection with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009879 | SM/10739 | New | 16/03/2022 | 7 | 5.37 | Yes | 5.37 |  | 26/05/2022 | 1 | 4.86 | MVS
312 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | TSM/009663 | SM/10741 | New | 17/02/2022 | 80 | 92.28 | Yes | 92.28 |  | 26/05/2022 | 1 | 82.95 | MVS
313 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM UTISHEY JHORA TO LOWER YOGDA | TSM/009657 | SM/10743 | New | 17/02/2022 | 87 | 79.81 | Yes | 79.81 |  | 25/05/2022 | 1 | 76.69 | MVS
314 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM OKHERBOTEY JHORA TO DUN | TSM/009647 | SM/10745 | New | 17/02/2022 | 90 | 91.35 | Yes | 91.35 |  | 26/05/2022 | 1 | 88.59 | MVS
315 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, | TSM/009603 | SM/11316 | Retrofitting | 17/02/2022 | 51 | 7.68 | Yes | 7.68 |  | 30/06/2022 | 2 | 7.09 | MVS
316 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA | TSM/010595 | SM/11334 | Retrofitting | 17/02/2022 | 246 | 33.35 | Yes | 33.35 |  | 30/06/2022 | 2 | 28.17 | MVS
317 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. | TSM/012578 | SM/11944 | New | 20/05/2022 | 818 | 923.75 | Yes | 923.75 |  | 16/08/2023 | 4 | 937.32 | MVS
318 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. | TSM/011221 | SM/12367 | New | 30/03/2022 | 1317 | 1786.06 | Yes | 1786.06 | 25/01/2024 | 06/02/2023 | 2 | 1750.73 | MVS
319 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. | TSM/011218 | SM/12368 | New | 30/03/2022 | 1738 | 2044.39 | Yes | 2044.39 | 26/09/2024 | 18/03/2024 | 4 | 1771.09 | MVS
320 | KALIMPONG | Neorakhola W/S Mnt. Division | RIYONG FOREST & RIYANG RAILWAY STATION PIPED WATER SUPPLY SCHEME UNDER TEESTA G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/010973 | SM/11376 | New | 30/03/2022 | 147 | 191.02 | Yes | 191.02 |  | 25/04/2023 | 6 | 189.16 | MVS
321 | KALIMPONG | Neorakhola W/S Mnt. Division | MANOPONG FOREST (PART) PIPED WATER SUPPLY SCHEME | TSM/012582 | SM/13602 | New | 20/05/2022 | 445 | 335.49 | Yes | 335.49 |  | 20/01/2023 | 3 | 324.97 | MVS
322 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | TSM/009526 | SM/11350 | New | 16/03/2022 | 35 | 26.38 | Yes | 26.38 |  | 12/07/2022 | 3 | 25.8 | MVS
323 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM HARESAY JHORA TO MUNSI DHURA and KARBUTAR | TSM/009639 | SM/11354 | New | 16/03/2022 | 106 | 143.23 | Yes | 143.23 |  | 21/09/2022 | 1 | 135.69 | MVS
324 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/014817 | SM/13615 | New | 22/08/2022 | 35 | 101.26 | Yes | 101.26 | 08/12/2022 | 01/02/2023 | 2 | 93.71 | MVS
325 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional Household tap connection from existing PWSS at Khaling dhura & Vah Tukbar( Bhutta Kheti) | TSM/011129 | SM/13352 | Retrofitting | 05/07/2022 | 249 | 62.01 | Yes | 62.01 |  | 03/11/2022 | 1 | 48.48 | MVS
326 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. | TSM/011930 | SM/13041 | New | 20/05/2022 | 850 | 1164.09 | Yes | 1164.09 |  | 21/10/2022 | 3 | 1168.73 | MVS
327 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | TSM/012882 | SM/13955 | New | 22/08/2022 | 241 | 237.69 | Yes | 237.69 |  | 09/12/2024 | 3 | 236.04 | MVS
328 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013039 | SM/13959 | New | 22/08/2022 | 165 | 228.01 | Yes | 228.01 |  | 14/12/2022 | 2 | 212.22 | MVS
329 | KALIMPONG | Neorakhola W/S Mnt. Division | SAMABIYONG TEA GARDEN PIPED WATER SUPPLY SCHEME. | TSM/011907 | SM/13611 | New | 15/07/2022 | 383 | 648.24 | Yes | 648.24 | 08/12/2022 | 09/02/2023 | 3 | 645.11 | MVS
330 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/012884 | SM/14148 | New | 22/08/2022 | 1583 | 1646.2 | Yes | 1646.2 | 30/11/2022 | 24/09/2024 | 8 | 1630.4 | MVS
331 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR PROPOSED GRAVETY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLINGKHASMAHAL, BLOCK : KALIMPONG - I, DISTRICT : Kalimpong | TSM/011803 | SM/14192 | New | 20/05/2022 | 690 | 839.64 | Yes | 839.64 | 23/10/2024 | 20/11/2024 | 2 | 790.91 | MVS
332 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR PROPOSED GRAVITY BASED & PUMPING BASED WATER SUPPLY SCHEME FOR BHALUKHOP KHAS MAHAL PWSS, BLOCK : KALIMPONG - I, District : Kalimpong | TSM/011692 | SM/14194 | New | 20/05/2022 | 1264 | 747.62 | Yes | 747.62 | 23/10/2024 | 12/07/2023 | 3 | 739.94 | MVS
333 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKUM KHASMAHAL (PART) UNDER YANGMAKUM G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | TSM/017434 | SM/16232 | New | 28/12/2022 | 206 | 380.82 | Yes | 380.82 | 08/02/2023 | 05/06/2023 | 2 | 378.2 | MVS
334 | DARJEELING | Neorakhola W/S Mnt. Division | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME | TSM/014897 | SM/16161 | New | 28/12/2022 | 393 | 322.85 | Yes | 322.85 | 08/02/2023 | 28/04/2023 | 3 | 314.46 | MVS
335 | DARJEELING | Neorakhola W/S Mnt. Division | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme | TSM/014826 | SM/16384 | New | 09/09/2022 | 384 | 557.87 | Yes | 557.87 | 12/03/2024 | 05/05/2025 | 3 | 547.63 | MVS
336 | DARJEELING | Neorakhola W/S Mnt. Division | BARA MUNGWA PIPED WATER SUPPLY SCHEME | TSM/016188 | SM/15893 | New | 28/12/2022 | 358 | 476.33 | Yes | 476.33 | 12/03/2024 | 18/06/2024 | 1 | 12.72 | MVS
337 | DARJEELING | Neorakhola W/S Mnt. Division | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME | TSM/018134 | SM/15897 | New | 28/12/2022 | 563 | 560.14 | Yes | 560.14 | 16/02/2024 | 25/09/2024 | 4 | 535.28 | MVS
338 | DARJEELING | Neorakhola W/S Mnt. Division | LAMAGAON PIPED WATER SUPPLY SCHEME. | TSM/019222 | SM/15868 | New | 28/12/2022 | 628 | 752.32 | Yes | 752.32 | 12/03/2024 | 10/05/2023 | 3 | 715.99 | MVS
339 | DARJEELING | Neorakhola W/S Mnt. Division | CHEGRA KHASMAHAL Piped Water Supply Scheme | TSM/018127 | SM/16141 | New | 28/12/2022 | 237 | 335.44 | Yes | 335.44 | 08/02/2023 | 04/05/2023 | 3 | 324.89 | MVS
340 | KALIMPONG | Neorakhola W/S Mnt. Division | KUMAI KHASMAHAL & KUMAI TEA GARDEN PWSS | TSM/015530 | SM/15937 | New | 09/09/2022 | 782 | 657.46 | Yes | 657.46 | 23/12/2022 | 03/03/2023 | 2 | 642.32 | MVS
341 | DARJEELING | Neorakhola W/S Mnt. Division | RELLING PIPED WATER SUPPLY SCHEME. | TSM/017939 | SM/15879 | New | 28/12/2022 | 643 | 937.57 | Yes | 937.57 | 08/02/2023 | 06/06/2023 | 3 | 901.47 | MVS
342 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | TSM/016211 | SM/18634 | New | 26/09/2022 | 1128 | 1305.54 | Yes | 1305.54 | 02/03/2023 | 08/07/2024 | 2 | 13.66 | MVS
343 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011830 | SM/18821 | New | 20/05/2022 | 869 | 1262.02 | Yes | 1262.02 | 01/09/2023 | 05/05/2025 | 1 | 28.61 | MVS
344 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING | TSM/011752 | SM/18822 | New | 20/05/2022 | 2031 | 3724.46 | Yes | 3724.46 | 22/02/2023 | 05/05/2025 | 4 | 3712.36 | MVS
345 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) UNDER PEDONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | TSM/012504 | SM/12629 | New | 20/05/2022 | 588 | 752.8 | Yes | 752.8 |  | 29/09/2022 | 2 | 733.03 | MVS
346 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for pemling forest under Kaffer - Kankebong G.P. Kalimpong Block-I, Dist-Kalimpong in connection under Neorakhola W/S & Mtc, Div. PHE. Dte. Kalimpong. | TSM/009887 | SM/10563 | New | 16/03/2022 | 34 | 62.89 | Yes | 62.89 |  | 26/05/2022 | 2 | 57.46 | MVS
347 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER KALIMPONG BLOCK - I UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009630 | SM/10694 | New | 17/02/2022 | 105 | 94.15 | Yes | 94.15 | 23/10/2024 | 02/04/2025 | 2 | 93.09 | MVS
348 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay | TSM/009477 | SM/10780 | Retrofitting | 27/01/2022 | 28 | 17.18 | Yes | 17.18 |  | 26/05/2022 | 2 | 16.83 | MVS
349 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for BIRIK FOREST VILLAGE under G.P. Kalimpong Block-I, District- Kalimpong in Connection under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | TSM/009884 | SM/10575 | New | 16/03/2022 | 43 | 49.33 | Yes | 49.33 |  | 26/05/2022 | 2 | 44.09 | MVS
350 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | TSM/009504 | SM/10837 | New | 17/02/2022 | 160 | 101.18 | Yes | 101.18 |  | 28/11/2024 | 3 | 93.64 | MVS
351 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household tap connection existing PWSS at Bunkulung | TSM/011139 | SM/11391 | Retrofitting | 30/03/2022 | 155 | 33.5 | Yes | 33.5 |  | 12/07/2022 | 1 | 27.91 | MVS
352 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam | TSM/011123 | SM/11393 | Retrofitting | 30/03/2022 | 1398 | 184.74 | Yes | 184.74 | 24/01/2023 | 12/07/2023 | 2 | 174.64 | MVS
353 | DARJEELING | Neorakhola W/S Mnt. Division | Piped water supply scheme for Lower Bish Acre, Ghayabari. | TSM/009513 | SM/11397 | New | 30/03/2022 | 80 | 69.47 | Yes | 69.47 |  | 23/12/2022 | 3 | 66.5 | MVS
354 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. | TSM/011219 | SM/11398 | New | 30/03/2022 | 225 | 379.74 | Yes | 379.74 | 07/03/2024 | 04/07/2024 | 3 | 335.84 | MVS
355 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/009888 | SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 27/01/2022 | 6 | 18.42 | Yes | 18.42 |  | 12/07/2022 | 5 | 17.9 | MVS
356 | DARJEELING | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | TSM/009889 | SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 27/01/2022 | 6 | 13.32 | Yes | 13.32 |  | 12/07/2022 | 3 | 12.89 | MVS
357 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA | TSM/009859 | SM/10799 | New | 17/02/2022 | 233 | 80.89 | Yes | 80.89 |  | 26/05/2022 | 1 | 47.25 | MVS
358 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | TSM/009852 | SM/10806 | New | 17/02/2022 | 588 | 122.1 | Yes | 122.1 |  | 26/05/2022 | 3 | 70.97 | MVS
359 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | TSM/009850 | SM/10808 | New | 17/02/2022 | 233 | 189.33 | Yes | 189.33 |  | 09/04/2025 | 3 | 175.93 | MVS
360 | KALIMPONG | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER GORUBATHAN BLOCK UNDER JJM AND JAL SWAPNO PROGRAMME | TSM/009664 | SM/10698 | New | 17/02/2022 | 169 | 206.41 | Yes | 206.41 |  | 25/05/2022 | 1 | 197.08 | MVS
361 | DARJEELING | Neorakhola W/S Mnt. Division | BARA CHENGA PIPED WATER SUPPLY SCHEME | TSM/010843 | SM/10816 | New | 16/03/2022 | 584 | 422.1 | Yes | 422.1 |  | 03/01/2024 | 6 | 3.96 | MVS
362 | DARJEELING | Neorakhola W/S Mnt. Division | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | TSM/009843 | SM/10829 | New | 17/02/2022 | 269 | 167.48 | Yes | 167.48 |  | 05/05/2025 | 3 | 124.64 | MVS
363 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM SISNEY JHORA TO SAMTHAR BAZAR | TSM/009660 | SM/10742 | New | 17/02/2022 | 252 | 197.78 | Yes | 197.78 |  | 25/05/2022 | 1 | 191.91 | MVS
364 | KALIMPONG | Neorakhola W/S Mnt. Division | PWS SCHEME FROM BANGLA JHORA TO JOGITAR | TSM/009634 | SM/10750 | New | 17/02/2022 | 60 | 65.73 | Yes | 65.73 |  | 03/04/2025 | 2 | 61.21 | MVS
365 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. | TSM/009599 | SM/11320 | Retrofitting | 17/02/2022 | 234 | 19.74 | Yes | 19.74 |  | 30/06/2022 | 2 | 17.94 | MVS
366 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III | TSM/009304 | SM/11301 | Retrofitting | 27/01/2022 | 45 | 8.63 | Yes | 8.63 |  | 30/06/2022 | 2 | 7.86 | MVS
367 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon | TSM/009307 | SM/11304 | Retrofitting | 27/01/2022 | 44 | 23.72 | Yes | 23.72 |  | 30/06/2022 | 2 | 20.4 | MVS
368 | DARJEELING | Neorakhola W/S Mnt. Division | Providing functional household Tap connection under JSP Programme for PWS Scheme Manju Dara Gaon | TSM/009483 | SM/11307 | Retrofitting | 27/01/2022 | 35 | 6.09 | Yes | 6.09 |  | 30/06/2022 | 1 | 5.33 | MVS
369 | DARJEELING | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA | TSM/010593 | SM/11332 | Retrofitting | 17/02/2022 | 244 | 26.39 | Yes | 26.39 |  | 30/06/2022 | 2 | 25.25 | MVS
370 | KALIMPONG | Neorakhola W/S Mnt. Division | DETAIL PROJECT REPORT OF SEPKHOLA PIPED WATER SUPPLY SCHEME (PWSS) UNDER MAZEOK FOREST, SAMTHAR G.P, BLOCK:-KALIMPONG-I, P.S:-KALIMPONG, DISTRICT:KALIMPONG. | TSM/011293 | SM/11577 | New | 30/03/2022 | 32 | 47.54 | Yes | 47.54 | 23/10/2024 | 17/12/2024 | 2 | 46.76 | MVS
371 | KALIMPONG | Neorakhola W/S Mnt. Division | creating gravity based provision of drinking water from spring water source for 06 numbers of Gram panchayats, under Gorubathan Block in the District of kalimpong under Neorakhola water supply Division , PHE Dte. Kalimpong. | TSM/010267 | SM/11370 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | 16/03/2022 | 6 | 27.84 | Yes | 27.84 |  | 17/07/2023 | 12 | 34.28 | MVS
372 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING | TSM/011929 | SM/11890 | New | 20/05/2022 | 609 | 760.91 | Yes | 760.91 |  | 29/09/2022 | 3 | 754.83 | MVS
373 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING | TSM/011829 | SM/12736 | New | 20/05/2022 | 990 | 1292.66 | Yes | 1292.66 |  | 03/11/2022 | 3 | 1282.53 | MVS
374 | KALIMPONG | Neorakhola W/S Mnt. Division | PWSS FROM BHARKHOP JHORA TO LOWER KAFFER | TSM/009553 | SM/11343 | New | 17/02/2022 | 85 | 99.53 | Yes | 99.53 |  | 30/06/2022 | 1 | 96.58 | MVS
375 | DARJEELING | Neorakhola W/S Mnt. Division | Providing household tap connection from existing scheme at Museykhola & Dokan Dhura | TSM/011125 | SM/11818 | Retrofitting | 25/04/2022 | 279 | 50.5 | Yes | 50.5 | 01/03/2023 | 31/10/2023 | 1 | 46.23 | MVS
376 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009533 | SM/11347 | New | 16/03/2022 | 96 | 39.89 | Yes | 39.89 |  | 12/07/2022 | 2 | 38.8 | MVS
377 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. | TSM/009264 | SM/11353 | New | 16/03/2022 | 200 | 72.84 | Yes | 72.84 |  | 12/07/2022 | 2 | 64.04 | MVS
378 | KALIMPONG | Neorakhola W/S Mnt. Division | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. | TSM/010916 | SM/11806 | New | 16/03/2022 | 139 | 204.57 | Yes | 204.57 |  | 25/04/2023 | 2 | 186.8 | MVS
379 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. | TSM/012510 | SM/13571 | New | 20/05/2022 | 1344 | 1420.81 | Yes | 1420.81 | 30/11/2022 | 05/05/2025 | 3 | 1411.87 | MVS
380 | DARJEELING | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING | TSM/011832 | SM/13042 | New | 20/05/2022 | 578 | 1047.9 | Yes | 1047.9 |  | 31/07/2024 | 4 | 1018.82 | MVS
381 | DARJEELING | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/013295 | SM/13960 | New | 22/08/2022 | 349 | 300.61 | Yes | 300.61 |  | 23/12/2022 | 2 | 280.55 | MVS
382 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | TSM/015692 | SM/15463 | New | 30/09/2022 | 165 | 226.88 | Yes | 226.88 | 02/12/2022 | 28/02/2023 | 3 | 202.59 | MVS
383 | KALIMPONG | Neorakhola W/S Mnt. Division | GORUBATHAN-I PWSS | TSM/014336 | SM/14172 | New | 22/08/2022 | 1818 | 1146.86 | Yes | 1146.86 | 27/04/2023 | 18/07/2023 | 2 | 1132.56 | MVS
384 | DARJEELING | Neorakhola W/S Mnt. Division | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | TSM/012888 | SM/14149 | New | 22/08/2022 | 946 | 1893.19 | Yes | 1893.19 | 30/11/2022 | 05/05/2025 | 4 | 1841.84 | MVS
385 | KALIMPONG | Neorakhola W/S Mnt. Division | SANTUK KHASMAHAL PIPED WATER SUPPLYSCHEME, BLOCK : KALIMPONG - II, DISTRICT :KALIMPONG | TSM/012585 | SM/14191 | New | 20/05/2022 | 915 | 693.21 | Yes | 693.21 |  | 13/06/2025 | 2 | 687.24 | MVS
386 | DARJEELING | Neorakhola W/S Mnt. Division | BLOOMFIELD TEA GARDEN PWSS | TSM/014905 | SM/15910 | New | 28/12/2022 | 556 | 447.08 | Yes | 447.08 | 16/02/2024 | 14/06/2024 | 4 | 432.73 | MVS
387 | DARJEELING | Neorakhola W/S Mnt. Division | RESHOP BAZAR PIPED WATER SUPPLY SCHEME | TSM/017530 | SM/15882 | New | 28/12/2022 | 181 | 423.41 | Yes | 423.41 | 08/02/2023 | 28/04/2023 | 2 | 418.07 | MVS
388 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/015164 | SM/16532 | New | 22/08/2022 | 1274 | 1658.37 | Yes | 1658.37 | 13/12/2022 | 01/08/2024 | 3 | 1647.44 | MVS
389 | KALIMPONG | Neorakhola W/S Mnt. Division | LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK: KALIMPONG-II, DISTRICT:-KALIMPONG | TSM/017521 | SM/16511 | New | 28/12/2022 | 1013 | 964.71 | Yes | 964.71 | 23/11/2023 | 05/06/2023 | 2 | 932.62 | MVS
390 | KALIMPONG | Neorakhola W/S Mnt. Division | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPOO FOREST UNDER SANGASEY G.P, BLOCK : KALIMPONG II, DISTRICT:KALIMPONG | TSM/017496 | SM/16513 | New | 28/12/2022 | 369 | 304 | Yes | 304 | 01/02/2023 | 10/05/2023 | 1 | 2.27 | MVS
391 | DARJEELING | Neorakhola W/S Mnt. Division | PWS Scheme for Sepoy Dhura Tea Garden | TSM/013289 | SM/15651 | New | 30/09/2022 | 378 | 525.04 | Yes | 525.04 | 23/12/2022 | 05/05/2025 | 4 | 513.68 | MVS
392 | DARJEELING | Neorakhola W/S Mnt. Division | MONGPOO CINKONA PLANTATION, ROLAK & LONKU KHASMAHAL PWSS | TSM/015045 | SM/17191 | New | 09/09/2022 | 1682 | 240.32 | Yes | 879.54 | 29/12/2022 | 28/04/2023 | 1 | 230.27 | MVS
393 | KALIMPONG | Neorakhola W/S Mnt. Division | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | TSM/009882 | SM/10600 | New | 16/03/2022 | 13 | 10.62 | Yes | 10.62 |  | 26/05/2022 | 2 | 10.28 | MVS
394 | DARJEELING | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | TSM/009530 | SM/11348 | New | 16/03/2022 | 150 | 27.68 | Yes | 27.68 |  | 25/11/2022 | 2 | 25.15 | MVS
395 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | TSM/014851 | SM/18636 | New | 22/08/2022 | 722 | 1046.24 | Yes | 1046.24 | 22/02/2023 | 05/05/2025 | 2 | 1039.55 | MVS
396 | KALIMPONG | Neorakhola W/S Mnt. Division | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | TSM/010479 | SM/10635 | New | 16/03/2022 | 70 | 143.53 | Yes | 143.53 |  | 30/06/2022 | 1 | 127.14 | MVS
397 | DARJEELING | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | TSM/015170 | SM/14147 | New | 22/08/2022 | 960 | 1120.63 | Yes | 1120.63 | 02/12/2022 | 26/02/2024 | 3 | 25.93 | MVS
398 | KALIMPONG | Neorakhola W/S Mnt. Division | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-I | TSM/020254 | SM/18442 | Augmentation | 28/12/2022 | 3573 | 3858.84 | Yes | 3858.84 | 29/08/2024 | 09/12/2024 | 2 | 3831.23 | MVS
399 | DARJEELING | Neorakhola W/S Mnt. Division | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA | TSM/012036 | SM/12737 | Support | 20/05/2022 | 0 | 8.66 | Yes | 8.66 |  | 19/04/2023 | 5 | 9.48 | MVS
400 | DARJEELING,KALIMPONG | Neorakhola W/S Mnt. Division | Conducting field survey of schools, Anganwadis, Health Centres, GP Buildings and Ashramsalas in the hilly district of Darjeeling & Kalimpong comprising 5 nos of block in the district of Darjeeling and 3 nos of blocks in the district of Kalimpong with a vi | TSM/009458 | SM/10139 | Support | 16/12/2021 | 0 | 7.7 | Yes | 15.41 |  | 10/02/2022 | 4 | 9.5 | MVS
401 | KALIMPONG | Neorakhola W/S Mnt. Division | Route survey using DGPS & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (W | TSM/009462 | SM/10140 | Support | 16/12/2021 | 0 | 436.51 | Yes | 436.51 |  | 31/12/2021 | 58 | 242.99 | MVS
402 | DARJEELING | Neorakhola W/S Mnt. Division | Proposed Estimate for Construction of Sub - Divisional Water Testing Lab over the existing PHE Division Building at Kurseong | TSM/014318 | SM/14195 | Support | 22/08/2022 | 0 | 59.93 | Yes | 59.93 |  |  | 0 | 0 | MVS
403 | DARJEELING | Neorakhola W/S Mnt. Division | Setting up of District Project Management Unit (DPMU) for Darjeeling (Hills) District under Jal Jeevan Mission (JJM). | TSM/020473 | SM/18270 | Support | 10/03/2023 | 0 | 45.27 | Yes | 45.27 | 16/05/2023 |  | 0 | 0 | MVS
404 | DARJEELING | Neorakhola W/S Mnt. Division | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co | TSM/022265 | SM/19010 | Support | 17/08/2023 | 0 | 699.39 | Yes | 699.39 |  | 10/07/2024 | 7 | 823.91 | MVS
405 | KALIMPONG | Neorakhola W/S Mnt. Division | Operational charges procurement of chemicals Glassware-computer maintenance of PHED managed laboratories related to water quality monitoring & surveillance under Jal Jeevan Mission | TSM/022923 | SM/19295 | Support | 09/03/2024 | 0 | 21.75 | Yes | 21.75 |  |  | 0 | 0 | MVS
406 | DARJEELING,KALIMPONG | Neorakhola W/S Mnt. Division | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under Jal Jeevan Mission (JJM) | TSM/013482 | SM/18271 | Support | 10/03/2023 | 0 | 183.23 | Yes | 366.46 | 19/09/2023 | 29/11/2024 | 2 | 173.5 | MVS
407 | KALIMPONG | Neorakhola W/S Mnt. Division | Supply Delivery and Installation of Computer & peripherals for official use under office of the Superintending Engineer, G.T.A Circle, P.H.E Dte. and Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | TSM/009872 | SM/10513 | Support | 27/01/2022 | 0 | 13.03 | Yes | 13.03 |  | 18/07/2022 | 3 | 25.26 | MVS
408 | DARJEELING | Neorakhola W/S Mnt. Division | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C | TSM/010684 | SM/10732 | Support | 16/03/2022 | 0 | 910.35 | Yes | 910.35 |  | 30/06/2022 | 7 | 371.06 | MVS
409 | DARJEELING,KALIMPONG | Neorakhola W/S Mnt. Division | DPR on Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring and Surveillance under Jal Jeevan Mission. | TSM/015746 | SM/15667 | Support | 09/09/2022 | 0 | 17.42 | Yes | 34.84 |  |  | 0 | 0 | MVS
410 | DARJEELING | Neorakhola W/S Mnt. Division | Collection of Drinking Water Samples from various spot sources, PWSS, Schools, Anganwadis, Health Centres and Springs under Darjeeling Hills for water testing at Sindhap sub-district laboratory Darjeeling managed by Neorakhola water supply and maintenance | TSM/013497 | SM/15668 | Support | 09/09/2022 | 0 | 13.71 | Yes | 13.71 |  | 03/03/2023 | 1 | 12.75 | MVS
411 | KALIMPONG | Neorakhola W/S Mnt. Division | Collection of Water Samples from different drinking water sources, tanks and reservoir etc. under Kalimpong district and submitting the same to the respective water testing laboratories (Neorakhola sub-district laboratory and Algarah sub-district laborato | TSM/013469 | SM/15669 | Support | 09/09/2022 | 0 | 27.41 | Yes | 27.41 |  | 03/03/2023 | 1 | 25.49 | MVS
412 | KALIMPONG | Neorakhola W/S Mnt. Division | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Darjeeling Division-II, PHE-GTA, Kalimpong. | TSM/012016 | SM/13680 | Support | 20/05/2022 | 0 | 6.46 | Yes | 6.46 |  | 10/05/2023 | 3 | 6 | MVS
413 | DARJEELING,KALIMPONG | Neorakhola W/S Mnt. Division | DPR regarding Procurement of Chemicals & Consumables, Glassware etc. | TSM/005381 | SM/06616 | Support | 05/11/2019 | 0 | 14.62 | Yes | 14.62 |  | 16/12/2020 | 4 | 12.87 | MVS
414 | DARJEELING,KALIMPONG | Neorakhola W/S Mnt. Division | Operational charges of PHED managed laboratories related to water quality monitoring & surveillance under Jal Jeevan Mission. | TSM/022922 | SM/19261 | Support | 09/03/2024 | 0 | 29.76 | Yes | 59.52 |  |  | 0 | 0 | MVS
415 | DARJEELING,KALIMPONG | Neorakhola W/S Mnt. Division | Collection, testing of drinking Water samples through FTKs & uploading charges related to Water Quality Monitoring & Surveillance under JJM for Kalimpong District and 5 Blocks of Darjeeling Hills | TSM/009495 | SM/10272 | Support | 16/12/2021 | 0 | 54.94 | Yes | 109.88 |  | 28/08/2024 | 6 | 3.65 | MVS
Total | [7 empty] | 184577 | 224906.6 |  | 225838.87 |  |  | 1164 | 198905.42